## CPs
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status Changed in the last month
STATUS - DEFINITION
DCP 266 | The calculation and application of IDNO discounts | To change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this CP is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | CDCM | 1 | Dylan Townsend/ John Lawton | David McCrone | 2016-03-09 | 23 |  | 2021-04-01 | The Working Group met on 05 March 2019 and 28 March 2019 to review the updated impact assessment and agree to the final elements of the second consultation document. It is expected that a consultation will be issued to industry on 17 April 2019 for a period of four weeks. The Working Group met on 24 May 2019, to review the collated consultation responses and are in the process of requesting a legal opinion and a review of the final legal text. The next meeting is due to be held on 18 June 2019 to review the draft change report. | N/A
DCP 325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20. | The intent of this Change Proposal is to combine, review and if appropriate, amend the requirements of Section 35A, Section 35B, Schedule 15 and Schedule 20 to improve transparency and efficiency in the data published by DNOs | General | 2 | Dylan Townsend / Hollie Nicholls | N/A | 2018-07-11 | 8 |  | Next scheduled release following approval | The Working Group are continuing to develop their solution and have a further Working Group meeting organised for 17 June 2019 to review a new tool developed by CEPA/TNEI and to continue to draft their second consultation document. | N/A
DCP 328 | Use of system charging for private networks with competition in supply | The intent of this change is to ensure that use of system charging remains cost-reflective when competition in supply on a private network is in place. | CDCM/ EDCM | 1 | Richard Colwill / John Lawton | Olivia Powis | 2018-08-15 | 9 |  | Next scheduled release following approval | The Working Group issued a consultation on 1st February for a period of three weeks to seek views on the proposed options and decide on which options should be considered further. The consultation responses have bene received and the Working Group have considered the feedback. The group has decided on which options should be considered further and is currently drafting the second consultation. | N/A
DCP 329 | Amend Requirements for Emergency De-energisation in Schedule 2B - National Terms of Connection | The intent of this Change Proposal is to revise/amend the National Terms of Connection, to allow for the De-energisation of a Customer’s Installation by the Customer without the need to obtain prior agreement from the Licenced Distributor, where the condition or manner of operation of the Distribution System or the connection equipment poses an immediate threat of injury or material damage to any person or property. | General | 2 | Richard Colwill / Angelo Fitzhenry | N/A | 2018-09-21 | 3 |  | Next scheduled release following approval | An initial meeting was held on 7th January and a consultation was released on 25th February for a period of three weeks to seek industry views. The consultation responses have now been received and the Working Group met on 25 April to review the responses. The Working Group met on 9 May to agree on the amended legal text. | N/A
DCP 332 | Appropriate treatment and allocation of Last Resort Supply Payment claim costs | The intent of this Change Proposal is to ensure that associated costs are recovered fairly and equitable from customers where a DNO Party receives a claim from a Supplier of Last Resort for a Last Resort Supply Payment claim | General | 1 | George Dawson / Hollie Nicholls | David McCrone | 2018-11-12 | 3 |  | 2021-04-01 | A Joint Working Group meeting with DCP 333 has been set up. The DCP 332 and DCP 333 Changes were issued for Consultation with a deadline of the 21st of May for comment and the Working Group are meeting on 14 June 2019 to review the responses and draft their change reports | N/A
DCP 333 | Appropriate treatment and allocation of eligible use of system bad debt costs | The intent of this Change Proposal is to ensure that associated costs are recovered fairly and equitable from customers where a DNO or IDNO Party incurs eligible use of system bad debt due to insolvency of electricity suppliers whose supply licence has subsequently been revoked | General | 1 | George Dawson / Hollie Nicholls | David McCrone | 2018-11-12 | 3 |  | 2021-04-01 | A Joint Working Group meeting with DCP 332 has been set up. The DCP 332 and DCP 333 Changes were issued for Consultation with a deadline of the 21st of May for comment and the Working Group are meeting on 14 June 2019 to review the responses and draft their Change Reports. | N/A
DCP 336 | Rota Disconnections and the publication of data by Nominated Central Source | The intent of this CP is to review and if appropriate amend the reference to the publication of a DVD by the Nominated Central Source for the publication of data for the Rota Disconnections. | General | 2 | Hollie Nicholls / Dylan Townsend | N/A | 2019-01-07 | 2 |  | First release following approval | The Working Group met on 07 May 2019 to review the consultation responses. Working Group members are now finalising their proposed legal text and will be drafting a Change Report for review at their next meeting on 11 June 2019 | N/A
DCP 340 | Notice period required to recover approved last resort supply payment claims which breach the materiality threshold | This CP seeks to remove the need for the Authority to direct that the periods of notice described in Clause 19.1A need not apply where the DNO Party has given notice to the Authority under new distribution licence condition 38B, in respect of Last Resort Supply Payment claims which result in breach of a DNO Party’s Materiality Threshold; and define how DNOs should calculate the change to previously published use of system charges required by that licence condition when the Materiality Threshold is breached. | CDCM /EDCM | 1 | George Dawson / Hollie Nicholls | David McCrone | 2019-02-01 | 1 |  | First DCUSA Release following approval and implementation of modifications to the licence. | The Working Group issued a consultation for response from parties before 21 May 2019. The Working Group are meeting on 14 June 2019 to review the responses and draft their change report. | N/A
DCP 341 | Removal of residual charging for storage facilities in the CDCM | This CP seeks to amend the application of residual charging in respect of storage generators in the CDCM. | CDCM | 1 | Dylan Townsend / John Lawton | Ankita Mehra | 2019-01-31 | 5 |  | 2021-04-01 | The Working Group had their first meeting on 01 April 2019 and are due to meet again on 12 April 2019 to review their legal text and modelling specification. The Secretariat is drafting a consultation document that will be reviewed during a meeting scheduled for 23 April 2019. The Working Group issued a consultation on 05 June 2019 for a period of three weeks. The working Group will next meet on 28 June 2019 to review the collated consultation responses and agree the next steps. | CONSULTATION
DCP 342 | Removal of residual charging for storage facilities in the EDCM | This CP seeks to amend the application of residual charging in respect of storage generators in the EDCM. | EDCM | 1 | Dylan Townsend / John Lawton | Ankita Mehra | 2019-01-31 | 5 |  | 2021-04-01 | The Working Group had their first meeting on 01 April 2019 and are due to meet again on 12 April 2019 to review their legal text and modelling specification. The Secretariat is drafting a consultation document that will be reviewed during a meeting scheduled for 23 April 2019. The Working Group issued a consultation on 05 June 2019 for a period of three weeks. The working Group will next meet on 28 June 2019 to review the collated consultation responses and agree the next steps. | CONSULTATION
DCP 343 | Use of a nominated calculation agent for the calculation of the LV mains split | This CP seeks to remove the need for the procurement of a nominated calculation agent for the purpose of calculating the ‘LV mains split’ and to make minor associated housekeeping changes. | General | 2 | Hollie Nicholls / Angelo Fitzhenry | Ankita Mehra | 2019-02-12 | 2 |  | First release following approval | The Working Group met on 04 June 2019 to review the responses to their consultation. They are currently drafting a change report and are meeting again on 26 June 2019 to review the draft Change Report and finalised legal text. | N/A
DCP 344 | Solutions for a new approach to billing and remittance | The intent of this Change Proposal seeks to introduce a new approach for billing that will create efficiencies for DCUSA Parties and better facilitate competition. | Billing | 1 | Richard Colwill / Dylan Townsend | N/A | 2019-02-26 | 1 |  | First release following approval | The Working Group has been formed and the first meeting was held on 22 May to diiscuss the change and any potentia solutions and the next meeting is scheduled for 13 June 2019.. | N/A
DCP 345 | Sandbox Application | The intent of this Change Proposal is to facilitate the processing of a sandbox application | General | 1 | Hollie Nicholls/ John Lawton | N/A | 2019-03-14 | 0 |  | First release following approval | The Working Group has been formed and the first meeting is scheduled for 05 July 2019 | N/A
STATUS - CHANGE REPORT
DCP 326 | Introduction of Load Diversification Identifiers for Load Managed Areas | This Change Proposal seeks to introduce a simplified process for retaining the diversifation of demand in Load Managed Areas (LMA) during the replacement of RTS controlled metering equipment by Suppliers or post the decommissioning of the Radio Teleswitch System (RTS) | General | 1 | Richard Colwill / John Lawton | Deborah Duke | 2018-07-10 | 9 |  | 2020-02-01 | The Working Group released a second consultation on 2nd April to seek feedback on thiis alternative solution in order to decide which solution should be recommended. The deadline for responses was 30th April. The Working Group met on 7th May to review the consultation responses. Following this review the Working Group agreed to move forwrad with the proposed solution regarding the use of LLFC. The Working Group plans to submit the Chnage Report to the June Panel.. | CHANGE REPORT
DCP 346 | Amendment to Code of Practice Confirmed Theft Definition | To update and align the Theft Code of Practice schedules to ensure the consistency in the definition of Confirmed Theft and investigation processes. | Theft | 2 | Austin Gash/ | N/A | 2019-05-15 | 0 |  | 2019-11-07 | The Change Report was issued to the DCUSA Panel on 19 June 2019. | CHANGE REPORT
STATUS - VOTING
N/A
STATUS - AWAITING AUTHORITY CONSENT
DCP 313 | Eligibility Criteria for EDCM Generation Credits | The intent of this Change Proposal is to improve transparency of the eligibility criteria for EDCM generators to receive super red credits and to improve consistency in the application thereof. | EDCM | 1 | Hollie Nicholls / John Lawton | David McCrone | 2017-10-20 | 14 |  | 2021-04-01 | The Change Report was issued for voting on 22 March 2019 with a deadline of 12 April 2019 | N/A
DCP 314 | Appropriate treatment of Bad Debt following appointment of Supplier of Last Resort | This DCUSA change proposal seeks to implement a process that is triggered in the event that a Supplier of Last Resort (SoLR) is appointed following a supplier default. Under these circumstances, it is proposed that Distribution Network Operators (DNOs) must credit Local Distribution Network Operators (LDNOs) for the amount of DUoS charges attributable to the defaulting supplier where the LDNO has not received payment. | Billing | 1 | Huw Neyroud/Hollie Nicholls / John Lawton | Chris Parish | 2018-01-02 | 12 |  | Next scheduled release following approval | DCP 314 has progressed to Authority decision after a vote on the Change and the alternate of the change both of which were rejected by Industry. The decision now rests with Ofgem | N/A
DCP 297 | Network Interventions SLA Enhancement | This CP seeks to change the mechanism whereby DNO’s are released from their obligations to meet the intervention SLA to one which is solely based on the accuracy of Suppliers smart meter roll-out forecasts. The DCUSA Panel has directed that this change be considered by the Interventions Working Group. | General | 1 | To be progressed by the Interventions Working Group | Michael Walls / Mark Hogan | 2017-04-07 | 4 |  | Next scheduled release following approval | The Change Report was initially submitted to the Panel in October, however the Panel agreed that further development of the Change Report was required and the IWG convened to address the feedback. The updated Change Report was approved by the Panel during their meeting on 20 December 2017 and it was issued to Parties for Voting. Voting closed on 18 January 2018 and a Change Declaration was issued to the Authority on 22 January 2018 with a recommendation from Parties to reject DCP 297. | N/A
STATUS - AWAITING IMPLEMENTATION
2019-06-27
DCP 295 | CVA Registrants acceding to the DCUSA | This change is to facilitate BSC Modification PXXX which is to oblige CVA Registrants connecting to a Distribution System to accede to the DCUSA which will negate the need for a bilateral Use of System Agreements between the LDSO and the CVA Registrants saving administrative cost and effort and promoting efficiency and consistency. The effect of this change will be to modify the legal text to include CVA Registrants in addition to Distributed Generation Parties mainly in Section 2A but also in Sections 1A, 1B, 1C, 2B, 2C and 3 and Schedules 9, 11, 19 and 21. | General | 1 | Richard Colwill/ Hollie Nicholls | Stephen Perry | 2017-03-07 | 5 |  | First release following approval | A Change Declaration was issued to the Authority on 19 March 2019 with a recommendation to reject DCP 295 | N/A
DCP 334 | Update to Schedule 15 ('Cost Information Table') to maintain alignment with the distribution licence | The intent of this Change Proposal is, subject to the sucessful implementation of associated licence changes, to align Schedule 15 ('Cost Information Table') with the latest version of the electricity distribution licence | General | 2 | Hollie Nicholls | N/A | 2018-11-13 | 0 |  | Next scheduled release following approval | This DCP progressed straight to change report status and will be issued to DCUSA Panel on 12 December for approval to proceed to the voting phase | N/A
DCP 337 | Resolution of Housekeeping Items | This CP seeks to address and where appropriate to implement a number of housekeeping items that have been identified over a period of time. | General | 2 | Dylan Townsend | N/A | 2019-01-08 | 0 |  | 2019-06-27 | At their meeting in February, the Panel approved this CP and agreed for it to be progressed to the Change Report phase. The Change Report is being presented to the Panel during their meeting on 20 March 2019 and if approved, it will be issued to Parties for voting on 22 March 2019. Parties voted to accept the solution and implementation date and as such it will be implemented on 27 June 2019. | AWAITING IMPLEMENTATION
DCP 339 | Amend definition of ‘Other Charges' | This CP seeks to remove a contradiction between the electricity distribution licence and the DCUSA by removing any reference to DNO Party obligations to Last Resort Supply Payments. | General | 2 | Hollie Nicholls | N/A | 2019-02-01 | 0 |  | First release following approval | The Change Report was issued for voting on 22 March 2019 with a deadline of 12 April 2019 | AWAITING IMPLEMENTATION
2020-04-01
DCP 311 | Clarification of NUF cap and collar calculations | The intent of this Change Proposal is to modify schedules 17 and 18 to clarify which years should be used when determining NUF caps and collars to be applied for each charging year, and to remove an additional year lag which has been built into the legal text for the cap and collar calculations for 2023/24 charges. | EDCM | 1 | N/A / John Lawton | Edda Dirks | 2017-10-18 | 3 |  | 2020-04-01 | A consultation was issued to industry on 12 February 2018. The Working Group have reviewed the consultation responses and are in the process of drafting a Change Report which is expected to be issued to the May Panel meeting. The Change Report was issued for voting on 18 May with voting ending on 11 June 2018. A Change Declaration has been submitted to the Authority with a recommendation from Parties to accept the change on 13 June 2018 The change was accepted and placed into the register with a set implementation date of 01 April 2020 | N/A
DCP 306 | Treatment of Ofgem Licence Fees within the PCDM | The intent of this Change Proposal is to increase the cost reflectivity of the Price Control Disaggregation Model by directly allocating the Ofgem licence fee to an appropriate network tier for the calculation of the Opex allocation driver. | General | 1 | Hollie Nicholls / John Lawton | David McCrone | 2017-07-12 | 6 |  | 2020-04-01 | Proposed Legal Text has been approved by the Legal Advisors and a Change Report was submitted to the DCUSA Panel for their meeting on 18 April 2018. The Panel approved the Change Report which was subsequently issued for voting on 20 April 2018. Voting will end on 14 May 2018. As DCP 306 is considered a Part 1 Matter, a Change Declaration was issued to the Authority on 16 May 2018. The change was accepted and placed into the register with a set implementation date of 01 April 2020 | N/A
2021-04-01
DCP 268 | DUoS Charging Using HH settlement data | The intent of this CP is to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | CDCM | 1 | Hollie Nicholls/ John Lawton | Lynda Carroll | 2016-03-14 | 10 |  | 2020-04-01 | The DCP 268 Working Group last met on 13 February where the consultation responses were reviewed. The Working Group last met on 28 March to finalise the Change Report, which has been issued to the Panel in April. .The Panel approved the Change Report which was subsequently issued for voting on 20 April 2018. Voting will end on 14 May 2018. As DCP 268 is considered a Part 1 Matter, a Change Declaration was issued to the Authority on 16 May 2018. | N/A
STATUS - APPEAL
n/a | n/a | [10 empty] | N/A
STATUS - IMPLEMENTED
N/a | N/a | [10 empty] | N/A
STATUS - REJECTED
n/a | n/a | [10 empty] | N/A
STATUS - WITHDRAWN
Change Register - June 2019

## Status Change
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status Changed in the last month
DCP 341 | Removal of residual charging for storage facilities in the CDCM | This CP seeks to amend the application of residual charging in respect of storage generators in the CDCM. | CDCM | 1 | Dylan Townsend / John Lawton | Ankita Mehra | 2019-01-31 | 5 |  | 2021-04-01 | The Working Group had their first meeting on 01 April 2019 and are due to meet again on 12 April 2019 to review their legal text and modelling specification. The Secretariat is drafting a consultation document that will be reviewed during a meeting scheduled for 23 April 2019. The Working Group issued a consultation on 05 June 2019 for a period of three weeks. The working Group will next meet on 28 June 2019 to review the collated consultation responses and agree the next steps. | CONSULTATION
DCP 342 | Removal of residual charging for storage facilities in the EDCM | This CP seeks to amend the application of residual charging in respect of storage generators in the EDCM. | EDCM | 1 | Dylan Townsend / John Lawton | Ankita Mehra | 2019-01-31 | 5 |  | 2021-04-01 | The Working Group had their first meeting on 01 April 2019 and are due to meet again on 12 April 2019 to review their legal text and modelling specification. The Secretariat is drafting a consultation document that will be reviewed during a meeting scheduled for 23 April 2019. The Working Group issued a consultation on 05 June 2019 for a period of three weeks. The working Group will next meet on 28 June 2019 to review the collated consultation responses and agree the next steps. | CONSULTATION
DCP 326 | Introduction of Load Diversification Identifiers for Load Managed Areas | This Change Proposal seeks to introduce a simplified process for retaining the diversifation of demand in Load Managed Areas (LMA) during the replacement of RTS controlled metering equipment by Suppliers or post the decommissioning of the Radio Teleswitch System (RTS) | General | 1 | Richard Colwill / John Lawton | Deborah Duke | 2018-07-10 | 9 |  | 2020-02-01 | The Working Group released a second consultation on 2nd April to seek feedback on thiis alternative solution in order to decide which solution should be recommended. The deadline for responses was 30th April. The Working Group met on 7th May to review the consultation responses. Following this review the Working Group agreed to move forwrad with the proposed solution regarding the use of LLFC. The Working Group plans to submit the Chnage Report to the June Panel.. | CHANGE REPORT
DCP 346 | Amendment to Code of Practice Confirmed Theft Definition | To update and align the Theft Code of Practice schedules to ensure the consistency in the definition of Confirmed Theft and investigation processes. | Theft | 2 | Austin Gash/ | N/A | 2019-05-15 | 0 |  | 2019-11-07 | The Change Report was issued to the DCUSA Panel on 19 June 2019. | CHANGE REPORT
DCP 337 | Resolution of Housekeeping Items | This CP seeks to address and where appropriate to implement a number of housekeeping items that have been identified over a period of time. | General | 2 | Dylan Townsend | N/A | 2019-01-08 | 0 |  | 2019-06-27 | At their meeting in February, the Panel approved this CP and agreed for it to be progressed to the Change Report phase. The Change Report is being presented to the Panel during their meeting on 20 March 2019 and if approved, it will be issued to Parties for voting on 22 March 2019. Parties voted to accept the solution and implementation date and as such it will be implemented on 27 June 2019. | AWAITING IMPLEMENTATION
DCP 339 | Amend definition of ‘Other Charges' | This CP seeks to remove a contradiction between the electricity distribution licence and the DCUSA by removing any reference to DNO Party obligations to Last Resort Supply Payments. | General | 2 | Hollie Nicholls | N/A | 2019-02-01 | 0 |  | First release following approval | The Change Report was issued for voting on 22 March 2019 with a deadline of 12 April 2019 | AWAITING IMPLEMENTATION
Change Register - May 2019

## CP Work Plans
The DCUSA Panel is invited to:
Change Proposal | Secretariat | CP Title | Change Report Due Date | Status | Date of Last Agreed Work Plans | Note the Change Proposal Status
DCP 266 | Dylan | The calculation and application of IDNO discounts | 2019-07-10 |  | 2019-03-20 | Note the Change Proposal Activity
DCP 325 | Hollie | Reviewing the requirements of Sections 35A ('Provision of Cost Information'), 35B ('Production of the Annual Review Pack'), Schedule 15 ('Cost Information Table') and Schedule 20 ('Production of the Annual Review Pack') | 2019-07-10 |  | 2018-09-19 | Approve the Extensions to the Change Proposal Assessment Process as detailed in the attached Work Plans
DCP 326 | Richard | Introduction of Load Diversification Identifiers for Load Managed Areas | 2019-06-12 | Change Report being presented to the Panel at June meeting | 2019-03-20 | Approve the Extensions to the DCP 328, DCP 343 and DCP 344 Work Plans
DCP 328 | Richard | Use of system charging for private networks with competition in supply | 2019-06-12 | Work Plan Due | 2019-03-20
DCP 329 | Richard | Amend Requirements for Emergency De-energisation in Schedule 2B - National Terms of Connection | 2019-07-12 |  | 2019-05-15
DCP 332 / 333 | Huw | Appropriate treatment and allocation of Last Resort Supply Payment claim costs/ Appropriate treatment and allocation of eligible use of system bad debt costs | 2019-06-12 | Work Plan Due (meeting to agree updated version was after paper day) will be submitted in July) | 2019-02-20
DCP 336 | Hollie | Rota Disconnections and the publication of data by Nominated Central Source | 2019-07-10 |  | 2019-04-17
DCP 340 | Huw | Notice period required to recover approved last resort supply payment claims which breach the materiality threshold | 2019-06-12 | Work Plan Due (meeting to agree updated version was after paper day) will be submitted in July) | 2019-04-17
DCP 341 /342 | Dylan | Removal of residual charging for storage facilities in the CDCM / Removal of residual charging for storage facilities in the EDCM | 2019-07-10 |  | 2019-04-17
DCP 343 | Hollie | Use of a nominated calculation agent for the calculation of the LV mains split | 2019-06-12 | Work Plan Due | 2019-04-17
DCP 344 | Richard | Solutions for a new approach to billing and remittance |  | Work Plan Due
DCP 345 | Hollie | Sandbox Application |  | Work Plan Due (after first meeting)
CP Work Plans

## Legal Text Overlap
YES
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17
YES
|  | PROGRESSING THROUGH CHANGE PROCESS (LEGAL TEXT TO BE BASELINED AGAINST 01/04/2020 PRE-RELEASE + DCP 268) | [8 empty] | OTHER | OTHER | AWAITING (01/04/2020 | IMPLEMENTATION PRE-RELEASE) | AWAITING IMPLEMENTATION (01/04/2021)
|  | DCP 343 | DCP 342 | DCP 341 | DCP 333 (Option D) | DCP 333 (Option C) | DCP 332 | DCP 325 | DCP 313 | DCP 266 | DCP 337 | DCP 334 | DCP 311 | DCP 306 | DCP 268
|  | Next Scheduled | 2021-04-01 | 2021-04-01 | Next Scheduled | Next Scheduled | Next Scheduled | Next Scheduled | 2021-04-01 | 2021-04-01 | 2019-06-27 | 2019-06-27 | 2020-04-01 | 2020-04-01 | 2021-04-01 |  | NOTES TO ASSIST
Schedules | Paragraph Number | Definition | Definition | Definition | Definition | Definition | Definition | Definition | Awaiting Authority Consent | Definition | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Number of CPs Impacting Paragraph
Schedule 15 | Table 1 | [6 empty] | YES |  |  |  | YES |  |  |  | 2
Schedule 15 | Table 2 | [6 empty] | YES | [7 empty] | 1
Schedule 15 | Table 3 | [6 empty] | YES | [7 empty] | 1
0
Schedule 16 | Introduction | [14 empty] | 0
Schedule 16 | 1 | [14 empty] | 0
Schedule 16 | 2 | [14 empty] | 0
Schedule 16 | 3 |  |  | YES | YES | YES | YES |  |  | YES |  |  |  |  | YES | 6
Schedule 16 | 4 | [14 empty] | 0
YES Column1: Schedule 16; YES Column2: 5; YES Column17: 0 | DCP 332/333 amends the diagram
Schedule 16 | 6 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 16 | 7 | [14 empty] | 0
Schedule 16 | 8 | [14 empty] | 0
Schedule 16 | 9 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 16 | 10 | [14 empty] | 0
YES Column1: Schedule 16; YES Column2: 11; YES Column17: 0 | DCP 268 amends the table below the paragraph
Schedule 16 | 12 | [13 empty] | YES | 1
Schedule 16 | 13 | [14 empty] | 0
Schedule 16 | 14 | [14 empty] | 0
Schedule 16 | 15 | [14 empty] | 0
Schedule 16 | 16 | [14 empty] | 0
Schedule 16 | 17 | [14 empty] | 0
Schedule 16 | 18 | [14 empty] | 0
Schedule 16 | 19 | [14 empty] | 0
Schedule 16 | 20 | [14 empty] | 0
Schedule 16 | 21 | [14 empty] | 0
Schedule 16 | 22 | [14 empty] | 0
Schedule 16 | 23 | [14 empty] | 0
Schedule 16 | 24 | [14 empty] | 0
Schedule 16 | 25 | [14 empty] | 0
Schedule 16 | 26 | [14 empty] | 0
Schedule 16 | 27 | [14 empty] | 0
Schedule 16 | 28 | [14 empty] | 0
YES Column1: Schedule 16; YES Column2: 29; YES Column17: 0 | Addition of 30A and 30 B
Schedule 16 | 30 | [14 empty] | 0
Schedule 16 | 31 | [14 empty] | 0
Schedule 16 | 32 | [14 empty] | 0
Schedule 16 | 33 | [14 empty] | 0
Schedule 16 | 34 |  |  | YES | [11 empty] | 1
Schedule 16 | 35 | [14 empty] | 0
Schedule 16 | 36 | [14 empty] | 0
Schedule 16 | 37 | [14 empty] | 0
Schedule 16 | 38 | [14 empty] | 0
Schedule 16 | 39 | [14 empty] | 0
Schedule 16 | 40 | [13 empty] | YES | 1
Schedule 16 | 41 | [14 empty] | 0
Schedule 16 | 41A | [14 empty] | 0
Schedule 16 | 41B | [14 empty] | 0
Schedule 16 | 42 |  |  | YES | [10 empty] | YES | 2
Schedule 16 | 42A | [14 empty] | 0
Schedule 16 | 43 | [13 empty] | YES | 1
Schedule 16 | 44 | [13 empty] | YES | 1
Schedule 16 | 45 | [13 empty] | YES | 1
Schedule 16 | 46 | [14 empty] | 0
Schedule 16 | 47 | [14 empty] | 0
Schedule 16 | 48 | [14 empty] | 0
Schedule 16 | 49 | [14 empty] | 0
Schedule 16 | 50 | [14 empty] | 0
Schedule 16 | 51 | [14 empty] | 0
YES Column1: Schedule 16; YES Column2: 52; YES Column11: YES; YES Column17: 1 | DCP 268 introduces Clause 52A
Schedule 16 | 52A | [13 empty] | YES | 1
Schedule 16 | 53 | [14 empty] | 0
Schedule 16 | 54 | [14 empty] | 0
Schedule 16 | 55 | [14 empty] | 0
Schedule 16 | 56 | [14 empty] | 0
Schedule 16 | 57 | [14 empty] | 0
Schedule 16 | 58 | [14 empty] | 0
Schedule 16 | 59 | [14 empty] | 0
Schedule 16 | 60 | [14 empty] | 0
Schedule 16 | 61 | [14 empty] | 0
Schedule 16 | 62 | [14 empty] | 0
Schedule 16 | 63 | [14 empty] | 0
Schedule 16 | 64 | [14 empty] | 0
Schedule 16 | 65 | [14 empty] | 0
Schedule 16 | 66 | [14 empty] | 0
Schedule 16 | 67 | [14 empty] | 0
Schedule 16 | 68 | [13 empty] | YES | 1
Schedule 16 | 69 | [14 empty] | 0
Schedule 16 | 70 |  |  | YES | [11 empty] | 1
Schedule 16 | 71 | [14 empty] | 0
Schedule 16 | 72 | [14 empty] | 0
Schedule 16 | 72A | [13 empty] | YES | 1
Schedule 16 | 73 | [14 empty] | 0
Schedule 16 | 74 |  |  | YES | [10 empty] | YES | 2
Schedule 16 | 75 | [14 empty] | 0
Schedule 16 | 76 | [14 empty] | 0
Schedule 16 | 77 | [14 empty] | 0
Schedule 16 | 78 | [14 empty] | 0
Schedule 16 | 79 | [14 empty] | 0
Schedule 16 | 80 | [13 empty] | YES | 1
Schedule 16 | 81 |  |  | YES | [10 empty] | YES | 2
Schedule 16 | 82 | [14 empty] | 0
Schedule 16 | 83 | [13 empty] | YES | 1
Schedule 16 | 84 | [13 empty] | YES | 1
Schedule 16 | 85 | [14 empty] | 0
Schedule 16 | 86 | [14 empty] | 0
Schedule 16 | 87 | [14 empty] | 0
Schedule 16 | 88 |  |  | YES | [11 empty] | 1
Schedule 16 | 89 | [14 empty] | 0
Schedule 16 | 90 | [14 empty] | 0
Schedule 16 | 91 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 16 | 92 |  |  | YES | [11 empty] | 1
Schedule 16 | 93 | [14 empty] | 0
Schedule 16 | 94 | [14 empty] | 0
Schedule 16 | 95 | [14 empty] | 0
Schedule 16 | 96 | [14 empty] | 0
Schedule 16 | 97 | [14 empty] | 0
Schedule 16 | 98 | [14 empty] | 0
Schedule 16 | 99 | [14 empty] | 0
Schedule 16 | 100 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 16 | 101 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 16 | 102 | [14 empty] | 0
Schedule 16 | 102A | [14 empty] | 0
Schedule 16 | 102B | [14 empty] | 0
Schedule 16 | 103 | [14 empty] | 0
Schedule 16 | 104 | [14 empty] | 0
Schedule 16 | 105 | [14 empty] | 0
Schedule 16 | 106 | [14 empty] | 0
Schedule 16 | 107 | [14 empty] | 0
Schedule 16 | 108 | [14 empty] | 0
Schedule 16 | 108A | [14 empty] | 0
Schedule 16 | 109 | [14 empty] | 0
Schedule 16 | 110 | [14 empty] | 0
Schedule 16 | 111 | [14 empty] | 0
Schedule 16 | 112 | [14 empty] | 0
Schedule 16 | 112A | [14 empty] | 0
Schedule 16 | 113 | [14 empty] | 0
Schedule 16 | 113A | [14 empty] | 0
Schedule 16 | 113B | [14 empty] | 0
Schedule 16 | 113C | [14 empty] | 0
Schedule 16 | 113D | [14 empty] | 0
Schedule 16 | 113E | [14 empty] | 0
Schedule 16 | 114 | [14 empty] | 0
Schedule 16 | 115 | [14 empty] | 0
Schedule 16 | 116 | [14 empty] | 0
Schedule 16 | 117 | [14 empty] | 0
Schedule 16 | 118 | [14 empty] | 0
Schedule 16 | 119 | [14 empty] | 0
Schedule 16 | 120 | [14 empty] | 0
Schedule 16 | 121 | [14 empty] | 0
Schedule 16 | 122 | [14 empty] | 0
Schedule 16 | 123 | [14 empty] | 0
Schedule 16 | 124 | [14 empty] | 0
Schedule 16 | 125 | [14 empty] | 0
Schedule 16 | 126 | [13 empty] | YES | 1
Schedule 16 | 127 | [13 empty] | YES | 1
Schedule 16 | 128 | [13 empty] | YES | 1
Schedule 16 | 129 | [13 empty] | YES | 1
Schedule 16 | 130 | [13 empty] | YES | 1
Schedule 16 | 131 | [13 empty] | YES | 1
Schedule 16 | 132 | [13 empty] | YES | 1
Schedule 16 | 132A | [13 empty] | YES | 1
YES Column1: Schedule 16; YES Column2: 132B; YES Column16: YES; YES Column17: 1 | DCP 268 introduces Clause 132C
YES Column1: Schedule 16; YES Column2: 132C; YES Column16: YES; YES Column17: 1 | DCP 268 introduces Clause 132D
Schedule 16 | 132D | [13 empty] | YES | 1
Schedule 16 | 133 | [13 empty] | YES | 1
Schedule 16 | 134 | [14 empty] | 0
Schedule 16 | 135 | [13 empty] | YES | 1
Schedule 16 | 135A |  |  | YES | [10 empty] | YES | 2
Schedule 16 | 135B | [13 empty] | YES | 1
Schedule 16 | 136 | [13 empty] | YES | 1
Schedule 16 | 137 | [14 empty] | 0
Schedule 16 | 138 | [14 empty] | 0
Schedule 16 | 139 | [14 empty] | 0
Schedule 16 | 140 | [14 empty] | 0
Schedule 16 | 140A | [13 empty] | YES | 1
Schedule 16 | 140B | [13 empty] | YES | 1
Schedule 16 | 140C | [13 empty] | YES | 1
Schedule 16 | 140D | [13 empty] | YES | 1
YES Column1: Schedule 16; YES Column2: 140E; YES Column16: YES; YES Column17: 1 | (DCP 268 amends table 5)
Schedule 16 | 141 |  |  | YES | [10 empty] | YES | 2
Schedule 16 | 142 | [13 empty] | YES | 1
Schedule 16 | 143 | [13 empty] | YES | 1
Schedule 16 | 144 | [13 empty] | YES | 1
Schedule 16 | 145 | [13 empty] | YES | 1
Schedule 16 | 146 | [13 empty] | YES | 1
Schedule 16 | 147 |  |  | YES | [10 empty] | YES | 2
Schedule 16 | 148 | [14 empty] | 0
Schedule 16 | 149 | [14 empty] | 0
Schedule 16 | 150 | [14 empty] | 0
Schedule 16 | 151 | [14 empty] | 0
Schedule 16 | 152 | [14 empty] | 0
Schedule 16 | 153 | [14 empty] | 0
Schedule 16 | 154 | [14 empty] | 0
Schedule 16 | 155 | [14 empty] | 0
Schedule 16 | 156 | [14 empty] | 0
Schedule 16 | 157 | [14 empty] | 0
Schedule 16 | 158 | [14 empty] | 0
Schedule 16 | 159 | [14 empty] | 0
Schedule 16 | 160 | [14 empty] | 0
Schedule 16 | 161 | [14 empty] | 0
Schedule 16 | 162 | [14 empty] | 0
Schedule 16 | 163 | [14 empty] | 0
Schedule 16 | 164 | [14 empty] | 0
Schedule 16 | 165 | [14 empty] | 0
Schedule 16 | 166 | [14 empty] | 0
Schedule 16 | 167 | [14 empty] | 0
Schedule 16 | 168 | [14 empty] | 0
Schedule 16 | 169 | [14 empty] | 0
Schedule 16 | 170 | [14 empty] | 0
Schedule 16 | 171 | [14 empty] | 0
Schedule 16 | 172 | [14 empty] | 0
Schedule 16 | 173 | [14 empty] | 0
Schedule 16 | 174 | [14 empty] | 0
Schedule 16 | 175 | [14 empty] | 0
Schedule 16 | 176 | [14 empty] | 0
Schedule 16 | 177 | [14 empty] | 0
Schedule 16 | Glossary |  |  | YES | YES | YES | YES |  |  |  | YES |  |  |  | YES | 6
0
Schedule 17 | Introduction |  | YES | [12 empty] | 1
Schedule 17 | 1 | [14 empty] | 0
Schedule 17 | 1.1 | [14 empty] | 0
Schedule 17 | 1.2 | [14 empty] | 0
Schedule 17 | 1.3 |  | YES |  | YES | YES | YES | [7 empty] | YES | 5
Schedule 17 | 1.4 | [14 empty] | 0
Schedule 17 | 1.5 | [14 empty] | 0
Schedule 17 | 1.6 | [14 empty] | 0
Schedule 17 | 1.7 | [14 empty] | 0
YES Column1: Schedule 17; YES Column2: 1.8; YES Column17: 0 | DCP 332/333 amends the diagram
Schedule 17 | 1.9 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 17 | 2 | [14 empty] | 0
Schedule 17 | 2.1 | [14 empty] | 0
Schedule 17 | 2.2 | [14 empty] | 0
Schedule 17 | 2.3 | [14 empty] | 0
Schedule 17 | 2.4 | [14 empty] | 0
Schedule 17 | 2.5 | [14 empty] | 0
Schedule 17 | 2.6 | [14 empty] | 0
Schedule 17 | 2.7 | [14 empty] | 0
Schedule 17 | 2.8 | [14 empty] | 0
Schedule 17 | 2.9 | [14 empty] | 0
Schedule 17 | 2.1 | [14 empty] | 0
Schedule 17 | 2.11 | [14 empty] | 0
Schedule 17 | 2.12 | [14 empty] | 0
Schedule 17 | 2.13 | [14 empty] | 0
Schedule 17 | 2.14 | [14 empty] | 0
Schedule 17 | 2.15 | [14 empty] | 0
Schedule 17 | 2.16 | [14 empty] | 0
Schedule 17 | 2.17 | [14 empty] | 0
Schedule 17 | 2.18 | [14 empty] | 0
Schedule 17 | 2.19 | [14 empty] | 0
Schedule 17 | 3 | [14 empty] | 0
Schedule 17 | 3.1 | [14 empty] | 0
Schedule 17 | 3.2 | [14 empty] | 0
Schedule 17 | 3.3 | [14 empty] | 0
Schedule 17 | 3.4 | [14 empty] | 0
Schedule 17 | 3.5 | [14 empty] | 0
Schedule 17 | 3.6 | [14 empty] | 0
Schedule 17 | 3.7 | [14 empty] | 0
Schedule 17 | 4 | [14 empty] | 0
Schedule 17 | 4.1 | [14 empty] | 0
Schedule 17 | 5 | [14 empty] | 0
Schedule 17 | 5.1 | [14 empty] | 0
Schedule 17 | 6 | [14 empty] | 0
Schedule 17 | 6.1 | [14 empty] | 0
YES Column1: Schedule 17; YES Column2: 6.2; YES Column17: 0 | (DCP 313 Option 1)
Schedule 17 | 6.3 | [7 empty] | YES | [6 empty] | 1
Schedule 17 | 7 | [14 empty] | 0
Schedule 17 | 7.1 | [14 empty] | 0
Schedule 17 | 8 | [14 empty] | 0
Schedule 17 | 8.1 | [14 empty] | 0
Schedule 17 | 8.2 | [14 empty] | 0
Schedule 17 | 8.3 | [14 empty] | 0
Schedule 17 | 8.4 | [14 empty] | 0
Schedule 17 | 9 | [14 empty] | 0
Schedule 17 | 9.1 | [14 empty] | 0
Schedule 17 | 9.2 | [14 empty] | 0
Schedule 17 | 9.3 | [14 empty] | 0
Schedule 17 | 10 | [14 empty] | 0
Schedule 17 | 10.1 | [14 empty] | 0
Schedule 17 | 10.2 | [14 empty] | 0
Schedule 17 | 10.3 | [14 empty] | 0
Schedule 17 | 10.4 | [14 empty] | 0
Schedule 17 | 11 | [14 empty] | 0
Schedule 17 | 11.1 | [14 empty] | 0
Schedule 17 | 12 | [14 empty] | 0
Schedule 17 | 12.1 | [14 empty] | 0
Schedule 17 | 12.2 | [14 empty] | 0
Schedule 17 | 12.3 | [14 empty] | 0
Schedule 17 | 13 | [14 empty] | 0
Schedule 17 | 13.1 | [14 empty] | 0
Schedule 17 | 13.2 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 17 | 13.3 | [14 empty] | 0
Schedule 17 | 13.4 | [14 empty] | 0
Schedule 17 | 14 | [14 empty] | 0
Schedule 17 | 14.1 | [14 empty] | 0
Schedule 17 | 14.2 | [14 empty] | 0
Schedule 17 | 14.3 | [14 empty] | 0
Schedule 17 | 14.4 | [14 empty] | 0
Schedule 17 | 14.5 | [14 empty] | 0
Schedule 17 | 15 | [14 empty] | 0
Schedule 17 | 15.1 | [14 empty] | 0
Schedule 17 | 15.2 | [14 empty] | 0
Schedule 17 | 15.3 | [14 empty] | 0
Schedule 17 | 15.4 | [14 empty] | 0
Schedule 17 | 15.5 | [14 empty] | 0
Schedule 17 | 15.6 | [14 empty] | 0
Schedule 17 | 15.7 | [14 empty] | 0
Schedule 17 | 15.8 | [14 empty] | 0
Schedule 17 | 15.9 | [14 empty] | 0
Schedule 17 | 15.1 | [14 empty] | 0
Schedule 17 | 15.11 | [14 empty] | 0
Schedule 17 | 15.12 | [14 empty] | 0
Schedule 17 | 15.15 | [14 empty] | 0
Schedule 17 | 16 | [14 empty] | 0
Schedule 17 | 16.1 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 17 | 16.2 | [14 empty] | 0
Schedule 17 | 16.3 | [14 empty] | 0
Schedule 17 | 16.4 | [14 empty] | 0
Schedule 17 | 16.5 | [14 empty] | 0
Schedule 17 | 16.6 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 17 | 16.7 | [14 empty] | 0
Schedule 17 | 16.8 | [14 empty] | 0
Schedule 17 | 16.9 | [14 empty] | 0
Schedule 17 | 16.1 | [14 empty] | 0
Schedule 17 | 17 | [14 empty] | 0
Schedule 17 | 17.1 | [14 empty] | 0
Schedule 17 | 17.2 | [14 empty] | 0
Schedule 17 | 17.3 | [14 empty] | 0
Schedule 17 | 18 | [14 empty] | 0
Schedule 17 | 18.1 | [14 empty] | 0
Schedule 17 | 18.2 | [14 empty] | 0
Schedule 17 | 18.3 | [14 empty] | 0
Schedule 17 | 18.4 | [14 empty] | 0
Schedule 17 | 18.5 | [11 empty] | YES |  |  | 1
Schedule 17 | 18.6 | [11 empty] | YES |  |  | 1
Schedule 17 | 18.7 | [11 empty] | YES |  |  | 1
Schedule 17 | 18.8 | [11 empty] | YES |  |  | 1
Schedule 17 | 18.9 | [14 empty] | 0
Schedule 17 | 18.1 | [14 empty] | 0
Schedule 17 | 18.11 | [14 empty] | 0
Schedule 17 | 18.12 | [14 empty] | 0
Schedule 17 | 18.13 | [14 empty] | 0
Schedule 17 | 18.14 | [14 empty] | 0
Schedule 17 | 18.15 | [14 empty] | 0
Schedule 17 | 18.16 | [14 empty] | 0
Schedule 17 | 18.17 | [14 empty] | 0
Schedule 17 | 18.18 |  | YES | [12 empty] | 1
Schedule 17 | 18.19 |  | YES | [12 empty] | 1
Schedule 17 | 18.2 |  | YES | [12 empty] | 1
Schedule 17 | 18.21 |  | YES | [12 empty] | 1
Schedule 17 | 19 | [14 empty] | 0
Schedule 17 | 19.1 | [14 empty] | 0
Schedule 17 | 19.2 | [14 empty] | 0
Schedule 17 | 19.3 | [14 empty] | 0
Schedule 17 | 19.4 | [14 empty] | 0
Schedule 17 | 19.5 | [14 empty] | 0
Schedule 17 | 19.6 | [14 empty] | 0
Schedule 17 | 19.7 | [14 empty] | 0
Schedule 17 | 19.8 | [14 empty] | 0
Schedule 17 | 19.9 | [14 empty] | 0
Schedule 17 | 19.1 | [14 empty] | 0
Schedule 17 | 19.11 | [14 empty] | 0
Schedule 17 | 20 | [14 empty] | 0
Schedule 17 | 20.1 | [14 empty] | 0
Schedule 17 | 20.2 | [14 empty] | 0
Schedule 17 | 20.3 | [14 empty] | 0
Schedule 17 | 20.4 | [14 empty] | 0
Schedule 17 | 20.5 | [14 empty] | 0
Schedule 17 | 20.6 | [14 empty] | 0
Schedule 17 | 20.7 | [14 empty] | 0
Schedule 17 | 20.8 | [14 empty] | 0
Schedule 17 | 20.9 | [14 empty] | 0
Schedule 17 | 21 | [14 empty] | 0
Schedule 17 | 21.1 | [14 empty] | 0
Schedule 17 | 21.2 | [14 empty] | 0
Schedule 17 | 22 | [14 empty] | 0
Schedule 17 | 22.1 | [14 empty] | 0
Schedule 17 | 22.2 | [14 empty] | 0
Schedule 17 | 22.3 | [14 empty] | 0
Schedule 17 | 22.4 | [14 empty] | 0
Schedule 17 | 23 | [14 empty] | 0
Schedule 17 | 23.1 | [14 empty] | 0
Schedule 17 | 23.2 | [14 empty] | 0
Schedule 17 | 23.3 | [14 empty] | 0
Schedule 17 | 23.4 | [14 empty] | 0
Schedule 17 | 23.5 | [14 empty] | 0
Schedule 17 | 24 | [14 empty] | 0
Schedule 17 | 24.1 |  |  |  | YES | YES | YES |  |  |  | YES |  |  |  |  | 4
Schedule 17 | 24.2 | [14 empty] | 0
Schedule 17 | 24.3 | [14 empty] | 0
Schedule 17 | 24.4 | [14 empty] | 0
Schedule 17 | 24.5 | [14 empty] | 0
Schedule 17 | 24.6 | [14 empty] | 0
Schedule 17 | 24.7 | [14 empty] | 0
Schedule 17 | 24.8 | [14 empty] | 0
Schedule 17 | 24.9 | [14 empty] | 0
Schedule 17 | 25 | [14 empty] | 0
Schedule 17 | 25.1 | [14 empty] | 0
Schedule 17 | 25.2 | [14 empty] | 0
Schedule 17 | 25.3 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 17 | 25.4 | [14 empty] | 0
Schedule 17 | 25.5 | [14 empty] | 0
Schedule 17 | 25.6 | [14 empty] | 0
Schedule 17 | 25.6A | [14 empty] | 0
Schedule 17 | 25.6B. | [14 empty] | 0
Schedule 17 | 25.7 | [14 empty] | 0
Schedule 17 | 25.8 | [14 empty] | 0
Schedule 17 | 25.9 | [14 empty] | 0
Schedule 17 | 25.1 | [14 empty] | 0
Schedule 17 | 25.11 | [14 empty] | 0
Schedule 17 | 25.11A | [14 empty] | 0
Schedule 17 | 25.12 | [14 empty] | 0
Schedule 17 | 25.12A | [14 empty] | 0
Schedule 17 | 25.13 | [14 empty] | 0
Schedule 17 | 25.14 | [14 empty] | 0
Schedule 17 | 25.14A | [14 empty] | 0
Schedule 17 | 25.14B | [14 empty] | 0
Schedule 17 | 25.14C | [14 empty] | 0
Schedule 17 | 25.14D | [14 empty] | 0
Schedule 17 | 25.15 | [14 empty] | 0
Schedule 17 | 25.15A | [14 empty] | 0
Schedule 17 | 25.16 | [14 empty] | 0
Schedule 17 | 25.17 | [14 empty] | 0
Schedule 17 | 25.18 | [14 empty] | 0
Schedule 17 | 25.19 | [14 empty] | 0
Schedule 17 | 26 | [14 empty] | 0
Schedule 17 | 26.1 | [14 empty] | 0
Schedule 17 | 26.2 | [14 empty] | 0
Schedule 17 | 26.3 | [14 empty] | 0
Schedule 17 | 26.4 | [14 empty] | 0
Schedule 17 | 26.5 | [14 empty] | 0
Schedule 17 | 26.6 | [14 empty] | 0
Schedule 17 | 26.7 | [14 empty] | 0
Schedule 17 | 26.8 | [14 empty] | 0
Schedule 17 | 26.9 | [14 empty] | 0
Schedule 17 | 26.1 | [14 empty] | 0
Schedule 17 | 26.11 | [14 empty] | 0
Schedule 17 | 27 | [14 empty] | 0
Schedule 17 | 27.1 | [14 empty] | 0
Schedule 17 | 27.2 | [14 empty] | 0
Schedule 17 | 27.3 | [14 empty] | 0
Schedule 17 | 27.4 | [14 empty] | 0
Schedule 17 | 28 | [14 empty] | 0
Schedule 17 | 28.1 | [14 empty] | 0
Schedule 17 | 28.2 | [14 empty] | 0
Schedule 17 | 29 | [14 empty] | 0
Schedule 17 | 29.1 | [14 empty] | 0
Schedule 17 | 29.2 | [14 empty] | 0
Schedule 17 | 29.3 | [14 empty] | 0
Schedule 17 | 29.4 | [14 empty] | 0
Schedule 17 | 30 | [14 empty] | 0
Schedule 17 | 30.1 | [14 empty] | 0
Schedule 17 | 30.2 | [14 empty] | 0
Schedule 17 | 30.3 | [14 empty] | 0
Schedule 17 | 30.4 | [14 empty] | 0
Schedule 17 | 30.5 | [14 empty] | 0
Schedule 17 | 30.6 | [14 empty] | 0
Schedule 17 | 30.7 | [14 empty] | 0
Schedule 17 | 30.8 | [14 empty] | 0
Schedule 17 | 30.9 | [14 empty] | 0
Schedule 17 | 30.1 | [14 empty] | 0
Schedule 17 | 30.11 | [14 empty] | 0
Schedule 17: Annex 1 | 1 | [14 empty] | 0
Schedule 17: Annex 1 | 2 | [14 empty] | 0
Schedule 17: Annex 1 | 2.1 | [14 empty] | 0
Schedule 17: Annex 1 | 2.2 | [14 empty] | 0
Schedule 17: Annex 1 | 2.3 | [14 empty] | 0
Schedule 17: Annex 1 | 2.4 | [14 empty] | 0
Schedule 17: Annex 1 | 2.5 | [14 empty] | 0
Schedule 17: Annex 1 | 3 | [14 empty] | 0
Schedule 17: Annex 1 | Definitions | [14 empty] | 0
Schedule 17: Annex 1 | 4 | [14 empty] | 0
Schedule 17: Annex 1 | 4.1 | [14 empty] | 0
Schedule 17: Annex 1 | 4.2 | [14 empty] | 0
Schedule 17: Annex 1 | 4.3 | [14 empty] | 0
Schedule 17: Annex 1 | 4.4 | [14 empty] | 0
Schedule 17: Annex 1 | 4.5 | [14 empty] | 0
Schedule 17: Annex 1 | 4.6 | [14 empty] | 0
Schedule 17: Annex 1 | 4.7 | [14 empty] | 0
Schedule 17: Annex 1 | 4.8 | [14 empty] | 0
Schedule 17: Annex 1 | 4.9 | [14 empty] | 0
Schedule 17: Annex 1 | 4.1 | [14 empty] | 0
Schedule 17: Annex 1 | 5 | [14 empty] | 0
Schedule 17: Annex 1 | 5.1 | [14 empty] | 0
Schedule 17: Annex 1 | 5.2 | [14 empty] | 0
Schedule 17: Annex 1 | 5.3 | [14 empty] | 0
Schedule 17: Annex 1 | 5.4 | [14 empty] | 0
Schedule 17: Annex 1 | 5.5 | [14 empty] | 0
Schedule 17: Annex 1 | 5.6 | [14 empty] | 0
Schedule 17: Annex 1 | 5.7 | [14 empty] | 0
Schedule 17: Annex 1 | 5.8 | [14 empty] | 0
Schedule 17: Annex 1 | 5.9 | [14 empty] | 0
Schedule 17: Annex 1 | 5.1 | [14 empty] | 0
Schedule 17: Annex 1 | 5.11 | [14 empty] | 0
Schedule 17: Annex 1 | 5.12 | [14 empty] | 0
Schedule 17: Annex 1 | 5.13 | [14 empty] | 0
Schedule 17: Annex 1 | 5.14 | [14 empty] | 0
Schedule 17: Annex 1 | 5.15 | [14 empty] | 0
Schedule 17: Annex 1 | 5.16 | [14 empty] | 0
Schedule 17: Annex 1 | 5.17 | [14 empty] | 0
Schedule 17: Annex 1 | 5.18 | [14 empty] | 0
Schedule 17: Annex 1 | 5.19 | [14 empty] | 0
Schedule 17: Annex 1 | 5.2 | [14 empty] | 0
Schedule 17: Annex 1 | 5.21 | [14 empty] | 0
Schedule 17: Annex 1 | 5.22 | [14 empty] | 0
Schedule 17: Annex 1 | 5.23 | [14 empty] | 0
Schedule 17: Annex 1 | 5.24 | [14 empty] | 0
Schedule 17: Annex 1 | 5.25 | [14 empty] | 0
Schedule 17: Annex 1 | 5.26 | [14 empty] | 0
Schedule 17: Annex 1 | 5.27 | [14 empty] | 0
Schedule 17: Annex 1 | 5.28 | [14 empty] | 0
Schedule 17: Annex 1 | 5.29 | [14 empty] | 0
Schedule 17: Annex 1 | 5.3 | [14 empty] | 0
Schedule 17: Annex 1 | 5.31 | [14 empty] | 0
Schedule 17: Annex 1 | 5.32 | [14 empty] | 0
Schedule 17: Annex 1 | 5.33 | [14 empty] | 0
Schedule 17: Annex 1 | 5.34 | [14 empty] | 0
Schedule 17: Annex 1 | 5.35 | [14 empty] | 0
Schedule 17: Annex 1 | 5.36 | [14 empty] | 0
Schedule 17: Annex 1 | 5.37 | [14 empty] | 0
Schedule 17: Annex 1 | 5.38 | [14 empty] | 0
Schedule 17: Annex 1 | 5.39 | [14 empty] | 0
Schedule 17: Annex 1 | 5.4 | [14 empty] | 0
Schedule 17: Annex 1 | 5.41 | [14 empty] | 0
Schedule 17: Annex 1 | 5.42 | [14 empty] | 0
Schedule 17: Annex 1 | 5.43 | [14 empty] | 0
Schedule 17: Annex 1 | 5.44 | [14 empty] | 0
Schedule 17: Annex 1 | 5.45 | [14 empty] | 0
Schedule 17: Annex 1 | 6 | [14 empty] | 0
Schedule 17: Annex 1 | 6.1 | [14 empty] | 0
Schedule 17: Annex 1 | 6.2 | [14 empty] | 0
Schedule 17: Annex 1 | 6.3 | [14 empty] | 0
Schedule 17: Annex 1 | 6.4 | [14 empty] | 0
Schedule 17: Annex 1 | 6.5 | [14 empty] | 0
Schedule 17: Annex 1 | 6.6 | [14 empty] | 0
Schedule 17: Annex 1 | 6.7 | [14 empty] | 0
Schedule 17: Annex 1 | 6.8 | [14 empty] | 0
Schedule 17: Annex 1 | 7 | [14 empty] | 0
Schedule 17: Annex 1 | 7.1 | [14 empty] | 0
Schedule 17: Annex 1 | 7.2 | [14 empty] | 0
Schedule 17: Annex 1 | 7.3 | [14 empty] | 0
Schedule 17: Annex 1 | 7.4 | [14 empty] | 0
Schedule 17: Annex 1 | 7.5 | [14 empty] | 0
Schedule 17: Annex 1 | 7.6 | [14 empty] | 0
Schedule 17: Annex 1 | 7.7 | [14 empty] | 0
Schedule 17: Annex 1 | 7.8 | [14 empty] | 0
Schedule 17: Annex 1 | 8 | [14 empty] | 0
Schedule 17: Annex 1 | 8.1 | [14 empty] | 0
Schedule 17: Annex 1 | 8.2 | [14 empty] | 0
Schedule 17: Annex 1 | 8.3 | [14 empty] | 0
Schedule 17: Annex 1 | 8.4 | [14 empty] | 0
Schedule 17: Annex 1 | 9 | [14 empty] | 0
Schedule 17: Annex 1 | 9.1 | [14 empty] | 0
Schedule 17: Annex 1 | 9.2 | [14 empty] | 0
Schedule 17: Annex 1 | 9.3 | [14 empty] | 0
Schedule 17: Annex 1 | 9.4 | [14 empty] | 0
Schedule 17: Annex 1 | 9.5 | [14 empty] | 0
Schedule 17: Annex 1 | 9.6 | [14 empty] | 0
Schedule 17: Annex 1 | 9.7 | [14 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [14 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [14 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [14 empty] | 0
Schedule 17: Annex 1 | Attachment 3 | [14 empty] | 0
Schedule 17: Annex 2 | Annex 2 | [14 empty] | 0
0
Schedule 18 | Introduction |  | YES | [12 empty] | 1
Schedule 18 | 1 | [14 empty] | 0
Schedule 18 | 1.1 | [14 empty] | 0
Schedule 18 | 1.2 | [14 empty] | 0
Schedule 18 | 1.3 |  | YES |  | YES | YES | YES | [8 empty] | 4
Schedule 18 | 1.4 | [14 empty] | 0
Schedule 18 | 1.5 | [14 empty] | 0
Schedule 18 | 1.6 | [14 empty] | 0
Schedule 18 | 1.7 | [14 empty] | 0
YES Column1: Schedule 18; YES Column2: 1.8; YES Column17: 0 | DCP 332/333 amends the diagram
Schedule 18 | 1.9 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 18 | 2 | [14 empty] | 0
Schedule 18 | 2.1 | [14 empty] | 0
Schedule 18 | 2.2 | [14 empty] | 0
Schedule 18 | 2.3 | [14 empty] | 0
Schedule 18 | 2.4 | [14 empty] | 0
Schedule 18 | 2.5 | [14 empty] | 0
Schedule 18 | 2.6 | [14 empty] | 0
Schedule 18 | 2.7 | [14 empty] | 0
Schedule 18 | 2.8 | [14 empty] | 0
Schedule 18 | 2.9 | [14 empty] | 0
Schedule 18 | 2.1 | [14 empty] | 0
Schedule 18 | 2.11 | [14 empty] | 0
Schedule 18 | 2.12 | [14 empty] | 0
Schedule 18 | 2.13 | [14 empty] | 0
Schedule 18 | 2.14 | [14 empty] | 0
Schedule 18 | 2.15 | [14 empty] | 0
Schedule 18 | 2.16 | [14 empty] | 0
Schedule 18 | 2.17 | [14 empty] | 0
Schedule 18 | 2.18 | [14 empty] | 0
Schedule 18 | 2.19 | [14 empty] | 0
Schedule 18 | 2.2 | [14 empty] | 0
Schedule 18 | 2.21 | [14 empty] | 0
Schedule 18 | 2.22 | [14 empty] | 0
Schedule 18 | 2.23 | [14 empty] | 0
Schedule 18 | 2.24 | [14 empty] | 0
Schedule 18 | 2.25 | [14 empty] | 0
Schedule 18 | 2.26 | [14 empty] | 0
Schedule 18 | 2.27 | [14 empty] | 0
Schedule 18 | 2.28 | [14 empty] | 0
Schedule 18 | 2.29 | [14 empty] | 0
Schedule 18 | 2.3 | [14 empty] | 0
Schedule 18 | 3 | [14 empty] | 0
Schedule 18 | 3.1 | [14 empty] | 0
Schedule 18 | 3.2 | [14 empty] | 0
Schedule 18 | 3.3 | [14 empty] | 0
Schedule 18 | 3.4 | [14 empty] | 0
Schedule 18 | 3.5 | [14 empty] | 0
Schedule 18 | 3.6 | [14 empty] | 0
Schedule 18 | 3.7 | [14 empty] | 0
Schedule 18 | 4 | [14 empty] | 0
Schedule 18 | 4.1 | [14 empty] | 0
Schedule 18 | 5 | [14 empty] | 0
Schedule 18 | 5.1 | [14 empty] | 0
Schedule 18 | 6 | [14 empty] | 0
Schedule 18 | 6.1 | [14 empty] | 0
Schedule 18 | 6.2 | [14 empty] | 0
Schedule 18 | 6.3 | [14 empty] | 0
YES Column1: Schedule 18; YES Column2: 6.4; YES Column17: 0 | (DCP 313 Option 1)
Schedule 18 | 6.5 | [7 empty] | YES | [6 empty] | 1
Schedule 18 | 7 | [14 empty] | 0
Schedule 18 | 7.1 | [14 empty] | 0
Schedule 18 | 8 | [14 empty] | 0
Schedule 18 | 8.1 | [14 empty] | 0
Schedule 18 | 8.2 | [14 empty] | 0
Schedule 18 | 8.3 | [14 empty] | 0
Schedule 18 | 8.4 | [14 empty] | 0
Schedule 18 | 9 | [14 empty] | 0
Schedule 18 | 9.1 | [14 empty] | 0
Schedule 18 | 9.2 | [14 empty] | 0
Schedule 18 | 10 | [14 empty] | 0
Schedule 18 | 10.1 | [14 empty] | 0
Schedule 18 | 10.2 | [14 empty] | 0
Schedule 18 | 10.3 | [14 empty] | 0
Schedule 18 | 10.4 | [14 empty] | 0
Schedule 18 | 10.5 | [14 empty] | 0
Schedule 18 | 11 | [14 empty] | 0
Schedule 18 | 11.1 | [14 empty] | 0
Schedule 18 | 12 | [14 empty] | 0
Schedule 18 | 12.1 | [14 empty] | 0
Schedule 18 | 12.2 | [14 empty] | 0
Schedule 18 | 12.3 | [14 empty] | 0
Schedule 18 | 12.4 | [14 empty] | 0
Schedule 18 | 12.5 | [14 empty] | 0
Schedule 18 | 12.6 | [14 empty] | 0
Schedule 18 | 13 | [14 empty] | 0
Schedule 18 | 13.1 | [14 empty] | 0
Schedule 18 | 13.2 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 18 | 13.3 | [14 empty] | 0
Schedule 18 | 13.4 | [14 empty] | 0
Schedule 18 | 14 | [14 empty] | 0
Schedule 18 | 14.1 | [14 empty] | 0
Schedule 18 | 14.2 | [14 empty] | 0
Schedule 18 | 14.3 | [14 empty] | 0
Schedule 18 | 14.4 | [14 empty] | 0
Schedule 18 | 14.5 | [14 empty] | 0
Schedule 18 | 15 | [14 empty] | 0
Schedule 18 | 15.1 | [14 empty] | 0
Schedule 18 | 15.2 | [14 empty] | 0
Schedule 18 | 15.3 | [14 empty] | 0
Schedule 18 | 15.4 | [14 empty] | 0
Schedule 18 | 15.5 | [14 empty] | 0
Schedule 18 | 15.6 | [14 empty] | 0
Schedule 18 | 15.7 | [14 empty] | 0
Schedule 18 | 15.8 | [14 empty] | 0
Schedule 18 | 15.9 | [14 empty] | 0
Schedule 18 | 15.1 | [14 empty] | 0
Schedule 18 | 15.11 | [14 empty] | 0
Schedule 18 | 15.12 | [14 empty] | 0
Schedule 18 | 15.15 | [14 empty] | 0
Schedule 18 | 16 | [14 empty] | 0
Schedule 18 | 16.1 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 18 | 16.2 | [14 empty] | 0
Schedule 18 | 16.3 | [14 empty] | 0
Schedule 18 | 16.4 | [14 empty] | 0
Schedule 18 | 16.5 | [14 empty] | 0
Schedule 18 | 16.6 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 18 | 16.7 | [14 empty] | 0
Schedule 18 | 16.8 | [14 empty] | 0
Schedule 18 | 16.9 | [14 empty] | 0
Schedule 18 | 16.1 | [14 empty] | 0
Schedule 18 | 17 | [14 empty] | 0
Schedule 18 | 17.1 | [14 empty] | 0
Schedule 18 | 17.2 | [14 empty] | 0
Schedule 18 | 17.3 | [14 empty] | 0
Schedule 18 | 18 | [14 empty] | 0
Schedule 18 | 18.1 | [14 empty] | 0
Schedule 18 | 18.2 | [14 empty] | 0
Schedule 18 | 18.3 | [14 empty] | 0
Schedule 18 | 18.4 | [14 empty] | 0
Schedule 18 | 18.5 | [11 empty] | YES |  |  | 1
Schedule 18 | 18.6 | [11 empty] | YES |  |  | 1
Schedule 18 | 18.7 | [11 empty] | YES |  |  | 1
Schedule 18 | 18.8 | [11 empty] | YES |  |  | 1
Schedule 18 | 18.9 | [14 empty] | 0
Schedule 18 | 18.1 | [14 empty] | 0
Schedule 18 | 18.11 | [14 empty] | 0
Schedule 18 | 18.12 | [14 empty] | 0
Schedule 18 | 18.13 | [14 empty] | 0
Schedule 18 | 18.14 | [14 empty] | 0
Schedule 18 | 18.15 | [14 empty] | 0
Schedule 18 | 18.16 | [14 empty] | 0
Schedule 18 | 18.17 | [14 empty] | 0
Schedule 18 | 18.18 |  | YES | [12 empty] | 1
Schedule 18 | 18.19 |  | YES | [12 empty] | 1
Schedule 18 | 18.2 |  | YES | [12 empty] | 1
Schedule 18 | 18.21 |  | YES | [12 empty] | 1
Schedule 18 | 19 | [14 empty] | 0
Schedule 18 | 19.1 | [14 empty] | 0
Schedule 18 | 19.2 | [14 empty] | 0
Schedule 18 | 19.3 | [14 empty] | 0
Schedule 18 | 19.4 | [14 empty] | 0
Schedule 18 | 19.5 | [14 empty] | 0
Schedule 18 | 19.6 | [14 empty] | 0
Schedule 18 | 19.7 | [14 empty] | 0
Schedule 18 | 19.8 | [14 empty] | 0
Schedule 18 | 19.9 | [14 empty] | 0
Schedule 18 | 19.1 | [14 empty] | 0
Schedule 18 | 19.11 | [14 empty] | 0
Schedule 18 | 20 | [14 empty] | 0
Schedule 18 | 20.1 | [14 empty] | 0
Schedule 18 | 20.2 | [14 empty] | 0
Schedule 18 | 20.3 | [14 empty] | 0
Schedule 18 | 20.4 | [14 empty] | 0
Schedule 18 | 20.5 | [14 empty] | 0
Schedule 18 | 20.6 | [14 empty] | 0
Schedule 18 | 20.7 | [14 empty] | 0
Schedule 18 | 20.8 | [14 empty] | 0
Schedule 18 | 20.9 | [14 empty] | 0
Schedule 18 | 21 | [14 empty] | 0
Schedule 18 | 21.1 | [14 empty] | 0
Schedule 18 | 21.2 | [14 empty] | 0
Schedule 18 | 22 | [14 empty] | 0
Schedule 18 | 22.1 | [14 empty] | 0
Schedule 18 | 22.2 | [14 empty] | 0
Schedule 18 | 22.3 | [14 empty] | 0
Schedule 18 | 22.4 | [14 empty] | 0
Schedule 18 | 23 | [14 empty] | 0
Schedule 18 | 23.1 | [14 empty] | 0
Schedule 18 | 23.2 | [14 empty] | 0
Schedule 18 | 23.3 | [14 empty] | 0
Schedule 18 | 23.4 | [14 empty] | 0
Schedule 18 | 23.5 | [14 empty] | 0
Schedule 18 | 24 | [14 empty] | 0
Schedule 18 | 24.1 |  |  |  | YES | YES | YES |  |  |  | YES |  |  |  |  | 4
Schedule 18 | 24.2 | [14 empty] | 0
Schedule 18 | 24.3 | [14 empty] | 0
Schedule 18 | 24.4 | [14 empty] | 0
Schedule 18 | 24.5 | [14 empty] | 0
Schedule 18 | 24.6 | [14 empty] | 0
Schedule 18 | 24.7 | [14 empty] | 0
Schedule 18 | 24.8 | [14 empty] | 0
Schedule 18 | 24.9 | [14 empty] | 0
Schedule 18 | 25 | [14 empty] | 0
Schedule 18 | 25.1 | [14 empty] | 0
Schedule 18 | 25.2 | [14 empty] | 0
Schedule 18 | 25.3 |  |  |  | YES | YES | YES | [8 empty] | 3
Schedule 18 | 25.4 | [14 empty] | 0
Schedule 18 | 25.5 | [14 empty] | 0
Schedule 18 | 25.6 | [14 empty] | 0
Schedule 18 | 25.6A | [14 empty] | 0
Schedule 18 | 25.6B. | [14 empty] | 0
Schedule 18 | 25.7 | [14 empty] | 0
Schedule 18 | 25.8 | [14 empty] | 0
Schedule 18 | 25.9 | [14 empty] | 0
Schedule 18 | 25.1 | [14 empty] | 0
Schedule 18 | 25.11 | [14 empty] | 0
Schedule 18 | 25.11A | [14 empty] | 0
Schedule 18 | 25.12 | [14 empty] | 0
Schedule 18 | 25.12A | [14 empty] | 0
Schedule 18 | 25.13 | [14 empty] | 0
Schedule 18 | 25.14 | [14 empty] | 0
Schedule 18 | 25.14A | [14 empty] | 0
Schedule 18 | 25.14B | [14 empty] | 0
Schedule 18 | 25.14C | [14 empty] | 0
Schedule 18 | 25.14D | [14 empty] | 0
Schedule 18 | 25.15 | [14 empty] | 0
Schedule 18 | 25.15A | [14 empty] | 0
Schedule 18 | 25.16 | [14 empty] | 0
Schedule 18 | 25.17 | [14 empty] | 0
Schedule 18 | 25.18 | [14 empty] | 0
Schedule 18 | 25.19 | [14 empty] | 0
Schedule 18 | 26 | [14 empty] | 0
Schedule 18 | 26.1 | [14 empty] | 0
Schedule 18 | 26.2 | [14 empty] | 0
Schedule 18 | 26.3 | [14 empty] | 0
Schedule 18 | 26.4 | [14 empty] | 0
Schedule 18 | 26.5 | [14 empty] | 0
Schedule 18 | 26.6 | [14 empty] | 0
Schedule 18 | 26.7 | [14 empty] | 0
Schedule 18 | 26.8 | [14 empty] | 0
Schedule 18 | 26.9 | [14 empty] | 0
Schedule 18 | 26.1 | [14 empty] | 0
Schedule 18 | 26.11 | [14 empty] | 0
Schedule 18 | 27 | [14 empty] | 0
Schedule 18 | 27.1 | [14 empty] | 0
Schedule 18 | 27.2 | [14 empty] | 0
Schedule 18 | 27.3 | [14 empty] | 0
Schedule 18 | 27.4 | [14 empty] | 0
Schedule 18 | 28 | [14 empty] | 0
Schedule 18 | 28.1 | [14 empty] | 0
Schedule 18 | 28.2 | [14 empty] | 0
Schedule 18 | 29 | [14 empty] | 0
Schedule 18 | 29.1 | [14 empty] | 0
Schedule 18 | 29.2 | [14 empty] | 0
Schedule 18 | 29.3 | [14 empty] | 0
Schedule 18 | 29.4 | [14 empty] | 0
Schedule 18 | 30 | [14 empty] | 0
Schedule 18 | 30.1 | [14 empty] | 0
Schedule 18 | 30.2 | [14 empty] | 0
Schedule 18 | 30.3 | [14 empty] | 0
Schedule 18 | 30.4 | [14 empty] | 0
Schedule 18 | 30.5 | [14 empty] | 0
Schedule 18 | 30.6 | [14 empty] | 0
Schedule 18 | 30.7 | [14 empty] | 0
Schedule 18 | 30.8 | [14 empty] | 0
Schedule 18 | 30.9 | [14 empty] | 0
Schedule 18 | 30.1 | [14 empty] | 0
Schedule 18 | 30.11 | [14 empty] | 0
Schedule 18: Annex 1 | 1 | [14 empty] | 0
Schedule 18: Annex 1 | 1.1 | [14 empty] | 0
Schedule 18: Annex 1 | 2 | [14 empty] | 0
Schedule 18: Annex 1 | 2.1 | [14 empty] | 0
Schedule 18: Annex 1 | 2.2 | [14 empty] | 0
Schedule 18: Annex 1 | 2.3 | [14 empty] | 0
Schedule 18: Annex 1 | 2.4 | [14 empty] | 0
Schedule 18: Annex 1 | 2.5 | [14 empty] | 0
Schedule 18: Annex 1 | 3 | [14 empty] | 0
Schedule 18: Annex 1 | Definitions | [14 empty] | 0
Schedule 18: Annex 1 | 4 | [14 empty] | 0
Schedule 18: Annex 1 | 4.1 | [14 empty] | 0
Schedule 18: Annex 1 | 4.2 | [14 empty] | 0
Schedule 18: Annex 1 | 4.3 | [14 empty] | 0
Schedule 18: Annex 1 | 4.4 | [14 empty] | 0
Schedule 18: Annex 1 | 4.5 | [14 empty] | 0
Schedule 18: Annex 1 | 4.6 | [14 empty] | 0
Schedule 18: Annex 1 | 4.7 | [14 empty] | 0
Schedule 18: Annex 1 | 4.8 | [14 empty] | 0
Schedule 18: Annex 1 | 4.9 | [14 empty] | 0
Schedule 18: Annex 1 | 5 | [14 empty] | 0
Schedule 18: Annex 1 | 5.1 | [14 empty] | 0
Schedule 18: Annex 1 | 5.2 | [14 empty] | 0
Schedule 18: Annex 1 | 5.3 | [14 empty] | 0
Schedule 18: Annex 1 | 5.4 | [14 empty] | 0
Schedule 18: Annex 1 | 5.5 | [14 empty] | 0
Schedule 18: Annex 1 | 5.6 | [14 empty] | 0
Schedule 18: Annex 1 | 5.7 | [14 empty] | 0
Schedule 18: Annex 1 | 5.8 | [14 empty] | 0
Schedule 18: Annex 1 | 5.9 | [14 empty] | 0
Schedule 18: Annex 1 | 5.1 | [14 empty] | 0
Schedule 18: Annex 1 | 5.11 | [14 empty] | 0
Schedule 18: Annex 1 | 5.12 | [14 empty] | 0
Schedule 18: Annex 1 | 5.13 | [14 empty] | 0
Schedule 18: Annex 1 | 5.14 | [14 empty] | 0
Schedule 18: Annex 1 | 5.15 | [14 empty] | 0
Schedule 18: Annex 1 | 5.16 | [14 empty] | 0
Schedule 18: Annex 1 | 5.17 | [14 empty] | 0
Schedule 18: Annex 1 | 5.18 | [14 empty] | 0
Schedule 18: Annex 1 | 5.19 | [14 empty] | 0
Schedule 18: Annex 1 | 5.2 | [14 empty] | 0
Schedule 18: Annex 1 | 5.21 | [14 empty] | 0
Schedule 18: Annex 1 | 5.22 | [14 empty] | 0
Schedule 18: Annex 1 | 5.23 | [14 empty] | 0
Schedule 18: Annex 1 | 5.24 | [14 empty] | 0
Schedule 18: Annex 1 | 5.25 | [14 empty] | 0
Schedule 18: Annex 1 | 5.26 | [14 empty] | 0
Schedule 18: Annex 1 | 5.27 | [14 empty] | 0
Schedule 18: Annex 1 | 5.28 | [14 empty] | 0
Schedule 18: Annex 1 | 5.29 | [14 empty] | 0
Schedule 18: Annex 1 | 5.3 | [14 empty] | 0
Schedule 18: Annex 1 | 5.31 | [14 empty] | 0
Schedule 18: Annex 1 | 5.32 | [14 empty] | 0
Schedule 18: Annex 1 | 5.33 | [14 empty] | 0
Schedule 18: Annex 1 | 5.34 | [14 empty] | 0
Schedule 18: Annex 1 | 5.35 | [14 empty] | 0
Schedule 18: Annex 1 | 5.36 | [14 empty] | 0
Schedule 18: Annex 1 | 5.37 | [14 empty] | 0
Schedule 18: Annex 1 | 5.38 | [14 empty] | 0
Schedule 18: Annex 1 | 5.39 | [14 empty] | 0
Schedule 18: Annex 1 | 5.4 | [14 empty] | 0
Schedule 18: Annex 1 | 5.41 | [14 empty] | 0
Schedule 18: Annex 1 | 5.42 | [14 empty] | 0
Schedule 18: Annex 1 | 6 | [14 empty] | 0
Schedule 18: Annex 1 | 6.1 | [14 empty] | 0
Schedule 18: Annex 1 | 6.2 | [14 empty] | 0
Schedule 18: Annex 1 | 6.3 | [14 empty] | 0
Schedule 18: Annex 1 | 6.4 | [14 empty] | 0
Schedule 18: Annex 1 | 6.5 | [14 empty] | 0
Schedule 18: Annex 1 | 6.6 | [14 empty] | 0
Schedule 18: Annex 1 | 6.7 | [14 empty] | 0
Schedule 18: Annex 1 | 6.8 | [14 empty] | 0
Schedule 18: Annex 1 | 6.9 | [14 empty] | 0
Schedule 18: Annex 1 | 6.1 | [14 empty] | 0
Schedule 18: Annex 1 | 6.11 | [14 empty] | 0
Schedule 18: Annex 1 | 6.12 | [14 empty] | 0
Schedule 18: Annex 1 | 6.13 | [14 empty] | 0
Schedule 18: Annex 1 | 6.14 | [14 empty] | 0
Schedule 18: Annex 1 | 6.15 | [14 empty] | 0
Schedule 18: Annex 1 | 6.16 | [14 empty] | 0
Schedule 18: Annex 1 | 6.17 | [14 empty] | 0
Schedule 18: Annex 1 | 6.18 | [14 empty] | 0
Schedule 18: Annex 1 | 6.19 | [14 empty] | 0
Schedule 18: Annex 1 | 6.2 | [14 empty] | 0
Schedule 18: Annex 1 | 6.21 | [14 empty] | 0
Schedule 18: Annex 1 | 6.22 | [14 empty] | 0
Schedule 18: Annex 1 | 6.23 | [14 empty] | 0
Schedule 18: Annex 1 | 6.24 | [14 empty] | 0
Schedule 18: Annex 1 | 6.25 | [14 empty] | 0
Schedule 18: Annex 1 | 6.26 | [14 empty] | 0
Schedule 18: Annex 1 | 6.27 | [14 empty] | 0
Schedule 18: Annex 1 | 6.28 | [14 empty] | 0
Schedule 18: Annex 1 | 6.29 | [14 empty] | 0
Schedule 18: Annex 1 | 6.3 | [14 empty] | 0
Schedule 18: Annex 1 | 6.31 | [14 empty] | 0
Schedule 18: Annex 1 | 6.32 | [14 empty] | 0
Schedule 18: Annex 1 | 6.33 | [14 empty] | 0
Schedule 18: Annex 1 | 6.34 | [14 empty] | 0
Schedule 18: Annex 1 | 7 | [14 empty] | 0
Schedule 18: Annex 1 | 7.1 | [14 empty] | 0
Schedule 18: Annex 1 | 7.2 | [14 empty] | 0
Schedule 18: Annex 1 | 7.3 | [14 empty] | 0
Schedule 18: Annex 1 | 7.4 | [14 empty] | 0
Schedule 18: Annex 1 | 7.5 | [14 empty] | 0
Schedule 18: Annex 1 | 8 | [14 empty] | 0
Schedule 18: Annex 1 | 8.1 | [14 empty] | 0
Schedule 18: Annex 1 | 8.2 | [14 empty] | 0
Schedule 18: Annex 1 | 8.3 | [14 empty] | 0
Schedule 18: Annex 1 | 8.4 | [14 empty] | 0
Schedule 18: Annex 1 | 8.5 | [14 empty] | 0
Schedule 18: Annex 1 | 8.6 | [14 empty] | 0
Schedule 18: Annex 1 | 8.7 | [14 empty] | 0
Schedule 18: Annex 1 | 8.8 | [14 empty] | 0
Schedule 18: Annex 1 | 8.9 | [14 empty] | 0
Schedule 18: Annex 1 | 8.1 | [14 empty] | 0
Schedule 18: Annex 1 | 8.11 | [14 empty] | 0
Schedule 18: Annex 1 | 8.12 | [14 empty] | 0
Schedule 18: Annex 1 | 8.13 | [14 empty] | 0
Schedule 18: Annex 1 | 8.14 | [14 empty] | 0
Schedule 18: Annex 1 | 8.15 | [14 empty] | 0
Schedule 18: Annex 1 | 8.16 | [14 empty] | 0
Schedule 18: Annex 1 | 8.17 | [14 empty] | 0
Schedule 18: Annex 1 | 8.18 | [14 empty] | 0
Schedule 18: Annex 1 | 8.19 | [14 empty] | 0
Schedule 18: Annex 1 | 8.2 | [14 empty] | 0
Schedule 18: Annex 1 | 8.21 | [14 empty] | 0
Schedule 18: Annex 1 | Attachment 1 | [14 empty] | 0
Schedule 18: Annex 1 | Attachment 2 | [14 empty] | 0
Schedule 18: Annex 1 | Attachment 3 | [14 empty] | 0
Schedule 18: Annex 2 | Annex 2 | [14 empty] | 0
0
Schedule 20 | Introduction | [6 empty] | YES | [7 empty] | 1
Schedule 20 | 1.1 | [6 empty] | YES | [7 empty] | 1
Schedule 20 | 2.1 | [6 empty] | YES | [7 empty] | 1
Schedule 20 | 3.1 | [6 empty] | YES | [7 empty] | 1
Schedule 20 | 3.2 | [6 empty] | YES | [7 empty] | 1
0
Schedule 29 | Introduction | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 1 | [14 empty] | 0
Schedule 29 | 1A | [8 empty] | YES | YES |  |  |  |  | 2
Schedule 29 | 2 | [14 empty] | 0
Schedule 29 | 3 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 4 | [14 empty] | 0
YES Column1: Schedule 29; YES Column2: 5; YES Column17: 0 | (DCP 306 amends the table under the paragraph)
Schedule 29 | 6 | [12 empty] | YES |  | 1
Schedule 29 | 7 | [14 empty] | 0
Schedule 29 | 8 | [14 empty] | 0
Schedule 29 | 9 | [14 empty] | 0
Schedule 29 | 10 | [14 empty] | 0
YES Column1: Schedule 29; YES Column2: 11; YES Column17: 0 | (DCP 306 introduces Clause 11A)
Schedule 29 | 11A | [12 empty] | YES |  | 1
Schedule 29 | 12 | [14 empty] | 0
Schedule 29 | 13 | [14 empty] | 0
Schedule 29 | 14 | [14 empty] | 0
Schedule 29 | 15 | [14 empty] | 0
Schedule 29 | 16 | [14 empty] | 0
Schedule 29 | 17 | [14 empty] | 0
Schedule 29 | 18 | [14 empty] | 0
YES Column1: Schedule 29; YES Column2: 19; YES Column17: 0 | (DCP 266 amends only the heading)
Schedule 29 | 20 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 21 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 22 | [14 empty] | 0
Schedule 29 | 23 | [14 empty] | 0
Schedule 29 | 24 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 25 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 26 | [14 empty] | 0
Schedule 29 | 27 | [14 empty] | 0
Schedule 29 | 28 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 29 | [14 empty] | 0
Schedule 29 | 30 | [14 empty] | 0
Schedule 29 | 31 | [14 empty] | 0
Schedule 29 | 32 | [14 empty] | 0
Schedule 29 | 33 | YES | [13 empty] | 1
Schedule 29 | 34 | YES | [13 empty] | 1
Schedule 29 | 35 | [14 empty] | 0
Schedule 29 | 36 | [14 empty] | 0
Schedule 29 | 37 | [14 empty] | 0
Schedule 29 | 38 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 39 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 40 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 41 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 42 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 43 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 44 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 45 | [14 empty] | 0
Schedule 29 | 46 | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 46A | [8 empty] | YES | [5 empty] | 1
Schedule 29 | 47 | [14 empty] | 0