## Slide 1: ElectraLink ETTOS WG MEETING 12 July 2016

## Slide 2
Key Milestones:
Key activities
Feb
Mar
WS1:
Implementation
WS2: Stakeholder
engagement
WS3: Code
Governance
WS0: Contract Negotiation
2016
Apr
Key Activities TBC
TRAS Steering Group
TOLS Working Group
On Track
At Risk
Missed
Complete
Key Meetings:
May
Jun
Jul
Aug
Sep
ECOES/Exoserve data access
Interim Tip-Off Service
Workshop 1
15/04
Workshop 2
Sign-off Operating Procedures
Setup Access to Secure Portal
Agree TCG Membership
Sign-off Advertising & Comms Plan
Portal available to all recipients
Agree Contract Parameters
TSG Approval of proposal
Negotiate Contract
Execution of UAT Functionality
Agreed processes Implemented in codes
Draft Enduring Gov. Processes
Consult on Proposed Enduring Solutions
Workshop 1
15/04
Workshop 2
Bespoke Online Reporting Interface
Microsite Build
Bespoke Tip-Off Line Set-up
Marketing planning & Implementation
1st Draft Code Processes to ETTOS
Fully Drafted CPs through change control
UAT Functionality (Approach, Script, Issue MGT, Defect sign-off)
ETTOS Bulletin 1
ETTOS Bulletin 2
ETTOS Bulletin 3
ETTOS Bulletin 4
Tripartite Agreement
Contract physically signed
EWG monthly deliverables
EWG monthly deliverables
EWG monthly deliverables
EWG monthly deliverables
EWG
PIA
Historic data to industry
Train call-handling agents
EWG meeting 1
EWG meeting 2
EWG meeting 3
EWG meeting 4

## Slide 3
ECOES access granted, work has begun on matching historic Electricity tip-offs
Gas Data provision – UNC Mod 584S and SPAA CP 16/344 in progress
Secure email system on track to testing W/C 25th July 2016
Marketing – Revised branding developed, Crimestoppers working with Ofgem on PR launch
Work Stream 1 – Service Implementation

## Slide 4
SPOC – a number of organisations still to provide details
Where SPOC has not been provided Crimestoppers using Contract Manager as initial point of contact
Work Stream 2 – Stakeholder Management

## Slide 5
DCUSA DCP 264 – Awaiting Authority Consent
SPAA CP 16/325 – Rejected a Change Borad
ETTOS Change Guideline agreed
Four Contract Change notifications (CNNs)
  CCN 001 Emergency Service – Rejected
  CCN 002 Additional ETTOS Users– Agreed in principle, requires SPPA and DCUSA CPs
  CCN 003 Gas Tip Off Dissemination- Agreed
  CCN 004 Email Alerts - Agreed
Work Stream 3 – Governance