## CPs
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst/WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status Change Code
STATUS - DEFINITION
DCP 169 | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | This Change Proposal (CP) seeks remove the restriction in paragraph 135 of Schedule 16 of DCUSA in order to allow the use of Seasonal Time of Day (SToD) tariffs to be calculated and applied. | CDCM | 1 | Claire Hynes/Rosalind Timperley | Keith Burwell | 2013-03-13 | 8 |  | On Hold | The Working Group is waiting for the Ofgem decision on DCP 228 before deciding on how to proceed with DCP 169. | N/A
DCP 226 | Housekeeping 66/72/73/77/80 | This CP seeks to review and revise the DCUSA document to incorporate housekeeping log items 66/72/73/77/80 | General | 2 | Fungai Madzivadondo/ Rosalind Timperley | Roberta Fernie | 2015-01-05 | 0 |  | Next Release Following Authority Consent | The Working Group invitation closed with only one interested person. It was agreed that that in addition to addressing the proposed housekeeping changes DCP 226 would also review the numbering and referencing throughout the DCUSA document. | N/A
DCP 243 | Treatment of Customer Contributions in the CDCM | ​This CP seeks to revise DCUSA Schedule 16 to utilise current source data to determine a common industry set of modelling inputs in order to improve clarity in the approach to be used in calculating ‘Customer contribution under the current connection charging policy’ for use in CDCM table 1060. | CDCM | 1 | Dylan Townsend/Rosalind Timperley | Lynda Carroll | 2015-06-05 | 11 |  | 2018-04-01 | DCP 243 Consultation three was issued to parties on 09 November 2016 and closed on 30 November 2016. The Working Group is due to meeti on 16 January 2017. | N/A
DCP 244 | MOP Leaving Site for Cat A Situations | ​This CP seeks to remove the DNO Intervention SLA for attending Category A jobs where the MOP operative will not or has not remained on site and to address housekeeping issues with the DCP 195A legal text | General | 1 | To be progressed by the Interventions Working Group | Angela Picciarello | 2015-06-19 | 2 |  | Next Release Following Authority Consent | The Working Group is waiting for Operational Delivery Group (ODG) to develop MOP guidance on leaving site where there is a category A situation. The CP has been placed on hold whilst this progressed. | N/A
DCP 251 | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | The intent of this proposal is to correct drafting errors in the specification of the distribution systems that are eligible for LDNO tariffs under the CDCM and under the EDCM and ensure that there the charging methodologies do not impose undue discrimination between licensed and licence-exempt distribution systems and restore the 50 per cent LDNO discount on indirect costs which was removed by the approved legal text for DCP 185 in cases where the fixed adder is negative.​ | CDCM | 1 | Dan Fittock/John Lawton | Keith Burwell | 2015-10-15 | 10 |  | Next release date after approval | The DCP 251 and DCP 252 consultation was issued to industry and identified Private Network Operators on 24 November 2016 with a response deadline of 30 December 2016. The Working Group met on 10 January 2017 and discussed the responses. | N/A
DCP 252 | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | The intent of this proposal is to correct drafting errors and inconsistencies in the specification of the distribution systems that are eligible for Portfolio tariffs under the EDCM (schedules 17 and 18) and establish arrangements that ensure that methodologies in Schedules 17 and 18 do not impose undue discrimination between licensed and licence exempt distribution systems.​ | EDCM | 1 | Dan Fittock/John Lawton | Keith Burwell | 2015-10-15 | 10 |  | Next release date after approval | The DCP 251 and DCP 252 consultation was issued to industry and identified Private Network Operators on 24 November 2016 with a response deadline of 30 December 2016. The Working Group met on 10 January 2017 and discussed the responses. | N/A
DCP 255 | Changes to Electricity (Connection Charges) Regulations 2002 | ​This CP seeks to incorporate changes in the CCCM as a result of changes to the Electricity (Connection Charges) Regulations 2002​. | CCCM | 2 | Dan Fittock/Claire Hynes | Lesley Ferrando | 2015-11-06 | 3 | On-hold until the Department of Business, Innovation and Skills finalise the ECCR 2016 legal text. | First practicable release after approval | The Working Group are awaiting the receipt of the final ECCR 2016 legal text from BEIS (formally DECC) before progressing this change. | N/A
DCP 266 | The calculation and application of IDNO discounts | To change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this CP is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | CDCM | 1 | Fungai Madzivadondo/ Roz Timperley | Donald Smith | 2016-03-09 | 5 |  | 2018-04-01 | DCP 266 Working Group met on 30 November 2016 and asked for the modelling consultant to provide further modelling options. The next Working Group Meeting is schedueld for 24 January 2017. | N/A
DCP 268 | DUoS Charging Using HH settlement data | The intent of this CP is to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | CDCM | 1 | Claire Hynes / John Lawton | Lynda Carroll | 2016-03-14 | 8 |  | 2019-04-01 | The DCP 268 Working Group have requested for the 01 April 2018 models to be updated with the DCP 268 solution. Once received and approved by DNOs the updated model will be issued with consultation two to parties. | N/A
DCP 274 | The application of export capacity charges in the EDCM | The intent of this CP is to amend the EDCM methodology to ensure that distributed generation and storage sites do not pay distribution use of system charges for the import and export from a site where the same assets are used. | EDCM | 1 | Dan Fittock/ Claire Hynes | Keith Burwell | 2016-06-10 | 2 |  | 2018-04-01 | The DCP 274 Working Group last met on 13 December 2016 to finalise the consultation. The consultation will be issued in January for a period of three weeks. | N/A
DCP 282 | Embedded Distribution Network Operator (EDNO) UMSO | This CP seeks to facilitate the management and trading of UMS apparatus connected to EDNO networks via the “host” DNO’s UMSO service on one combined inventory, without the need for additional MPANs, following a request from the customer to the EDNO to do so. | General | 1 | Claire Hynes/ John Lawton | Stephen Perry | 2016-09-14 | 1 |  | First release following approval | The Working Group issued a consultation to Parties on 16 December 2016 and responses are due by 13 January 2017. The Working Group will meet on the 27 January 2017 to consider the consultation responses. | N/A
DCP 283 | The calculation of generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators | CDCM | 1 | Dylan Townsend / John Lawton |  | 2016-10-12 | 1 |  | 2019-04-01 | A RFI was sent out to DNO parties on the 21 December 2016 and responses to this RFI are due by 13 January 2017. The next meeting of the DCP 283 Working Group is scheduled for 23 January 2017 | N/A
DCP 284 | The application of scaling to generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators by including an element of scaling. | CDCM |  | Dylan Townsend / John Lawton |  | 2016-10-12 | 2 |  | 2019-04-01 | The Working Group are in the process of drafting a consultation. The next meeting of the DCP 284 Working Group is scheduled for 23 January 2017. | N/A
DCP 286 | Formalising the Theft Steering Group | This change proposes to formally delegate the DCUSA Panel and DCUSA Ltd Board powers in relation to the Theft Risk Assessment Service (TRAS) and Energy Theft Tip Off Line Service (ETTOS) to the Theft Steering Group (TSG) | TRAS |  | Fungai Madzivadondo/Sarah Jones |  | 2016-11-09 | 0 |  | First release following approval | DCP 286 is in the process of being withdrawn by the Proposer after guidance from the DCUSA and SPAA Legal Advisor. Parties have been provided with an opportunity to take ownership of this change by the 18 January 2017. | N/A
DCP 287 | Generation credits in the EDCM | The intent of this Change Proposal is to amend the calculation of credits for embedded generation in the EDCM to take account of potential cost savings for DNOs that can be attributed to embedded generation in the areas of transmission exit charges, direct costs, indirect costs and network rates. | EDCM | 1 | Dylan Townsend/ Dan Fittock | Edda Dirks | 2016-12-07 | 0 |  | 2019-04-01 | A Working Group invitation has been issued to parties with a closing date of the 13 January 2017.. | Definition
DCP 288 | Introduction of the Electricity Theft Detection Incentive Scheme | The intent of this Change Proposal (CP) is to introduce an Electricity Theft Detection Incentive Scheme in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014 | TRAS | 1 | Fungai Madzivadondo/Sarah Jones |  | 2016-12-12 | 0 |  | 2017-06-01 | At the TIG meeting on 10 January 2017 the group discussed the DCP 288 intent and the principles of the proposed change. The draft DCP 288 consultation will be reviewed at the next TIG meeting. | Definition
DCP 289 | Creation of Distribution Charging Methodology Development Group | The intent of this CP is to formalise the creation of a new single Standing Issues Working Group for the Use of System charging methodologies and related topics within DCUSA. | General/ Urgent | 1 | Claire Hynes |  | 2016-12-16 | 0 |  | 2018-04-01 | This change has been designated as urgent and will go straight to change report. | Definition
STATUS - CHANGE REPORT
DCP 281 | Changes to Schedule 19 – Portfolio Billing | This CP seeks to ensure that HH Portfolio data is reported to DNOs in a consistent manner by all embedded LDSOs and to define how revised data must be reported. | EDCM | 2 | Dan Fittock/ Claire Hynes | Lynda Carroll | 2016-09-14 | 0 |  | Next release date after approval | The Working Group are aimimg to submit a change report to the January 2017 DCUSA Panel. | N/A
STATUS - VOTING
DCP 285 | Schedule 23, Appendix 1 SLC References | The intent of this change is to remove references to Supply Licence Condition (SLC) 12.16 in Schedule 23, Appendix 1 and replace them with the updated SLC references. | General |  | Fungai Madzivadondo/Sarah Jones |  | 2016-10-12 | 0 |  | First release following approval | DCP 285 Change Report was issued to Parties to vote on by 20 January 2017. | Voting
STATUS - AWAITING AUTHORITY CONSENT
DCP 263 | NTC DEH Gap | This CP seeks to amend the NTC so that they cater for DNOs’ connections to non-metered DEH networks.There should be no impact from this change on the applicability of the NTC to boundary metered DEHs or on the contractual terms suppliers put in place by virtue of Schedule 2A of DCUSA. | General | 1 | Dan Fittock/Claire Hynes | Lesley Ferrando | 2016-01-22 | 3 |  | First practicable release after approval | The DCP 263 Change Report has been submitted to Ofgem for decision with a recommendation from Parties to reject the change. It is noted that 6 DNOs voted to accept the change and 1 IDNO to reject the change. | N/A
STATUS - AWAITING IMPLEMENTATION
2017-02-23
DCP 275 | Code Governance Review 3 & SLC 22 | The CP seeks to implement the distribution licence changes arising from Ofgem’s Code Governance Review Phase 3 Final Proposals impacting DCUSA governance. | General | 1 | Fungai Madzivadondo/ Peter Waymont |  | 2016-06-10 | 0 |  | 2017-02-23 | The DCP 275 Change was approved on 15 November 2016 for implementation on 23 February 2017. | N/A
DCP 277 | Schedule 25 – Amendment to Appendix 2 - Conditionality | Following on from the changes in DCP 272, the TRAS Expert Group has reviewed the conditionality for data items within the TRAS Service Providers Programming Manual and seeks to update some of the data items conditional/mandatory status because the current conditionality cannot be always met. Additionally, some JCode/RGMA Codes also require back population as they were missed on the original drafting. | TRAS | 2 | Keavy Larkin/Sarah Jones | Jon Dixon | 2016-07-11 | 1 |  | 2017-02-23 | The DCP 277 Change was approved on 17 November 2016 for implementation on 23 February 2017. | N/A
DCP 278 | Allocation of Users to the ETTOS Secure Email Service | This CP seeks to include the rules for allocation of user accounts for the ETTOS secure email service in the DCUSA | ETTOS | 2 | Fungai Madzivadondo/Sarah Jones | Jon Dixon | 2016-07-13 | 2 |  | Next release date after approval | The DCP 278 Change was approved on 15 December 2016 for implementation on 23 February 2017. | Awaiting Implementation
DCP 279 | Linking Credit Cover to the Annual Iteration Process | This change proposal has been submitted in order to update those clauses in DCUSA Schedule 1 (Credit Cover) that refer to the ‘Regulatory Asset Value (RAV)’ as the new price control, RIIO-ED1, redefines the calculation of a DNO’s Regulatory Asset Value. | General | 2 | Claire Hynes |  | 2016-07-29 | 1 |  | 2017-02-23 | The DCP 279 Change was approved on 23 December 2016 for implementation on 23 February 2017. | Awaiting Implementation
DCP 280 | Clarification of TRAS Accession Process | This CP proposes to amend the TRAS Schedules to clarify the TRAS accession process. It has been assessed that there is a three-month time lag between a new Supplier starting to register metering systems and actually submitting data into TRAS. This time lag has not been reflected within the current TRAS Schedule and a change is required to explicitly reference the time lag so new parties are clear when they need to provide their initial data submission. The three-month time lag will also ensure that the new Supplier has time to work with the Service Provider to start submitting data. | TRAS | 2 | Fungai Madzivadondo/Sarah Jones | Jon Dixon | 2016-08-18 | 2 |  | Next release date after approval | The DCP 280 Change was approved on 15 December 2016 for implementation on 23 February 2017. | Awaiting Implementation
2017-04-01
DCP 138 | Implementation of alternative network use factor (NUF) calculation method in EDCM | This CP seeks to amend the method of calculating Network Use Factors for EDCM demand customers as defined within DCUSA to address the concerns raised by Ofgem in Condition 3 of the Ofgem decision document on EDCM import charges published in September 2011. | EDCM | 1 | Fungai Madzivadondo/Simon Yeo | Keith Burwell | 2012-06-18 | 9 |  | 2017-04-01 | The Authority directs that modification DCP 138 be made. The CP will be implemented on 1 April 2017. | N/A
DCP 227 | Removing the inconsistency in the application of Peaking Probabilities in the CDCM | ​The proposal changes the way that peaking probabilities are applied in the CDCM and therefore affects CDCM tariffs. | CDCM | 1 | Rosalind Timperley /George Moran |  | 2015-01-13 | 4 |  | 2017-04-01 | The Authority directed for DCP 227 to be made and implemented on 1 April 2017. | N/A
2018-04-01
DCP 161 | Excess Capacity Charges | To improve the cost reflectivity of the excess capacity charge calculation within the CDCM and EDCM by removing the customer contributions and adding in any additional costs that should be attributed to this charge. Also, to consider applying the excess capacity charge on either a monthly, seasonal or time of day basis. | CDCM | 1 | Michael Walls/Chris Ong | Keith Burwell | 2013-02-06 | 12 |  | 2018-04-01 | The Authority directed for DCP 161 to be made and implemented on 1 April 2018. | N/A
DCP 222 | Non Billing Of Excess Reactive Power Charges | This CP proposes the removal of the excess reactive power charge when a DNO requests that a generator operates outside of the 0.95 power factor limit. | CDCM | 1 | Fungai Madzivadondo/Dave Wornell | Nisha Doshi | 2014-12-02 | 11 |  | 2018-04-01 | The Authority directed for DCP 222 to be made and implemented on 1 April 2018. | N/A
DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | CDCM | 1 | Rosalind Timperley/ Chris Ong | Bethany Hanna | 2015-01-13 | 4 |  | 2018-04-01 | The Authority directed for DCP 228 to be made and implemented on 1 April 2018. | N/A
DCP 234 | Merging the PCDM and extended PCDM | The intent of the CP is to replace the Price Control Disaggregation (PCDM) and extended PCDM models with one model.To create a new schedule in DCUSA which contains the legal text that relates to IDNO charging that is currently contained in Schedules 16, 17 and 18. | CDCM and EDCM | 1 | Claire Hynes/ Claire Campbell | Lynda Carroll | 2015-02-27 | 7 |  | 2018-04-01 | The Authority directed for DCP 234 to be made and implemented on 1 April 2018. | N/A
DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | The intent of this proposal is to align table 1001 in the CDCM to the current format of table in Schedule 15. | CDCM | 2 | Fungai Madzivadondo/John Lawton | Lynda Carroll | 2016-05-18 | 2 |  | 2018-04-01 | Parties voted to approve the change on the 17 October 2016 for implementation on the 01 April 2018. | N/A
STATUS - APPEAL
n/a | n/a
STATUS - IMPLEMENTED
n/a | n/a
STATUS - REJECTED
n/a | n/a
STATUS - WITHDRAWN
n/a | n/a
Change Register - January 2017

## Status Change
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst/WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status Chnaged in the last Month
STATUS - DEFINITION
DCP 169 | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | This Change Proposal (CP) seeks remove the restriction in paragraph 135 of Schedule 16 of DCUSA in order to allow the use of Seasonal Time of Day (SToD) tariffs to be calculated and applied. | CDCM | 1 | Claire Hynes/Rosalind Timperley | Keith Burwell | 2013-03-13 | 8 |  | On Hold | The Working Group is waiting for the Ofgem decision on DCP 228 before deciding on how to proceed with DCP 169. | N/A
DCP 226 | Housekeeping 66/72/73/77/80 | This CP seeks to review and revise the DCUSA document to incorporate housekeeping log items 66/72/73/77/80 | General | 2 | Fungai Madzivadondo/ Rosalind Timperley | Roberta Fernie | 2015-01-05 | 0 |  | Next Release Following Authority Consent | The Working Group invitation closed with only one interested person. It was agreed that that in addition to addressing the proposed housekeeping changes DCP 226 would also review the numbering and referencing throughout the DCUSA document. | N/A
DCP 243 | Treatment of Customer Contributions in the CDCM | ​This CP seeks to revise DCUSA Schedule 16 to utilise current source data to determine a common industry set of modelling inputs in order to improve clarity in the approach to be used in calculating ‘Customer contribution under the current connection charging policy’ for use in CDCM table 1060. | CDCM | 1 | Dylan Townsend/Rosalind Timperley | Lynda Carroll | 2015-06-05 | 11 |  | 2018-04-01 | DCP 243 Consultation three was issued to parties on 09 November 2016 and closed on 30 November 2016. The Working Group is due to meeti on 16 January 2017. | N/A
DCP 244 | MOP Leaving Site for Cat A Situations | ​This CP seeks to remove the DNO Intervention SLA for attending Category A jobs where the MOP operative will not or has not remained on site and to address housekeeping issues with the DCP 195A legal text | General | 1 | To be progressed by the Interventions Working Group | Angela Picciarello | 2015-06-19 | 2 |  | Next Release Following Authority Consent | The Working Group is waiting for Operational Delivery Group (ODG) to develop MOP guidance on leaving site where there is a category A situation. The CP has been placed on hold whilst this progressed. | N/A
DCP 251 | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | The intent of this proposal is to correct drafting errors in the specification of the distribution systems that are eligible for LDNO tariffs under the CDCM and under the EDCM and ensure that there the charging methodologies do not impose undue discrimination between licensed and licence-exempt distribution systems and restore the 50 per cent LDNO discount on indirect costs which was removed by the approved legal text for DCP 185 in cases where the fixed adder is negative.​ | CDCM | 1 | Dan Fittock/John Lawton | Keith Burwell | 2015-10-15 | 10 |  | Next release date after approval | The DCP 251 and DCP 252 consultation was issued to industry and identified Private Network Operators on 24 November 2016 with a response deadline of 30 December 2016. The Working Group met on 10 January 2017 and discussed the responses. | N/A
DCP 252 | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | The intent of this proposal is to correct drafting errors and inconsistencies in the specification of the distribution systems that are eligible for Portfolio tariffs under the EDCM (schedules 17 and 18) and establish arrangements that ensure that methodologies in Schedules 17 and 18 do not impose undue discrimination between licensed and licence exempt distribution systems.​ | EDCM | 1 | Dan Fittock/John Lawton | Keith Burwell | 2015-10-15 | 10 |  | Next release date after approval | The DCP 251 and DCP 252 consultation was issued to industry and identified Private Network Operators on 24 November 2016 with a response deadline of 30 December 2016. The Working Group met on 10 January 2017 and discussed the responses. | N/A
DCP 255 | Changes to Electricity (Connection Charges) Regulations 2002 | ​This CP seeks to incorporate changes in the CCCM as a result of changes to the Electricity (Connection Charges) Regulations 2002​. | CCCM | 2 | Dan Fittock/Claire Hynes | Lesley Ferrando | 2015-11-06 | 3 | On-hold until the Department of Business, Innovation and Skills finalise the ECCR 2016 legal text. | First practicable release after approval | The Working Group are awaiting the receipt of the final ECCR 2016 legal text from BEIS (formally DECC) before progressing this change. | N/A
DCP 266 | The calculation and application of IDNO discounts | To change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this CP is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | CDCM | 1 | Fungai Madzivadondo/ Roz Timperley | Donald Smith | 2016-03-09 | 5 |  | 2018-04-01 | DCP 266 Working Group met on 30 November 2016 and asked for the modelling consultant to provide further modelling options. The next Working Group Meeting is schedueld for 24 January 2017. | N/A
DCP 268 | DUoS Charging Using HH settlement data | The intent of this CP is to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | CDCM | 1 | Claire Hynes / John Lawton | Lynda Carroll | 2016-03-14 | 8 |  | 2019-04-01 | The DCP 268 Working Group have requested for the 01 April 2018 models to be updated with the DCP 268 solution. Once received and approved by DNOs the updated model will be issued with consultation two to parties. | N/A
DCP 274 | The application of export capacity charges in the EDCM | The intent of this CP is to amend the EDCM methodology to ensure that distributed generation and storage sites do not pay distribution use of system charges for the import and export from a site where the same assets are used. | EDCM | 1 | Dan Fittock/ Claire Hynes | Keith Burwell | 2016-06-10 | 2 |  | 2018-04-01 | The DCP 274 Working Group last met on 13 December 2016 to finalise the consultation. The consultation will be issued in January for a period of three weeks. | N/A
DCP 282 | Embedded Distribution Network Operator (EDNO) UMSO | This CP seeks to facilitate the management and trading of UMS apparatus connected to EDNO networks via the “host” DNO’s UMSO service on one combined inventory, without the need for additional MPANs, following a request from the customer to the EDNO to do so. | General | 1 | Claire Hynes/ John Lawton | Stephen Perry | 2016-09-14 | 1 |  | First release following approval | The Working Group issued a consultation to Parties on 16 December 2016 and responses are due by 13 January 2017. The Working Group will meet on the 27 January 2017 to consider the consultation responses. | N/A
DCP 283 | The calculation of generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators | CDCM | 1 | Dylan Townsend / John Lawton |  | 2016-10-12 | 1 |  | 2019-04-01 | A RFI was sent out to DNO parties on the 21 December 2016 and responses to this RFI are due by 13 January 2017. The next meeting of the DCP 283 Working Group is scheduled for 23 January 2017 | N/A
DCP 284 | The application of scaling to generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators by including an element of scaling. | CDCM |  | Dylan Townsend / John Lawton |  | 2016-10-12 | 2 |  | 2019-04-01 | The Working Group are in the process of drafting a consultation. The next meeting of the DCP 284 Working Group is scheduled for 23 January 2017. | N/A
DCP 286 | Formalising the Theft Steering Group | This change proposes to formally delegate the DCUSA Panel and DCUSA Ltd Board powers in relation to the Theft Risk Assessment Service (TRAS) and Energy Theft Tip Off Line Service (ETTOS) to the Theft Steering Group (TSG) | TRAS |  | Fungai Madzivadondo/Sarah Jones |  | 2016-11-09 | 0 |  | First release following approval | DCP 286 is in the process of being withdrawn by the Proposer after guidance from the DCUSA and SPAA Legal Advisor. Parties have been provided with an opportunity to take ownership of this change by the 18 January 2017. | N/A
DCP 287 | Generation credits in the EDCM | The intent of this Change Proposal is to amend the calculation of credits for embedded generation in the EDCM to take account of potential cost savings for DNOs that can be attributed to embedded generation in the areas of transmission exit charges, direct costs, indirect costs and network rates. | EDCM | 1 | Dylan Townsend/ Dan Fittock | Edda Dirks | 2016-12-07 | 0 |  | 2019-04-01 | A Working Group invitation has been issued to parties with a closing date of the 13 January 2017.. | Definition
DCP 288 | Introduction of the Electricity Theft Detection Incentive Scheme | The intent of this Change Proposal (CP) is to introduce an Electricity Theft Detection Incentive Scheme in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014 | TRAS | 1 | Fungai Madzivadondo/Sarah Jones |  | 2016-12-12 | 0 |  | 2017-06-01 | At the TIG meeting on 10 January 2017 the group discussed the DCP 288 intent and the principles of the proposed change. The draft DCP 288 consultation will be reviewed at the next TIG meeting. | Definition
DCP 289 | Creation of Distribution Charging Methodology Development Group | The intent of this CP is to formalise the creation of a new single Standing Issues Working Group for the Use of System charging methodologies and related topics within DCUSA. | General/ Urgent | 1 | Claire Hynes |  | 2016-12-16 | 0 |  | 2018-04-01 | This change has been designated as urgent and will go straight to change report. | Definition
STATUS - CHANGE REPORT
DCP 281 | Changes to Schedule 19 – Portfolio Billing | This CP seeks to ensure that HH Portfolio data is reported to DNOs in a consistent manner by all embedded LDSOs and to define how revised data must be reported. | EDCM | 2 | Dan Fittock/ Claire Hynes | Lynda Carroll | 2016-09-14 | 0 |  | Next release date after approval | The Working Group are aimimg to submit a change report to the January 2017 DCUSA Panel. | N/A
STATUS - VOTING
DCP 285 | Schedule 23, Appendix 1 SLC References | The intent of this change is to remove references to Supply Licence Condition (SLC) 12.16 in Schedule 23, Appendix 1 and replace them with the updated SLC references. | General |  | Fungai Madzivadondo/Sarah Jones |  | 2016-10-12 | 0 |  | First release following approval | DCP 285 Change Report was issued to Parties to vote on by 20 January 2017. | Voting
STATUS - AWAITING AUTHORITY CONSENT
DCP 263 | NTC DEH Gap | This CP seeks to amend the NTC so that they cater for DNOs’ connections to non-metered DEH networks.There should be no impact from this change on the applicability of the NTC to boundary metered DEHs or on the contractual terms suppliers put in place by virtue of Schedule 2A of DCUSA. | General | 1 | Dan Fittock/Claire Hynes | Lesley Ferrando | 2016-01-22 | 3 |  | First practicable release after approval | The DCP 263 Change Report has been submitted to Ofgem for decision with a recommendation from Parties to reject the change. It is noted that 6 DNOs voted to accept the change and 1 IDNO to reject the change. | N/A
STATUS - AWAITING IMPLEMENTATION
2017-02-23
DCP 275 | Code Governance Review 3 & SLC 22 | The CP seeks to implement the distribution licence changes arising from Ofgem’s Code Governance Review Phase 3 Final Proposals impacting DCUSA governance. | General | 1 | Fungai Madzivadondo/ Peter Waymont |  | 2016-06-10 | 0 |  | 2017-02-23 | The DCP 275 Change was approved on 15 November 2016 for implementation on 23 February 2017. | N/A
DCP 277 | Schedule 25 – Amendment to Appendix 2 - Conditionality | Following on from the changes in DCP 272, the TRAS Expert Group has reviewed the conditionality for data items within the TRAS Service Providers Programming Manual and seeks to update some of the data items conditional/mandatory status because the current conditionality cannot be always met. Additionally, some JCode/RGMA Codes also require back population as they were missed on the original drafting. | TRAS | 2 | Keavy Larkin/Sarah Jones | Jon Dixon | 2016-07-11 | 1 |  | 2017-02-23 | The DCP 277 Change was approved on 17 November 2016 for implementation on 23 February 2017. | N/A
DCP 278 | Allocation of Users to the ETTOS Secure Email Service | This CP seeks to include the rules for allocation of user accounts for the ETTOS secure email service in the DCUSA | ETTOS | 2 | Fungai Madzivadondo/Sarah Jones | Jon Dixon | 2016-07-13 | 2 |  | Next release date after approval | The DCP 278 Change was approved on 15 December 2016 for implementation on 23 February 2017. | Awaiting Implementation
DCP 279 | Linking Credit Cover to the Annual Iteration Process | This change proposal has been submitted in order to update those clauses in DCUSA Schedule 1 (Credit Cover) that refer to the ‘Regulatory Asset Value (RAV)’ as the new price control, RIIO-ED1, redefines the calculation of a DNO’s Regulatory Asset Value. | General | 2 | Claire Hynes |  | 2016-07-29 | 1 |  | 2017-02-23 | The DCP 279 Change was approved on 23 December 2016 for implementation on 23 February 2017. | Awaiting Implementation
DCP 280 | Clarification of TRAS Accession Process | This CP proposes to amend the TRAS Schedules to clarify the TRAS accession process. It has been assessed that there is a three-month time lag between a new Supplier starting to register metering systems and actually submitting data into TRAS. This time lag has not been reflected within the current TRAS Schedule and a change is required to explicitly reference the time lag so new parties are clear when they need to provide their initial data submission. The three-month time lag will also ensure that the new Supplier has time to work with the Service Provider to start submitting data. | TRAS | 2 | Fungai Madzivadondo/Sarah Jones | Jon Dixon | 2016-08-18 | 2 |  | Next release date after approval | The DCP 280 Change was approved on 15 December 2016 for implementation on 23 February 2017. | Awaiting Implementation
2017-04-01
DCP 138 | Implementation of alternative network use factor (NUF) calculation method in EDCM | This CP seeks to amend the method of calculating Network Use Factors for EDCM demand customers as defined within DCUSA to address the concerns raised by Ofgem in Condition 3 of the Ofgem decision document on EDCM import charges published in September 2011. | EDCM | 1 | Fungai Madzivadondo/Simon Yeo | Keith Burwell | 2012-06-18 | 9 |  | 2017-04-01 | The Authority directs that modification DCP 138 be made. The CP will be implemented on 1 April 2017. | N/A
DCP 227 | Removing the inconsistency in the application of Peaking Probabilities in the CDCM | ​The proposal changes the way that peaking probabilities are applied in the CDCM and therefore affects CDCM tariffs. | CDCM | 1 | Rosalind Timperley /George Moran |  | 2015-01-13 | 4 |  | 2017-04-01 | The Authority directed for DCP 227 to be made and implemented on 1 April 2017. | N/A
2018-04-01
DCP 161 | Excess Capacity Charges | To improve the cost reflectivity of the excess capacity charge calculation within the CDCM and EDCM by removing the customer contributions and adding in any additional costs that should be attributed to this charge. Also, to consider applying the excess capacity charge on either a monthly, seasonal or time of day basis. | CDCM | 1 | Michael Walls/Chris Ong | Keith Burwell | 2013-02-06 | 12 |  | 2018-04-01 | The Authority directed for DCP 161 to be made and implemented on 1 April 2018. | N/A
DCP 222 | Non Billing Of Excess Reactive Power Charges | This CP proposes the removal of the excess reactive power charge when a DNO requests that a generator operates outside of the 0.95 power factor limit. | CDCM | 1 | Fungai Madzivadondo/Dave Wornell | Nisha Doshi | 2014-12-02 | 11 |  | 2018-04-01 | The Authority directed for DCP 222 to be made and implemented on 1 April 2018. | N/A
DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | CDCM | 1 | Rosalind Timperley/ Chris Ong | Bethany Hanna | 2015-01-13 | 4 |  | 2018-04-01 | The Authority directed for DCP 228 to be made and implemented on 1 April 2018. | N/A
DCP 234 | Merging the PCDM and extended PCDM | The intent of the CP is to replace the Price Control Disaggregation (PCDM) and extended PCDM models with one model.To create a new schedule in DCUSA which contains the legal text that relates to IDNO charging that is currently contained in Schedules 16, 17 and 18. | CDCM and EDCM | 1 | Claire Hynes/ Claire Campbell | Lynda Carroll | 2015-02-27 | 7 |  | 2018-04-01 | The Authority directed for DCP 234 to be made and implemented on 1 April 2018. | N/A
DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | The intent of this proposal is to align table 1001 in the CDCM to the current format of table in Schedule 15. | CDCM | 2 | Fungai Madzivadondo/John Lawton | Lynda Carroll | 2016-05-18 | 2 |  | 2018-04-01 | Parties voted to approve the change on the 17 October 2016 for implementation on the 01 April 2018. | N/A
STATUS - APPEAL
n/a | n/a
STATUS - IMPLEMENTED
n/a | n/a
STATUS - REJECTED
n/a | n/a
STATUS - WITHDRAWN
n/a | n/a
Change Register - January 2017

## CP Work Plans
The DCUSA Panel is invited to:
Change Proposal | Secretariat | CP Title | Change Report Due Date | Status | Date of Last Agreed Work Plans | Note the Change Proposal Status
DCP 169 | Roz | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | On hold |  |  | Note the Change Proposal Activity
DCP 226 | Fungai | Housekeeping 66/72/73/77/80 | On hold |  |  | Approve the Extensions to the Change Proposal Assessment Process
DCP 243 | Dylan | Treatment of Customer Contributions in the CDCM | 2017-01-11 | Work Plan Submitted for Approval |  | Approve the DCPs 243 and 274 Work Plans
DCP 244 | Roz | MOP Leaving Site for Cat A Situations | CP on hold. First Work Plan to be submitted
DCP 251 | Dan | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | 2017-04-12 |  | 2016-12-21
DCP 252 | Dan | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | 2017-04-12 |  | 2016-12-21
DCP 255 | Claire | Changes to Electricity (Connection Charges) Regulations 2002 | On hold
DCP 266 | Dylan | The calculation and application of IDNO discounts | 2017-02-08 |  | 2016-11-16
DCP 268 | Claire | DUoS Charging Using HH settlement data | 2017-03-08 |  | 2016-12-21
DCP 274 | Dan | The application of export capacity charges in the EDCM | 2017-01-11 | Work Plan Submitted for Approval
DCP 281 | Claire | Changes to Schedule 19 – Portfolio Billing | 2017-02-08 |  | 2016-11-16
DCP 282 | Claire | EDNO UMSO | 2017-02-08 |  | 2016-11-16
DCP 283 | Dylan | The calculation of generation credits in the CDCM | 2017-08-18 |  | 2016-12-21
DCP 284 | Dylan | The application of scaling to generation credits in the CDCM | 2017-05-10 |  | 2016-12-21
DCP 286 | Fungai | Formalising the Theft Steering Group | 2017-03-15 | In the process of being withdrawn
DCP 287 | Dan | Generation credits in the EDCM | 2017-04-12 | First Workplan due (after first meeting)
DCP 288 | Fungai | Introduction of the Electricity Theft Detection Incentive Scheme | 2017-04-12 | First Workplan due (after first meeting)
DCP 289 | Claire | Creation of Distribution Charging Methodology Development Group | 2017-01-11 | Straight to Change Report
CP Work Plans

## Legal Text Overlap
Colour Code
February 2016 |  |  | Red Text = Legal text close to being completed but not yet finalised
Black Text = Finalised Legal text that will not change further (i.e. version to be included in Change Report)
Yellow Highlight = Paragraph changed by more than one CP
Awaiting Implementation
CP Number | DCP 284 | DCP 283 | DCP 274 | DCP 268 | DCP 266 | DCP 252 | DCP 251 | DCP 243 | DCP 169 | DCP 273 | DCP 227 | DCP 138 | DCP 161 | DCP 228 | DCP 222 | DCP 234
Implementation Date | [9 empty] | 2018-04-01 | 2017-04-01 | 2017-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01
Status | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | on Hold | Developed | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation
DCUSA Schedule 15
Impacted Paragraphs |  |  |  | Table 3 | [8 empty] | Table 3 (para 4.1)
DCUSA Schedule 16 |  |  |  | para 3 | [5 empty] | para 3
Impacted Paragraphs | [12 empty] | 3a
|  |  |  | 12 | [8 empty] | 12
14
40,42,42A,43
45,52A,
68,72,72A,74
|  |  |  | 80,81,83,84 | [11 empty] | 3(b)
97
98 and 99
[11 empty] | 67 to 72 |  |  |  |  | 100 to 120 (including the tables and headings)
124 and 125
[13 empty] | 81 |  |  | Glossary
| 92 to 95 | [12 empty] | 92 to 95
126,127,128,
129130
|  |  |  | 131,132, | 109,111 to 113A & 113D,118 to 124
132A,132B
135,135A
135B,136
|  |  |  | 140A-140E | [8 empty] | 131
|  |  |  | 141 table 4 &5 | [8 empty] | 136
141 (table 5)
|  |  |  | 142143 | [10 empty] | 146 (table 7)
|  |  |  | 144,145, | [8 empty] | 147 (table 8 & 9)
146 table 6& 7
|  |  |  | 147 table 8& 9 | [8 empty] | 153
157 - deleted
173
177 (originally 176)
DCUSA Schedule 17
Impacted Paragraphs | [12 empty] | 1.3 |  |  | 25
25.1
25.2
[12 empty] | 18.6 to 18.8 |  |  |  | 25.3 to 25.18 (including the tables and headings).
25.19
30.6
DCUSA Schedule 18
Impacted Paragraphs | [12 empty] | 1.3 |  |  | 25
25.1
25.2
25.3 to 25.18 (including the tables and headings).
[12 empty] | 18.7 to 18.8 |  |  |  | 25.19
30.6
DCUSA Schedule 20
Impacted Paragraphs |  |  |  | 1.1 | [8 empty] | 1.1
Charging Methodology CPs Legal Text Overlap Tracker