## Slide 1: ElectraLink ETTOS WG MEETING 14 June 2016

## Slide 2
Key Milestones:
Key activities
Feb
Mar
WS1:
Implementation
WS2: Stakeholder
engagement
WS3: Code
Governance
WS0: Contract Negotiation
2016
Apr
Key Activities TBC
TRAS Steering Group
TOLS Working Group
On Track
At Risk
Missed
Complete
Key Meetings:
May
Jun
Jul
Aug
Sep
ECOES/Exoserve data access
Interim Tip-Off Service
Workshop 1
15/04
Workshop 2
Sign-off Operating Procedures
Setup Access to Secure Portal
Agree TCG Membership
Sign-off Advertising & Comms Plan
Portal available to all recipients
Agree Contract Parameters
TSG Approval of proposal
Negotiate Contract
Execution of UAT Functionality
Agreed processes Implemented in codes
Draft Enduring Gov. Processes
Consult on Proposed Enduring Solutions
Workshop 1
15/04
Workshop 2
Bespoke Online Reporting Interface
Microsite Build
Bespoke Tip-Off Line Set-up
Marketing planning & Implementation
1st Draft Code Processes to ETTOS
Fully Drafted CPs through change control
UAT Functionality (Approach, Script, Issue MGT, Defect sign-off)
ETTOS Bulletin 1
ETTOS Bulletin 2
ETTOS Bulletin 3
ETTOS Bulletin 4
Tripartite Agreement
Contract physically signed
EWG monthly deliverables
EWG monthly deliverables
EWG monthly deliverables
EWG monthly deliverables
EWG
PIA
Historic data to industry
Train call-handling agents
EWG meeting 1
EWG meeting 2
EWG meeting 3
EWG meeting 4

## Slide 3
ECOES Application submitted – awaiting outcome from MEC
Gas Data provision – UNC Mod required, planned for July Mods Panel
Marketing agency appointed
Work Stream 1 – Service Implementation

## Slide 4
First e-bulletin issued to stakeholders
SPOC – a number of organisations still to provide details
Work Stream 2 – Stakeholder Management

## Slide 5
SPAA and DCUSA CPs issued – voting complete by mid June
Draft Change Guideline for decision at today’s meeting
Four Contract Change notifications (CNNs) raised
Work Stream 3 – Governance