## Document History
Change Log
Date | Version | Description | Author

## Risks Handed Over
TRAS Project Risk Log
[8 empty] | Current Status |  |  | Last Reported
Int. Ref | Ext. Ref | Internal / External | Date added | Last Updated | Risk / Issue | Risk Description | Risk Impact | Likelihood (1-5) | Impact (1-5) | Risk Score | Likelihood (1-5) | Risk Score (Last Reported) | Actions/ Mitigations | Action Owner | Date Due | Status
Note on M6: Kevin Lam: There is no likelihood score applied as the risk has now materialised into an issue

## Change log
TRAS - Change Request Log
Change Ref | Requestor | Date Raised | Issued date | IA Due Date | Approved Date | Category | Title of Change | Description of Change | Last Reported Status date | Current Status | Status update | CCN Statuses
In Draft
Submitted to Experian
IA Received
IA Circulated for review
Approved TWG
Rejected TWG
Approved TSG
TRAS006 | ElectraLink | 2015-09-02 | 2015-09-02 | 2015-09-16 | N/A | Implementation Programme | Additional Supplier On Boarding Costs | This change is to increase the Charges defined in Schedule 11 of the Agreement to facilitate additional activity that Experian indicates that it needs to undertake to deliver section 5 of Schedule 2 – Services Description | 2015-09-14 | Withdrawn | 03/09/15: Sent to Experian to be assessed. 08/09/15: Electralink PMO to check progress on CCN with Experian 23/09/15: Dawn Leighton sent this reply, Further to my conversation with Paul on Friday, I have created a comments log against this Change Proposal capturing the requirements outlined here and awaiting further feedback this week (Paul indicated your full response would be with us by close of business Friday). The authors of our response have access to the comments log and will be notified as this is updated - to enable a prompt response once we receive all feedback. 21/10/15: A side letter has been written and sent to Experian to stand in stead of this change request. The CCN should be withdrawn. | Rejected TSG
TRAS007 | Electralink | 2015-09-08 | 2015-09-08 | 2015-09-22 | N/A | Contract Administration | Remove reference in TRAS Contract Schedule 18 (Clause 6.4 (f)) | The removal of reference in TRAS Contract Schedule 18 (Clause 6.4 (f)) to the chair of the Arbitral Tribunal being British. | 2015-09-14 | Withdrawn | 08/09/15: CCN (TRAS007) raised and sent to Experian for approval. 15/09/15: As this is a minor change which has no impact on Experian we accept this change. In order to reduce administrative overhead for both parties, this will be incorporated in the changes initiated under TRAS005 | To be Signed
TRAS008 | ElectraLink | 2015-09-22 | 2015-09-22 | 2015-10-06 | 2015-11-03 | Supplier Administration | Housekeeping of Supplier name and Tiers | Following the initial data drop phase of the TRAS programme, a number of administrative errors have been found in either the Supplier Tracker and/or the SPOC list. It was mutually agreed that an administrative change request would be raised to correct this information. | 2016-03-29 | Implemented | 22/09/15: Change request has been issused to Experian so currently within the impact Assessment period of 10 W/days which completes on 06/10/15. 03/11/15: Signed by Kevin and Kirsty and sent to Experian. 29/03/16: Countersigned CCN returned by Experian. IMPLEMENTED | Signed by DCUSA/SPAA
TRAS009 | ElectraLink | 2015-09-30 | 2015-10-01 | 2015-10-15 | N/A | Tip Off Line | Improve the timing of provision of tip-offs to Suppliers once they have been received from the tip-off line service provider. | Experian will receive tip-offs from the tip-off line service provider on a monthly basis. The proposed operating model states that these tip offs will not be passed to Suppliers until the next round of qualified outliers as this is when Experian will identify the relevant Supplier. This may be up to 2 month later, depending on when the tip-offs are received by Experian. Experian will receive tip-offs from the tip-off line service provider on a monthly basis. The proposed operating model states that these tip offs will not be passed to Suppliers until the next round of qualified outliers as this is when Experian will identify the relevant Supplier. This may be up to 2 month later, depending on when the tip-offs are received by Experian. | 2016-03-30 | Withdrawn | 30/09/15: Natasha raised CCN (TRA009) raised in meeting reference TWG/150915/08 | Signed by Experian
TRAS010 | ElectraLink | 2015-09-30 | 2015-10-01 | 2015-10-15 | N/A | Tip Off Line | Impact of reducing the timescales for provision of tip-offs form the tip-off service provider to Experian, and onwards to Suppliers | Experian will receive tip-offs from the tip-off line service provider on a monthly basis. The proposed operating model states that these tip offs will not be passed to Suppliers until the next round of qualified outliers as this is when Experian will identify the relevant Supplier. This may be up to 2 month later, depending on when the tip-offs are received by Experian. This change is to determine the impact of reducing overall tip-off provision cycle, including the speed at which tip-offs are sent from the tip-off line service provider to Experian, and the time taken for Experian to subsequently issue the tip-offs to the relevant Supplier(s). Experian is asked to consider options, including but not limited to: • Within day end to end process; • Within week end to end process; • Fortnightly end to end process; • Within calendar month end to end process. | 2016-09-30 | Withdrawn | 30/09/15: Natasha raised CCN (TRA010) raised in meeting reference TWG/150915/09 | Signed and Sent to Experian
TRAS011 | ElectraLink | 2015-10-22 | 2015-10-29 | 2015-11-12 | 2016-02-08 | New Tier 3 Supplier | Add Crown Oil to Multi-User Hunter Instance | It has been identified that Crown Oil will need to be added to the multi-occupancy instance of Hunter in order to receive their Qualified outliers as they have ~4000 supply points. SPOC Name MPPID Fuel Supply Points Crown Oil CRWL Gas 4000 | 2016-03-29 | Implemented | 11/11/15: IA Received from Experian 24/11/15: This CCN was approved in advance at the TSG meeting on 29th October. As such, this CCN can now be signed. 08/02/16: Signed at last TSG meeting and sent to Experian. 29/03/16: Countersigned CCN returned by Experian. IMPLEMENTED | Implemented
TRAS012 | ElectraLink | 2015-10-22 | 2015-10-30 | 2015-11-13 | 2016-02-08 | New Tier 3 Supplier | Add Hanbury Energy to Multi-User Hunter Instance | It has been identified that Hanbury Energy will need to be added to the multi-occupancy instance of Hunter in order to receive their Qualified outliers as they have ~3 supply points. SPOC Name MPPID Fuel Supply Points Hanbury REGE Gas 3 | 2016-03-29 | Implemented | 11/11/15: IA Received from Experian 24/11/15: This CCN was approved in advance at the TSG meeting on 29th October. As such, this CCN can now be signed. 08/02/16: Signed at last TSG meeting and sent to Experian. 29/03/16: Countersigned CCN returned by Experian. IMPLEMENTED | Withdrawn
TRAS013 | ElectraLink | 2015-10-22 |  | 1900-01-13 | N/A | New Tier 3 Supplier | Add Iridium Energy Supply to Multi-User Hunter Instance |  | 2015-11-24 | Withdrawn | 24/11/15: This CCN was raised when it was suggested the Supplier may require access to TRAS. However, further investigation found that this Supplier was not yet a SPAA or DCUSA party. | Closed
TRAS014 | ElectraLink | 2015-10-22 | 2015-10-29 | 2015-11-12 | 2016-02-08 | New Tier 3 Supplier | Add Marble Power Limited to Multi-User Hunter Instance | It has been identified that Marble Power Ltd will need to be added to the multi-occupancy instance of Hunter in order to receive their Qualified outliers as they have ~supply points. SPOC Name MPPID Fuel Supply Points Marble Power Ltd MARB Gas/Electricity - | 2016-03-29 | Implemented | 11/11/15: IA Received from Experian 24/11/15: This CCN was approved in advance at the TSG meeting on 29th October. As such, this CCN can now be signed. 08/02/16: Signed at last TSG meeting and sent to Experian. 29/03/16: Countersigned CCN returned by Experian. IMPLEMENTED
TRAS015 | ElectraLink | 2015-10-22 | 2015-10-29 | 2015-11-12 | 2016-02-08 | New Tier 2 Supplier | Add Single Use Hunter Instance for E (Gas and Electricity) Ltd | It has been identified that E (Gas and Electricity)- 209 will need a single instance of Hunter in order to receive their Qualified outliers as they have ~more than 50,000 supply points. | 2016-03-29 | Implemented | 16/11/15: IA Received from Experian 24/11/15: This CCN was approved in advance at the TSG meeting on 29th October. As such, this CCN can now be signed. 08/02/16: Signed at last TSG meeting and sent to Experian. 29/03/16: Countersigned CCN returned by Experian. IMPLEMENTED
TRAS016 | ElectraLink | 2015-10-22 | 2015-10-29 | 2015-11-12 | 2016-02-08 | New Tier 2 Supplier | Add Single Use Hunter Instance for Flow Energy Ltd | It has been identified that Flow Energy Ltd- 323 will need a single instance of Hunter in order to receive their Qualified outliers as they have ~more than 50,000 supply points. | 2016-03-29 | Implemented | 16/11/15: IA Received from Experian 24/11/15: This CCN was approved in advance at the TSG meeting on 29th October. As such, this CCN can now be signed. 08/02/16: Signed at last TSG meeting and sent to Experian. 29/03/16: Countersigned CCN returned by Experian. IMPLEMENTED
TRAS017 | ElectraLink | 2015-10-22 | 2015-10-30 | 2015-11-13 | 2016-02-08 | New Tier 2 Supplier | Add Single Use Hunter Instance for Hudson Energy Supply UK Limited | It has been identified that Hudson Energy Supply UK Ltd 374 will need a single instance of Hunter in order to receive their Qualified outliers as they have ~more than 50,000 supply points. | 2016-03-29 | Implemented | 16/11/15: IA Received from Experian 24/11/15: This CCN was approved in advance at the TSG meeting on 29th October. As such, this CCN can now be signed. 08/02/16: Signed at last TSG meeting and sent to Experian. 29/03/16: Countersigned CCN returned by Experian. IMPLEMENTED
TRAS018 | ElectraLink | 2015-10-22 | 2015-10-30 | 2015-11-13 | 2016-02-08 | Administration | Change of company name EPG Energy | This is an administrative change request to correct this information. 1. Contributor 256, Energy Data Company Limited. Name should be “EPG Energy Limited”, MPID is “ENDC”. The MPID amendments detailed are to ensure that a recognisable MPID is in use, for Electricity market participants, this is their (primary) MPID and for Gas only market participants, this is their three letter gas MPID plus an additional appropriate letter. | 2016-03-29 | Implemented | 11/11/15: IA Received from Experian 24/11/15: Although this is an administrative change, the IA requires formal approval prior to signature. 01/12/15: Approved at TSG on 1st December, decision to be ratified then CCN to be signed. 08/02/16: Signed at last TSG meeting and sent to Experian. 29/03/16: Countersigned CCN returned by Experian. IMPLEMENTED
TRAS019 | ElectraLink | 2015-10-30 | 2015-10-30 | 2015-11-13 | N/A | Data Submission | 5 working day delay of data submission | This change request asks for the impact on the TRAS of submitting the data 1, 2, or 5 working days late if a Supplier's data submission is still to be imported. | 2016-11-16 | Withdrawn | NK:16/11/15 - As per email received from Experian (Dawn on 13/11/15 @ 15:59) "Having checked the suppliers statistics from the data team today it transpires that EDF have submitted their data. In light of this, could you please withdraw change proposal TRAS019." -There is no cost activity associated to this CCN
TRAS021 | ElectraLink | 2015-11-06 | 2015-11-06 | 2015-11-20 |  | Remove Supplier | Remove Kensington Power from the baseline list of suppliers | Kensington Power to be removed from the baseline list of suppliers | 2016-03-29 | Implemented | 08/02/16: Signed at last TSG meeting and sent to Experian. 29/03/16: Countersigned CCN returned by Experian. IMPLEMENTED
EXP-TRAS-CP-0003 | Experian | 2015-12-22 | 2015-12-22 | N/A |  | Hunter | Tier 3 Worklist | By configuring a reduced sub-set of work-lists, namely ‘Residential Outliers’ & ‘Commercial Outliers’. Each work-list would still be sorted from highest to lowest priority | 2016-03-29 | Implemented | 08/02/16: Signed at last TSG meeting and sent to Experian. 29/03/16: Countersigned CCN returned by Experian. IMPLEMENTED
Formulas:
IA Due Date = [Issued date]+14

## Actions
TRAS Phase 4 Action Log
2016-06-07
ID | Reference | Action | Responsible Owner | Action Owner | Source | Date raised | Due Date | Progress Update | Status
1 | AS001 | Proposal from XoServe on Crimnestoppers' (CS) access to gas data. | XoServe | Sarah Jones | SPAA | 2016-04-14 | 2016-04-14 | UNC Mod to go to Mods Panel Meetng 21st July - if accepted data available form 15th August | OPEN
2 | AS002 | Sponsorship for CS' access to ECOES (electricity) data pending from one Supplier | CS | Sarah Jones | CS | 2016-04-27 | 2016-04-29 | Application submitted to MEC and access agreed | CLOSED
48 | TSG/20150826/04 | Submit any supporting evidence for the response to Experian by w/e 30 August | Suppliers | Ken Henwood | TRAS SG (Phase 4) | 2015-08-26 | TBC | 10-sep-15 - completed. | CLOSED
49 | TSG/20150826/05 | Confirm whether the additional data submitted by SSE and SPOW will be included the segmentation. | ElectraLink | Paul Gath | TRAS SG (Phase 4) | 2015-08-26 | 2015-09-09 | 09-Sept-15 - Confirm with Paul Gath that additional data will not be inculded in the segmentation from 3rd august? | CLOSED
51 | TSG/20150826/07 | Draft ToR for the TRAS Security Sub Group to include wider security issues, all aspects of testing and the requirement for security experts to participate in the group. | Ben Haworth | Ben Haworth | TRAS SG (Phase 4) | 2015-08-26 | 2015-09-16 | 09-Sep-15 - Security Sub-Group meeting is scheduled for the 16th Sept 15. | CLOSED
53 | TSG/20150826/09 | Submit a proposal for Phase 5. | Elizabeth Lawlor | Elizabeth Lawlor | TRAS SG (Phase 4) | 2015-08-26 | 2015-09-14 | 8/10/15: The scope of Phase 5 is on the agenda for discussion. 29/10/15: Proposal to be submitted to November TSG. Action duplicated. CLOSED. | CLOSED
56 | TRTC040915/02 | Produce a description of the Section 29 proposal and share it with the Working Group for review prior to presenting it to the ICO on 9 September. | Paul Gath | Kevin Henwood | TRTC (Phase 4) | 2015-09-05 | 2015-09-07 | Produce produced on the 9-sep-15 | CLOSED
58 |  | Add Stuart Hunter to TRAS WG distribution list | Stokely Sawyers | Stokely Sawyers | Energy-TRAS/PMO | 2015-09-07 | 2015-09-07 | 09-sep-15 - Added Stuart Hunter to TRAS Working grp distribution list so he receives all meeting dates and papers. | CLOSED
59 |  | Send to Kevin Henwood ElectraLink’s list of all suppliers who should be TRAS recipients | Ben Haworth | Ben Haworth | TRAS Weekly Call | 2015-09-04 | 2015-09-10 | 08-Sep-15: Follow up with Ben Haworth to confirm list has been compiled and sent over to Kevin 09-Sep-15: Ben has not sent information to Kevin at Experian. But he has it on his to do list 11-sep-15: Experian have been sent a list of suppliers using TRAS. | CLOSED
60 |  | Send to Ben Haworth Experian's list of all suppliers who should be TRAS recipients | Kevin Henwood | Ken Henwood | TRAS Weekly Call | 2015-09-04 | 2015-09-10 | 09-sep-15 - completed | CLOSED
61 |  | Provide full list of dependencies on ElectraLink, SPAA, DCUSA and Suppliers to ElectraLink | Paul Gath | Kevin Henwood | TRAS Weekly Call | 2015-09-04 | 2015-09-10 | 09-Sep-15 - Paul Gath will chase Kevin Henwood 17-sep-15 - Dependences issued today by Experian. | CLOSED
63 |  | please send to Lorna the times and dates of any TRAS meetings that are scheduled between now and the middle of October. | Stokely Sawyers | Stokely Sawyers | Energy-TRAS/PMO | 2015-09-07 | 2015-09-07 | 07-sept-15: SS compiled and emailed all impending meeting for TRAS up to October. | CLOSED
67 |  | ElectraLink on behalf of SPAA and DCUSA will issue next week to Experian a contract change agreeing to a negotiated fee that recognises the additional costs incurred by Experian to provide resources to on-board Recipients in support of testing and subsequent live use of TRAS. | Paul Gath | Paul Gath | Energy-TRAS/W3 | 2015-08-28 | 2015-09-16 | 02-sep-15 - CCN TRAS006 rasied and issued to experian for impact assessment and approval. The 10 day SLA (Service Level Agreement) requires a response on the 16-sep-15. | CLOSED
69 |  | Withdraw Ben Trasler (Opus Energy) from TRAS Working Group Dist list | Stokely Sawyers | Stokely Sawyers | Energy-TRAS/PMO | 2015-09-01 | 2015-09-01 | 01-Sept-15: SS removed Ben from TRAS distribution list as he requested and sent an email to Ben to confirm action completed. | CLOSED
71 |  | SS chase PG on update to Change Controls | Stokely Sawyers | Paul Gath | Email | 2015-09-07 | 2015-09-07 | 08-sept-15: Paul Gath and Paul Pettit have provided both written and verbal updates for currently open changes. All relevant CCN's have been issued to Experian for impact assessment or approval. | CLOSED
73 |  | We discussed a fair processing DP checklist, which I believe was going to be sent to Experian for review. Has this review taken place yet? | Richard Vernon | Paul Gath | Energy-TRAS/W1 | 2015-09-03 | 2015-09-04 | 03-Sept-15: Experian were due to update at end of this week. 08-sep-15 - Experian have responded and the response has been issued to TRAS WG members. | CLOSED
74 |  | Andrew Sherry of ENWL would like copies of TRAS procedures. • The enduring TRAS Governance Group • The TRAS Change Process • The TRAS Disputes Process | Paul Gath | Ben Haworth | Energy-TRAS/PMO | 2015-09-03 | 2015-09-09 | 10-09-15 Completed | CLOSED
75 |  | The Experian deliverable 9.3.3.3 – Recipient Data Processing and Data Warehouse Design v1.0 together with a blank comments log are to be issued to SPAA/DCUSA for feedback. | Paul Gath | Paul Gath | Energy-TRAS/W1 | 2015-09-03 | 2015-09-03 | 03-sep-15 - Paul Gath has distributed to SPAA/DCUSA for comments. | CLOSED
78 |  | Npower share concerns about the UAT testing criteria such as if there are less then max 10 suppliers. Will additional data be required to support UAT. Is there a proposed UAT timeline at this stage of the programme. | Ben Haworth | Ben Haworth | Energy-TRAS/W1 | 2015-09-04 | 2015-09-04 | 04-sep-15 - Ben has reaponded - There will be no need to provide additional data for UAT. The live data will be used in an isolated test environment. We don’t have a detailed timeline at this stage, although UAT begins in February. | CLOSED
79 |  | Adam Carden request to be removed from the TRAS Working Group distribution list and add National.Changes@ss.com | Stokely Sawyers | Stokely Sawyers | Energy-TRAS/PMO | 2015-09-09 | 2015-09-09 | 09-sep-15 - National.changes@sse.com has been added to TRAS WG distribution list and Adam Carden has been omitted. | CLOSED
80 |  | Experian issue a combined data quality report. | Paul Gath | Stokely Sawyers | Energy-TRAS/W1 | 2015-09-04 | 2015-09-10 | 09-sep-15 - What is update on this file, is it to be shared with suppliers 10-sep-15 - Data to be shared with suppliers, due date 11-Sep-15. Absolutely before TRAS WG information should be distributed. | CLOSED
82 |  | Distribute papers and agenda for TRAS security subgroup | Ben Haworth | Stokely Sawyers | Verbal | 2015-09-09 | 2015-09-09 | 09-sep-15 - Paper and Agenda have been distribute to security delegates and complete TRAS WG today to prepare for meeting on the 16th Sept @10:00 | CLOSED
83 |  | The question of I&C suppliers which was based upon the number of supply points for which data was submitted works out that there are in fact four more suppliers to add as Tier 2 suppliers. | Ben Haworth | Ben Haworth | TRAS Huddle/WS1 | 2015-09-10 | 2015-09-11 | Electralink may need to issue a new CCN to reflect the change in information. Once list of I&C suppliers is confirmed with Goverance services. | CLOSED
84 |  | Paul Pettit to review British Gas security questionnaire form before security subgroup meeting. | Paul Pettitt | Paul Pettit | TRAS Huddle/WS1 | 2015-09-10 | 2015-09-15 | 10-Sep-15 - complete before the security sub group meeting on the 16-Sep-15 | CLOSED
86 |  | Confirm name of new Experian resource (who will manage supplier engagements for data drop) | Kevin Henwood | Kevin Henwood | TRAS Telecon | 2015-09-11 | 2015-09-14 | 15-Sep-15 - Kevin Henwood has now confirmed the full time resources for supplier engagement for data drops going forward: John Hardcastle – Lead contact for Supplier On-boarding and new to Experian Richard Deere – Re-assigned into this role to provide continuity Ben Haworth to arrange meeting with John Hardcastle to progress supplier engagement for November data drop. Action closed. | CLOSED
87 | TRTC100915/01 | Add the CrimeStoppers’ operating model to somewhere near the top of the Working Group agenda and reissue the agenda on Mon 14 September. | Paul Gath | Paul Gath | TRAS Crimestoppers teleconference | 2015-09-10 | 2015-09-14 | This was done and discussed at the Working Group and subsequently at the Steering Group. | CLOSED
88 | TRTC100915/02 | Invite CrimeStoppers to the Working Group meeting at ElectraLink’s office on 15 September. | Kevin Henwood | Kevin Henwood | TRAS Crimestoppers teleconference | 2015-09-10 | 2015-09-14 | 14-Sep-15: Crimestoppers has been invited and confirmed attendance for the meeting on 15 Sept 2015. Action closed. | CLOSED
89 | TRTC100915/03 | Issue for information the proposed tip-off dataset to be sent from CrimeStoppers to Experian on a monthly basis. | Paul Gath | Paul Gath | TRAS Crimestoppers teleconference | 2015-09-10 | 2015-09-11 | Schedule agreed. | CLOSED
92 | TRTC100915/06 | Invite Andrew Warwick to the Working Group meeting at ElectraLink’s office on 15 September. | Kevin Henwood | Kevin Henwood | TRAS Crimestoppers teleconference | 2015-09-10 | 2015-09-11 | 14-Sep-2015: Meeting invite issued to Andrew Warwick, which he has confirmed he will dial in to the relevant section of the meeting. Action completed and closed. | CLOSED
98 | TSS/20150916/03 | Project risk to be added relating to the possibility that Experian may provide unacceptable answers to the Security Questionnaire, preventing completion of Security User Acceptance Testing. | ElectraLink | Paul Gath | TRAS Security subgroup | 2015-09-16 |  | 18-sep-15 - This will be included into the RISK register as advised by Ben Haworth. 23/09/15: This risk has now been added to the project risk register. CLOSED | CLOSED
99 | TSS/20150916/04 | Visit to Experian Data Centre to be arranged so that the Global Security Policy can be viewed and any further questions raised in relation to the Security Questionnaire on 14th October 2015. | Ben Haworth | Ben Haworth | TRAS Security subgroup | 2015-09-16 | 2015-10-14 | 23/09/15: Experian have proposed a visit on 19th October as the week including 14th October is already full. The TSS has asked whether it is necessary to visit Nottingham to view the GSP and whether an alternative is to view the GSP in London. 07/10/15: Visit confirmed for 19 October. | CLOSED
100 | TSS/20150916/05 | TRAS SharePoint Portal access to be provided to TSS members. | Ben Haworth | Ben Haworth | TRAS Security subgroup | 2015-09-16 | TBC | Ben Haworth to grant access t the TRAS Sharepoint portal to TRAS SS (PMO to identify completion date) | CLOSED
101 | TSS/20150916/06 | Procurement materials, contract, and project documentation to be reviewed in relation to use of live data in testing/development. | Ben Haworth | Ben Haworth | TRAS Security subgroup | 2015-09-16 | TBC | 23/09/15: BH has reviewed the materials and found support of the position to use live data in testing. A paper will be drafted for the TSS to review. 07/10/15: Paper drafted and discussed. See related action TSS/20151007/01. | CLOSED
102 | TSS/20150916/07 | Materials provided to SSE in relation to security issues to be distributed to the TSS with permission of Experian. | Ben Haworth | Ben Haworth | TRAS Security subgroup | 2015-09-16 |  | 23/09/15: BH discussed this with Experian who said that the materials provided to SSE were in strict confidence. BH explained that the materials are key to the functioning of the TSS and that they would need to be provided for review by the group. 07/10/15: Experian has indicated that any relevant information will be included in the responses to the questionnaire. | CLOSED
108 | TSS/20151007/03 | Collate the comments received from action TSS/20151007/03 and issue the consolidated responses to the TSS sub group by email by close of business on Friday 09 October 2015. | Natasha Khan | Natasha Khan | TRAS Security subgroup | 2015-10-07 | 2015-10-09 | 09/10/15: Had received responses from EON only and have since collated the results | CLOSED
109 | TSS/20150923/04 | Issue the consolidated comments from action TSS/20151007/03 and issue to Experian to help preparation for the meeting on 14 October. ElectraLink should make it clear to Experian that this is not a formal or final response. | Natasha Khan | Natasha Khan | TRAS Security subgroup | 2015-10-07 | 2015-10-09 |  | CLOSED
114 | TSS/20150923/02 | Questions with preferred responses to be circulated for decision on acceptance criteria. | ElectraLink | ElectraLink | TRAS Security subgroup |  |  | 07/10/15: Circulated and no responses received. Approved. | CLOSED
115 | TSS/20150923/03 | Inform Experian of preferred review cycle of responses to Questionnaire. | ElectraLink | ElectraLink | TRAS Security subgroup |  |  | 07/10/15: Experian informed. | CLOSED
119 |  | raise a new action relating to Kirstysemail
139 | TWG/150915/01 | Request information from Experian on the quality of all of the data received so that any issues can be addressed before the monthly data feeds commence in November. Ensure that Experian explain the content of the reports issued. | ElectraLink |  |  |  |  | 13/10/15: Data quality report issued to each Supplier who provided data with a key to explain the report. Surgeries to be arranged with Suppliers to assist with the submission of data. CLOSED | CLOSED
140 | TWG/150915/02 | Remind Experian that any future documents which require review or approval by the Working Group are issued in advance. | ElectraLink |  |  |  |  | 13/10/15: ElectraLink has fed this back to Experian. Timescales for document reviews included on the agenda. CLOSED | CLOSED
141 | TWG/150915/03 | Review the TRAM and clarify whether the solution developed by Experian for address matching meets the requirements, specifically in relation to the differentiation between the process developed for residential and commercial properties. | ElectraLink |  |  |  |  | 13/10/15: Details of address matching for residential and commercial properties is not included in the TRAM. This action has been superseded as Experian will not be required to match tip offs. CLOSED | CLOSED
142 | TWG/150915/04 | Provide additional information on the impact of amending the matching process to enable address only matching for commercial properties. | Experian |  |  |  |  | 13/10/15: This action has been superseded as Experian will not be required to match tip offs. CLOSED | CLOSED
143 | TWG/150915/05 | Work with Crimestoppers to develop a process for dealing with tip offs that cannot be matched to a Supplier. | ElectraLink |  |  |  |  | 13/10/15: To be included in work stream 5. CLOSED | CLOSED
144 | TWG/150915/06 | Further define the reporting format of management information from Experian to SPAA and DCUSA to ensure that all relevant information is included, specifically information regarding non matched tip offs | Experian |  |  |  |  | 13/10/15: This action is linked to the tip off line and has been superseded as Experian will not be required to match tip offs. CLOSED | CLOSED
145 | TWG/150915/07 | Section 6 of the operating model be amended to clarify that feedback from Suppliers in relation to the tip off may be provided via Hunter or the monthly feedback file. | Experian |  |  |  |  | 13/10/15: This action has been superseded as Experian will not be required to match tip offs. CLOSED | CLOSED
146 | TWG/150915/08 | Raise a Change Request to determine the costs of reducing the timescales to enable Experian to send tip offs for Suppliers more quickly having received monthly feeds from Crimestoppers. | ElectraLink |  |  |  |  | 13/10/15: This action has been superseded as Experian will not be required to match tip offs. CLOSED | CLOSED
147 | TWG/150915/09 | Raise a Change Request to determine the impact of reducing the timescales by which Crimestoppers should provide tip offs to Experian e.g. daily, weekly, fortnightly. | ElectraLink |  |  |  |  | 13/10/15: To be included in work stream 5. CLOSED | CLOSED
148 | TWG/150915/10 | Develop a process for handling instances of Change of Supplier to enable a tip - off to be re-allocated to the new Supplier once the old Supplier provides feedback that they have lost the site in accordance with clause 10.13 of TRAS Contract Schedule 2. | Experian |  |  |  |  | 13/10/15: This action has been superseded as Experian will not be required to match tip offs. CLOSED | CLOSED
149 | TWG/150915/11 | Add a risk to the Risk Register to cover concerns regarding non-domestic Suppliers receiving a lesser service compared to domestic Suppliers based on the proposed Crimestoppers’ operating model. | ElectraLink |  |  |  |  | 13/10/15: This action has been superseded as Experian will not be required to match tip offs. CLOSED | CLOSED
150 | TWG/150915/12 | Update the TEG ToRs and TRAS Change Guideline to reflect the working group response to the consultation comments, and circulate to the group. | ElectraLink |  |  |  |  | 13/10/15: Updated documents provided as attachments 2 and 3 to the minutes for the last meeting. CLOSED | CLOSED
151 | TWG/150915/13 | Issue the consultation responses in relation to the TRAS Dispute Procedure to Wragges for comment. | ElectraLink |  |  |  |  | 13/10/15: Response issued and response from Wragges received and discussed by the Governance Subgroup. CLOSED | CLOSED
152 | TWG/150915/14 | Convene a TRAS governance meeting to consider draft SPAA and DCUSA Change Proposals required to reflect the TEG ToRs and the TRAS change control process, comments on the Dispute Procedure, and also to agree the contents of Changes Proposals required in relation to payment default and cost recovery | ElectraLink |  |  |  |  | 13/10/15: Governance Subgroup meeting held on 30 September 2015. A report from this group is included under the Work stream 3 update. CLOSED | CLOSED
153 | TWG/150915/15 | Review and approve the functional user acceptance test documents by correspondence by 22 September 2015. | All |  |  |  |  | 13/10/15: No responses. An issue is being discussed by the Security Subgroup regarding the use of live data for testing. CLOSED | CLOSED
154 | TWG/150915/16 | Review and approve the security user acceptance test document by correspondence by 22 September 2015. | All |  |  |  |  | 13/10/15: No responses. Deemed approval. CLOSED | CLOSED
164 | TSG/20150923/05 | Highlight to Experian that SPAA and DCUSA has requested the relief event notice be formally withdrawn. | ElectraLink |  |  |  |  | 8/10/15: ElectraLink has raised this with Experian and will continue to progress the issue. ONGOING. 29/10/15: Experian has agreed to withdraw the original CCN that was raised as a result of the relief event. A new CCN will be raised for discussion at the next TSG meeting. This CCN will recognise that data wasn't submitted by 3 August and that the TRAM will only incorporate data that was received before the 3 August deadline. The relief notice should be withdrawn at this stage. CLOSED | CLOSED
165 | TSG/20151008/02 | Feed back to Experian the concern that the proposed 30 minute surgery sessions for each Supplier may not be sufficient. | ElectraLink |  |  |  |  | 29/10/15: Surgery timescales extended. CLOSED | CLOSED
166 | TSG/20151008/03 | Ask Experian to clarify what would happen where a Supplier who has already been onboarded fails to meet the November data drop deadline | ElectraLink |  |  |  |  | 29/10/15: Experian has sent the following clarification: 'The impact for an energy supplier of not submitting their data by the November deadline is that their data would not be available for development and testing until the December data submission is received. Suppliers who miss the December data submission date will not be able to participate in UAT as 2 months’ worth of data is necessary for TRAS UAT'. CLOSED | CLOSED
167 | TSG/20151008/04 | Add a future agenda item on the recovery of costs for onboarding new entrants. | ElectraLink |  |  |  |  | 29/10/15: Recovery of costs for including new entrants to be added to the agenda for the November TSG. ONGOING. | CLOSED
168 | TSG/20151008/05 | Produce a list of Suppliers who have not onboarded to share with the TSG at the next meeting on 21 October 2015. | ElectraLink |  |  |  |  | 29/10/15: List of Suppliers ready for November data drop included in the project status update. CLOSED | CLOSED
169 | TSG/20151008/06 | Update the side letter and issue to the TSG for ex committee review. The TSG will be asked to recommend approval by the SPAA and DCUSA Boards. | ElectraLink |  |  |  |  | 29/10/15: Side letter approved ex committee and agreed by Experian. CLOSED. | CLOSED
170 | TSG/20151008/08 | Produce a proposal for Work stream 5 for approval by the TSG. This will include the commercial arrangements with Crimestoppers, data protection considerations, the technical process for routing tip offs to Suppliers and the delivery of the launch campaign and microsite. | ElectraLink |  |  |  |  | 29/10/15: Workstream 5 proposal included on the agenda. CLOSED. | CLOSED
171 | TSG/20151008/09 | Raise a CCN to remove references to the tip off line from the TRAS Contract. It will be clear that costs incurred by Experian to date will be borne by Experian. | ElectraLink |  |  |  |  | 29/10/15: CCN on the agenda for approval. CLOSED. | CLOSED
172 | TSG/20151008/10 | Ensure that where the response to the security questionnaire references Experian's global security policy, it includes the policy version and clause so answers can be tracked at a later date. | ElectraLink |  |  |  |  | 29/10/15: Experian has provided its final submission and did not include the policy version and clause. ElectraLink has circulated the response to the Security Subgroup and informed Experian that it may be rejected due to the lack of this information. CLOSED | CLOSED
173 | TSG/20152008/12 | Include a slot on the agenda for the next TRAS Working Group meeting before Experian arrive to clarify the issues that need to be discussed and the approach to take. | ElectraLink |  |  |  |  | 29/10/15: Included on the agenda for the October TWG meeting. CLOSED | CLOSED
174 | TSG/20152008/13 | Update the joint working arrangements document to clarify the requirements in relation to payment default and the decision making process for ex committee decisions required where meetings are not quorate. This should be circulated to SPAA EC and DCUSA Panel members for ex committee decision. | ElectraLink |  |  |  |  | 29/10/15: Updated document on the agenda for the November TSG meeting. CLOSED | CLOSED
175 | TSG/20152008/14 | Separate future TSG agendas into open and closed sessions. | ElectraLink |  |  |  |  | 29/10/15: This will be done for future meetings. CLOSED | CLOSED
176 | TSG/20152008/15 | Provide feedback to ElectraLink on the TRAS Microsite paper. | SPAA EC and DCUSA Panel Members |  |  |  |  | 29/10/15: No feedback received. This will now form part of Workstream 5. CLOSED | CLOSED
177 | TSG/20152008/17 | Circulate the legal drafting for the TRAS Dispute CPs to SPAA EC and DCUSA Panel members with a request that they review the text from a SPAA and DCUSA perspective and provide comments to ElectraLink by 23 October 2015. | ElectraLink |  |  |  |  | 29/10/15: Legal drafting circulated. No comments received. CLOSED. | CLOSED
178 | TSG/20152008/18 | Review the legal drafting for the TRAS Dispute CPs and amend references from Secretariat to TRAS Contract Manager where appropriate, and include a definition of TRAS Contract Manager in the Codes. | ElectraLink |  |  |  |  | 29/10/15: All references to Secretariat replaced with TRAS Contract Manager and definition included. CLOSED. | CLOSED
179 | TSG/20152008/19 | Re-circulate Experian's PIA for review and comment (document 9.3.1.5). | ElectraLink |  |  |  |  | 29/10/15: Experian's PIA circulated. CLOSED. | CLOSED
180 | TSG/20152008/20 | Request that Experian provides positive confirmation to justify the use of all data items once the scorecard has been developed. | ElectraLink |  |  |  |  | 29/10/15: This has been done and a note circulated to industry. The PIA will be re-issued once the scorecard has been developed. CLOSED. | CLOSED
181 | TSG/20152008/21 | Share version 0.6 of the SPAA and DCUSA PIA with Suppliers. | ElectraLink |  |  |  |  | 29/10/15: V0.6 of the SPAA and DCUSA PIA shared. CLOSED. | CLOSED
182 | TSG/20152008/24 | Add an agenda item to the next TRAS Working Group meeting to discuss the creation of a standard set of Customer FAQs. | ElectraLink |  |  |  |  | 29/10/15: FAQs discussed at the October TWG meeting. CLOSED | CLOSED

## Decisions
TRAS Phase 4 Decision Log
ID | Reference | Decision | By | Date raised | Type

## Assumptions
TRAS Phase 4 Assumptions
Ref ID | Date Raised | Description | Workstream | Assumption last validated: | Status | Comments
AS001 | 2016-04-15 | Industry (SPAA & DCUSA) respond to requests in a timely manner so as not to delay the implementation process | WS1 |  | Open
AS002 | 2016-04-15 | Ofgem respondsto requests in a timely manner so as not to delay the implementation process | WS1 |  | Open
AS003 | 2016-04-15 | The Service Provider, Crimestoppers (CS), develops and provides systems and services tro time and quality | WS1 |  | Open
AS004 | 2016-04-15 | The service will be considered BAU after go-live | WS1 |  | Open
AS005 | 2016-04-15 | Once the service is live there will be a need for ongoing performance management of the service | WS3 |  | Open
AS006 | 2016-04-15 | Any changes to code or contract between now and go-live does not cause re-work | WS1 |  | Open
AS007 | 2016-04-15 | As data controller, CS will complete a draft of the Privacy Impact Assessment (PIA) prior to the 1st EWG meeting on 10 May 2016 | WS1 |  | Open
AS008 | 2016-04-15 | The EWG and TWG will be available for the UAT phase - <<check with E & P>> | WS1 |  | Open

## Issues
TRAS Phase 4 Issues
Ref #: | Date Raised | Workstream | Description | Owner | Status | Last Update: | Status Update

## Dependencies
TRAS - Project Dependencies
Ref #: | Date Raised | Workstream | Description | Mitigation | Dependency date | Owner | Status | Last Update: | Status Update
DP001
DP002
DP003
DP004
DP005
DP006
DP007
DP008
DP009
DP010
DP011
DP012
DP013
DP014
DP015
DP016
DP017
DP018
DP019
DP020
DP021
DP022
DP023
DP024
DP025
DP026

## ETTOS SPOC
MPID | Company Group | Primary SPOC | Primary SPOC E-mail Address | Secondary SPOC | Secondary SPOC E-mail Address

## Risks
TRAS Project Risk Log
[8 empty] | Current Status |  |  | Last Reported
Int. Ref | Ext. Ref | Internal / External | Date added | Last Updated | Risk / Issue | Risk Description | Risk Impact | Likelihood (1-5) | Impact (1-5) | Risk Score | Likelihood (1-5) | Risk Score (Last Reported) | Actions/ Mitigations | Action Owner | Date Due | Status
IR001 | RS001 | External | 2016-04-25 | 2016-06-03 | Risk | Access to Gas Data There has been a continuous delay in the agreement for CS to access gas data from XoServe and their proposal is still awaited. | This is a dependency to the essence of the ETTOS service and delay would impact the entire implementation | 4 | 4 | 16 |  | 0 | UNC Modification expected to go to UNC Mods Panel on 21st July - if agreed and allowing for appeals window data should be available 15th August. Manage Ofgem to chase XoServe to agree and send proposals | Sarah Jones | Ongoing | Open
IR002 | RS002 | Internal | 2016-04-26 | 2016-04-26 | Risk | Tight Timelines Project delays as Service go-live has tight implementation timelines. | Small margin for error | 2 | 5 | 10 |  |  | Ensure industry is as responsive as possible via timely and relevant communication | GS & Imp teams | Ongoing | Open
IR003 | RS003 | External | 2016-04-26 | 2016-04-26 | Risk | Timely Sign-Off Possible risk due to timeliness of sign-off from industry. | Delays to September 2016 go-live | 3 | 4 | 12 |  |  | Clarity of communiction from EWG to industry | EWG | Ongoing | Open
IR004 | RS004 | External | 2016-04-26 | 2016-06-03 | Risk | PIA Readiness Crimestoppers not having written a PIA before have suggested assistance from ElectraLink. | Lack of PIA weill have Data Protection Act implications | 2 | 2 | 4 |  |  | Integrate with CS' existing risk & security assessment policies and ElectraLink have supplied guidelines from the Information Commissioner's Office | CS | 2016-06-14 | Open
IR005 | RS005 | Internal | 2016-05-09 | 2016-05-09 | Risk | Low Response to SPOC Request A Crimestoppers requirement is to have a POC to send secure e-mails to. | Once CPs are formally approved this will become a compliance issue which will be taken forward through SPAA & DCUSA. | 3 | 4 | 12 |  |  | Flag the risk at the EWG on 14 June as well as resend the request to appropriate parties. | EL / Industry | 2016-06-14 | Open
IR006 | RS006 | External | 2016-05-20 | 2016-05-20 | Risk | Delay in dissemination of historic leads for testing Due to planned system updates historic data from Crimestoppers’ will not be available until mid July | Potential for delay of september go-live if problems identified during testing with historic data. | 2 | 3 | 6 |  |  | Monitor progress with Crimestoppers | CS | 2016-06-20 | Open
Note on M8: Kevin Lam: There is no likelihood score applied as the risk has now materialised into an issue

## ETTOS Governance Calendar
2015 | [14 empty] | 2016
| January | February | March | April | May | June | July | August | September | October |  | November |  | December |  | January |  | February
Saturday
Sunday | [11 empty] | 1
Monday | [5 empty] | 1 | [5 empty] | 2 |  |  |  |  | 1
Tuesday | [5 empty] | 2 |  |  | 1 |  |  | 3 |  | 1 |  |  | 2
Wednesday |  |  |  | 1 |  | 3 | 1 |  | 2 |  |  | 4 |  | 2 |  |  | 3
Thursday | 1 |  |  | 2 |  | 4 | 2 |  | 3 | 1 |  | 5 |  | 3 |  |  | 4
Friday | 2 |  |  | 3 | 1 | 5 | 3 |  | 4 | 2 |  | 6 |  | 4 | 1 |  | 5
Saturday | 3 |  |  | 4 | 2 | 6 | 4 | 1 | 5 | 3 |  | 7 |  | 5 | 2 |  | 6
Sunday | 4 | 1 | 1 | 5 | 3 | 7 | 5 | 2 | 6 | 4 |  | 8 |  | 6 | 3 |  | 7
Monday | 5 | 2 | 2 | 6 | 4 | 8 | 6 | 3 | 7 | 5 |  | 9 |  | 7 | 4 |  | 8
Tuesday | 6 | 3 | 3 | 7 | 5 | 9 | 7 | 4 | 8 | 6 |  | 10 |  | 8 | 5 |  | 9
Wednesday | 7 | 4 | 4 | 8 | 6 | 10 | 8 | 5 | 9 | 7 |  | 11 |  | 9 | 6 |  | 10
Thursday | 8 | 5 | 5 | 9 | 7 | 11 | 9 | 6 | 10 | 8 |  | 12 |  | 10 | 7 |  | 11
Friday | 9 | 6 | 6 | 10 | 8 | 12 | 10 | 7 | 11 | 9 |  | 13 |  | 11 | 8 |  | 12
Saturday | 10 | 7 | 7 | 11 | 9 | 13 | 11 | 8 | 12 | 10 |  | 14 |  | 12 | 9 |  | 13
Sunday | 11 | 8 | 8 | 12 | 10 | 14 | 12 | 9 | 13 | 11 |  | 15 |  | 13 | 10 |  | 14
Monday | 12 | 9 | 9 | 13 | 11 | 15 | 13 | 10 | 14 | 12 |  | 16 |  | 14 | 11 |  | 15
Tuesday | 13 | 10 | 10 | 14 | 12 | 16 | 14 | 11 | 15 | 13 |  | 17 |  | 15 | 12 |  | 16
Wednesday | 14 | 11 | 11 | 15 | 13 | 17 | 15 | 12 | 16 | 14 |  | 18 |  | 16 | 13 |  | 17
Thursday | 15 | 12 | 12 | 16 | 14 | 18 | 16 | 13 | 17 | 15 |  | 19 |  | 17 | 14 |  | 18
Friday | 16 | 13 | 13 | 17 | 15 | 19 | 17 | 14 | 18 | 16 |  | 20 |  | 18 | 15 |  | 19
Saturday | 17 | 14 | 14 | 18 | 16 | 20 | 18 | 15 | 19 | 17 |  | 21 |  | 19 | 16 |  | 20
Sunday | 18 | 15 | 15 | 19 | 17 | 21 | 19 | 16 | 20 | 18 |  | 22 |  | 20 | 17 |  | 21
Monday | 19 | 16 | 16 | 20 | 18 | 22 | 20 | 17 | 21 | 19 |  | 23 |  | 21 | 18 |  | 22
Tuesday | 20 | 17 | 17 |  | 19 | 23 | 21 | 18 | 22 | 20 |  | 24 |  | 22 | 19 |  | 23
Wednesday | 21 | 18 | 18 | 22 | 20 | 24 | 22 | 19 | 23 | 21 |  | 25 |  | 23 | 20 |  | 24
Thursday | 22 | 19 | 19 | 23 | 21 | 25 | 23 | 20 | 24 | 22 |  | 26 |  | 24 | 21 |  | 25
Friday | 23 | 20 | 20 | 24 | 22 | 26 | 24 | 21 | 25 | 23 |  | 27 |  | 25 | 22 |  | 26
Saturday | 24 | 21 | 21 | 25 | 23 | 27 | 25 | 22 | 26 | 24 |  | 28 |  | 26 | 23 |  | 27
Sunday | 25 | 22 | 22 | 26 | 24 | 28 | 26 | 23 | 27 | 25 |  | 29 |  | 27 | 24 |  | 28
Monday | 26 | 23 | 23 | 27 | 25 | 29 | 27 | 24 | 28 | 26 |  | 30 |  | 28 | 25 |  | 29
Tuesday | 27 | 24 | 24 | 28 | 26 | 30 | 28 | 25 | 29 | 27 |  |  |  | 29 | 26
Wednesday | 28 | 25 | 25 | 29 | 27 |  | 29 | 26 | 30 | 28 |  |  |  | 30 | 27
Thursday | 29 | 26 | 26 |  | 28 |  | 30 | 27 |  | 29 |  |  |  | 31 | 28
Friday | 30 | 27 | 27 |  | 29 |  | 31 | 28 |  | 30 |  |  |  |  | 29
Saturday | 31 | 28 | 28 |  | 30 |  |  | 29 |  | 31 |  |  |  |  | 30
Sunday |  |  | 29 |  | 31 |  |  | 30 | [6 empty] | 31
Monday |  |  | 30 |  |  |  |  | 31
Tuesday |  |  | 31
Wednesday
Thursday
Friday
Saturday
Sunday
Monday
Tuesday
Key
TRAS WG
DCUSA
SPAA-EC
TRAS SS