## Horizon Scan
DCUSA Horizon Scan 2019 - 2023
YEAR | [10 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023
MONTH | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
BREXIT | BREXIT
Access and Forward Looking Charges: SCR | Access and Forward Looking Charges: SCR
Targeted Charging Review (TCR): SCR on Residual Charges | Targeted Charging Review (TCR): SCR on Residual Charges
Faster Switching and CRS | Faster Switching and CRS
Market Wide HH Settlement | Market Wide HH Settlement |  |  |  |  | FINAL DWG REPORT |  |  | OFGEM FULL BUSINESS CASE DECISION |  | CODE & LICENCE CHANGES DRAFTED AND MADE BY OFGEM (WITH INDUSTRY SUPPORT / CONSULTATION) | [11 empty] | TRANSITION TO TARGET OPERATING MODEL | [23 empty] | TARGET OPERATING MODEL FULLY EFFECTIVE
2022 UK General Election |  |  |  | 2022 UK General Election
BEIS Smart Systems and Flexibility Plan | BEIS Smart Systems and Flexibility Plan
Smart Meter Rollout | Smart Meter Rollout
ENA Open Networks Project | ENA Open Networks Project
Retail Energy Code Consequential Changes | Retail Energy Code Consequential Changes
BEIS Energy Codes Review | BEIS Energy Codes Review
Decisions on RIIO-ED2 | [37 empty] | Decisions on RIIO-ED2

## Commentary
Horizon Item | Commentary | Update
Brexit | • The UK exit from the EU is likely to have consequential impacts on the UK Energy Market. • The steer from Ofgem is for changes to industry codes be taken forward through the industry-led code change process. Code administrators reviewed the codes to identify where changes may be required in the event the UK leaves the EU without a deal. • It was noted that Ofgem expects industry to ensure modifications to the codes are raised in a timely way to minimise uncertainty for market participants. To achieve this, Ofgem’s view is that it is vital that ‘day 1’ code changes are prioritised and the regulatory framework is updated. These are the consequential changes required to update industry codes in line with the post-EU Exit domestic legislation. • A DCUSA Change Proposal (DCP) has not been drafted as yet, however it is noted that all of the relevant information to do so is in place and once the decision is known it will drafted and issued to the DCUSA legal advisors to confirm the red line version. The DCUSA legal advisors have been involved in the process to date and so it is not expected to take more than a few days to turn around. The required changes to DCUSA are of a minor nature and none (if not changed) will render any element of DCUSA inoperable. • Article 50 has been extended and the view from Ofgem is that preparations for the potential of exiting the EU without a deal should now focus on 31 October 2019. During the extension they expect Code Administrators to keep the changes under review in case new legislation/code changes cause the modifications that were previously prepared to be out of date.
Access and Forward Looking Charges: SCR | Scope of the SCR and wider review In Ofgem's July 2018 consultation, they set out different options for our role and that of industry and stakeholders in leading a review of access and forward-looking charging arrangements. On 18 December 2018 Ofgem launched an SCR to take forward - - a review of the definition and choice of access rights for transmission and distribution users - a wide-ranging review of distribution network charges (Distribution Use of System (DUoS) charges) - a review of the distribution connection charging boundary, and - a focused review of transmission network charges (Transmission Network Use of System (TNUoS) charges) Ofgem have decided to exclude from the SCR – - Introducing fixed duration long-term access rights - Introducing geographically exclusive local access rights which do not allow access to the rest of the system - Wider changes to transmission network charges - The transmission connection charging boundary. Ofgem think that the Electricity System Operator and network companies should separately take forward the following as part of the wider review, outside the SCR - - a review of aspects of allocation of access rights, including improved queue management and the scope for trading - a review of balancing services charges. This is being taken forward by the Electricity System Operator through a balancing services charges task force
Targeted Charging Review (TCR): SCR on Residual Charges | On 4 August 2017 Ofgem launched their Targeted Charging Review - Significant Code Review. The main objectives of this SCR are to: - consider reform of residual charging for transmission and distribution, for both generation and demand, to ensure it meets the interests of consumers, both now and in future; and - keep the other ‘embedded benefits’ that may be distorting investment or dispatch decisions under review. The SCR was launched to address our concern that the current framework for residual charging may drive inefficient behaviours from some network users, and result in adverse impacts on some network users, and hence consumer. Ofgem proposed the creation of the Charging Futures Forum (CFF) as a wide-reaching forum which will take direction from stakeholders on charging policy. As the code which contains the current charging models, it is highly likely that DCUSA will be discussed in depth at this forum and that the DCUSA charging models will be subject to review and eventual change as a result of these discussions. On 28 November 2018 Ofgem issued 'Targeted Charging Review: Minded to decision and draft impact assessment' This takes the form of a further consultation on two aspects of change which will form the direction that Ofgem will give to the industry next year: - On the best way of setting the transmission and distribution residual charges; and on some of the remaining “Embedded Benefits” – which are different charging arrangements for smaller generators connected to the distribution system (called ‘smaller embedded generators’), compared to larger generators. Both of these are covered by a Significant Code Review where Ofgem are establishing the basis for detailed changes to be made by the industry. On setting transmission and distribution residual charges, after significant analysis of different approaches, Ofgem have chosen two leading options which are: - A Fixed Charge. Charges are set for individuals in customer segments, with these segments being based on an existing industry approach (preferred option) - An Agreed Capacity Charge. For those larger users who have a specified agreed capacity, a charge would be calculated directly. Capacity for households and smaller business would be based on assumed levels.
Faster Switching and CRS | The Faster Switching Programme and Centralised Registration Service (CRS) are likely to impact DCUSA in terms of how flows are sent and handled, with the expectation that DCUSA flows and communications will continue to utilise current arrangements, however these are expected to flow via the CRS. It is also possible that some aspects of the DCUSA could be transferred. In the February 2018, Ofgem set out the following high level timeline for the production of the REC and associated governance:  Q2-4 2018: Consult on transitional arrangements and key changes to enduring provisions, initiate statutory consultation on creation of the REC  Q1 2019: potential for REC v1 to take effect providing governance for transitional requirements, and establish RECCo to initiate procurement of enduring REC code administrator.  Q4 2019: initiate statutory consultation on modification of enduring licence conditions, issue final draft of code modifications to be pursued through SCR process; and,  CSS go-live (possibly Q4 2020): Conclude the SCR, move CSS funding arrangements from SEC to REC and programme hands over responsibility to standard ‘business as usual’ governance.
Market Wide HH Settlement | Following an updated to the Panel at their February 2019 meeting the following timeline of events related to Market Wide HH Settlement will continue to be monitored with respect to impacts on the DCUSA. DWG’s report to Ofgem on preferred TOM & requirements = End Jan 2019 DWG’s consultation on preferred TOM & requirements = Feb/Mar 2019 Ofgem’s Request for Information (participant costs/impacts) = Spring 2019 DWG’s consultation on transition approach = June/July 2019 BSC impact assessment on implementing/transitioning TOM = June/July 2019 DWG’s final report to Ofgem = August 2019 Ofgem’s full business case decision = Late 2019 Code & licence changes drafted and made by ofgem (with industry support / consultation) = ~2020 Transition to TOM = ~2021-2022 TOM fully effective = ~2023 Run-off of previous Settlement Days = ~2023+
2022 General Election | It is expected that the energy industry will be the focus of a number of election pledges during the 2023 UK General Election, with the likely emphasis being on network reinforcement with the increasing number of electric cars in the UK, energy storage and DG arrangements - all having impacts on DCUSA and the pricing models.
BEIS Smart Systems and Flexibility Plan | In July 2017 BEIS issued a paper on Smart Systems and their Flexibility Plan which contains a number of recommendations that could have impacts on DCUSA, such as removing barriers for electricity storage on the network, linking microgeneration and smart metering and modifying industry codes on a wholesale level to incorporate energy storage. The plan detailed key focus areas in response to an electricity system undergoing changes such as: • increased use of low-carbon sources, • increased uptake of electric vehicles (EVs) and smart technologies, • the growth of distributed energy and the role of flexibility. The initial plan set out 29 specific actions for BEIS and Ofgem to carry out to achieve a smart and flexible future energy system. On 16 October 2018, BEIS and Ofgem released a progress report that said, to date, 15 of the 29 actions in the plan have been implemented across the three fields: • removing barriers to smart technologies • enabling smart homes and businesses, and • making markets work for flexibility. The report committed to delivering the remaining 14 forward actions by 2022. In addition, BEIS and Ofgem have identified nine related actions beyond those set out in the plan since its publication. For instance, the BEIS intends to consult on the treatment of electricity storage facilities with respect to the current national planning threshold to ensure they face no barriers to deployment. Some of these issues are expected to impact DCUSA in 2019.
Smart Meter Rollout | Ofgem's Smart Meter Rolliut programme has placed obligations on Suppliers to complete rollout of SMETS compliant meters by the end of 2020. Smart Meter Rollout Profiles are collated via DCUSA to aid Meter Operators in their resource allocations for rollout activites.
ENA Open Networks Project | The objectives of the Open Networks Project for the first phase of work in 2017 are to: 1. Develop improved T-D processes around connections, planning, shared TSO/DSO services and operation 2. Assess the gaps between the experience our customers currently receive and what they would like and identify any further changes to close the gaps within the context of ‘level playing field’ and common T & D approach 3. Develop a more detailed view of the required transition from DNO to DSO including the impacts on existing organisation capability 4. Consider the charging requirements of enduring electricity transmission/distribution systems Second Phase in 2018 and then beyond to RIIO ED2/T2 (2023): Phase 2: Impact Assessment of Options and Preferred Design Phase 3: Regulatory Enactment Phase 4: Design, Build and Test
Retail Energy Code Consequential Changes | At its September meeting the DCUSA Panel was provided with an update on Ofgem’s Switching Programme. As part of this update, it was highlighted to Panel members that an Ofgem led Significant Code Review (SCR) has been initiated to ensure that consequential changes to industry codes as a result of the new switching arrangements are delivered in a co-ordinated manner.
BEIS Energy Codes Review | Government and Ofgem are launching a joint comprehensive review into the codes which govern the energy system. The aim of the review is to consider options for improving the existing arrangements, including scope for fundamental reform. Previous reviews by Ofgem have delivered notable improvements to code governance, but further changes appear to be necessary given the scale of ongoing industry change. Ofgem plan to revisit the CMA code governance remedies in light of the latest energy market developments. The review will consider the entirety of the rules underpinning the electricity and gas networks, and the wholesale and retail markets. The questions to be addressed by the review include: - Purpose of Codes: consider whether a code system is still appropriate for all the areas of rules in the energy system, and whether there is scope to handle some elements of codes differently – for example, in code guidance, commercial contracts, or consumer protection legislation. This will explore how a more risk-based approach seen in other regulated industries may apply to energy. - Content of Codes: Ofgem will seek stakeholders’ views on whether the content of codes is up-to-date, relevant and applicable, and whether and how it may be improved. This will explore the role that digital technology may play in this regard. - Governance of Codes: Ofgem will assess the effectiveness of the current industry governance arrangements. In light of that, we will consider alternative models of governance and whether these may be more effective than the status quo. - Process of changing codes: a key aim of the review is to develop a regulatory framework capable of delivering strategic, whole-system solutions in the interests of consumers. This means considering how new arrangements can be made more forward-looking, rather than reactive. - Transition: Ofgem will give careful consideration to the process of moving from the current code environment to the desired end state. They will need to develop a transition model which will ensure smooth running of markets, and minimise any transition costs. Process & outputs This review will work closely with ongoing policy work on the future of the retail market and a new approach to data, given the close interactions between them. Ofgem aim to consult on changes to the existing arrangements by summer 2019. The timeline for the introduction of any new arrangements will take into account wider market developments and seek to remain coherent with other reforms currently underway across the energy sector.
Decisions on RIIO-ED2 | RIIO-ED2will be the next round of network price controls to start from 2023. Ofgem alongside industry are currently working in developing the RIIO-2 price conrols across gas distribution businesses and system operators, although it is understood that this work will feed into the electrcity distriburtion price controls: OPEN LETTER ON THE RIIO-2 FRAMEWORK PUBLISHED: 12TH JUL 2017 This set out the context for the development of RIIO-2 and seeks views from stakeholders on the RIIO-2 framework. STAKEHOLDER ENGAGEMENT FOR THE RIIO-2 FRAMEWORK REVIEW PUBLISHED: 20TH SEP 2017 This letter set out Ofgem’s Stakeholder Engagement Plan for the RIIO-2 Framework Review. RIIO-2 FRAMEWORK CONSULTATION PUBLISHED: 7TH MAR 2018 CLOSED: 2ND MAY 2018 Ofgem consulted on the framework to set the next round of price controls for the companies that operate the gas and electricity networks in GB. RIIO-2 ENHANCED STAKEHOLDER ENGAGEMENT GUIDANCE PUBLISHED: 28TH MAR 2018 Ofgem published their guidance on the enhancements they are making to the stakeholder engagement that will underpin riio-2. RIIO-2 FRAMEWORK DECISION PUBLISHED: 30TH JUL 2018 Ofgem’s decision on the framework we will use to set price controls for the companies that run the gas and electricity networks in Great Britain (RIIO-2) RIIO-2 BUSINESS PLANS INITIAL GUIDANCE DOCUMENT PUBLISHED: 28TH SEP 2018 Initial guidance to help energy network companies and their stakeholders understand the type of information they will expect to see in their RIIO-2 business plans

## Background
No | Task | Status | Owner | Outlook date
1 | Significant Code Review: Ofgem consultation on Central Registration Service provision | September 2015 – The Panel agreed for the consultation should be added to the Log as it might have an impact on the DCUSA, details of the consultation can be found at the following link: https://www.ofgem.gov.uk/sites/default/files/docs/2015/07/crs_dcc_licence_consultation_final3.pdf | Panel | Ongoing
October 2015 – It was noted that Ofgem has had presentations on the consultation at other Panels and AS took an action to find out if Ofgem would be carrying out a presentation on their consultation to the DCUSA Panel.
December 2015 – the Panel noted Ofgem presented on their consultation at the November Panel meeting
February 2016 – The Panel noted that the Ofgem Workshops have are now in progress and the DCUSA Panel should be aware of the discussions at the workshops as there may be changes that might have an impact on the DCCUSA.
May 2016 – The Panel noted that a CMA presentation took place at the DCUSA Panel April Panel meeting. The Panel requested that Ofgem provide periodical updates on the progress of the faster switching project. AS took an action to confirm whether Ofgem can establish formal communication routes for industry bodies that are not represented on the Central Registration Project (faster switching) Workgroups. This would give these bodies insight into the development of the project and potential impacts.
June 2016 – It was noted that AS is to organise a presentation on the Central Registration Project (faster switching) Workgroups. It was noted that this would be useful towards the end of the year so that the impacts of the project can feed into the DCUSA budget setting processes for 2017/18.
July 2016 – AS informed that the Panel that Ofgem will be providing a presentation on the Central Registration Project (faster switching) later on in the year.
September 2016 - The Panel noted that Ofgem will provide a general update on the Central Registration Project (faster switching) at the October meeting.
October 2016 - Ofgem presented on the Central Registration Project (faster switching). It was noted that the purpose of the presentation was to: Request views on Ofgem’s proposed reform packages; Test initial thinking on the RFI; and Set out Ofgem’s next steps
December 2016 – The Panel noted that a Request for Information (RFI) is expected to be issued in January regarding faster switching.
January 2017 – The Panel agreed to wait and see if any impacts are identified as a result of the RFI
February 2017 – Panel members noted that they will review responses once they become available. The Chair noted that there appears to be limited impact to DCUSA however will wait for outcome as it is dependent upon the what the scope is.
June 2017 – The Panel noted that the EDAG are meeting with Ofgem on 22 June 2017.
July 2017 – The Panel noted that Ofgem are favouring Option Model 2A.
October 2017 - the Panel noted that a consultation titled ‘Delivering Faster and More Reliable Switching: proposed new switching arrangements’ has been issued. It was also noted that the scope of a Retail Energy Code (REC) relating to the provision of faster switching is set out within the document. The Panel requested that the Secretariat review the consultation and confirm if there are references to TRAS and if so can be noted in the log. It was noted that the SPAA EC plan to speak with Ofgem about TRAS going into a single REC.
5 | Significant Code Review: Half Hourly Settlement. | January 2016 - Ofgem has initiated a review to establish cost effective half hourly settlement for all consumers. | Panel | Ongoing
February 2016 – The Panel noted that the Ofgem Open letter on Half Hourly Settlement was issued in December 2015 and is now closed. Ofgem is reviewing the responses and the next step is to publish the responses in March 2016.
March 2016 – The Panel noted that Ofgem published the responses to their Open letter on Half Hourly Settlement on 09 March 2016. The responses can be found at the following link: https://www.ofgem.gov.uk/publications-and-updates/elective-half-hourly-settlement-publication-responses-december-open-letter
May 2016 - AS informed the Panel that conclusions on Half Hourly Settlement will be published at the end of May 2016.
June 2016 – The Panel noted Ofgem’s conclusions on ‘HH Elective Settlement’ in relation to the impact on DCP 268 ‘DUoS Charging Using HH Settlement Data’.
The Panel noted that Ofgem expects the change to be implemented by early 2017. The Panel noted that there is no immediate barrier under DCP 268 and agreed that the CP should run its normal course.
September 2016 – It was noted that DCP 268 was raised to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. This is a standalone change. The DCP 268 Working Group is developing the CP solution and the proposed implementation date is 1 April 2019.
November 2016 - The DCUSA Panel agreed to not provide a response to Ofgem’s consultation on Half-Hourly (HH)Settlement as it was considered that Parties responses to this consultation should be sufficient.
December 2016 - Panel agreed to discuss the results of the consultation once they are available.
January 2017 – The Panel will review the outcomes of the Ofgem HH settlement consultation and noted Ofgems’ response to this is due to be published shortly.
February 2017 – The Panel noted that they will wait for Ofgem to publish the results of the consultation.
March 2017 – The Panel noted that they are awaiting the outcomes from the Ofgem consultation on a Significant Code Review
May 2017 – It was noted that the outcome is expected in the first quarter of 2018. The Ofgem representative noted that Ofgem expect to publish a launch statement after the UK general election.
June 2017 – The Panel noted that Ofgem expect to publish a launch statement in December.
July 2017 – The Panel noted that industry is awaiting the next Ofgem launch statement.
August 2017 – The Ofgem representative noted that Ofgem issued a launched statement on 24 July 2017. The statement Included a timeline for the project and set out a revised scope. The statement also provides responses to Novembers consultation and sets out the proposed operating model for Half Hourly Settlement. It was noted that Elexon will lead the Target Operating Model Design Working Group. VM noted that feedback on the operating model and applications to join the Working Group are being sought by 1 September 2017.
October 2017 - An ELEXON representative noted that a high-level plan has been produced for progression of ELEXON led work to support Ofgem in its Significant Code Review (SCR) on Mandatory Half-Hourly Settlement (HHS). It was noted that documents are available on the ELEXON website but is considered an external group and not a BSC committee. The DWG has had its first meeting where they discussed three strawman options. It was noted that a link is available to access the DWG page on the ELEXON website and the Panel requested for the Secretariat to add the link to the Monitoring Activities Log.
7 | Decisions on RIIO-ED2 | OPEN LETTER ON THE RIIO-2 FRAMEWORK PUBLISHED: 12TH JUL 2017 THIS SET OUT THE CONTEXT FOR THE DEVELOPMENT OF RIIO-2 AND SEEKS VIEWS FROM STAKEHOLDERS ON THE RIIO-2 FRAMEWORK.
STAKEHOLDER ENGAGEMENT FOR THE RIIO-2 FRAMEWORK REVIEW PUBLISHED: 20TH SEP 2017 THIS LETTER SET OUT OFGEM’S STAKEHOLDER ENGAGEMENT PLAN FOR THE RIIO-2 FRAMEWORK REVIEW.
RIIO-2 FRAMEWORK CONSULTATION PUBLISHED: 7TH MAR 2018 CLOSED: 2ND MAY 2018 OFGEM CONSULTED ON THE FRAMEWORK TO SET THE NEXT ROUND OF PRICE CONTROLS FOR THE COMPANIES THAT OPERATE THE GAS AND ELECTRICITY NETWORKS IN GB.
RIIO-2 ENHANCED STAKEHOLDER ENGAGEMENT GUIDANCE PUBLISHED: 28TH MAR 2018 OFGEM PUBLISHED THEIR GUIDANCE ON THE ENHANCEMENTS WE ARE MAKING TO THE STAKEHOLDER ENGAGEMENT THAT WILL UNDERPIN RIIO-2.
RIIO-2 FRAMEWORK DECISION PUBLISHED: 30TH JUL 2018 OFGEM’S DECISION ON THE FRAMEWORK WE WILL USE TO SET PRICE CONTROLS FOR THE COMPANIES THAT RUN THE GAS AND ELECTRICITY NETWORKS IN GREAT BRITAIN (RIIO-2)
RIIO-2 BUSINESS PLANS INITIAL GUIDANCE DOCUMENT PUBLISHED: 28TH SEP 2018 INITIAL GUIDANCE TO HELP ENERGY NETWORK COMPANIES AND THEIR STAKEHOLDERS UNDERSTAND THE TYPE OF INFORMATION WE WILL EXPECT TO SEE IN THEIR RIIO-2 BUSINESS PLANS
Ofgem is expecting to finalise the framework in summer 2018.