## Sheet1
DCMDG Issues | [6 empty] | DCUSA Change Proposals | [5 empty] | Ofgem CFF Task Forces | Ofgem Driven Reviews | Other Industry Reviews/Impacts | External Impacts
No. | Originator | Area | Description | Synopsis | Status | Target Implementation | No. | Area | Description | Synopsis | Status | Target Implementation
[7 empty] | 161 | CDCM | Excess Capacity Charges | To improve the cost reflectivity of the excess capacity charge calculation within the CDCM and EDCM by removing the customer contributions and adding in any additional costs that should be attributed to this charge. Also, to consider applying the excess capacity charge on either a monthly, seasonal or time of day basis. | Approved (Awaiting Implementation) | 2018-04-01 | Forward Looking Charging | Residuals | BEIS Smart Systems and Flexibility Plan. | UK Election
[7 empty] | 222 | CDCM | Non Billing of Excess Reactive Power Charges | The removal of the excess reactive power charge when a DNO requests that a generator operates outside of the 0.95 power factor limit | Approved (Awaiting Implementation) | 2018-04-01 | Access | Mandatory HH Settlement | Electric Vehicles | Brexit
[7 empty] | 228 | CDCM | Revenue Matching in the CDCM | The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | Approved (Awaiting Implementation) | 2018-04-01 |  | RIIO-2 | Storage | Labour Party Energy Manifesto
[7 empty] | 234 | CDCM & EDCM | Merging the PCDM and extended PCDM | To replace the Price Control Disaggregation Model (PCDM) and extended PCDM models with one model. To create a new schedule in DCUSA which contains the legal text that relates to IDNO charging that is currently contained in Schedules 16, 17 and 18. | Approved (Awaiting Implementation) | 2018-04-01 |  |  | Distributed Generation
[7 empty] | 243 | CDCM | Treatment of Customer Contributions in the CDCM | This CP seeks to revise DCUSA Schedule 16 to utilise current source data to determine a common industry set of modelling inputs in order to improve clarity in the approach to be used in calculating ‘Customer contribution under the current connection charging policy’ for use in CDCM table 1060. | Consultation | 2020-04-01 |  |  | IDNOs
[7 empty] | 266 | CDCM | The Calculation and Application of IDNO Discounts | The intent of this change proposal is to change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this change proposal is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | Definition | 2020-04-01 |  |  | Dual Use Assets
[7 empty] | 268 | CDCM | DUoS Charging using HH Settlement Data | The intent of this proposal is to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | Change Report | 2020-04-01 |  |  | Judicial Review on Embedded Benefits
[7 empty] | 273 | CDCM | Align CDCM Table 1001 (Target Revenue) to latest Schedule 15 Template | The intent of this proposal is to align table 1001 in the CDCM to the current format of table in in Schedule 15. | Approved (Awaiting Implementation) | 2018-04-01 |  |  | ENA Consulatation on Electricity Network Innovation Strategy
[7 empty] | 283 | CDCM | The Calculation of Generation Credits in the CDCM | The intent of this change proposal is to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators. | Definition | 2020-04-01 |  |  | ENA Consulatation on the annual review of CACoP
[7 empty] | 287 | EDCM | Generation Credits in the EDCM | The intent of this Change Proposal is to amend the calculation of credits for embedded generation in the EDCM to take account of potential cost savings for DNOs that can be attributed to embedded generation in the areas of transmission exit charges, direct costs, indirect costs and network rates. | Consultation | 2020-04-01
[7 empty] | 290 | CDCM & EDCM | Housekeeping Change to Update PCDM Model References | The intent of this Change Proposal is to facilitate the updating of the title, model number and issue date of the PDCM as referenced in Schedules 16, 17 and 18, which was not correctly applied in the legal text of DCP234. | Approved (Awaiting Implementation) | 2018-04-01
[7 empty] | 293 | CDCM, EDCM & PCDM | Charging Methodology Cut-Off Date | DCUSA has a requirement for DNOs to provide fifteen months’ notice of changes to Use of System charges. This necessitates DNOs to have complete and final versions of the charging methodologies and a complete and final suite of fully tested charging models (CDCM, EDCM, PCDM and ARP) for the relevant charging year prior to initiating the calculation and validation of revised charges. This change looks to establish a cut-off date for the finalisation of the charging methodologies at 17 months prior to the date that the methodology would become effective. Establishing this cut-off date will provide a 2-month time window for DCUSA to provide charging models and DNOs to test the new charging models and then to calculate, test and approve revised charges. | Approved (Awaiting Implementation) | 2018-04-01
[7 empty] | 294 | CCCM | Capacity Management Following Acceptance of Connection Offer | This change seeks to put arrangements in place that set out the principles under which the unutilised maximum capacity specified in connection offers or in bilateral connection agreements with IDNOs can be managed in an economic and efficient manner whilst protecting the legitimate requirements of parties requiring Capacity which was agreed in connection offers. | Consultation | Next Release Following Approval
[7 empty] | 305 | EDCM | LDNO Boundary Level Definitions in the EDCM | The intent of this change proposal is to amend the definitions and application of DNO/LDNO boundaries under the EDCM to avoid instances of double-and/or non-charging for certain assets. | Definition | 2020-04-01
[7 empty] | 306 | PCDM | Treatmen of Ofgem License Fees within the PCDM | The intent of this Change Proposal is to increase the cost reflectivity of the Price Control Disaggregation Model by directly allocating the Ofgem licence fee to an appropriate network tier for the calculation of the Opex allocation driver | Definition | 2020-04-01
[7 empty] | 311 | EDCM | Clarification of NUF Cap & Collar Calculations | The intent of this Change Proposal is to modify schedules 17 and 18 to clarify which years should be used when determining NUF caps and collars to be applied for each charging year, and to remove an additional year lag which has been built into the legal text for the cap and collar calculations for 2023/24 charges | Definition | 2020-04-01
[7 empty] | 313 | EDCM | Eligibility Criteria for EDCM Generation Credits | The intent of this Change Proposal is to improve transparency of the eligibility criteria for EDCM generators to receive super red credits, and to improve consistency in the application thereof. | Definition | 2020-04-01