## CPs
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst/WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status Changed in the last month
STATUS - DEFINITION
DCP 243 | Treatment of Customer Contributions in the CDCM | ​This CP seeks to revise DCUSA Schedule 16 to utilise current source data to determine a common industry set of modelling inputs in order to improve clarity in the approach to be used in calculating ‘Customer contribution under the current connection charging policy’ for use in CDCM table 1060. | CDCM | 1 | Dylan Townsend/ John Lawton | Dominic Green | 2015-06-05 | 18 |  | 2020-04-01 | The Working Group agreed to proceed to final consultation after deciding on which option to proceed with and issued the final consultation on 27 October 2017. The Working Group are due to meeting on 12 January 2018 to review the consultation responses. | CONSULTATION
DCP 266 | The calculation and application of IDNO discounts | To change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this CP is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | CDCM | 1 | Dylan Townsend/ John Lawton | Tim Aldridge | 2016-03-09 | 9 |  | 2020-04-01 | Amended modelling was requested and has been receieved, the group met on 25 September to review the modelling and impact assessment and are met again on 12 October to review the draft consultation document. Futher Impact anaysis has been requested by the group which will include all DNO areas. The updated Impact Assessment has been receieved and the Working Group are reviewing this. The next meeting is scheduled for mid to late January, pending availability of the group. | NO
DCP 268 | DUoS Charging Using HH settlement data | The intent of this CP is to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | CDCM | 1 | Dan Fittock / John Lawton | Lynda Carroll | 2016-03-14 | 10 |  | 2020-04-01 | DCUSA Parties voted to accept the Solution and to reject the implementation date. The Authority's decision to send back DCP 268 was received on 20 October and the Working Group is due to reconvene to review Ofgem's feedback on 11 January 2018. | DEFINITION
DCP 287 | Generation credits in the EDCM | The intent of this Change Proposal is to amend the calculation of credits for embedded generation in the EDCM to take account of potential cost savings for DNOs that can be attributed to embedded generation in the areas of transmission exit charges, direct costs, indirect costs and network rates. | EDCM | 1 | Dan Fittock / John Lawton | Edda Dirks | 2016-12-07 | 8 |  | 2020-04-01 | The Working Group last met on 11 December 2017 to review the RFI results received from DNOs. The Working Group is next scheduled to convene on 23 January 2017 to review the draft second Cosnultation document. | NO
DCP 294 | Capacity Management Following Acceptance of Connection Offer | This CP seeks to put arrangements in place that set out the principles under which the unutilised maximum capacity specified in connection offers or in bilateral connection agreements with IDNOs can be managed in an economic and efficient manner whilst protecting the legitimate requirements of parties requiring Capacity which was agreed in connection offers. | CCCM | 1 | Hollie Nichollls/ John Lawton | Moshe Kinshuck | 2017-03-01 | 6 |  | First release following approval | The first Working Group meeting took place on the 20 April 2017 and it was agreed that legal advice was required before a solution could be progressed on this CP. The Working Group are in the process of finalising the legal advice questions for submission to the DCUSA Panel for approval. The Panel requested that the Working Group review what legal advice had already been obtained for previous CPs. The Working Group are reviewing this and if the advice is still needed, questions will be submitted to Panel in August. The group reviewed the legal questions and agreed that they were no longer needed. A consultation has been issued to industry for comment by close of play on 17 November 2017. The group will be meeting to review consultation responses and agree next steps for the change on 13 December 2017. | CONSULTATION
DCP 302 | Moving Made Safe Instances To Cat B | To change the Category definition(s) to allow Category A incidents that have been made safe by the meter operator to be reclassified and reported as Category B. | General | 1 | To be progressed by the Interventions Working Group | Angela Picciariello | 2017-06-16 | 3 |  | June 2018 | At the June DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group (IWG). The IWG drafted a consultation which was issued 29 August with responses due 19 September. The IWG are in the process of finalising the Change Report, which is expected to be provided to the Panel for consideration in January 2018. | N/A
DCP 304 | Metering Works by Non-Appointed Meter Operator | This Change Proposal seeks to widen the scope of DCUSA to allow suppliers and their meter operators to break seals and work on metering equipment at metering points for which they are not the appointed meter operator. | General | 1 | To be progressed by the Interventions Working Group | Michael Walls | 2017-07-11 | 3 |  | June 2018 | At the June DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group (IWG). The IWG drafted a consultation which was issued 29 August with responses due 19 September. The IWG are in the process of finalising the Change Report, which is expected to be provided to the Panel for consideration in January 2018. | N/A
DCP 305 | LDNO Boundary Level Definitions in the EDCM | The intent of this change proposal is to amend the definitions and application of DNO/LDNO boundaries under the EDCM to avoid instances of double- and/or non-charging for certain assets. | EDCM | 1 | Dan Fittock / John Lawton | Tim Aldridge | 2017-07-12 | 2 |  | 2020-04-01 | The Working Group met on 21 November to review the draft consultation document. As a result of the review, it was agreed that an RFI would be required to nswer some outstanding questions. The Working Group is next due to meet on 8 January 2017 to review the RFI responses. | N/A
DCP 306 | Treatment of Ofgem Licence Fees within the PCDM | The intent of this Change Proposal is to increase the cost reflectivity of the Price Control Disaggregation Model by directly allocating the Ofgem licence fee to an appropriate network tier for the calculation of the Opex allocation driver. | General | 1 | Hollie Nicholls / John Lawton | Tim Aldridge | 2017-07-12 | 3 |  | 2020-04-01 | A Working Group invitation was issued to Parties and the first Working Group meeting is in the process of being set up. The first WG meeting was held on 8th September. A draft consultation document has been produced for the group to review with a view to issue to the industry for comment on 18th/19th September 2017. Work Plan to be issued to the September panel for approval. A consultation has been issued to the industry and their responses have been collated. Consultation responses have been reviewed by the working group and a modelling request has been issued to Reckon. An impact assessment is being completed by DNOs/Reckon and second consultation is currently being drafted. | N/A
DCP 307 | Requiring IDNOs to comply with D2021 billing | This Change Proposal seeks to extend compliance with D2021 billing to IDNOs, as it currently is with all other distributors, in order to automate the process and support a more accurate and efficient billing process. | General | 1 | Joseph Underwood / Dan Fittock | George Huang | 2017-08-16 | 1 |  | Next scheduled release following approval | First workgroup meeting was on 01 November 2017. Consultation is currently being drafted. | N/A
DCP 311 | Clarification of NUF cap and collar calculations | The intent of this Change Proposal is to modify schedules 17 and 18 to clarify which years should be used when determining NUF caps and collars to be applied for each charging year, and to remove an additional year lag which has been built into the legal text for the cap and collar calculations for 2023/24 charges. | EDCM | 1 | Joseph Underwood / John Lawton | Edda Dirks | 2017-10-18 | 0 |  |  | The first Working Group meeting was held on 27 November 2017. A consultation is currently being drafted and the Working Group will next meet on 16 January 2018 to review the draft consultation document. | DEFINITION
DCP 312 | Standardisation of the Reporting of HH Portfolio Billing Data by EDNOs | The intent of this change is to develop a consistent approach to the formatting of HH Portfolio Billing data for reporting purposed under Schedule 19. | General | 1 | Dan Fittock / John Lawton | Tim Aldridge | 2017-10-19 | 0 |  | Next scheduled release following approval | The first Working Group meeting is due to convene on 12 December 2017 to run through the CP and highlight any potenital issues for the first consultation. | DEFINITION
DCP 313 | Eligibility Criteria for EDCM Generation Credits | The intent of this Change Proposal is to improve transparency of the eligibility criteria for EDCM generators to receive super red credits and to improve consistency in the application thereof. | EDCM | 1 | Hollie Nicholls / John Lawton | Edda Dirks | 2017-10-20 | 1 |  | 2020-04-01 | The Working Group met for the first time on 04 December 2017 to review the CP form. The Working Group are in the process of drafting a consultation and completing an impact assessment on the EDCM. The Working Group are due to meet again in January. | DEFINITION
STATUS - CHANGE REPORT
DCP 283 | The calculation of generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators | CDCM | 1 | Dylan Townsend / John Lawton | Edda Dirks | 2016-10-12 | 11 |  | 2020-04-01 | The Working Group issued their second consultation on 01 September 2017. The Working Group met on 3 October to review the consultation responses and again on 22 November to review a draft version of the Change Report. The Change Report will be issued to the Panel for approval at their December meeting. | NO
DCP 288, DCP 288A DCP 288B | Introduction of the Electricity Theft Detection Incentive Scheme DCP 288B - Equitable Theft Detection Incentive Scheme - | The intent of this Change Proposal (CP) is to introduce an Electricity Theft Detection Incentive Scheme in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014 DCP 288B seeks to create an equitable scheme which suitably incentivises detection of electricity theft without distorting competition and hampering effective functioning of the market in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014. | THEFT | 1 | Fungai Madzivadondo | Jon Dixon | 2016-12-12 | 7 |  | TBD | The DCP 288, 288A and 288B consultation was issued to the industry on 22 August with a deadline of 14 Septemebr 2017. The TIG met on 19 Septemember 2017 to review the consultatiuon responses. Legal text was issued to the legal advisor for review and the Change Report will be issued to the Panel for approval at their December meeting. | N/A
DCP 295 | CVA Registrants acceding to the DCUSA | This change is to facilitate BSC Modification PXXX which is to oblige CVA Registrants connecting to a Distribution System to accede to the DCUSA which will negate the need for a bilateral Use of System Agreements between the LDSO and the CVA Registrants saving administrative cost and effort and promoting efficiency and consistency. The effect of this change will be to modify the legal text to include CVA Registrants in addition to Distributed Generation Parties mainly in Section 2A but also in Sections 1A, 1B, 1C, 2B, 2C and 3 and Schedules 9, 11, 19 and 21. | General | 1 | Hollie Nicholls/ Dan Fittock | Stephen Perry | 2017-03-07 | 2 |  | First release following approval | A Change Report has been issued to the Panel for their October meeting. One Working Group member has noticed a potential issue that may have impacts on this change and is currently investigating. An updated change report may be issued to the Panel if appropriate. | N/A
DCP 297 | Network Interventions SLA Enhancement | This CP seeks to change the mechanism whereby DNO’s are released from their obligations to meet the intervention SLA to one which is solely based on the accuracy of Suppliers smart meter roll-out forecasts. The DCUSA Panel has directed that this change be considered by the Interventions Working Group. | General | 1 | To be progressed by the Interventions Working Group | Michael Walls / Mark Hogan | 2017-04-07 | 4 |  | First release following approval | At the April DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group (IWG). The IWG discussed and consulted upon the CP over the course of the year, which resulted in the Change Report being submitted to the Panel in October. It was agreed that further development of the Change Report is required and the IWG convened to address the feedback. The updated Change Report has been included in the meeting papers for consideration at the December Panel meeting. | N/A
STATUS - VOTING
VOTING
STATUS - AWAITING AUTHORITY CONSENT
STATUS - AWAITING IMPLEMENTATION
2018-02-22
DCP 308 | Notice period to change Revenue Protection Agent | This Change Proposal seeks to require that a Party provides three months’ notice in the event they wish to change their Revenue Protection Agent. | General | 2 | Fungai Madzivadondo | N/A |  | N/A |  | Next scheduled release following approval | A Change Report was issued to the Panel for their October meeting. The Panel approved the Change Report and it was issued to Parties for Voting. Voting closes on 10 November 2017. | VOTING
DCP 309 | Reporting ETTOS Identified Theft to the TRAS Service Provider | This Change Proposal seeks is to amend the Supplier process for reporting theft identified through the Energy Theft Tip-Off Service (ETTOS) to the TRAS Service Provider. | Theft | 2 | Fungai Madzivadondo | N/A |  | N/A |  | Next scheduled release following approval | A Change Report was issued to the Panel for their October meeting. The Panel approved the Change Report and it was issued to Parties for Voting. Voting closes on 10 November 2017. | VOTING
2018-04-01
DCP 161 | Excess Capacity Charges | To improve the cost reflectivity of the excess capacity charge calculation within the CDCM and EDCM by removing the customer contributions and adding in any additional costs that should be attributed to this charge. Also, to consider applying the excess capacity charge on either a monthly, seasonal or time of day basis. | CDCM | 1 | Michael Walls/Chris Ong | Keith Burwell | 2013-02-06 | 12 |  | 2018-04-01 | The Authority directed for DCP 161 to be made and implemented on 1 April 2018. | N/A
DCP 222 | Non Billing Of Excess Reactive Power Charges | This CP proposes the removal of the excess reactive power charge when a DNO requests that a generator operates outside of the 0.95 power factor limit. | CDCM | 1 | Fungai Madzivadondo/Dave Wornell | Nisha Doshi | 2014-12-02 | 11 |  | 2018-04-01 | The Authority directed for DCP 222 to be made and implemented on 1 April 2018. | N/A
DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | CDCM | 1 | Rosalind Timperley/ Chris Ong | Bethany Hanna | 2015-01-13 | 4 |  | 2018-04-01 | The Authority directed for DCP 228 to be made and implemented on 1 April 2018. | N/A
DCP 234 | Merging the PCDM and extended PCDM | The intent of the CP is to replace the Price Control Disaggregation (PCDM) and extended PCDM models with one model.To create a new schedule in DCUSA which contains the legal text that relates to IDNO charging that is currently contained in Schedules 16, 17 and 18. | CDCM and EDCM | 1 | Claire Hynes/ Claire Campbell | Lynda Carroll | 2015-02-27 | 7 |  | 2018-04-01 | The Authority directed for DCP 234 to be made and implemented on 1 April 2018. | N/A
DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | The intent of this proposal is to align table 1001 in the CDCM to the current format of table in Schedule 15. | CDCM | 2 | Fungai Madzivadondo/John Lawton | Lynda Carroll | 2016-05-18 | 2 |  | 2018-04-01 | Parties voted to approve the change on the 17 October 2016 for implementation on the 01 April 2018. | N/A
DCP 290 | Housekeeping Change to Update PCDM Model References | The intent of this Change Proposal is to facilitate the updating of the title, model number and issue date of the PDCM as referenced in Schedules 16, 17 and 18, which was not correctly applied in the legal text of DCP234. | CDCM/EDCM | 2 | Dan Fittock | N/A | 2017-01-17 | 0 |  | 2018-04-01 | Parties voted to approve the change on 10 March 2017 for implementation on 01 April 2018. | N/A
DCP 293 | Charging methodology cut-off date | This Change looks to establish a cut-off date for the finalisation of charging methodologies at 17 months prior to the date that the methodology would become effective. Establishing this cut-off date will provide a 2-month time window for DCUSA to provide charging models and DNOs to test the new charging models and then to calculate, test and approve revised charges. | General | 1 | Hollie Nicholls / Dylan Townsend | Sean Hennity | 2017-02-14 | 3 |  | 2019-04-01 | A change declaration was sent to Ofgem for their determination on 17 October 2017. On 21 November 2017 the Authority directed for DCP 293 to be made and implemented on 01 April 2018. | AWAITING AUTHORITY CONSENT
DCP 310 | ENA Office Move | This Change Proposal seeks to amend the ENA’s address details due to their forthcoming office move. | General | 2 | Joseph Underwood | N/A |  | N/A |  | 2018-04-01 | A Change Report was issued to the Panel for their October meeting. The Panel approved the Change Report and it was issued to Parties for Voting. Voting closed on 10 November 2017 with Parties voting to approve the change.for implementation on 01 April 2018. | VOTING
STATUS - APPEAL
n/a | n/a | [10 empty] | N/A
STATUS - IMPLEMENTED
IMPLEMENTED
STATUS - REJECTED
N/A
STATUS - WITHDRAWN
N/A
Change Register - December 2017

## Status Change
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst/WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status Changed in the last month | Status Changed in the last month
STATUS - DEFINITION
DCP 243 | Treatment of Customer Contributions in the CDCM | ​This CP seeks to revise DCUSA Schedule 16 to utilise current source data to determine a common industry set of modelling inputs in order to improve clarity in the approach to be used in calculating ‘Customer contribution under the current connection charging policy’ for use in CDCM table 1060. | CDCM | 1 | Dylan Townsend/ John Lawton | Dominic Green | 2015-06-05 | 18 |  | 2020-04-01 | The Working Group agreed to proceed to final consultation after deciding on which option to proceed with and issued the final consultation on 27 October 2017. The Working Group are due to meeting on 12 January 2018 to review the consultation responses. | CONSULTATION | N/A
DCP 266 | The calculation and application of IDNO discounts | To change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this CP is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | CDCM | 1 | Dylan Townsend/ John Lawton | Tim Aldridge | 2016-03-09 | 9 |  | 2020-04-01 | Amended modelling was requested and has been receieved, the group met on 25 September to review the modelling and impact assessment and are met again on 12 October to review the draft consultation document. Futher Impact anaysis has been requested by the group which will include all DNO areas. The updated Impact Assessment has been receieved and the Working Group are reviewing this. The next meeting is scheduled for mid to late January, pending availability of the group. | NO | N/A
DCP 268 | DUoS Charging Using HH settlement data | The intent of this CP is to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | CDCM | 1 | Dan Fittock / John Lawton | Lynda Carroll | 2016-03-14 | 10 |  | 2020-04-01 | DCUSA Parties voted to accept the Solution and to reject the implementation date. The Authority's decision to send back DCP 268 was received on 20 October and the Working Group is due to reconvene to review Ofgem's feedback on 11 January 2018. | DEFINITION | N/A
DCP 287 | Generation credits in the EDCM | The intent of this Change Proposal is to amend the calculation of credits for embedded generation in the EDCM to take account of potential cost savings for DNOs that can be attributed to embedded generation in the areas of transmission exit charges, direct costs, indirect costs and network rates. | EDCM | 1 | Dan Fittock / John Lawton | Edda Dirks | 2016-12-07 | 8 |  | 2020-04-01 | The Working Group last met on 11 December 2017 to review the RFI results received from DNOs. The Working Group is next scheduled to convene on 23 January 2017 to review the draft second Cosnultation document. | NO | N/A
DCP 294 | Capacity Management Following Acceptance of Connection Offer | This CP seeks to put arrangements in place that set out the principles under which the unutilised maximum capacity specified in connection offers or in bilateral connection agreements with IDNOs can be managed in an economic and efficient manner whilst protecting the legitimate requirements of parties requiring Capacity which was agreed in connection offers. | CCCM | 1 | Hollie Nichollls/ John Lawton | Moshe Kinshuck | 2017-03-01 | 6 |  | First release following approval | The first Working Group meeting took place on the 20 April 2017 and it was agreed that legal advice was required before a solution could be progressed on this CP. The Working Group are in the process of finalising the legal advice questions for submission to the DCUSA Panel for approval. The Panel requested that the Working Group review what legal advice had already been obtained for previous CPs. The Working Group are reviewing this and if the advice is still needed, questions will be submitted to Panel in August. The group reviewed the legal questions and agreed that they were no longer needed. A consultation has been issued to industry for comment by close of play on 17 November 2017. The group will be meeting to review consultation responses and agree next steps for the change on 13 December 2017. | CONSULTATION | N/A
DCP 302 | Moving Made Safe Instances To Cat B | To change the Category definition(s) to allow Category A incidents that have been made safe by the meter operator to be reclassified and reported as Category B. | General | 1 | To be progressed by the Interventions Working Group | Angela Picciariello | 2017-06-16 | 3 |  | June 2018 | At the June DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group (IWG). The IWG drafted a consultation which was issued 29 August with responses due 19 September. The IWG are in the process of finalising the Change Report, which is expected to be provided to the Panel for consideration in January 2018. | N/A | N/A
DCP 304 | Metering Works by Non-Appointed Meter Operator | This Change Proposal seeks to widen the scope of DCUSA to allow suppliers and their meter operators to break seals and work on metering equipment at metering points for which they are not the appointed meter operator. | General | 1 | To be progressed by the Interventions Working Group | Michael Walls | 2017-07-11 | 3 |  | June 2018 | At the June DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group (IWG). The IWG drafted a consultation which was issued 29 August with responses due 19 September. The IWG are in the process of finalising the Change Report, which is expected to be provided to the Panel for consideration in January 2018. | N/A | N/A
DCP 305 | LDNO Boundary Level Definitions in the EDCM | The intent of this change proposal is to amend the definitions and application of DNO/LDNO boundaries under the EDCM to avoid instances of double- and/or non-charging for certain assets. | EDCM | 1 | Dan Fittock / John Lawton | Tim Aldridge | 2017-07-12 | 2 |  | 2020-04-01 | The Working Group met on 21 November to review the draft consultation document. As a result of the review, it was agreed that an RFI would be required to nswer some outstanding questions. The Working Group is next due to meet on 8 January 2017 to review the RFI responses. | N/A | N/A
DCP 306 | Treatment of Ofgem Licence Fees within the PCDM | The intent of this Change Proposal is to increase the cost reflectivity of the Price Control Disaggregation Model by directly allocating the Ofgem licence fee to an appropriate network tier for the calculation of the Opex allocation driver. | General | 1 | Hollie Nicholls / John Lawton | Tim Aldridge | 2017-07-12 | 3 |  | 2020-04-01 | A Working Group invitation was issued to Parties and the first Working Group meeting is in the process of being set up. The first WG meeting was held on 8th September. A draft consultation document has been produced for the group to review with a view to issue to the industry for comment on 18th/19th September 2017. Work Plan to be issued to the September panel for approval. A consultation has been issued to the industry and their responses have been collated. Consultation responses have been reviewed by the working group and a modelling request has been issued to Reckon. An impact assessment is being completed by DNOs/Reckon and second consultation is currently being drafted. | N/A | N/A
DCP 307 | Requiring IDNOs to comply with D2021 billing | This Change Proposal seeks to extend compliance with D2021 billing to IDNOs, as it currently is with all other distributors, in order to automate the process and support a more accurate and efficient billing process. | General | 1 | Joseph Underwood / Dan Fittock | George Huang | 2017-08-16 | 1 |  | Next scheduled release following approval | First workgroup meeting was on 01 November 2017. Consultation is currently being drafted. | N/A | N/A
DCP 311 | Clarification of NUF cap and collar calculations | The intent of this Change Proposal is to modify schedules 17 and 18 to clarify which years should be used when determining NUF caps and collars to be applied for each charging year, and to remove an additional year lag which has been built into the legal text for the cap and collar calculations for 2023/24 charges. | EDCM | 1 | Joseph Underwood / John Lawton | Edda Dirks | 2017-10-18 | 0 |  |  | The first Working Group meeting was held on 27 November 2017. A consultation is currently being drafted and the Working Group will next meet on 16 January 2018 to review the draft consultation document. | DEFINITION | N/A
DCP 312 | Standardisation of the Reporting of HH Portfolio Billing Data by EDNOs | The intent of this change is to develop a consistent approach to the formatting of HH Portfolio Billing data for reporting purposed under Schedule 19. | General | 1 | Dan Fittock / John Lawton | Tim Aldridge | 2017-10-19 | 0 |  | Next scheduled release following approval | The first Working Group meeting is due to convene on 12 December 2017 to run through the CP and highlight any potenital issues for the first consultation. | DEFINITION | N/A
DCP 313 | Eligibility Criteria for EDCM Generation Credits | The intent of this Change Proposal is to improve transparency of the eligibility criteria for EDCM generators to receive super red credits and to improve consistency in the application thereof. | EDCM | 1 | Hollie Nicholls / John Lawton | Edda Dirks | 2017-10-20 | 1 |  | 2020-04-01 | The Working Group met for the first time on 04 December 2017 to review the CP form. The Working Group are in the process of drafting a consultation and completing an impact assessment on the EDCM. The Working Group are due to meet again in January. | DEFINITION | N/A
STATUS - CHANGE REPORT
DCP 283 | The calculation of generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators | CDCM | 1 | Dylan Townsend / John Lawton | Edda Dirks | 2016-10-12 | 11 |  | 2020-04-01 | The Working Group issued their second consultation on 01 September 2017. The Working Group met on 3 October to review the consultation responses and again on 22 November to review a draft version of the Change Report. The Change Report will be issued to the Panel for approval at their December meeting. | NO | CHANGE REPORT
DCP 288, DCP 288A DCP 288B | Introduction of the Electricity Theft Detection Incentive Scheme DCP 288B - Equitable Theft Detection Incentive Scheme - | The intent of this Change Proposal (CP) is to introduce an Electricity Theft Detection Incentive Scheme in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014 DCP 288B seeks to create an equitable scheme which suitably incentivises detection of electricity theft without distorting competition and hampering effective functioning of the market in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014. | THEFT | 1 | Fungai Madzivadondo | Jon Dixon | 2016-12-12 | 7 |  | TBD | The DCP 288, 288A and 288B consultation was issued to the industry on 22 August with a deadline of 14 Septemebr 2017. The TIG met on 19 Septemember 2017 to review the consultatiuon responses. Legal text was issued to the legal advisor for review and the Change Report will be issued to the Panel for approval at their December meeting. | N/A | CHANGE REPORT
DCP 295 | CVA Registrants acceding to the DCUSA | This change is to facilitate BSC Modification PXXX which is to oblige CVA Registrants connecting to a Distribution System to accede to the DCUSA which will negate the need for a bilateral Use of System Agreements between the LDSO and the CVA Registrants saving administrative cost and effort and promoting efficiency and consistency. The effect of this change will be to modify the legal text to include CVA Registrants in addition to Distributed Generation Parties mainly in Section 2A but also in Sections 1A, 1B, 1C, 2B, 2C and 3 and Schedules 9, 11, 19 and 21. | General | 1 | Hollie Nicholls/ Dan Fittock | Stephen Perry | 2017-03-07 | 2 |  | First release following approval | A Change Report has been issued to the Panel for their October meeting. One Working Group member has noticed a potential issue that may have impacts on this change and is currently investigating. An updated change report may be issued to the Panel if appropriate. | N/A | N/A
DCP 297 | Network Interventions SLA Enhancement | This CP seeks to change the mechanism whereby DNO’s are released from their obligations to meet the intervention SLA to one which is solely based on the accuracy of Suppliers smart meter roll-out forecasts. The DCUSA Panel has directed that this change be considered by the Interventions Working Group. | General | 1 | To be progressed by the Interventions Working Group | Michael Walls / Mark Hogan | 2017-04-07 | 4 |  | First release following approval | At the April DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group (IWG). The IWG discussed and consulted upon the CP over the course of the year, which resulted in the Change Report being submitted to the Panel in October. It was agreed that further development of the Change Report is required and the IWG convened to address the feedback. The updated Change Report has been included in the meeting papers for consideration at the December Panel meeting. | N/A | CHANGE REPORT
STATUS - VOTING
[12 empty] | VOTING | N/A
STATUS - AWAITING AUTHORITY CONSENT
N/A
STATUS - AWAITING IMPLEMENTATION
2018-02-22
DCP 308 | Notice period to change Revenue Protection Agent | This Change Proposal seeks to require that a Party provides three months’ notice in the event they wish to change their Revenue Protection Agent. | General | 2 | Fungai Madzivadondo | N/A |  | N/A |  | Next scheduled release following approval | A Change Report was issued to the Panel for their October meeting. The Panel approved the Change Report and it was issued to Parties for Voting. Voting closes on 10 November 2017. | VOTING | AWAITING IMPLEMENTATION
DCP 309 | Reporting ETTOS Identified Theft to the TRAS Service Provider | This Change Proposal seeks is to amend the Supplier process for reporting theft identified through the Energy Theft Tip-Off Service (ETTOS) to the TRAS Service Provider. | Theft | 2 | Fungai Madzivadondo | N/A |  | N/A |  | Next scheduled release following approval | A Change Report was issued to the Panel for their October meeting. The Panel approved the Change Report and it was issued to Parties for Voting. Voting closes on 10 November 2017. | VOTING | AWAITING IMPLEMENTATION
2018-04-01
DCP 161 | Excess Capacity Charges | To improve the cost reflectivity of the excess capacity charge calculation within the CDCM and EDCM by removing the customer contributions and adding in any additional costs that should be attributed to this charge. Also, to consider applying the excess capacity charge on either a monthly, seasonal or time of day basis. | CDCM | 1 | Michael Walls/Chris Ong | Keith Burwell | 2013-02-06 | 12 |  | 2018-04-01 | The Authority directed for DCP 161 to be made and implemented on 1 April 2018. | N/A | N/A
DCP 222 | Non Billing Of Excess Reactive Power Charges | This CP proposes the removal of the excess reactive power charge when a DNO requests that a generator operates outside of the 0.95 power factor limit. | CDCM | 1 | Fungai Madzivadondo/Dave Wornell | Nisha Doshi | 2014-12-02 | 11 |  | 2018-04-01 | The Authority directed for DCP 222 to be made and implemented on 1 April 2018. | N/A | N/A
DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | CDCM | 1 | Rosalind Timperley/ Chris Ong | Bethany Hanna | 2015-01-13 | 4 |  | 2018-04-01 | The Authority directed for DCP 228 to be made and implemented on 1 April 2018. | N/A | N/A
DCP 234 | Merging the PCDM and extended PCDM | The intent of the CP is to replace the Price Control Disaggregation (PCDM) and extended PCDM models with one model.To create a new schedule in DCUSA which contains the legal text that relates to IDNO charging that is currently contained in Schedules 16, 17 and 18. | CDCM and EDCM | 1 | Claire Hynes/ Claire Campbell | Lynda Carroll | 2015-02-27 | 7 |  | 2018-04-01 | The Authority directed for DCP 234 to be made and implemented on 1 April 2018. | N/A | N/A
DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | The intent of this proposal is to align table 1001 in the CDCM to the current format of table in Schedule 15. | CDCM | 2 | Fungai Madzivadondo/John Lawton | Lynda Carroll | 2016-05-18 | 2 |  | 2018-04-01 | Parties voted to approve the change on the 17 October 2016 for implementation on the 01 April 2018. | N/A | N/A
DCP 290 | Housekeeping Change to Update PCDM Model References | The intent of this Change Proposal is to facilitate the updating of the title, model number and issue date of the PDCM as referenced in Schedules 16, 17 and 18, which was not correctly applied in the legal text of DCP234. | CDCM/EDCM | 2 | Dan Fittock | N/A | 2017-01-17 | 0 |  | 2018-04-01 | Parties voted to approve the change on 10 March 2017 for implementation on 01 April 2018. | N/A | N/A
DCP 293 | Charging methodology cut-off date | This Change looks to establish a cut-off date for the finalisation of charging methodologies at 17 months prior to the date that the methodology would become effective. Establishing this cut-off date will provide a 2-month time window for DCUSA to provide charging models and DNOs to test the new charging models and then to calculate, test and approve revised charges. | General | 1 | Hollie Nicholls / Dylan Townsend | Sean Hennity | 2017-02-14 | 3 |  | 2019-04-01 | A change declaration was sent to Ofgem for their determination on 17 October 2017. On 21 November 2017 the Authority directed for DCP 293 to be made and implemented on 01 April 2018. | AWAITING AUTHORITY CONSENT | AWAITING IMPLEMENTATION
DCP 310 | ENA Office Move | This Change Proposal seeks to amend the ENA’s address details due to their forthcoming office move. | General | 2 | Joseph Underwood | N/A |  | N/A |  | 2018-04-01 | A Change Report was issued to the Panel for their October meeting. The Panel approved the Change Report and it was issued to Parties for Voting. Voting closed on 10 November 2017 with Parties voting to approve the change.for implementation on 01 April 2018. | VOTING | AWAITING IMPLEMENTATION
STATUS - APPEAL
n/a | n/a | [10 empty] | N/A | N/A
STATUS - IMPLEMENTED
[12 empty] | IMPLEMENTED | N/A
STATUS - REJECTED
[12 empty] | N/A | N/A
STATUS - WITHDRAWN
[12 empty] | N/A | N/A
Change Register - December 2017

## CP Work Plans
The DCUSA Panel is invited to:
Change Proposal | Secretariat | CP Title | Change Report Due Date | Status | Date of Last Agreed Work Plans | Note the Change Proposal Status
DCP 243 | Dylan | Treatment of Customer Contributions in the CDCM | 2018-01-10 |  | 2017-09-20 | Approve the DCP 294, 304, 311, 312 and 313 Work Plans
DCP 266 | Dylan | The calculation and application of IDNO discounts | 2018-01-10 |  | 2017-10-18
DCP 283 | Dylan | The calculation of generation credits in the CDCM | 2017-12-13 | Change Report Issued | 2017-11-15
DCP 287 | Dan | Generation credits in the EDCM | 2018-01-10 |  | 2017-04-25
DCP 288 | Fungai | Introduction of the Electricity Theft Detection Incentive Scheme | 2017-12-13 | Change Report Issued | 2017-10-18
DCP 294 | Hollie | Capacity Management Following Acceptance of Connection Offer | 2017-12-13 | Work Plan Due | 2017-08-16
DCP 295 | Hollie | CVA Registrants acceding to the DCUSA | 2017-10-11 | Change Report submitted in October but hasn't been issued due to potential issue raised by the Proposer which is still under investigation | 2017-07-19
DCP 297 | IWG | Network Interventions SLA Enhancement | 2017-10-11 | Change Report Issued | 2017-09-20
DCP 302 | IWG | Moving Made Safe Instances To Cat B | 2017-12-13 | Work Plan Due (next meeting 18 December) | 2017-08-16
DCP 304 | IWG | Metering Works by Non-Appointed Meter Operator | 2017-12-13 | Work Plan Due | 2017-09-20
DCP 305 | Dan | LDNO Boundary Level Definitions in the EDCM | 2018-02-14 |  | 2017-10-18
DCP 306 | Hollie | Treatment of Ofgem Licence Fees within the PCDM | 2018-02-14 |  | 2017-09-20
DCP 307 | Joe | Requiring IDNOs to comply with D2021 billing | 2018-05-09 |  | 2017-11-15
DCP 311 | Joe | Eligibility Criteria for EDCM Generation Credits |  | First Work Plan Due
DCP 312 | Dan | Standardisation of the Reporting of HH Portfolio Billing Data by EDNOs |  | First Work Plan Due
DCP 313 | Hollie | Clarification of NUF cap and collar calculations |  | First Work Plan Due
CP Work Plans

## OLD_Legal Text Overlap
February 2016
Awaiting Implementation
CP Number | DCP 293 | DCP 291 | DCP 287 | DCP 283 | DCP 274 | DCP 268 | DCP 266 | DCP 252 | DCP 251 | DCP 243 | DCP 273 | DCP 161 | DCP 228 | DCP 222 | DCP 234
Implementation Date | [10 empty] | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01
Status | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Developed | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation
DCUSA Schedule 15
Impacted Paragraphs | [5 empty] | Table 3 | [5 empty] | Table 3 (para 4.1)
DCUSA Schedule 16 | Prior to Introduction |  |  |  |  | para 3 |  |  |  |  | para 3
Impacted Paragraphs | [11 empty] | 3a
| para 3 |  |  |  |  | 12 | [5 empty] | 12
14
40,42,42A,43
45,52A,
68,72,72A,74
[6 empty] | 80,81,83,84 | [8 empty] | 3(b)
97
98 and 99
100 to 120 (including the tables and headings)
124 and 125
[12 empty] | 81 |  |  | Glossary
92 to 95
126,127,128,
129130
[6 empty] | 131,132, | 109,111 to 113A & 113D,118 to 124
132A,132B
135,135A
135B,136
[6 empty] | 140A-140E | [5 empty] | 131
[6 empty] | 141 table 4 &5 | [5 empty] | 136
141 (table 5)
[6 empty] | 142143 | [7 empty] | 146 (table 7)
[6 empty] | 144,145, | [5 empty] | 147 (table 8 & 9)
146 table 6& 7
[6 empty] | 147 table 8& 9 | [5 empty] | 153
157 - deleted
173
177 (originally 176)
DCUSA Schedule 17 | Prior to Introduction
Impacted Paragraphs | [11 empty] | 1.3 |  |  | 25
| para 1.3 (a) | [13 empty] | 25.1
|  | 6.3 | 9.2, 9.3, 16.7 | [11 empty] | 25.2
25.3 to 25.18 (including the tables and headings).
25.19
DCUSA Schedule 18 | Prior to Introduction
Impacted Paragraphs | [11 empty] | 1.3 |  |  | 25
| para 1.3 (a) | 6.5 | 9.2, 9.3, 16.7 | [11 empty] | 25.1
25.2
25.3 to 25.18 (including the tables and headings).
25.19
DCUSA Schedule 20 | Prior to Introduction
Impacted Paragraphs | [5 empty] | 1.1 | [5 empty] | 1.1
DCUSA Schedule xx | Prior to Introduction
Impacted Paragraphs
| Clause 1 | [6 empty] | Clause 1 | Clause 1
[8 empty] | Title | Title
Charging Methodology CPs Legal Text Overlap Tracker
Colour Code
Red Text = Legal text close to being completed but not yet finalised
Black Text = Finalised Legal text that will not change further (i.e. version to be included in Change Report)
Yellow Highlight = Paragraph changed by more than one CP

## New_Legal Text Overlap
YES
YES
|  | Progressing through change process (legal text to be baselined against pre-release text) |  |  |  | Awaiting Implementation (not in pre-release) |  | Progressing through change process (legal text to be baselined against pre-release text) |  |  |  |  | Awaiting Implementation (pre-release) |  |  |  |  | Implemented (to be cross checked against pre-rlease)
|  | DCP 313 | DCP 311 | DCP 306 | DCP 305 | DCP 293 | DCP 290 | DCP 287 | DCP 283 | DCP 268 | DCP 266 | DCP 243 | DCP 273 | DCP 161 | DCP 228 | DCP 222 | DCP 234 | DCP 292 | DCP 226 | Number of CPs
|  | 2020-04-01 | 2020-04-01 | 2020-04-01 | 2020-04-01 | 2018-04-01 | 2018-04-01 | 2020-04-01 | 2020-04-01 | 2020-04-01 | 2020-04-01 | 2020-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2017-06-29 | 2017-11-02 | Impacting Clause
Schedules | Clause Number | Under Development | Under Development | Under Development | Under Development | Awaiting Implementation | Awaiting Implementation | Under Development | Under Development | Under Development | Under Development | Under Development | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Implemented | Implemented |  | NOTES TO ASSIST
Schedule 15 | Table 1 | [18 empty] | 0
Schedule 15 | Table 2 | [18 empty] | 0
Schedule 15 | Table 3 | [12 empty] | YES |  |  |  | YES |  | 2 | DCP 161 Introduces new column (Exceeded capacity charge p/kVA/day)
Schedule 16 | Introduction |  |  |  |  | YES |  |  | YES | [10 empty] | 2 | DCP 293 introduces an introductory paragraph ar the start of the Schedule
Schedule 16 | 1 | [18 empty] | 0
Schedule 16 | 2 | [18 empty] | 0
Schedule 16 | 3 |  |  |  |  | YES | YES |  | YES | YES |  | YES | YES | YES |  | YES | YES |  |  | 9
Schedule 16 | 4 | [18 empty] | 0
Schedule 16 | 5 | [18 empty] | 0
Schedule 16 | 6 | [18 empty] | 0
Schedule 16 | 7 | [18 empty] | 0
Schedule 16 | 8 | [18 empty] | 0
Schedule 16 | 9 | [18 empty] | 0
Schedule 16 | 10 | [18 empty] | 0
Schedule 16 | 11 | [18 empty] | 0
Schedule 16 | 12 | [8 empty] | YES |  |  |  | YES | [5 empty] | 2 | DCP 268 amends the table below the paragraph
Schedule 16 | 13 | [18 empty] | 0
Schedule 16 | 14 | [12 empty] | YES | [5 empty] | 1
Schedule 16 | 15 | [18 empty] | 0
Schedule 16 | 16 | [18 empty] | 0
Schedule 16 | 17 | [18 empty] | 0
Schedule 16 | 18 | [18 empty] | 0
Schedule 16 | 19 | [18 empty] | 0
Schedule 16 | 20 | [18 empty] | 0
Schedule 16 | 21 | [18 empty] | 0
Schedule 16 | 22 | [18 empty] | 0
Schedule 16 | 23 | [18 empty] | 0
Schedule 16 | 24 | [18 empty] | 0
Schedule 16 | 25 | [18 empty] | 0
Schedule 16 | 26 | [18 empty] | 0
Schedule 16 | 27 | [18 empty] | 0
Schedule 16 | 28 | [18 empty] | 0
Schedule 16 | 29 | [18 empty] | 0
Schedule 16 | 30 | [10 empty] | YES | [7 empty] | 1 | Addition of 30A and 30 B
Schedule 16 | 31 | [7 empty] | YES |  |  | YES | [7 empty] | 2 | DCP 283 and 243 (working groups are aware of and have taken into account the interaction
Schedule 16 | 32 | [18 empty] | 0
Schedule 16 | 33 | [18 empty] | 0
Schedule 16 | 34 | [18 empty] | 0
Schedule 16 | 35 | [18 empty] | 0
Schedule 16 | 36 | [18 empty] | 0
Schedule 16 | 37 | [18 empty] | 0
Schedule 16 | 38 | [18 empty] | 0
Schedule 16 | 39 | [18 empty] | 0
Schedule 16 | 40 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 41 | [18 empty] | 0
Schedule 16 | 41A | [17 empty] | YES | 1
Schedule 16 | 41B | [18 empty] | 0
Schedule 16 | 42 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 42A | [18 empty] | 0
Schedule 16 | 43 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 44 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 45 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 46 | [18 empty] | 0
Schedule 16 | 47 | [18 empty] | 0
Schedule 16 | 48 | [18 empty] | 0
Schedule 16 | 49 | [18 empty] | 0
Schedule 16 | 50 | [18 empty] | 0
Schedule 16 | 51 | [18 empty] | 0
Schedule 16 | 52 | [9 empty] | YES | [8 empty] | 1
Schedule 16 | 52A | [8 empty] | YES | [9 empty] | 1 | DCP 268 introduces Clause 52A
Schedule 16 | 53 | [18 empty] | 0
Schedule 16 | 54 | [18 empty] | 0
Schedule 16 | 55 | [18 empty] | 0
Schedule 16 | 56 | [18 empty] | 0
Schedule 16 | 57 | [18 empty] | 0
Schedule 16 | 58 | [18 empty] | 0
Schedule 16 | 59 | [18 empty] | 0
Schedule 16 | 60 | [18 empty] | 0
Schedule 16 | 61 | [18 empty] | 0
Schedule 16 | 62 | [18 empty] | 0
Schedule 16 | 63 | [18 empty] | 0
Schedule 16 | 64 | [18 empty] | 0
Schedule 16 | 65 | [18 empty] | 0
Schedule 16 | 66 | [18 empty] | 0
Schedule 16 | 67 | [18 empty] | 0
Schedule 16 | 68 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 69 | [18 empty] | 0
Schedule 16 | 70 | [18 empty] | 0
Schedule 16 | 71 | [18 empty] | 0
Schedule 16 | 72 | [18 empty] | 0
Schedule 16 | 72A | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 73 | [18 empty] | 0
Schedule 16 | 74 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 75 | [18 empty] | 0
Schedule 16 | 76 | [18 empty] | 0
Schedule 16 | 77 | [18 empty] | 0
Schedule 16 | 78 | [18 empty] | 0
Schedule 16 | 79 | [18 empty] | 0
Schedule 16 | 80 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 81 | [8 empty] | YES |  |  |  | YES | [5 empty] | 2
Schedule 16 | 82 | [18 empty] | 0
Schedule 16 | 83 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 84 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 85 | [18 empty] | 0
Schedule 16 | 86 | [18 empty] | 0
Schedule 16 | 87 | [18 empty] | 0
Schedule 16 | 88 | [18 empty] | 0
Schedule 16 | 89 | [18 empty] | 0
Schedule 16 | 90 | [18 empty] | 0
Schedule 16 | 91 | [18 empty] | 0
Schedule 16 | 92 | [13 empty] | YES |  |  |  |  | 1
Schedule 16 | 93 | [13 empty] | YES |  |  |  |  | 1
Schedule 16 | 94 | [13 empty] | YES |  |  |  |  | 1
Schedule 16 | 95 | [13 empty] | YES |  |  |  |  | 1
Schedule 16 | 96 | [18 empty] | 0
Schedule 16 | 97 | [15 empty] | YES |  |  | 1
Schedule 16 | 98 | [15 empty] | YES |  |  | 1
Schedule 16 | 99 | [15 empty] | YES |  |  | 1
Schedule 16 | 100 | [15 empty] | YES |  |  | 1
Schedule 16 | 101 | [15 empty] | YES |  | YES | 2 | (DCP 234 deletes this Clause including table/s)) (DCP 226 amended a row of the table)
Schedule 16 | 102 | [15 empty] | YES |  |  | 1
Schedule 16 | 102A | [15 empty] | YES |  |  | 1
Schedule 16 | 102B | [15 empty] | YES |  |  | 1
Schedule 16 | 103 | [15 empty] | YES |  |  | 1
Schedule 16 | 104 | [15 empty] | YES |  |  | 1
Schedule 16 | 105 | [15 empty] | YES |  |  | 1
Schedule 16 | 106 | [15 empty] | YES |  |  | 1
Schedule 16 | 107 | [15 empty] | YES |  |  | 1
Schedule 16 | 108 | [15 empty] | YES |  |  | 1
Schedule 16 | 108A | [15 empty] | YES |  |  | 1
Schedule 16 | 109 | [15 empty] | YES |  |  | 1
Schedule 16 | 110 | [15 empty] | YES |  |  | 1
Schedule 16 | 111 | [15 empty] | YES |  |  | 1
Schedule 16 | 112 | [15 empty] | YES |  |  | 1
Schedule 16 | 112A | [15 empty] | YES |  |  | 1
Schedule 16 | 113 | [15 empty] | YES |  |  | 1
Schedule 16 | 113A | [15 empty] | YES |  |  | 1
Schedule 16 | 113B | [15 empty] | YES |  |  | 1
Schedule 16 | 113C | [15 empty] | YES |  |  | 1
Schedule 16 | 113D | [15 empty] | YES |  |  | 1
Schedule 16 | 113E | [15 empty] | YES |  |  | 1
Schedule 16 | 114 | [15 empty] | YES |  |  | 1
Schedule 16 | 115 | [15 empty] | YES |  |  | 1
Schedule 16 | 116 | [15 empty] | YES |  |  | 1
Schedule 16 | 117 | [15 empty] | YES |  |  | 1
Schedule 16 | 118 | [15 empty] | YES |  |  | 1
Schedule 16 | 119 | [15 empty] | YES |  |  | 1
Schedule 16 | 120 | [15 empty] | YES |  |  | 1
Schedule 16 | 121 | [15 empty] | YES |  |  | 1
Schedule 16 | 122 | [15 empty] | YES |  |  | 1
Schedule 16 | 123 | [15 empty] | YES |  |  | 1
Schedule 16 | 124 | [15 empty] | YES |  |  | 1
Schedule 16 | 125 | [15 empty] | YES |  |  | 1
Schedule 16 | 126 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 127 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 128 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 129 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 130 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 131 | [8 empty] | YES |  |  |  | YES | [5 empty] | 2
Schedule 16 | 132 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 132A | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 132B | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 132C | [8 empty] | YES | [9 empty] | 1 | DCP 268 introduces Clause 132C
Schedule 16 | 132D | [8 empty] | YES | [9 empty] | 1 | DCP 268 introduces Clause 132D
Schedule 16 | 133 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 134 | [18 empty] | 0
Schedule 16 | 135 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 135A | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 135B | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 136 | [8 empty] | YES |  |  |  | YES | [5 empty] | 2
Schedule 16 | 137 | [18 empty] | 0
Schedule 16 | 138 | [18 empty] | 0
Schedule 16 | 139 | [18 empty] | 0
Schedule 16 | 140 | [18 empty] | 0
Schedule 16 | 140A | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 140B | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 140C | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 140D | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 140E | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 141 | [8 empty] | YES |  |  |  | YES | [5 empty] | 2 | Amendment to table 5
Schedule 16 | 142 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 143 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 144 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 145 | [8 empty] | YES | [9 empty] | 1
Schedule 16 | 146 | [8 empty] | YES | [5 empty] | YES |  |  |  | 2 | DCP 222 Amendment to table 7
Schedule 16 | 147 | [8 empty] | YES |  |  |  | YES |  |  |  |  | YES | 3 | (DCP 161 Amendment to table 8 and 9) (DCP 226 amended the paragraph)
Schedule 16 | 148 | [18 empty] | 0
Schedule 16 | 149 | [18 empty] | 0
Schedule 16 | 150 | [18 empty] | 0
Schedule 16 | 151 | [18 empty] | 0
Schedule 16 | 152 | [18 empty] | 0
Schedule 16 | 153 | [12 empty] | YES | [5 empty] | 1
Schedule 16 | 154 | [18 empty] | 0
Schedule 16 | 155 | [18 empty] | 0
Schedule 16 | 156 | [18 empty] | 0
Schedule 16 | 157 | [12 empty] | YES | [5 empty] | 1
Schedule 16 | 158 | [18 empty] | 0
Schedule 16 | 159 | [18 empty] | 0
Schedule 16 | 160 | [18 empty] | 0
Schedule 16 | 161 | [18 empty] | 0
Schedule 16 | 162 | [18 empty] | 0
Schedule 16 | 163 | [18 empty] | 0
Schedule 16 | 164 | [18 empty] | 0
Schedule 16 | 165 | [18 empty] | 0
Schedule 16 | 166 | [18 empty] | 0
Schedule 16 | 167 | [18 empty] | 0
Schedule 16 | 168 | [18 empty] | 0
Schedule 16 | 169 | [18 empty] | 0
Schedule 16 | 170 | [18 empty] | 0
Schedule 16 | 171 | [18 empty] | 0
Schedule 16 | 172 | [18 empty] | 0
Schedule 16 | 173 | [12 empty] | YES | [5 empty] | 1
Schedule 16 | 174 | [18 empty] | 0
Schedule 16 | 175 | [18 empty] | 0
Schedule 16 | 176 | [18 empty] | 0
Schedule 16 | 177 | [12 empty] | YES | [5 empty] | 1
Schedule 16 | Glossary | [8 empty] | YES | [6 empty] | YES |  |  | 2 | Delete definition of "EHV Reduction Ratio".
Schedule 17 | Introduction |  |  |  |  | YES | [13 empty] | 1 | DCP 293 introduces an introductory paragraph at the start of the Schedule
Schedule 17 | 1 | [18 empty] | 0
Schedule 17 | 1.1 | [18 empty] | 0
Schedule 17 | 1.2 | [18 empty] | 0
Schedule 17 | 1.3 |  |  |  |  | YES | YES |  |  | YES |  |  |  | YES | [5 empty] | 4
Schedule 17 | 1.4 | [18 empty] | 0
Schedule 17 | 1.5 | [18 empty] | 0
Schedule 17 | 1.6 | [18 empty] | 0
Schedule 17 | 1.7 | [18 empty] | 0
Schedule 17 | 1.8 | [18 empty] | 0
Schedule 17 | 1.9 | [17 empty] | YES | 1 | DCP 226 amends numbering of 'Figure'
Schedule 17 | 2 | [18 empty] | 0
Schedule 17 | 2.1 | [18 empty] | 0
Schedule 17 | 2.2 | [18 empty] | 0
Schedule 17 | 2.3 | [18 empty] | 0
Schedule 17 | 2.4 | [18 empty] | 0
Schedule 17 | 2.5 | [18 empty] | 0
Schedule 17 | 2.6 | [18 empty] | 0
Schedule 17 | 2.7 | [18 empty] | 0
Schedule 17 | 2.8 | [18 empty] | 0
Schedule 17 | 2.9 | [18 empty] | 0
Schedule 17 | 2.1 | [18 empty] | 0
Schedule 17 | 2.11 | [18 empty] | 0
Schedule 17 | 2.12 | [18 empty] | 0
Schedule 17 | 2.13 | [18 empty] | 0
Schedule 17 | 2.14 | [18 empty] | 0
Schedule 17 | 2.15 | [18 empty] | 0
Schedule 17 | 2.16 | [18 empty] | 0
Schedule 17 | 2.17 | [18 empty] | 0
Schedule 17 | 2.18 | [18 empty] | 0
Schedule 17 | 2.19 | [18 empty] | 0
Schedule 17 | 3 | [18 empty] | 0
Schedule 17 | 3.1 | [18 empty] | 0
Schedule 17 | 3.2 | [18 empty] | 0
Schedule 17 | 3.3 | [18 empty] | 0
Schedule 17 | 3.4 | [17 empty] | YES | 1 | DCP 226 amends numbering of 'Table'
Schedule 17 | 3.5 | [18 empty] | 0
Schedule 17 | 3.6 | [17 empty] | YES | 1 | DCP 226 amends numbering of 'Table'
Schedule 17 | 3.7 | [18 empty] | 0
Schedule 17 | 4 | [18 empty] | 0
Schedule 17 | 4.1 | [18 empty] | 0
Schedule 17 | 5 | [18 empty] | 0
Schedule 17 | 5.1 | [18 empty] | 0
Schedule 17 | 6 | [18 empty] | 0
Schedule 17 | 6.1 | [18 empty] | 0
Schedule 17 | 6.2 | [18 empty] | 0
Schedule 17 | 6.3 | YES | [17 empty] | 1 | (DCP 313 Option 1)
Schedule 17 | 7 | [18 empty] | 0
Schedule 17 | 7.1 | [18 empty] | 0
Schedule 17 | 8 | [18 empty] | 0
Schedule 17 | 8.1 | [18 empty] | 0
Schedule 17 | 8.2 | [18 empty] | 0
Schedule 17 | 8.3 | [18 empty] | 0
Schedule 17 | 8.4 | [18 empty] | 0
Schedule 17 | 9 | [18 empty] | 0
Schedule 17 | 9.1 | [18 empty] | 0
Schedule 17 | 9.2 | [18 empty] | 0
Schedule 17 | 9.3 | [18 empty] | 0
Schedule 17 | 10 | [18 empty] | 0
Schedule 17 | 10.1 | [18 empty] | 0
Schedule 17 | 10.2 | [18 empty] | 0
Schedule 17 | 10.3 | [18 empty] | 0
Schedule 17 | 10.4 | [18 empty] | 0
Schedule 17 | 11 | [18 empty] | 0
Schedule 17 | 11.1 | [18 empty] | 0
Schedule 17 | 12 | [18 empty] | 0
Schedule 17 | 12.1 | [18 empty] | 0
Schedule 17 | 12.2 | [18 empty] | 0
Schedule 17 | 12.3 | [18 empty] | 0
Schedule 17 | 13 | [18 empty] | 0
Schedule 17 | 13.1 | [18 empty] | 0
Schedule 17 | 13.2 | [18 empty] | 0
Schedule 17 | 13.3 | [18 empty] | 0
Schedule 17 | 13.4 | [18 empty] | 0
Schedule 17 | 14 | [18 empty] | 0
Schedule 17 | 14.1 | [18 empty] | 0
Schedule 17 | 14.2 | [18 empty] | 0
Schedule 17 | 14.3 | [18 empty] | 0
Schedule 17 | 14.4 | [18 empty] | 0
Schedule 17 | 14.5 | [18 empty] | 0
Schedule 17 | 15 | [18 empty] | 0
Schedule 17 | 15.1 | [18 empty] | 0
Schedule 17 | 15.2 | [18 empty] | 0
Schedule 17 | 15.3 | [18 empty] | 0
Schedule 17 | 15.4 | [18 empty] | 0
Schedule 17 | 15.5 | [18 empty] | 0
Schedule 17 | 15.6 | [17 empty] | YES | 1 | DCP 226 Amends the heading of the table in this paragraph
Schedule 17 | 15.7 | [18 empty] | 0
Schedule 17 | 15.8 | [18 empty] | 0
Schedule 17 | 15.9 | [18 empty] | 0
Schedule 17 | 15.1 | [18 empty] | 0
Schedule 17 | 15.11 | [18 empty] | 0
Schedule 17 | 15.12 | [18 empty] | 0
Schedule 17 | 15.15 | [18 empty] | 0
Schedule 17 | 16 | [18 empty] | 0
Schedule 17 | 16.1 | [18 empty] | 0
Schedule 17 | 16.2 | [18 empty] | 0
Schedule 17 | 16.3 | [18 empty] | 0
Schedule 17 | 16.4 | [18 empty] | 0
Schedule 17 | 16.5 | [18 empty] | 0
Schedule 17 | 16.6 | [18 empty] | 0
Schedule 17 | 16.7 | [18 empty] | 0
Schedule 17 | 16.8 | [18 empty] | 0
Schedule 17 | 16.9 | [18 empty] | 0
Schedule 17 | 16.1 | [18 empty] | 0
Schedule 17 | 17 | [18 empty] | 0
Schedule 17 | 17.1 | [18 empty] | 0
Schedule 17 | 17.2 | [18 empty] | 0
Schedule 17 | 17.3 | [18 empty] | 0
Schedule 17 | 18 | [18 empty] | 0
Schedule 17 | 18.1 | [18 empty] | 0
Schedule 17 | 18.2 | [18 empty] | 0
Schedule 17 | 18.3 | [18 empty] | 0
Schedule 17 | 18.4 | [18 empty] | 0
Schedule 17 | 18.5 |  | YES | [16 empty] | 1
Schedule 17 | 18.6 |  | YES | [15 empty] | YES | 2 | DCP 226 amends numbering of 'Table and references'
Schedule 17 | 18.7 |  | YES | [15 empty] | YES | 2 | DCP 226 amends numbering of 'Table and references'
Schedule 17 | 18.8 |  | YES | [15 empty] | YES | 2 | DCP 226 amends numbering of 'Table and references'
Schedule 17 | 18.9 | [18 empty] | 0
Schedule 17 | 18.1 | [18 empty] | 0
Schedule 17 | 18.11 | [18 empty] | 0
Schedule 17 | 18.12 | [18 empty] | 0
Schedule 17 | 18.13 | [18 empty] | 0
Schedule 17 | 18.14 | [18 empty] | 0
Schedule 17 | 18.15 | [18 empty] | 0
Schedule 17 | 18.16 | [18 empty] | 0
Schedule 17 | 18.17 | [18 empty] | 0
Schedule 17 | 18.18 | [18 empty] | 0
Schedule 17 | 18.19 | [18 empty] | 0
Schedule 17 | 18.2 | [18 empty] | 0
Schedule 17 | 18.21 | [18 empty] | 0
Schedule 17 | 19 | [18 empty] | 0
Schedule 17 | 19.1 | [18 empty] | 0
Schedule 17 | 19.2 | [18 empty] | 0
Schedule 17 | 19.3 | [18 empty] | 0
Schedule 17 | 19.4 | [18 empty] | 0
Schedule 17 | 19.5 | [18 empty] | 0
Schedule 17 | 19.6 | [18 empty] | 0
Schedule 17 | 19.7 | [18 empty] | 0
Schedule 17 | 19.8 | [18 empty] | 0
Schedule 17 | 19.9 | [18 empty] | 0
Schedule 17 | 19.1 | [18 empty] | 0
Schedule 17 | 19.11 | [18 empty] | 0
Schedule 17 | 20 | [18 empty] | 0
Schedule 17 | 20.1 | [18 empty] | 0
Schedule 17 | 20.2 | [18 empty] | 0
Schedule 17 | 20.3 | [18 empty] | 0
Schedule 17 | 20.4 | [18 empty] | 0
Schedule 17 | 20.5 | [18 empty] | 0
Schedule 17 | 20.6 | [18 empty] | 0
Schedule 17 | 20.7 | [18 empty] | 0
Schedule 17 | 20.8 | [18 empty] | 0
Schedule 17 | 20.9 | [18 empty] | 0
Schedule 17 | 21 | [18 empty] | 0
Schedule 17 | 21.1 | [17 empty] | YES | 1 | DCP 226 amends numbering of 'Table and references'
Schedule 17 | 21.2 | [17 empty] | YES | 1 | DCP 226 amends numbering of 'Table and references'
Schedule 17 | 22 | [18 empty] | 0
Schedule 17 | 22.1 | [18 empty] | 0
Schedule 17 | 22.2 | [18 empty] | 0
Schedule 17 | 22.3 | [18 empty] | 0
Schedule 17 | 22.4 | [18 empty] | 0
Schedule 17 | 23 | [18 empty] | 0
Schedule 17 | 23.1 | [18 empty] | 0
Schedule 17 | 23.2 | [18 empty] | 0
Schedule 17 | 23.3 | [18 empty] | 0
Schedule 17 | 23.4 | [18 empty] | 0
Schedule 17 | 23.5 | [18 empty] | 0
Schedule 17 | 24 | [18 empty] | 0
Schedule 17 | 24.1 | [18 empty] | 0
Schedule 17 | 24.2 | [18 empty] | 0
Schedule 17 | 24.3 | [18 empty] | 0
Schedule 17 | 24.4 |  |  |  | YES | [14 empty] | 1
Schedule 17 | 24.5 |  |  |  | YES | [14 empty] | 1
Schedule 17 | 24.6 |  |  |  | YES | [14 empty] | 1
Schedule 17 | 24.7 |  |  |  | YES | [14 empty] | 1
Schedule 17 | 24.8 |  |  |  | YES | [13 empty] | YES | 2 | DCP 226 amends the heading for the table
Schedule 17 | 24.9 |  |  |  | YES | [14 empty] | 1
Schedule 17 | 25 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.1 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.2 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.3 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.4 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.5 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.6 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.6A | [15 empty] | YES |  |  | 1
Schedule 17 | 25.6B. | [15 empty] | YES |  |  | 1
Schedule 17 | 25.7 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.8 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.9 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.1 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.11 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.11A | [15 empty] | YES |  |  | 1
Schedule 17 | 25.12 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.12A | [15 empty] | YES |  |  | 1
Schedule 17 | 25.13 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.14 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.14A | [15 empty] | YES |  |  | 1
Schedule 17 | 25.14B | [15 empty] | YES |  |  | 1
Schedule 17 | 25.14C | [15 empty] | YES |  |  | 1
Schedule 17 | 25.14D | [15 empty] | YES |  |  | 1
Schedule 17 | 25.15 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.15A | [15 empty] | YES |  | YES | 2 | (DCP 234 deletes this Clause including table/s)) (DCP 226 amended a row of the table)
Schedule 17 | 25.16 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.17 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.18 | [15 empty] | YES |  |  | 1
Schedule 17 | 25.19 | [15 empty] | YES |  |  | 1
Schedule 17 | 26 | [18 empty] | 0
Schedule 17 | 26.1 | [18 empty] | 0
Schedule 17 | 26.2 | [18 empty] | 0
Schedule 17 | 26.3 |  |  |  | YES | [14 empty] | 1
Schedule 17 | 26.4 | [18 empty] | 0
Schedule 17 | 26.5 | [18 empty] | 0
Schedule 17 | 26.6 | [18 empty] | 0
Schedule 17 | 26.7 |  |  |  | YES | [14 empty] | 1
Schedule 17 | 26.8 | [18 empty] | 0
Schedule 17 | 26.9 | [18 empty] | 0
Schedule 17 | 26.1 |  |  |  | YES | [14 empty] | 1
Schedule 17 | 26.11 | [18 empty] | 0
Schedule 17 | 27 | [18 empty] | 0
Schedule 17 | 27.1 | [18 empty] | 0
Schedule 17 | 27.2 | [18 empty] | 0
Schedule 17 | 27.3 | [18 empty] | 0
Schedule 17 | 27.4 | [18 empty] | 0
Schedule 17 | 28 | [18 empty] | 0
Schedule 17 | 28.1 | [18 empty] | 0
Schedule 17 | 28.2 | [18 empty] | 0
Schedule 17 | 29 | [18 empty] | 0
Schedule 17 | 29.1 | [18 empty] | 0
Schedule 17 | 29.2 | [18 empty] | 0
Schedule 17 | 29.3 | [18 empty] | 0
Schedule 17 | 29.4 | [18 empty] | 0
Schedule 17 | 30 | [18 empty] | 0
Schedule 17 | 30.1 | [18 empty] | 0
Schedule 17 | 30.2 | [18 empty] | 0
Schedule 17 | 30.3 | [18 empty] | 0
Schedule 17 | 30.4 | [18 empty] | 0
Schedule 17 | 30.5 | [18 empty] | 0
Schedule 17 | 30.6 | [18 empty] | 0
Schedule 17 | 30.7 | [18 empty] | 0
Schedule 17 | 30.8 | [18 empty] | 0
Schedule 17 | 30.9 | [18 empty] | 0
Schedule 17 | 30.1 | [18 empty] | 0
Schedule 17 | 30.11 | [18 empty] | 0
Schedule 17: Annex 1 | 1 | [18 empty] | 0
Schedule 17: Annex 1 | 2 | [18 empty] | 0
Schedule 17: Annex 1 | 2.1 | [18 empty] | 0
Schedule 17: Annex 1 | 2.2 | [18 empty] | 0
Schedule 17: Annex 1 | 2.3 | [18 empty] | 0
Schedule 17: Annex 1 | 2.4 | [18 empty] | 0
Schedule 17: Annex 1 | 2.5 | [18 empty] | 0
Schedule 17: Annex 1 | 3 | [18 empty] | 0
Schedule 17: Annex 1 | Definitions | [18 empty] | 0
Schedule 17: Annex 1 | 4 | [18 empty] | 0
Schedule 17: Annex 1 | 4.1 | [18 empty] | 0
Schedule 17: Annex 1 | 4.2 | [18 empty] | 0
Schedule 17: Annex 1 | 4.3 | [18 empty] | 0
Schedule 17: Annex 1 | 4.4 | [18 empty] | 0
Schedule 17: Annex 1 | 4.5 | [18 empty] | 0
Schedule 17: Annex 1 | 4.6 | [18 empty] | 0
Schedule 17: Annex 1 | 4.7 | [18 empty] | 0
Schedule 17: Annex 1 | 4.8 | [18 empty] | 0
Schedule 17: Annex 1 | 4.9 | [17 empty] | YES | 1 | DCP 226 amends numbering of 'Table and references'
Schedule 17: Annex 1 | 4.1 | [18 empty] | 0
Schedule 17: Annex 1 | 5 | [18 empty] | 0
Schedule 17: Annex 1 | 5.1 | [18 empty] | 0
Schedule 17: Annex 1 | 5.2 | [18 empty] | 0
Schedule 17: Annex 1 | 5.3 | [18 empty] | 0
Schedule 17: Annex 1 | 5.4 | [18 empty] | 0
Schedule 17: Annex 1 | 5.5 | [18 empty] | 0
Schedule 17: Annex 1 | 5.6 | [18 empty] | 0
Schedule 17: Annex 1 | 5.7 | [18 empty] | 0
Schedule 17: Annex 1 | 5.8 | [18 empty] | 0
Schedule 17: Annex 1 | 5.9 | [18 empty] | 0
Schedule 17: Annex 1 | 5.1 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure'
Schedule 17: Annex 1 | 5.11 | [18 empty] | 0
Schedule 17: Annex 1 | 5.12 | [18 empty] | 0
Schedule 17: Annex 1 | 5.13 | [18 empty] | 0
Schedule 17: Annex 1 | 5.14 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Table'
Schedule 17: Annex 1 | 5.15 | [18 empty] | 0
Schedule 17: Annex 1 | 5.16 | [18 empty] | 0
Schedule 17: Annex 1 | 5.17 | [18 empty] | 0
Schedule 17: Annex 1 | 5.18 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Table'
Schedule 17: Annex 1 | 5.19 | [18 empty] | 0
Schedule 17: Annex 1 | 5.2 | [18 empty] | 0
Schedule 17: Annex 1 | 5.21 | [18 empty] | 0
Schedule 17: Annex 1 | 5.22 | [18 empty] | 0
Schedule 17: Annex 1 | 5.23 | [18 empty] | 0
Schedule 17: Annex 1 | 5.24 | [18 empty] | 0
Schedule 17: Annex 1 | 5.25 | [18 empty] | 0
Schedule 17: Annex 1 | 5.26 | [18 empty] | 0
Schedule 17: Annex 1 | 5.27 | [18 empty] | 0
Schedule 17: Annex 1 | 5.28 | [18 empty] | 0
Schedule 17: Annex 1 | 5.29 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure/s'
Schedule 17: Annex 1 | 5.3 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure'
Schedule 17: Annex 1 | 5.31 | [18 empty] | 0
Schedule 17: Annex 1 | 5.32 | [18 empty] | 0
Schedule 17: Annex 1 | 5.33 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure'
Schedule 17: Annex 1 | 5.34 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Table'
Schedule 17: Annex 1 | 5.35 | YES | [17 empty] | 1 | (DCP 313 Option 2)
Schedule 17: Annex 1 | 5.36 | YES | [17 empty] | 1 | (DCP 313 Option 2)
Schedule 17: Annex 1 | 5.37 | [18 empty] | 0
Schedule 17: Annex 1 | 5.38 | [18 empty] | 0
Schedule 17: Annex 1 | 5.39 | [18 empty] | 0
Schedule 17: Annex 1 | 5.4 | [18 empty] | 0
Schedule 17: Annex 1 | 5.41 | [18 empty] | 0
Schedule 17: Annex 1 | 5.42 | [18 empty] | 0
Schedule 17: Annex 1 | 5.43 | [18 empty] | 0
Schedule 17: Annex 1 | 5.44 | [18 empty] | 0
Schedule 17: Annex 1 | 5.45 | [18 empty] | 0
Schedule 17: Annex 1 | 6 | [18 empty] | 0
Schedule 17: Annex 1 | 6.1 | [18 empty] | 0
Schedule 17: Annex 1 | 6.2 | [18 empty] | 0
Schedule 17: Annex 1 | 6.3 | [18 empty] | 0
Schedule 17: Annex 1 | 6.4 | [18 empty] | 0
Schedule 17: Annex 1 | 6.5 | [18 empty] | 0
Schedule 17: Annex 1 | 6.6 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure'
Schedule 17: Annex 1 | 6.7 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure'
Schedule 17: Annex 1 | 6.8 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure/s'
Schedule 17: Annex 1 | 7 | [18 empty] | 0
Schedule 17: Annex 1 | 7.1 | [18 empty] | 0
Schedule 17: Annex 1 | 7.2 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure'
Schedule 17: Annex 1 | 7.3 | [18 empty] | 0
Schedule 17: Annex 1 | 7.4 | [18 empty] | 0
Schedule 17: Annex 1 | 7.5 | [18 empty] | 0
Schedule 17: Annex 1 | 7.6 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure'
Schedule 17: Annex 1 | 7.7 | [18 empty] | 0
Schedule 17: Annex 1 | 7.8 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure'
Schedule 17: Annex 1 | 8 | [18 empty] | 0
Schedule 17: Annex 1 | 8.1 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure'
Schedule 17: Annex 1 | 8.2 | [18 empty] | 0
Schedule 17: Annex 1 | 8.3 | [18 empty] | 0
Schedule 17: Annex 1 | 8.4 | [18 empty] | 0
Schedule 17: Annex 1 | 9 | [18 empty] | 0
Schedule 17: Annex 1 | 9.1 | [18 empty] | 0
Schedule 17: Annex 1 | 9.2 | [18 empty] | 0
Schedule 17: Annex 1 | 9.3 | [18 empty] | 0
Schedule 17: Annex 1 | 9.4 | [18 empty] | 0
Schedule 17: Annex 1 | 9.5 | [18 empty] | 0
Schedule 17: Annex 1 | 9.6 | [18 empty] | 0
Schedule 17: Annex 1 | 9.7 | [18 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure' in paragraph 3
Schedule 17: Annex 1 | Attachment 1 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Tables' in paragraphs 4 and 5
Schedule 17: Annex 1 | Attachment 1 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Tables' in paragraph 8
Schedule 17: Annex 1 | Attachment 3 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Tables' in paragraph 3
Schedule 17: Annex 2 | Annex 2 | [18 empty] | 0
Schedule 18 | Introduction |  |  |  |  | YES | [13 empty] | 1 | DCP 293 introduces an introductory paragraph at the start of the Schedule
Schedule 18 | 1 | [18 empty] | 0
Schedule 18 | 1.1 | [18 empty] | 0
Schedule 18 | 1.2 | [18 empty] | 0
Schedule 18 | 1.3 |  |  |  |  | YES | YES |  |  | YES |  |  |  | YES | [5 empty] | 4
Schedule 18 | 1.4 | [18 empty] | 0
Schedule 18 | 1.5 | [17 empty] | YES | 1 | DCP 226 amended the paragraph
Schedule 18 | 1.6 | [18 empty] | 0
Schedule 18 | 1.7 | [18 empty] | 0
Schedule 18 | 1.8 | [18 empty] | 0
Schedule 18 | 1.9 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure'
Schedule 18 | 2 | [18 empty] | 0
Schedule 18 | 2.1 | [18 empty] | 0
Schedule 18 | 2.2 | [18 empty] | 0
Schedule 18 | 2.3 | [18 empty] | 0
Schedule 18 | 2.4 | [18 empty] | 0
Schedule 18 | 2.5 | [18 empty] | 0
Schedule 18 | 2.6 | [18 empty] | 0
Schedule 18 | 2.7 | [18 empty] | 0
Schedule 18 | 2.8 | [18 empty] | 0
Schedule 18 | 2.9 | [18 empty] | 0
Schedule 18 | 2.1 | [18 empty] | 0
Schedule 18 | 2.11 | [18 empty] | 0
Schedule 18 | 2.12 | [18 empty] | 0
Schedule 18 | 2.13 | [18 empty] | 0
Schedule 18 | 2.14 | [18 empty] | 0
Schedule 18 | 2.15 | [18 empty] | 0
Schedule 18 | 2.16 | [18 empty] | 0
Schedule 18 | 2.17 | [18 empty] | 0
Schedule 18 | 2.18 | [18 empty] | 0
Schedule 18 | 2.19 | [18 empty] | 0
Schedule 18 | 2.2 | [18 empty] | 0
Schedule 18 | 2.21 | [18 empty] | 0
Schedule 18 | 2.22 | [18 empty] | 0
Schedule 18 | 2.23 | [18 empty] | 0
Schedule 18 | 2.24 | [18 empty] | 0
Schedule 18 | 2.25 | [18 empty] | 0
Schedule 18 | 2.26 | [18 empty] | 0
Schedule 18 | 2.27 | [18 empty] | 0
Schedule 18 | 2.28 | [18 empty] | 0
Schedule 18 | 2.29 | [18 empty] | 0
Schedule 18 | 2.3 | [18 empty] | 0
Schedule 18 | 3 | [18 empty] | 0
Schedule 18 | 3.1 | [18 empty] | 0
Schedule 18 | 3.2 | [18 empty] | 0
Schedule 18 | 3.3 | [18 empty] | 0
Schedule 18 | 3.4 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Table'
Schedule 18 | 3.5 | [18 empty] | 0
Schedule 18 | 3.6 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Table'
Schedule 18 | 3.7 | [18 empty] | 0
Schedule 18 | 4 | [18 empty] | 0
Schedule 18 | 4.1 | [18 empty] | 0
Schedule 18 | 5 | [18 empty] | 0
Schedule 18 | 5.1 | [18 empty] | 0
Schedule 18 | 6 | [18 empty] | 0
Schedule 18 | 6.1 | [18 empty] | 0
Schedule 18 | 6.2 | [18 empty] | 0
Schedule 18 | 6.3 | [18 empty] | 0
Schedule 18 | 6.4 | [18 empty] | 0
Schedule 18 | 6.5 | YES | [17 empty] | 1 | (DCP 313 Option 1)
Schedule 18 | 7 | [18 empty] | 0
Schedule 18 | 7.1 | [18 empty] | 0
Schedule 18 | 8 | [18 empty] | 0
Schedule 18 | 8.1 | [18 empty] | 0
Schedule 18 | 8.2 | [18 empty] | 0
Schedule 18 | 8.3 | [18 empty] | 0
Schedule 18 | 8.4 | [18 empty] | 0
Schedule 18 | 9 | [18 empty] | 0
Schedule 18 | 9.1 | [18 empty] | 0
Schedule 18 | 9.2 | [18 empty] | 0
Schedule 18 | 10 | [18 empty] | 0
Schedule 18 | 10.1 | [18 empty] | 0
Schedule 18 | 10.2 | [18 empty] | 0
Schedule 18 | 10.3 | [18 empty] | 0
Schedule 18 | 10.4 | [18 empty] | 0
Schedule 18 | 10.5 | [18 empty] | 0
Schedule 18 | 11 | [18 empty] | 0
Schedule 18 | 11.1 | [18 empty] | 0
Schedule 18 | 12 | [18 empty] | 0
Schedule 18 | 12.1 | [18 empty] | 0
Schedule 18 | 12.2 | [18 empty] | 0
Schedule 18 | 12.3 | [18 empty] | 0
Schedule 18 | 12.4 | [18 empty] | 0
Schedule 18 | 12.5 | [18 empty] | 0
Schedule 18 | 12.6 | [18 empty] | 0
Schedule 18 | 13 | [18 empty] | 0
Schedule 18 | 13.1 | [18 empty] | 0
Schedule 18 | 13.2 | [18 empty] | 0
Schedule 18 | 13.3 | [17 empty] | YES | 1 | ?? DCP 226 was to amend 13.6 but Clause does not / no longer exist/s but text noe appears in 13.3 and still needs to be amended
Schedule 18 | 13.4 | [18 empty] | 0
Schedule 18 | 14 | [18 empty] | 0
Schedule 18 | 14.1 | [18 empty] | 0
Schedule 18 | 14.2 | [18 empty] | 0
Schedule 18 | 14.3 | [18 empty] | 0
Schedule 18 | 14.4 | [18 empty] | 0
Schedule 18 | 14.5 | [18 empty] | 0
Schedule 18 | 15 | [18 empty] | 0
Schedule 18 | 15.1 | [18 empty] | 0
Schedule 18 | 15.2 | [18 empty] | 0
Schedule 18 | 15.3 | [18 empty] | 0
Schedule 18 | 15.4 | [18 empty] | 0
Schedule 18 | 15.5 | [18 empty] | 0
Schedule 18 | 15.6 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Table'
Schedule 18 | 15.7 | [18 empty] | 0
Schedule 18 | 15.8 | [18 empty] | 0
Schedule 18 | 15.9 | [18 empty] | 0
Schedule 18 | 15.1 | [18 empty] | 0
Schedule 18 | 15.11 | [18 empty] | 0
Schedule 18 | 15.12 | [18 empty] | 0
Schedule 18 | 15.15 | [18 empty] | 0
Schedule 18 | 16 | [18 empty] | 0
Schedule 18 | 16.1 | [18 empty] | 0
Schedule 18 | 16.2 | [18 empty] | 0
Schedule 18 | 16.3 | [18 empty] | 0
Schedule 18 | 16.4 | [18 empty] | 0
Schedule 18 | 16.5 | [18 empty] | 0
Schedule 18 | 16.6 | [18 empty] | 0
Schedule 18 | 16.7 | [18 empty] | 0
Schedule 18 | 16.8 | [18 empty] | 0
Schedule 18 | 16.9 | [18 empty] | 0
Schedule 18 | 16.1 | [18 empty] | 0
Schedule 18 | 17 | [18 empty] | 0
Schedule 18 | 17.1 | [18 empty] | 0
Schedule 18 | 17.2 | [18 empty] | 0
Schedule 18 | 17.3 | [18 empty] | 0
Schedule 18 | 18 | [18 empty] | 0
Schedule 18 | 18.1 | [18 empty] | 0
Schedule 18 | 18.2 | [18 empty] | 0
Schedule 18 | 18.3 | [18 empty] | 0
Schedule 18 | 18.4 | [18 empty] | 0
Schedule 18 | 18.5 |  | YES | [16 empty] | 1
Schedule 18 | 18.6 |  | YES | [15 empty] | YES | 2 | DCP 226 amended the numbering of the 'Table and references'
Schedule 18 | 18.7 |  | YES | [15 empty] | YES | 2 | DCP 226 amended the numbering of the 'Table and references'
Schedule 18 | 18.8 |  | YES | [15 empty] | YES | 2 | DCP 226 amended the numbering of the 'Table and references'
Schedule 18 | 18.9 | [18 empty] | 0
Schedule 18 | 18.1 | [18 empty] | 0
Schedule 18 | 18.11 | [18 empty] | 0
Schedule 18 | 18.12 | [18 empty] | 0
Schedule 18 | 18.13 | [18 empty] | 0
Schedule 18 | 18.14 | [18 empty] | 0
Schedule 18 | 18.15 | [18 empty] | 0
Schedule 18 | 18.16 | [18 empty] | 0
Schedule 18 | 18.17 | [18 empty] | 0
Schedule 18 | 18.18 | [18 empty] | 0
Schedule 18 | 18.19 | [18 empty] | 0
Schedule 18 | 18.2 | [18 empty] | 0
Schedule 18 | 18.21 | [18 empty] | 0
Schedule 18 | 19 | [18 empty] | 0
Schedule 18 | 19.1 | [18 empty] | 0
Schedule 18 | 19.2 | [18 empty] | 0
Schedule 18 | 19.3 | [18 empty] | 0
Schedule 18 | 19.4 | [18 empty] | 0
Schedule 18 | 19.5 | [18 empty] | 0
Schedule 18 | 19.6 | [18 empty] | 0
Schedule 18 | 19.7 | [18 empty] | 0
Schedule 18 | 19.8 | [18 empty] | 0
Schedule 18 | 19.9 | [18 empty] | 0
Schedule 18 | 19.1 | [18 empty] | 0
Schedule 18 | 19.11 | [18 empty] | 0
Schedule 18 | 20 | [18 empty] | 0
Schedule 18 | 20.1 | [18 empty] | 0
Schedule 18 | 20.2 | [18 empty] | 0
Schedule 18 | 20.3 | [18 empty] | 0
Schedule 18 | 20.4 | [18 empty] | 0
Schedule 18 | 20.5 | [18 empty] | 0
Schedule 18 | 20.6 | [18 empty] | 0
Schedule 18 | 20.7 | [18 empty] | 0
Schedule 18 | 20.8 | [18 empty] | 0
Schedule 18 | 20.9 | [18 empty] | 0
Schedule 18 | 21 | [18 empty] | 0
Schedule 18 | 21.1 | [18 empty] | 0
Schedule 18 | 21.2 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Table and references'
Schedule 18 | 22 | [18 empty] | 0
Schedule 18 | 22.1 | [18 empty] | 0
Schedule 18 | 22.2 | [18 empty] | 0
Schedule 18 | 22.3 | [18 empty] | 0
Schedule 18 | 22.4 | [18 empty] | 0
Schedule 18 | 23 | [18 empty] | 0
Schedule 18 | 23.1 | [18 empty] | 0
Schedule 18 | 23.2 | [18 empty] | 0
Schedule 18 | 23.3 | [18 empty] | 0
Schedule 18 | 23.4 | [18 empty] | 0
Schedule 18 | 23.5 | [18 empty] | 0
Schedule 18 | 24 | [18 empty] | 0
Schedule 18 | 24.1 | [18 empty] | 0
Schedule 18 | 24.2 | [18 empty] | 0
Schedule 18 | 24.3 |  |  |  | YES | [14 empty] | 1
Schedule 18 | 24.4 |  |  |  | YES | [14 empty] | 1
Schedule 18 | 24.5 |  |  |  | YES | [14 empty] | 1
Schedule 18 | 24.6 |  |  |  | YES | [14 empty] | 1
Schedule 18 | 24.7 |  |  |  | YES | [14 empty] | 1
Schedule 18 | 24.8 |  |  |  | YES | [13 empty] | YES | 2 | DCP 226 amended the numbering of the 'Table'
Schedule 18 | 24.9 |  |  |  | YES | [14 empty] | 1
Schedule 18 | 25 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.1 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.2 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.3 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.4 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.5 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.6 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.6A | [15 empty] | YES |  |  | 1
Schedule 18 | 25.6B. | [15 empty] | YES |  |  | 1
Schedule 18 | 25.7 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.8 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.9 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.1 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.11 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.11A | [15 empty] | YES |  |  | 1
Schedule 18 | 25.12 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.12A | [15 empty] | YES |  |  | 1
Schedule 18 | 25.13 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.14 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.14A | [15 empty] | YES |  |  | 1
Schedule 18 | 25.14B | [15 empty] | YES |  |  | 1
Schedule 18 | 25.14C | [15 empty] | YES |  |  | 1
Schedule 18 | 25.14D | [15 empty] | YES |  |  | 1
Schedule 18 | 25.15 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.15A | [15 empty] | YES |  |  | 1
Schedule 18 | 25.16 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.17 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.18 | [15 empty] | YES |  |  | 1
Schedule 18 | 25.19 | [15 empty] | YES |  |  | 1
Schedule 18 | 26 | [18 empty] | 0
Schedule 18 | 26.1 | [18 empty] | 0
Schedule 18 | 26.2 | [18 empty] | 0
Schedule 18 | 26.3 |  |  |  | YES | [14 empty] | 1
Schedule 18 | 26.4 | [18 empty] | 0
Schedule 18 | 26.5 | [18 empty] | 0
Schedule 18 | 26.6 | [18 empty] | 0
Schedule 18 | 26.7 |  |  |  | YES | [14 empty] | 1
Schedule 18 | 26.8 | [18 empty] | 0
Schedule 18 | 26.9 | [18 empty] | 0
Schedule 18 | 26.1 |  |  |  | YES | [14 empty] | 1
Schedule 18 | 26.11 | [18 empty] | 0
Schedule 18 | 27 | [18 empty] | 0
Schedule 18 | 27.1 | [18 empty] | 0
Schedule 18 | 27.2 | [18 empty] | 0
Schedule 18 | 27.3 | [18 empty] | 0
Schedule 18 | 27.4 | [18 empty] | 0
Schedule 18 | 28 | [18 empty] | 0
Schedule 18 | 28.1 | [18 empty] | 0
Schedule 18 | 28.2 | [18 empty] | 0
Schedule 18 | 29 | [18 empty] | 0
Schedule 18 | 29.1 | [18 empty] | 0
Schedule 18 | 29.2 | [18 empty] | 0
Schedule 18 | 29.3 | [18 empty] | 0
Schedule 18 | 29.4 | [18 empty] | 0
Schedule 18 | 30 | [18 empty] | 0
Schedule 18 | 30.1 | [18 empty] | 0
Schedule 18 | 30.2 | [18 empty] | 0
Schedule 18 | 30.3 | [18 empty] | 0
Schedule 18 | 30.4 | [18 empty] | 0
Schedule 18 | 30.5 | [18 empty] | 0
Schedule 18 | 30.6 | [18 empty] | 0
Schedule 18 | 30.7 | [18 empty] | 0
Schedule 18 | 30.8 | [18 empty] | 0
Schedule 18 | 30.9 | [18 empty] | 0
Schedule 18 | 30.1 | [18 empty] | 0
Schedule 18 | 30.11 | [18 empty] | 0
Schedule 18: Annex 1 | 1 | [18 empty] | 0
Schedule 18: Annex 1 | 1.1 | [18 empty] | 0
Schedule 18: Annex 1 | 2 | [18 empty] | 0
Schedule 18: Annex 1 | 2.1 | [18 empty] | 0
Schedule 18: Annex 1 | 2.2 | [18 empty] | 0
Schedule 18: Annex 1 | 2.3 | [18 empty] | 0
Schedule 18: Annex 1 | 2.4 | [18 empty] | 0
Schedule 18: Annex 1 | 2.5 | [18 empty] | 0
Schedule 18: Annex 1 | 3 | [18 empty] | 0
Schedule 18: Annex 1 | Definitions | [18 empty] | 0
Schedule 18: Annex 1 | 4 | [18 empty] | 0
Schedule 18: Annex 1 | 4.1 | [18 empty] | 0
Schedule 18: Annex 1 | 4.2 | [18 empty] | 0
Schedule 18: Annex 1 | 4.3 | [18 empty] | 0
Schedule 18: Annex 1 | 4.4 | [18 empty] | 0
Schedule 18: Annex 1 | 4.5 | [18 empty] | 0
Schedule 18: Annex 1 | 4.6 | [18 empty] | 0
Schedule 18: Annex 1 | 4.7 | [18 empty] | 0
Schedule 18: Annex 1 | 4.8 | [18 empty] | 0
Schedule 18: Annex 1 | 4.9 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Tables/Figures and references'
Schedule 18: Annex 1 | 5 | [18 empty] | 0
Schedule 18: Annex 1 | 5.1 | [18 empty] | 0
Schedule 18: Annex 1 | 5.2 | [18 empty] | 0
Schedule 18: Annex 1 | 5.3 | [18 empty] | 0
Schedule 18: Annex 1 | 5.4 | [18 empty] | 0
Schedule 18: Annex 1 | 5.5 | [18 empty] | 0
Schedule 18: Annex 1 | 5.6 | [18 empty] | 0
Schedule 18: Annex 1 | 5.7 | [18 empty] | 0
Schedule 18: Annex 1 | 5.8 | [18 empty] | 0
Schedule 18: Annex 1 | 5.9 | [18 empty] | 0
Schedule 18: Annex 1 | 5.1 | [18 empty] | 0
Schedule 18: Annex 1 | 5.11 | [18 empty] | 0
Schedule 18: Annex 1 | 5.12 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure'
Schedule 18: Annex 1 | 5.13 | [18 empty] | 0
Schedule 18: Annex 1 | 5.14 | [18 empty] | 0
Schedule 18: Annex 1 | 5.15 | [18 empty] | 0
Schedule 18: Annex 1 | 5.16 | [18 empty] | 0
Schedule 18: Annex 1 | 5.17 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Table'
Schedule 18: Annex 1 | 5.18 | [18 empty] | 0
Schedule 18: Annex 1 | 5.19 | [18 empty] | 0
Schedule 18: Annex 1 | 5.2 | [18 empty] | 0
Schedule 18: Annex 1 | 5.21 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Table'
Schedule 18: Annex 1 | 5.22 | [18 empty] | 0
Schedule 18: Annex 1 | 5.23 | [18 empty] | 0
Schedule 18: Annex 1 | 5.24 | [18 empty] | 0
Schedule 18: Annex 1 | 5.25 | [18 empty] | 0
Schedule 18: Annex 1 | 5.26 | [18 empty] | 0
Schedule 18: Annex 1 | 5.27 | [18 empty] | 0
Schedule 18: Annex 1 | 5.28 | [18 empty] | 0
Schedule 18: Annex 1 | 5.29 | [18 empty] | 0
Schedule 18: Annex 1 | 5.3 | [18 empty] | 0
Schedule 18: Annex 1 | 5.31 | YES | [17 empty] | 1 | (DCP 313 Option 2)
Schedule 18: Annex 1 | 5.32 | YES | [17 empty] | 1 | (DCP 313 Option 2)
Schedule 18: Annex 1 | 5.33 | [18 empty] | 0
Schedule 18: Annex 1 | 5.34 | [18 empty] | 0
Schedule 18: Annex 1 | 5.35 | [18 empty] | 0
Schedule 18: Annex 1 | 5.36 | [18 empty] | 0
Schedule 18: Annex 1 | 5.37 | [18 empty] | 0
Schedule 18: Annex 1 | 5.38 | [18 empty] | 0
Schedule 18: Annex 1 | 5.39 | [18 empty] | 0
Schedule 18: Annex 1 | 5.4 | [18 empty] | 0
Schedule 18: Annex 1 | 5.41 | [18 empty] | 0
Schedule 18: Annex 1 | 5.42 | [18 empty] | 0
Schedule 18: Annex 1 | 6 | [18 empty] | 0
Schedule 18: Annex 1 | 6.1 | [18 empty] | 0
Schedule 18: Annex 1 | 6.2 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Figure'
Schedule 18: Annex 1 | 6.3 | [18 empty] | 0
Schedule 18: Annex 1 | 6.4 | [18 empty] | 0
Schedule 18: Annex 1 | 6.5 | [18 empty] | 0
Schedule 18: Annex 1 | 6.6 | [18 empty] | 0
Schedule 18: Annex 1 | 6.7 | [18 empty] | 0
Schedule 18: Annex 1 | 6.8 | [18 empty] | 0
Schedule 18: Annex 1 | 6.9 | [18 empty] | 0
Schedule 18: Annex 1 | 6.1 | [18 empty] | 0
Schedule 18: Annex 1 | 6.11 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Table'
Schedule 18: Annex 1 | 6.12 | [18 empty] | 0
Schedule 18: Annex 1 | 6.13 | [18 empty] | 0
Schedule 18: Annex 1 | 6.14 | [18 empty] | 0
Schedule 18: Annex 1 | 6.15 | [18 empty] | 0
Schedule 18: Annex 1 | 6.16 | [18 empty] | 0
Schedule 18: Annex 1 | 6.17 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Table reference' in the paragraph
Schedule 18: Annex 1 | 6.18 | [18 empty] | 0
Schedule 18: Annex 1 | 6.19 | [18 empty] | 0
Schedule 18: Annex 1 | 6.2 | [18 empty] | 0
Schedule 18: Annex 1 | 6.21 | [18 empty] | 0
Schedule 18: Annex 1 | 6.22 | [18 empty] | 0
Schedule 18: Annex 1 | 6.23 | [18 empty] | 0
Schedule 18: Annex 1 | 6.24 | [18 empty] | 0
Schedule 18: Annex 1 | 6.25 | [18 empty] | 0
Schedule 18: Annex 1 | 6.26 | [18 empty] | 0
Schedule 18: Annex 1 | 6.27 | [18 empty] | 0
Schedule 18: Annex 1 | 6.28 | [18 empty] | 0
Schedule 18: Annex 1 | 6.29 | [18 empty] | 0
Schedule 18: Annex 1 | 6.3 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Tables/Figures and references'
Schedule 18: Annex 1 | 6.31 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Tables/Figures and references'
Schedule 18: Annex 1 | 6.32 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Table'
Schedule 18: Annex 1 | 6.33 | [18 empty] | 0
Schedule 18: Annex 1 | 6.34 | [18 empty] | 0
Schedule 18: Annex 1 | 7 | [18 empty] | 0
Schedule 18: Annex 1 | 7.1 | [17 empty] | YES | 1 | DCP 226 amended the paragraph
Schedule 18: Annex 1 | 7.2 | [18 empty] | 0
Schedule 18: Annex 1 | 7.3 | [18 empty] | 0
Schedule 18: Annex 1 | 7.4 | [18 empty] | 0
Schedule 18: Annex 1 | 7.5 | [18 empty] | 0
Schedule 18: Annex 1 | 8 | [18 empty] | 0
Schedule 18: Annex 1 | 8.1 | [18 empty] | 0
Schedule 18: Annex 1 | 8.2 | [18 empty] | 0
Schedule 18: Annex 1 | 8.3 | [18 empty] | 0
Schedule 18: Annex 1 | 8.4 | [18 empty] | 0
Schedule 18: Annex 1 | 8.5 | [18 empty] | 0
Schedule 18: Annex 1 | 8.6 | [18 empty] | 0
Schedule 18: Annex 1 | 8.7 | [18 empty] | 0
Schedule 18: Annex 1 | 8.8 | [18 empty] | 0
Schedule 18: Annex 1 | 8.9 | [18 empty] | 0
Schedule 18: Annex 1 | 8.1 | [18 empty] | 0
Schedule 18: Annex 1 | 8.11 | [18 empty] | 0
Schedule 18: Annex 1 | 8.12 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Tables/Figures and references'
Schedule 18: Annex 1 | 8.13 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Tables/Figures and references'
Schedule 18: Annex 1 | 8.14 | [18 empty] | 0
Schedule 18: Annex 1 | 8.15 | [18 empty] | 0
Schedule 18: Annex 1 | 8.16 | [18 empty] | 0
Schedule 18: Annex 1 | 8.17 | [18 empty] | 0
Schedule 18: Annex 1 | 8.18 | [18 empty] | 0
Schedule 18: Annex 1 | 8.19 | [17 empty] | YES | 1 | DCP 226 amended the numbering of the 'Table reference'
Schedule 18: Annex 1 | 8.2 | [18 empty] | 0
Schedule 18: Annex 1 | 8.21 | [18 empty] | 0
Schedule 18: Annex 1 | Attachment 1 | [18 empty] | 0
Schedule 18: Annex 1 | Attachment 2 | [18 empty] | 0 | DCP 226 amended the numbering of the 'Tables/Figures and references'
Schedule 18: Annex 1 | Attachment 3 | [18 empty] | 0 | DCP 226 amended the numbering of the 'Tables/Figures and references'
Schedule 18: Annex 2 | Annex 2 | [18 empty] | 0 | DCP 226 amended the numbering of the 'Tables/Figures and references'
Schedule 20 | Introduction |  |  |  |  | YES | [13 empty] | 1 | DCP 293 introduces an introductory paragraph at the start of the Schedule
Schedule 20 | 1.1 |  |  |  |  | YES |  |  |  | YES |  |  | YES | YES |  | YES |  |  |  | 5
Schedule 20 | 2.1 | [18 empty] | 0
Schedule 20 | 3.1 | [18 empty] | 0
Schedule 20 | 3.2 | [18 empty] | 0
Schedule X | Introduction |  |  |  |  | YES | [13 empty] | 1 | DCP 293 introduces an introductory paragraph at the start of the Schedule
Schedule X | 1 | [15 empty] | YES |  |  | 1
Schedule X | 1A |  |  |  |  | YES | [13 empty] | 1 | DCP 293 introduces paragraph 1A
Schedule X | 2 | [15 empty] | YES |  |  | 1
Schedule X | 3 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 4 | [15 empty] | YES |  |  | 1
Schedule X | 5 | [15 empty] | YES |  |  | 1
Schedule X | 6 |  |  | YES | [12 empty] | YES |  |  | 2 | (DCP 306 amends the table under the paragraph)
Schedule X | 7 | [15 empty] | YES |  |  | 1
Schedule X | 8 | [15 empty] | YES |  |  | 1
Schedule X | 9 | [15 empty] | YES |  |  | 1
Schedule X | 10 | [15 empty] | YES |  |  | 1
Schedule X | 11 | [15 empty] | YES |  |  | 1
Schedule X | 11A |  |  | YES | [15 empty] | 1 | (DCP 306 introduces Clause 11A)
Schedule X | 12 | [15 empty] | YES |  |  | 1
Schedule X | 13 | [15 empty] | YES |  |  | 1
Schedule X | 14 | [15 empty] | YES |  |  | 1
Schedule X | 15 | [15 empty] | YES |  |  | 1
Schedule X | 16 | [15 empty] | YES |  |  | 1
Schedule X | 17 | [15 empty] | YES |  |  | 1
Schedule X | 18 | [15 empty] | YES |  |  | 1
Schedule X | 19 | [15 empty] | YES |  |  | 1
Schedule X | 20 | [9 empty] | YES | [5 empty] | YES |  |  | 2 | (DCP 266 amends only the heading)
Schedule X | 21 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 22 | [15 empty] | YES |  |  | 1
Schedule X | 23 | [15 empty] | YES |  |  | 1
Schedule X | 24 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 25 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 26 | [15 empty] | YES |  |  | 1
Schedule X | 27 | [15 empty] | YES |  |  | 1
Schedule X | 28 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 29 | [15 empty] | YES |  |  | 1
Schedule X | 30 | [15 empty] | YES |  |  | 1
Schedule X | 31 | [15 empty] | YES |  |  | 1
Schedule X | 32 | [15 empty] | YES |  |  | 1
Schedule X | 33 | [15 empty] | YES |  |  | 1
Schedule X | 34 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 35 | [15 empty] | YES |  |  | 1
Schedule X | 36 | [15 empty] | YES |  |  | 1
Schedule X | 37 | [15 empty] | YES |  |  | 1
Schedule X | 38 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 39 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 40 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 41 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 42 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 43 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 44 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 45 |  |  |  | YES | [11 empty] | YES |  |  | 2
Schedule X | 46 | [9 empty] | YES | [5 empty] | YES |  |  | 2
Schedule X | 46A | [9 empty] | YES | [8 empty] | 1
Schedule X | 47 | [15 empty] | YES |  |  | 1