## CPs
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst/WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status
STATUS - DEFINITION
DCP 243 | Treatment of Customer Contributions in the CDCM | ​This CP seeks to revise DCUSA Schedule 16 to utilise current source data to determine a common industry set of modelling inputs in order to improve clarity in the approach to be used in calculating ‘Customer contribution under the current connection charging policy’ for use in CDCM table 1060. | CDCM | 1 | Dylan Townsend/ John Lawton | Dominic Green | 2015-06-05 | 15 |  | 2019-04-01 | The Working Group issued a RFI in February 2017. The Working Group met on 21 March 2017 to review the responses to the RFI and decide which option to proceed with. The Working Group agreed to proceed to final consultation after deciding on which option to proceed with and are currently drafting the final consultation document which is expected to be issued in October.
DCP 266 | The calculation and application of IDNO discounts | To change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this CP is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | CDCM | 1 | Dylan Townsend/ John Lawton | Tim Aldridge | 2016-03-09 | 7 |  | 2019-04-01 | The Working Group met on 24 January 2017 and were presented with a new model (Method GM) which combines Method M model and the Method G model which was presented to the WG in November. An Impact Assessment request has been sent to the Modelling Consultant in March. The Impact Assessment has been circulated to the Working Group. The Working Group met on 20 June 2017 and are in the process of drafting a consultation. Amended modelling was requested and has been receieved, the group will meet on 25 September to review the modelling and impact assessment.
DCP 283 | The calculation of generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators | CDCM | 1 | Dylan Townsend / John Lawton | Edda Dirks | 2016-10-12 | 9 |  | 2019-04-01 | The Working Group issued a Consultation on 14 March 2017 which closed on 04 April 2017. The Working Group met on 7 April 2017 to review the consultation responses. The Working Group have met on 4 May 2017 and have agreed to proceed with a second consultation to parties and will include legal text and impacts. The the Working Group met on 22 June 2017. The Working Group issued their second consultation on 01 September 2017.
DCP 287 | Generation credits in the EDCM | The intent of this Change Proposal is to amend the calculation of credits for embedded generation in the EDCM to take account of potential cost savings for DNOs that can be attributed to embedded generation in the areas of transmission exit charges, direct costs, indirect costs and network rates. | EDCM | 1 | Dan Fittock / John Lawton | Edda Dirks | 2016-12-07 | 3 |  | 2020-04-01 | The DCP 287 Working Group last met on the 7 September and are continuing to refine the consultation document.
DCP 288, DCP 288A DCP 288B | Introduction of the Electricity Theft Detection Incentive Scheme DCP 288B - Equitable Theft Detection Incentive Scheme - | The intent of this Change Proposal (CP) is to introduce an Electricity Theft Detection Incentive Scheme in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014 DCP 288B seeks to create an equitable scheme which suitably incentivises detection of electricity theft without distorting competition and hampering effective functioning of the market in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014. | THEFT | 1 | Fungai Madzivadondo/ Rachel Collis | Jon Dixon | 2016-12-12 | 7 |  | TBD | The DCP 288, 288A and 288B consultation was issued to the industry on 22 August with a deadline of 14 Septemebr 2017. The TIG will meet on 19 Septemember 2017 to review the consultatiuon responses.
DCP 291 | Application of Generation Credits to EDCM Customers | The intent of this Change Proposal is to apply EDCM generation credits to all generators whether intermittent or non-intermittent, on the basis that a LRIC/FCP charge 1 exists. | EDCM | 1 | Hollie Nicholls/ Dan Fittock | Edda Dirks | 2017-02-10 | 3 |  | 2019-04-01 | The DCP 291 Working Group met on 05 May to discuss the previous Ofgem decision on Decision on F Factor setting for Intermittent Generators and to review the draft consultation document. The Working Group will next meet on 5 June to discuss the RFI results from DNOs to find out what, if any, impacts could be on providing credits to intermittent generators. The Working Group have reviewed the RFI responses which details the impacts associated with the CP. A further Working Group meeting is scheduled for 21 September to discuss the next steps of the CP as there are some concerns about the intent from some of the DNOs.
DCP 294 | Capacity Management Following Acceptance of Connection Offer | This CP seeks to put arrangements in place that set out the principles under which the unutilised maximum capacity specified in connection offers or in bilateral connection agreements with IDNOs can be managed in an economic and efficient manner whilst protecting the legitimate requirements of parties requiring Capacity which was agreed in connection offers. | CCCM | 1 | Hollie Nichollls/ John Lawton | Moshe Kinshuck | 2017-03-01 | 3 |  | First release following approval | The first Working Group meeting took place on the 20 April 2017 and it was agreed that legal advice was required before a solution could be progressed on this CP. The Working Group are in the process of finalising the legal advice questions for submission to the DCUSA Panel for approval. The Panel requested that the Working Group review what legal advice had already been obtained for previous CPs. The Working Group are reviewing this and if the advice is still needed, questions will be submitted to Panel in August. The group reviewed the legal questions and agreed that they were no longer needed. A draft consultation has been produced for WG comments.
DCP 295 | CVA Registrants acceding to the DCUSA | This change is to facilitate BSC Modification PXXX which is to oblige CVA Registrants connecting to a Distribution System to accede to the DCUSA which will negate the need for a bilateral Use of System Agreements between the LDSO and the CVA Registrants saving administrative cost and effort and promoting efficiency and consistency. The effect of this change will be to modify the legal text to include CVA Registrants in addition to Distributed Generation Parties mainly in Section 2A but also in Sections 1A, 1B, 1C, 2B, 2C and 3 and Schedules 9, 11, 19 and 21. | General | 1 | Hollie Nicholls/ Dan Fittock | Stephen Perry | 2017-03-07 | 1 |  | First release following approval | A Working Group invitation was issued to Parties and the first Working Group meeting is in the process of being set up. The Working Group met on 3 July 2017 and are in the process of drafting a consultation. A consultation was issued to the Industry for response on 24 July. The deadline for responses is 14 August. Consultation responses have been collated and the group are meeting on 15th September to discuss and to agree next steps.
DCP 297 | Network Interventions SLA Enhancement | This CP seeks to change the mechanism whereby DNO’s are released from their obligations to meet the intervention SLA to one which is solely based on the accuracy of Suppliers smart meter roll-out forecasts. The DCUSA Panel has directed that this change be considered by the Interventions Working Group. | General | 1 | To be progressed by the Interventions Working Group | Michael Walls | 2017-04-07 | 0 |  | First release following approval | At the April DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group (IWG). The IWG have discussed the CP at their recent meeting and have issued a consultation which closed on 10 July 2017. The IWG reviewed the responses at their meeting on 14 August and are expecting to submit a change report to the Panel in October.
DCP 302 | Moving Made Safe Instances To Cat B | To change the Category definition(s) to allow Category A incidents that have been made safe by the meter operator to be reclassified and reported as Category B. | General | 1 | To be progressed by the Interventions Working Group |  |  | 1 |  | 2017-10-01 | At the June DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group (IWG). The IWG are drafted a consultation which was issued 29 August with responses due 19 September.
DCP 304 | Metering Works by Non-Appointed Meter Operator | This Change Proposal seeks to widen the scope of DCUSA to allow suppliers and their meter operators to break seals and work on metering equipment at metering points for which they are not the appointed meter operator. | General | 1 | To be progressed by the Interventions Working Group | Michael Walls |  | 0 |  |  | At the June DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group (IWG). The IWG are drafted a consultation which was issued 29 August with responses due 19 September.
DCP 305 | LDNO Boundary Level Definitions in the EDCM | The intent of this change proposal is to amend the definitions and application of DNO/LDNO boundaries under the EDCM to avoid instances of double- and/or non-charging for certain assets. | EDCM | 1 | Dan Fittock / John Lawton |  |  | 0 |  |  | The first Working Group meeting is due on 22 September 2017.
DCP 306 | Treatment of Ofgem Licence Fees within the PCDM | The intent of this Change Proposal is to increase the cost reflectivity of the Price Control Disaggregation Model by directly allocating the Ofgem licence fee to an appropriate network tier for the calculation of the Opex allocation driver. | General | 1 | Hollie Nicholls / John Lawton | Tim Aldridge | 2017-07-12 | 1 |  | 2020-04-01 | A Working Group invitation was issued to Parties and the first Working Group meeting is in the process of being set up. The first WG meeting was held on 8th September. A draft consultation document has been produced for the group to review with a view to issue to the industry for comment on 18th/19th September 2017. Work Plan to be issued to the September panel for approval
STATUS - CHANGE REPORT
DCP 300 | Panel Members and Alternates | To reword the DCUSA sections around panel members and alternates, particularly around election and participation at meetings, to better reflect practicalities and solve issues with the current processes. | General | 2 | Dan Fittock |  | 2017-05-15 |  |  | 2017-10-01 | The Change Report and Change Declaration previously issued were incorrect as they reported that DCP 300 was a Part 1 Matter, where it should be a Part 2 Matter. Following Panel discussions, it was agreed that Shareholder approval to amend the Articles of Association was required before a revised Change Report should be issued for voting.
DCP 293 | Charging methodology cut-off date | This change looks to establish a cut-off date for the finalisation of the charging methodologies at 17 months prior to the date that the methodology would become effective. Establishing this cut-off date will provide a 2-month time window for DCUSA to provide charging models and DNOs to test the new charging models and then to calculate, test and approve revised charges. | General | 1 | Hollie Nicholls/ Dylan Townsend | Sean Hennity | 2017-02-14 | 3 |  | First release following approval | The Working Group met on the 21 March 2017 to analyse the CP and the outcome of the DCP 164 Authority Decision. The Working Group issued a consultation to Parties which closed on 10 July 2017. The Working Group met on 14 July 2017 to review the consultation responses and are now in the process of finalising the Change Report. The Proposer noted an error with the legal text which has been sent to the legal advisor for finalisation. The Change Report should be issued to the September Panel.
DCP 226 | Housekeeping 66/72/73/77/80 | This CP seeks to review and revise the DCUSA document to incorporate housekeeping log items 66/72/73/77/80 | General | 2 | Dylan Townsend |  | 2015-01-05 | 0 |  | Next Release Following Authority Consent | The Working Group invitation closed with only one interested person. It was agreed that in addition to addressing the proposed housekeeping changes DCP 226 would also review the numbering and referencing throughout the DCUSA document. Draft legal text has been provided by the Proposer which has since been reviewed by the DCUSA legal advisor. A Change Report has been issued to the September Panel.
STATUS - VOTING
STATUS - AWAITING AUTHORITY CONSENT
DCP 268 | DUoS Charging Using HH settlement data | The intent of this CP is to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | CDCM | 1 | Dan Fittock / John Lawton | Lynda Carroll? | 2016-03-14 | 10 |  | 2019-04-01 | DCUSA Parties voted to accept the Solution and to reject the implementation date. DCP 268 is currently awaiting a determination by the Authority.
STATUS - AWAITING IMPLEMENTATION
2017-10-01
2017-11-02
DCP 299 | Clarify Distributor reporting requirement to the ETTOS Service Provider | The intent of this Change Proposal is to add a requirement for Electricity Distributors to notify the ETTOS Service Provider of instances where tip-offs cannot be linked with a currently traded MPAN. | ETTOS | 2 | Fungai Madzivadondo |  | 2017-05-10 | 0 |  | 2017-11-02 | Parties voted to approve the change on the 18 July 2017 for implementation on the 02 November 2017.
DCP 301 | Update Schedule 25 - Appendix 2 data items | The intent of this Change Proposal is to update supply address data items in DCUSA Schedule 25, Appendix 2 to align with the commercial and residential consumption and outcome tabs of the TRAS Programming Manual. | TRAS | 2 | Fungai Madzivadondo |  | 2017-06-12 | 0 |  | 2017-11-02 | Parties voted to approve the change on the 08 August 2017 for implementation on the 02 November 2017
2018-04-01
DCP 161 | Excess Capacity Charges | To improve the cost reflectivity of the excess capacity charge calculation within the CDCM and EDCM by removing the customer contributions and adding in any additional costs that should be attributed to this charge. Also, to consider applying the excess capacity charge on either a monthly, seasonal or time of day basis. | CDCM | 1 | Michael Walls/Chris Ong | Keith Burwell | 2013-02-06 | 12 |  | 2018-04-01 | The Authority directed for DCP 161 to be made and implemented on 1 April 2018.
DCP 222 | Non Billing Of Excess Reactive Power Charges | This CP proposes the removal of the excess reactive power charge when a DNO requests that a generator operates outside of the 0.95 power factor limit. | CDCM | 1 | Fungai Madzivadondo/Dave Wornell | Nisha Doshi | 2014-12-02 | 11 |  | 2018-04-01 | The Authority directed for DCP 222 to be made and implemented on 1 April 2018.
DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | CDCM | 1 | Rosalind Timperley/ Chris Ong | Bethany Hanna | 2015-01-13 | 4 |  | 2018-04-01 | The Authority directed for DCP 228 to be made and implemented on 1 April 2018.
DCP 234 | Merging the PCDM and extended PCDM | The intent of the CP is to replace the Price Control Disaggregation (PCDM) and extended PCDM models with one model.To create a new schedule in DCUSA which contains the legal text that relates to IDNO charging that is currently contained in Schedules 16, 17 and 18. | CDCM and EDCM | 1 | Claire Hynes/ Claire Campbell | Lynda Carroll | 2015-02-27 | 7 |  | 2018-04-01 | The Authority directed for DCP 234 to be made and implemented on 1 April 2018.
DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | The intent of this proposal is to align table 1001 in the CDCM to the current format of table in Schedule 15. | CDCM | 2 | Fungai Madzivadondo/John Lawton | Lynda Carroll | 2016-05-18 | 2 |  | 2018-04-01 | Parties voted to approve the change on the 17 October 2016 for implementation on the 01 April 2018.
DCP 290 | Housekeeping Change to Update PCDM Model References | The intent of this Change Proposal is to facilitate the updating of the title, model number and issue date of the PDCM as referenced in Schedules 16, 17 and 18, which was not correctly applied in the legal text of DCP234. | CDCM/EDCM | 2 | Dan Fittock |  | 2017-01-17 | 0 |  | 2018-04-01 | Parties voted to approve the change on 10 March 2017 for implementation on 01 April 2018.
STATUS - APPEAL
n/a | n/a
STATUS - IMPLEMENTED
DCP 289 | Creation of Distribution Charging Methodology Development Group | The intent of this CP is to formalise the creation of a new single Standing Issues Working Group for the Use of System charging methodologies and related topics within DCUSA. | General/ Urgent | 1 | Da n Fittock/ Claire Hynes | Vivian Marangoni | 2016-12-06 | 2 |  | Within 5 Working Days of Approval or next DCUSA release following Authority consent - 01 September 2017 | DCUSA Parties voted to accept all solutions to DCP 289, with a preference of DCP 289A. DCP 289 was implemented on 01 September.
STATUS - REJECTED
DCP 251 | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | The intent of this proposal is to correct drafting errors in the specification of the distribution systems that are eligible for LDNO tariffs under the CDCM and under the EDCM and ensure that there the charging methodologies do not impose undue discrimination between licensed and licence-exempt distribution systems and restore the 50 per cent LDNO discount on indirect costs which was removed by the approved legal text for DCP 185 in cases where the fixed adder is negative.​ | CDCM | 1 | Dan Fittock/John Lawton | Tim Aldridge | 2015-10-15 | 18 |  | Next release date after approval | DCUSA Parties voted to reject DCPs 251 and 252 and the proposals are currently awaiting a determination by the Authority.
DCP 252 | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | The intent of this proposal is to correct drafting errors and inconsistencies in the specification of the distribution systems that are eligible for Portfolio tariffs under the EDCM (schedules 17 and 18) and establish arrangements that ensure that methodologies in Schedules 17 and 18 do not impose undue discrimination between licensed and licence exempt distribution systems.​ | EDCM | 1 | Dan Fittock/John Lawton | Tim Aldridge | 2015-10-15 | 18 |  | Next release date after approval | DCUSA Parties voted to reject DCPs 251 and 252 and the proposals are currently awaiting a determination by the Authority.
STATUS - WITHDRAWN
Change Register - September 2017
Note on G46: Dylan Townsend: Is this correct?
Note on G47: Dylan Townsend: Is this correct

## Status Change
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst/WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status Updated in the last Month
STATUS - DEFINITION
DCP 243 | Treatment of Customer Contributions in the CDCM | ​This CP seeks to revise DCUSA Schedule 16 to utilise current source data to determine a common industry set of modelling inputs in order to improve clarity in the approach to be used in calculating ‘Customer contribution under the current connection charging policy’ for use in CDCM table 1060. | CDCM | 1 | Dylan Townsend/ John Lawton | Dominic Green | 2015-06-05 | 15 |  | 2019-04-01 | The Working Group issued a RFI in February 2017. The Working Group met on 21 March 2017 to review the responses to the RFI and decide which option to proceed with. The Working Group agreed to proceed to final consultation after deciding on which option to proceed with and are currently drafting the final consultation document which is expected to be issued in October. | N/A
DCP 266 | The calculation and application of IDNO discounts | To change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this CP is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | CDCM | 1 | Dylan Townsend/ John Lawton | Tim Aldridge | 2016-03-09 | 7 |  | 2019-04-01 | The Working Group met on 24 January 2017 and were presented with a new model (Method GM) which combines Method M model and the Method G model which was presented to the WG in November. An Impact Assessment request has been sent to the Modelling Consultant in March. The Impact Assessment has been circulated to the Working Group. The Working Group met on 20 June 2017 and are in the process of drafting a consultation. Amended modelling was requested and has been receieved, the group will meet on 25 September to review the modelling and impact assessment. | N/A
DCP 283 | The calculation of generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators | CDCM | 1 | Dylan Townsend / John Lawton | Edda Dirks | 2016-10-12 | 9 |  | 2019-04-01 | The Working Group issued a Consultation on 14 March 2017 which closed on 04 April 2017. The Working Group met on 7 April 2017 to review the consultation responses. The Working Group have met on 4 May 2017 and have agreed to proceed with a second consultation to parties and will include legal text and impacts. The the Working Group met on 22 June 2017. The Working Group issued their second consultation on 01 September 2017. | CONSULTATION
DCP 287 | Generation credits in the EDCM | The intent of this Change Proposal is to amend the calculation of credits for embedded generation in the EDCM to take account of potential cost savings for DNOs that can be attributed to embedded generation in the areas of transmission exit charges, direct costs, indirect costs and network rates. | EDCM | 1 | Dan Fittock / John Lawton | Edda Dirks | 2016-12-07 | 3 |  | 2020-04-01 | The DCP 287 Working Group last met on the 7 September and are continuing to refine the consultation document. | N/A
DCP 288, DCP 288A DCP 288B | Introduction of the Electricity Theft Detection Incentive Scheme DCP 288B - Equitable Theft Detection Incentive Scheme - | The intent of this Change Proposal (CP) is to introduce an Electricity Theft Detection Incentive Scheme in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014 DCP 288B seeks to create an equitable scheme which suitably incentivises detection of electricity theft without distorting competition and hampering effective functioning of the market in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014. | THEFT | 1 | Fungai Madzivadondo/ Rachel Collis | Jon Dixon | 2016-12-12 | 7 |  | TBD | The DCP 288, 288A and 288B consultation was issued to the industry on 22 August with a deadline of 14 Septemebr 2017. The TIG will meet on 19 Septemember 2017 to review the consultatiuon responses. | CONSULTATION
DCP 291 | Application of Generation Credits to EDCM Customers | The intent of this Change Proposal is to apply EDCM generation credits to all generators whether intermittent or non-intermittent, on the basis that a LRIC/FCP charge 1 exists. | EDCM | 1 | Hollie Nicholls/ Dan Fittock | Edda Dirks | 2017-02-10 | 3 |  | 2019-04-01 | The DCP 291 Working Group met on 05 May to discuss the previous Ofgem decision on Decision on F Factor setting for Intermittent Generators and to review the draft consultation document. The Working Group will next meet on 5 June to discuss the RFI results from DNOs to find out what, if any, impacts could be on providing credits to intermittent generators. The Working Group have reviewed the RFI responses which details the impacts associated with the CP. A further Working Group meeting is scheduled for 21 September to discuss the next steps of the CP as there are some concerns about the intent from some of the DNOs. | N/A
DCP 294 | Capacity Management Following Acceptance of Connection Offer | This CP seeks to put arrangements in place that set out the principles under which the unutilised maximum capacity specified in connection offers or in bilateral connection agreements with IDNOs can be managed in an economic and efficient manner whilst protecting the legitimate requirements of parties requiring Capacity which was agreed in connection offers. | CCCM | 1 | Hollie Nichollls/ John Lawton | Moshe Kinshuck | 2017-03-01 | 3 |  | First release following approval | The first Working Group meeting took place on the 20 April 2017 and it was agreed that legal advice was required before a solution could be progressed on this CP. The Working Group are in the process of finalising the legal advice questions for submission to the DCUSA Panel for approval. The Panel requested that the Working Group review what legal advice had already been obtained for previous CPs. The Working Group are reviewing this and if the advice is still needed, questions will be submitted to Panel in August. The group reviewed the legal questions and agreed that they were no longer needed. A draft consultation has been produced for WG comments. | N/A
DCP 295 | CVA Registrants acceding to the DCUSA | This change is to facilitate BSC Modification PXXX which is to oblige CVA Registrants connecting to a Distribution System to accede to the DCUSA which will negate the need for a bilateral Use of System Agreements between the LDSO and the CVA Registrants saving administrative cost and effort and promoting efficiency and consistency. The effect of this change will be to modify the legal text to include CVA Registrants in addition to Distributed Generation Parties mainly in Section 2A but also in Sections 1A, 1B, 1C, 2B, 2C and 3 and Schedules 9, 11, 19 and 21. | General | 1 | Hollie Nicholls/ Dan Fittock | Stephen Perry | 2017-03-07 | 1 |  | First release following approval | A Working Group invitation was issued to Parties and the first Working Group meeting is in the process of being set up. The Working Group met on 3 July 2017 and are in the process of drafting a consultation. A consultation was issued to the Industry for response on 24 July. The deadline for responses is 14 August. Consultation responses have been collated and the group are meeting on 15th September to discuss and to agree next steps. | N/A
DCP 297 | Network Interventions SLA Enhancement | This CP seeks to change the mechanism whereby DNO’s are released from their obligations to meet the intervention SLA to one which is solely based on the accuracy of Suppliers smart meter roll-out forecasts. The DCUSA Panel has directed that this change be considered by the Interventions Working Group. | General | 1 | To be progressed by the Interventions Working Group | Michael Walls | 2017-04-07 | 0 |  | First release following approval | At the April DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group (IWG). The IWG have discussed the CP at their recent meeting and have issued a consultation which closed on 10 July 2017. The IWG reviewed the responses at their meeting on 14 August and are expecting to submit a change report to the Panel in October. | N/A
DCP 302 | Moving Made Safe Instances To Cat B | To change the Category definition(s) to allow Category A incidents that have been made safe by the meter operator to be reclassified and reported as Category B. | General | 1 | To be progressed by the Interventions Working Group |  |  | 1 |  | 2017-10-01 | At the June DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group (IWG). The IWG are drafted a consultation which was issued 29 August with responses due 19 September. | CONSULTATION
DCP 304 | Metering Works by Non-Appointed Meter Operator | This Change Proposal seeks to widen the scope of DCUSA to allow suppliers and their meter operators to break seals and work on metering equipment at metering points for which they are not the appointed meter operator. | General | 1 | To be progressed by the Interventions Working Group | Michael Walls |  | 0 |  |  | At the June DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group (IWG). The IWG are drafted a consultation which was issued 29 August with responses due 19 September. | CONSULTATION
DCP 305 | LDNO Boundary Level Definitions in the EDCM | The intent of this change proposal is to amend the definitions and application of DNO/LDNO boundaries under the EDCM to avoid instances of double- and/or non-charging for certain assets. | EDCM | 1 | Dan Fittock / John Lawton |  |  | 0 |  |  | The first Working Group meeting is due on 22 September 2017. | N/A
DCP 306 | Treatment of Ofgem Licence Fees within the PCDM | The intent of this Change Proposal is to increase the cost reflectivity of the Price Control Disaggregation Model by directly allocating the Ofgem licence fee to an appropriate network tier for the calculation of the Opex allocation driver. | General | 1 | Hollie Nicholls / John Lawton | Tim Aldridge | 2017-07-12 | 1 |  | 2020-04-01 | A Working Group invitation was issued to Parties and the first Working Group meeting is in the process of being set up. The first WG meeting was held on 8th September. A draft consultation document has been produced for the group to review with a view to issue to the industry for comment on 18th/19th September 2017. Work Plan to be issued to the September panel for approval | N/A
STATUS - CHANGE REPORT
DCP 300 | Panel Members and Alternates | To reword the DCUSA sections around panel members and alternates, particularly around election and participation at meetings, to better reflect practicalities and solve issues with the current processes. | General | 2 | Dan Fittock |  | 2017-05-15 |  |  | 2017-10-01 | The Change Report and Change Declaration previously issued were incorrect as they reported that DCP 300 was a Part 1 Matter, where it should be a Part 2 Matter. Following Panel discussions, it was agreed that Shareholder approval to amend the Articles of Association was required before a revised Change Report should be issued for voting. | N/A
DCP 293 | Charging methodology cut-off date | This change looks to establish a cut-off date for the finalisation of the charging methodologies at 17 months prior to the date that the methodology would become effective. Establishing this cut-off date will provide a 2-month time window for DCUSA to provide charging models and DNOs to test the new charging models and then to calculate, test and approve revised charges. | General | 1 | Hollie Nicholls/ Dylan Townsend | Sean Hennity | 2017-02-14 | 3 |  | First release following approval | The Working Group met on the 21 March 2017 to analyse the CP and the outcome of the DCP 164 Authority Decision. The Working Group issued a consultation to Parties which closed on 10 July 2017. The Working Group met on 14 July 2017 to review the consultation responses and are now in the process of finalising the Change Report. The Proposer noted an error with the legal text which has been sent to the legal advisor for finalisation. The Change Report should be issued to the September Panel. | CHANGE REPORT
DCP 226 | Housekeeping 66/72/73/77/80 | This CP seeks to review and revise the DCUSA document to incorporate housekeeping log items 66/72/73/77/80 | General | 2 | Dylan Townsend |  | 2015-01-05 | 0 |  | Next Release Following Authority Consent | The Working Group invitation closed with only one interested person. It was agreed that in addition to addressing the proposed housekeeping changes DCP 226 would also review the numbering and referencing throughout the DCUSA document. Draft legal text has been provided by the Proposer which has since been reviewed by the DCUSA legal advisor. A Change Report has been issued to the September Panel. | CHANGE REPORT
STATUS - VOTING
N/A
STATUS - AWAITING AUTHORITY CONSENT
DCP 268 | DUoS Charging Using HH settlement data | The intent of this CP is to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | CDCM | 1 | Dan Fittock / John Lawton | Lynda Carroll? | 2016-03-14 | 10 |  | 2019-04-01 | DCUSA Parties voted to accept the Solution and to reject the implementation date. DCP 268 is currently awaiting a determination by the Authority. | N/A
STATUS - AWAITING IMPLEMENTATION
2017-10-01
N/A
2017-11-02
DCP 299 | Clarify Distributor reporting requirement to the ETTOS Service Provider | The intent of this Change Proposal is to add a requirement for Electricity Distributors to notify the ETTOS Service Provider of instances where tip-offs cannot be linked with a currently traded MPAN. | ETTOS | 2 | Fungai Madzivadondo |  | 2017-05-10 | 0 |  | 2017-11-02 | Parties voted to approve the change on the 18 July 2017 for implementation on the 02 November 2017. | N/A
DCP 301 | Update Schedule 25 - Appendix 2 data items | The intent of this Change Proposal is to update supply address data items in DCUSA Schedule 25, Appendix 2 to align with the commercial and residential consumption and outcome tabs of the TRAS Programming Manual. | TRAS | 2 | Fungai Madzivadondo |  | 2017-06-12 | 0 |  | 2017-11-02 | Parties voted to approve the change on the 08 August 2017 for implementation on the 02 November 2017 | N/A
2018-04-01
DCP 161 | Excess Capacity Charges | To improve the cost reflectivity of the excess capacity charge calculation within the CDCM and EDCM by removing the customer contributions and adding in any additional costs that should be attributed to this charge. Also, to consider applying the excess capacity charge on either a monthly, seasonal or time of day basis. | CDCM | 1 | Michael Walls/Chris Ong | Keith Burwell | 2013-02-06 | 12 |  | 2018-04-01 | The Authority directed for DCP 161 to be made and implemented on 1 April 2018. | N/A
DCP 222 | Non Billing Of Excess Reactive Power Charges | This CP proposes the removal of the excess reactive power charge when a DNO requests that a generator operates outside of the 0.95 power factor limit. | CDCM | 1 | Fungai Madzivadondo/Dave Wornell | Nisha Doshi | 2014-12-02 | 11 |  | 2018-04-01 | The Authority directed for DCP 222 to be made and implemented on 1 April 2018. | N/A
DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | CDCM | 1 | Rosalind Timperley/ Chris Ong | Bethany Hanna | 2015-01-13 | 4 |  | 2018-04-01 | The Authority directed for DCP 228 to be made and implemented on 1 April 2018. | N/A
DCP 234 | Merging the PCDM and extended PCDM | The intent of the CP is to replace the Price Control Disaggregation (PCDM) and extended PCDM models with one model.To create a new schedule in DCUSA which contains the legal text that relates to IDNO charging that is currently contained in Schedules 16, 17 and 18. | CDCM and EDCM | 1 | Claire Hynes/ Claire Campbell | Lynda Carroll | 2015-02-27 | 7 |  | 2018-04-01 | The Authority directed for DCP 234 to be made and implemented on 1 April 2018. | N/A
DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | The intent of this proposal is to align table 1001 in the CDCM to the current format of table in Schedule 15. | CDCM | 2 | Fungai Madzivadondo/John Lawton | Lynda Carroll | 2016-05-18 | 2 |  | 2018-04-01 | Parties voted to approve the change on the 17 October 2016 for implementation on the 01 April 2018. | N/A
DCP 290 | Housekeeping Change to Update PCDM Model References | The intent of this Change Proposal is to facilitate the updating of the title, model number and issue date of the PDCM as referenced in Schedules 16, 17 and 18, which was not correctly applied in the legal text of DCP234. | CDCM/EDCM | 2 | Dan Fittock |  | 2017-01-17 | 0 |  | 2018-04-01 | Parties voted to approve the change on 10 March 2017 for implementation on 01 April 2018. | N/A
STATUS - APPEAL
n/a | n/a | [10 empty] | N/A
STATUS - IMPLEMENTED
DCP 289 | Creation of Distribution Charging Methodology Development Group | The intent of this CP is to formalise the creation of a new single Standing Issues Working Group for the Use of System charging methodologies and related topics within DCUSA. | General/ Urgent | 1 | Da n Fittock/ Claire Hynes | Vivian Marangoni | 2016-12-06 | 2 |  | Within 5 Working Days of Approval or next DCUSA release following Authority consent - 01 September 2017 | DCUSA Parties voted to accept all solutions to DCP 289, with a preference of DCP 289A. DCP 289 was implemented on 01 September. | IMPLEMENTED
STATUS - REJECTED
DCP 251 | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | The intent of this proposal is to correct drafting errors in the specification of the distribution systems that are eligible for LDNO tariffs under the CDCM and under the EDCM and ensure that there the charging methodologies do not impose undue discrimination between licensed and licence-exempt distribution systems and restore the 50 per cent LDNO discount on indirect costs which was removed by the approved legal text for DCP 185 in cases where the fixed adder is negative.​ | CDCM | 1 | Dan Fittock/John Lawton | Tim Aldridge | 2015-10-15 | 18 |  | Next release date after approval | DCUSA Parties voted to reject DCPs 251 and 252 and the proposals are currently awaiting a determination by the Authority. | REJECTED
DCP 252 | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | The intent of this proposal is to correct drafting errors and inconsistencies in the specification of the distribution systems that are eligible for Portfolio tariffs under the EDCM (schedules 17 and 18) and establish arrangements that ensure that methodologies in Schedules 17 and 18 do not impose undue discrimination between licensed and licence exempt distribution systems.​ | EDCM | 1 | Dan Fittock/John Lawton | Tim Aldridge | 2015-10-15 | 18 |  | Next release date after approval | DCUSA Parties voted to reject DCPs 251 and 252 and the proposals are currently awaiting a determination by the Authority. | REJECTED
STATUS - WITHDRAWN
N/A
Change Register - September 2017
Note on G46: Dylan Townsend: Is this correct?
Note on G47: Dylan Townsend: Is this correct

## CP Work Plans
The DCUSA Panel is invited to:
Change Proposal | Secretariat | CP Title | Change Report Due Date | Status | Date of Last Agreed Work Plans | Note the Change Proposal Status
DCP 243 | Dylan | Treatment of Customer Contributions in the CDCM | 2017-09-13 | Work Plan Due | 2017-07-19 | Approve the DCP 243, 283, 297, 304 and 306 Work Plans
DCP 266 | Dylan | The calculation and application of IDNO discounts | 2017-10-11 |  | 2017-06-21
DCP 283 | Dylan | The calculation of generation credits in the CDCM | 2017-09-13 | Work Plan Due | 2016-12-21
DCP 287 | Dan | Generation credits in the EDCM | 2018-01-10 |  | 2017-04-25
DCP 288 | Fungai | Introduction of the Electricity Theft Detection Incentive Scheme | 2017-10-11 |  | 2017-06-21
DCP 291 | Hollie | Application of Generation Credits to EDCM Customers | 2017-09-13 | Work Plan Due (next meeting 21 September) | 2017-04-19
DCP 293 | Hollie | Charging methodology cut-off date | 2017-07-12 | Change Report Due (final legal text out for approval) | 2017-04-19
DCP 294 | Hollie | Capacity Management Following Acceptance of Connection Offer | 2017-12-13 |  | 2017-08-09
DCP 295 | Hollie | CVA Registrants acceding to the DCUSA | 2017-10-11 |  | 2017-07-19
DCP 297 | IWG | Network Interventions SLA Enhancement | 2017-09-13 | Work Plan Due | 2017-08-09
DCP 302 | IWG | Moving Made Safe Instances To Cat B | 2017-12-13 |  | 2017-08-09
DCP 304 | IWG | Metering Works by Non-Appointed Meter Operator |  | First Work Plan due
DCP 305 | Dan | LDNO Boundary Level Definitions in the EDCM |  | First Work Plan due (after first meeting)
DCP 306 | Hollie | Treatment of Ofgem Licence Fees within the PCDM |  | Work Plan Due
CP Work Plans

## Legal Text Overlap
February 2016
Awaiting Implementation
CP Number | DCP 293 | DCP 291 | DCP 287 | DCP 283 | DCP 274 | DCP 268 | DCP 266 | DCP 252 | DCP 251 | DCP 243 | DCP 273 | DCP 161 | DCP 228 | DCP 222 | DCP 234
Implementation Date | [10 empty] | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01
Status | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Developed | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation
DCUSA Schedule 15
Impacted Paragraphs | [5 empty] | Table 3 | [5 empty] | Table 3 (para 4.1)
DCUSA Schedule 16 | Prior to Introduction |  |  |  |  | para 3 |  |  |  |  | para 3
Impacted Paragraphs | [11 empty] | 3a
| para 3 |  |  |  |  | 12 | [5 empty] | 12
14
40,42,42A,43
45,52A,
68,72,72A,74
[6 empty] | 80,81,83,84 | [8 empty] | 3(b)
97
98 and 99
100 to 120 (including the tables and headings)
124 and 125
[12 empty] | 81 |  |  | Glossary
92 to 95
126,127,128,
129130
[6 empty] | 131,132, | 109,111 to 113A & 113D,118 to 124
132A,132B
135,135A
135B,136
[6 empty] | 140A-140E | [5 empty] | 131
[6 empty] | 141 table 4 &5 | [5 empty] | 136
141 (table 5)
[6 empty] | 142143 | [7 empty] | 146 (table 7)
[6 empty] | 144,145, | [5 empty] | 147 (table 8 & 9)
146 table 6& 7
[6 empty] | 147 table 8& 9 | [5 empty] | 153
157 - deleted
173
177 (originally 176)
DCUSA Schedule 17 | Prior to Introduction
Impacted Paragraphs | [11 empty] | 1.3 |  |  | 25
| para 1.3 (a) | [13 empty] | 25.1
|  | 6.3 | 9.2, 9.3, 16.7 | [11 empty] | 25.2
25.3 to 25.18 (including the tables and headings).
25.19
DCUSA Schedule 18 | Prior to Introduction
Impacted Paragraphs | [11 empty] | 1.3 |  |  | 25
| para 1.3 (a) | 6.5 | 9.2, 9.3, 16.7 | [11 empty] | 25.1
25.2
25.3 to 25.18 (including the tables and headings).
25.19
DCUSA Schedule 20 | Prior to Introduction
Impacted Paragraphs | [5 empty] | 1.1 | [5 empty] | 1.1
DCUSA Schedule xx | Prior to Introduction
Impacted Paragraphs
| Clause 1 | [6 empty] | Clause 1 | Clause 1
[8 empty] | Title | Title
Charging Methodology CPs Legal Text Overlap Tracker
Colour Code
Red Text = Legal text close to being completed but not yet finalised
Black Text = Finalised Legal text that will not change further (i.e. version to be included in Change Report)
Yellow Highlight = Paragraph changed by more than one CP