## CPs
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst/WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status
STATUS - DEFINITION
DCP 226 | Housekeeping 66/72/73/77/80 | This CP seeks to review and revise the DCUSA document to incorporate housekeeping log items 66/72/73/77/80 | General | 2 | Fungai Madzivadondo/ Rosalind Timperley | Roberta Fernie | 2015-01-05 | 0 |  | Next Release Following Authority Consent | The Working Group invitation closed with only one interested person. It was agreed that in addition to addressing the proposed housekeeping changes DCP 226 would also review the numbering and referencing throughout the DCUSA document. Draft legal text has been provided by the Proposer which has since been reviewed by the DCUSA legal advisor. It is expected that a Change Report will be drafted and presented to the Panel in June
DCP 243 | Treatment of Customer Contributions in the CDCM | ​This CP seeks to revise DCUSA Schedule 16 to utilise current source data to determine a common industry set of modelling inputs in order to improve clarity in the approach to be used in calculating ‘Customer contribution under the current connection charging policy’ for use in CDCM table 1060. | CDCM | 1 | Dylan Townsend/ Rosalind Timperley | Lynda Carroll | 2015-06-05 | 15 |  | 2018-04-01 | The Working Group issued a RFI in February 2017. The Working Group met on 21 March 2017 to review the responses to the RFI and decide which option to proceed with. The Working Group agreed to proceed to final consultation after deciding on which option to proceed with and are currently drafting the final consultation document.
DCP 244 | MOP Leaving Site for Cat A Situations | ​This CP seeks to remove the DNO Intervention SLA for attending Category A jobs where the MOP operative will not or has not remained on site and to address housekeeping issues with the DCP 195A legal text | General | 1 | To be progressed by the Interventions Working Group | Angela Picciarello | 2015-06-19 | 2 |  | Next Release Following Authority Consent | The Working Group is waiting for Operational Delivery Group (ODG) to develop MOP guidance on leaving site where there is a category A situation. The CP has been placed on hold whilst this progressed.The Interventions Working Group are considering offline the prospects of a ‘Cat A made safe code’ and DCP 244 will be added to the April agenda for discussion.
DCP 266 | The calculation and application of IDNO discounts | To change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this CP is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | CDCM | 1 | Dylan Townsend/ Rosalind Timperley | Donald Smith | 2016-03-09 | 6 |  | 2018-04-01 | The Working Group met on 24 January 2017 and were presented with a new model (Method GM) which combines Method M model and the Method G model which was presented to the WG in November. An Impact Assessment request has been sent to the Modelling Consultant in March. The Impact Assessment will be circulated to the Working Group and the next Working Group meeting will be held in June.
DCP 268 | DUoS Charging Using HH settlement data | The intent of this CP is to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | CDCM | 1 | Claire Hynes / John Lawton | Lynda Carroll | 2016-03-14 | 10 |  | 2019-04-01 | The DCP 268 Working Group met on the 05 April 2017 to review the legal text and modelling support request. The Working Group are in the process of drafting the change report with an aim of submitting it to the June DCUSA Panel.
DCP 274 | The application of export capacity charges in the EDCM | The intent of this CP is to amend the EDCM methodology to ensure that distributed generation and storage sites do not pay distribution use of system charges for the import and export from a site where the same assets are used. | EDCM | 1 | Dan Fittock/ Claire Hynes | Keith Burwell | 2016-06-10 | 4 |  | 2019-04-01 | The DCP 274 Working Group last met on 9 May to discuss the gathered evidence in support of the CPs intent. The Working Group agreed that there was still currently insufficient evidence to support the CPs intent and actions were taken by WG members to review the historic Ofgem communications for background information on why this was not implemented previously, in order to guide the WG to a decision on whether the CP should progress.
DCP 283 | The calculation of generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators | CDCM | 1 | Dylan Townsend / John Lawton | Edda Dirks | 2016-10-12 | 6 |  | 2019-04-01 | The Working Group issued a Consultation on 14 March 2017 which closed on 04 April 2017. The Working Group met on 7 April 2017 to review the consultation responses. The Working Group have met on 4 May 2017 and have agreed to proceed with a second consultation to parties and will include legal text and impacts.
DCP 287 | Generation credits in the EDCM | The intent of this Change Proposal is to amend the calculation of credits for embedded generation in the EDCM to take account of potential cost savings for DNOs that can be attributed to embedded generation in the areas of transmission exit charges, direct costs, indirect costs and network rates. | EDCM | 1 | Dylan Townsend/ Dan Fittock | Edda Dirks | 2016-12-07 | 2 |  | 2020-04-01 | The DCP 287 Working Group is due to meet on 12 May to review the gathered evidence to support the intent of the CP and to review the draft consultation document.
DCP 288 & DCP 288A | Introduction of the Electricity Theft Detection Incentive Scheme | The intent of this Change Proposal (CP) is to introduce an Electricity Theft Detection Incentive Scheme in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014 | TRAS | 1 | Fungai Madzivadondo/Rachel Collis | Jon Dixon | 2016-12-12 | 0 |  | TBD | The TIG review the DCP 288 consultation on 29 March. The group further discussed the principles of the CP at their meeting on 10 April noting that Ofgem had confirmed they are happy for the group to revise the originally proposed volume, costs and implementation timescales. An Alternative CP was also raised at the meeting. The TIG will discuss the preferred solution at the May TIG meeting taking into account responses from the TRAS Theft Target consultation. The legal text for both the original and alternate CP will be discussed at the May TIG meeting.
DCP 291 | Application of Generation Credits to EDCM Customers | The intent of this Change Proposal is to apply EDCM generation credits to all generators whether intermittent or non-intermittent, on the basis that a LRIC/FCP charge 1 exists. | EDCM | 1 | Dylan Townsend/ Dan Fittock | Edda Dirks | 2017-02-10 | 1 |  | 2019-04-01 | The DCP 291 Working Group met on 05 May to discuss the previous Ofgem decision on Decision on F Factor setting for Intermittent Generators and to review the draft consultation document. The Working Group will next meet on 5 June to discuss the RFI results from DNOs to find out what, if any, impacts could be on providing credits to intermittent generators.
DCP 293 | Charging methodology cut-off date | This change looks to establish a cut-off date for the finalisation of the charging methodologies at 17 months prior to the date that the methodology would become effective. Establishing this cut-off date will provide a 2-month time window for DCUSA to provide charging models and DNOs to test the new charging models and then to calculate, test and approve revised charges. | General | 1 | Angie Castillo/ Claire Hynes | Lynda Carroll | 2017-02-14 | 1 |  | First release following approval | The Working Group met on the 21 March 2017 to analyse the CP and the outcome of the DCP 164 Authority Decision. The Working Group are in the process of drafting a consultation for issue to Parties.
DCP 294 | Capacity Management Following Acceptance of Connection Offer | This CP seeks to put arrangements in place that set out the principles under which the unutilised maximum capacity specified in connection offers or in bilateral connection agreements with IDNOs can be managed in an economic and efficient manner whilst protecting the legitimate requirements of parties requiring Capacity which was agreed in connection offers. | CCCM | 1 | Dan Fitock/ Claire Hynes |  | 2017-03-01 | 0 |  | First release following approval | The first Working Group meeting took place on the 20 April 2017 and it was agreed that legal advice was required before a solution could be progressed on this CP. The Working Group are in the process of finalising the legal advice questions for submission to the DCUSA Panel for approval.
DCP 295 | CVA Registrants acceding to the DCUSA | This change is to facilitate BSC Modification PXXX which is to oblige CVA Registrants connecting to a Distribution System to accede to the DCUSA which will negate the need for a bilateral Use of System Agreements between the LDSO and the CVA Registrants saving administrative cost and effort and promoting efficiency and consistency. The effect of this change will be to modify the legal text to include CVA Registrants in addition to Distributed Generation Parties mainly in Section 2A but also in Sections 1A, 1B, 1C, 2B, 2C and 3 and Schedules 9, 11, 19 and 21. | General | 1 | Dylan Townsend/ Dan Fittock |  | 2017-03-07 | 0 |  | First release following approval | A Working Group invitation was issued to Parties and the first Working Group meeting is in the process of being set up.
DCP 297 | Network Interventions SLA Enhancement | This CP seeks to change the mechanism whereby DNO’s are released from their obligations to meet the intervention SLA to one which is solely based on the accuracy of Suppliers smart meter roll-out forecasts. The DCUSA Panel has directed that this change be considered by the Interventions Working Group. | General | 1 |  |  | 2017-04-07 | 0 |  | First release following approval | At the April DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group.
STATUS - CHANGE REPORT
DCP 251 | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | The intent of this proposal is to correct drafting errors in the specification of the distribution systems that are eligible for LDNO tariffs under the CDCM and under the EDCM and ensure that there the charging methodologies do not impose undue discrimination between licensed and licence-exempt distribution systems and restore the 50 per cent LDNO discount on indirect costs which was removed by the approved legal text for DCP 185 in cases where the fixed adder is negative.​ | CDCM | 1 | Dan Fittock/John Lawton | Keith Burwell | 2015-10-15 | 18 |  | Next release date after approval | The DCP 251 and DCP 252 Working Group last met on 13 April 2017 and finalised the Change Reports. These have now been submitted with the meeting papers for the May Panel meeting.
DCP 252 | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | The intent of this proposal is to correct drafting errors and inconsistencies in the specification of the distribution systems that are eligible for Portfolio tariffs under the EDCM (schedules 17 and 18) and establish arrangements that ensure that methodologies in Schedules 17 and 18 do not impose undue discrimination between licensed and licence exempt distribution systems.​ | EDCM | 1 | Dan Fittock/John Lawton | Keith Burwell | 2015-10-15 | 18 |  | Next release date after approval | The DCP 251 and DCP 252 Working Group last met on 13 April 2017 and finalised the Change Reports. These have now been submitted with the meeting papers for the May Panel meeting.
DCP 289 | Creation of Distribution Charging Methodology Development Group | The intent of this CP is to formalise the creation of a new single Standing Issues Working Group for the Use of System charging methodologies and related topics within DCUSA. | General/ Urgent | 1 | Da n Fittock/ Claire Hynes | Vivian Marangoni | 2016-12-16 | 2 |  | Within 5 Working Days of Approval or next DCUSA release following Authority consent | The Working Group met on the 07 April 2017 to consider the consultation responses. The Working Group have agreed to take three solutions forward to the change report stage. This change report has been submitted with the meeting papers for the May Panel meeting.
DCP 296 | Notification Process for Remedied DCUSA Payment Default(s) | This CP seeks to amend the DCUSA drafting to obligate the DCUSA Panel to notify DNOs and IDNOs to cease suspension of registration services where the Party has remedied a DCUSA Payment Default. | General | 2 | Dylan Townsend |  | 2017-04-07 | 0 |  | 2017-06-29 | At the April DCUSA Panel meeting, it was determined that this change should proceed to the change report phase. The DCP 296 Change Report has been submitted with the meeting papers for the May Panel meeting.
STATUS - VOTING
DCP 292 | Align DCUSA Schedule 15 table 3 to the CDCM tariff structure following the approval DCP 222 ‘Non billing of Excess Reactive Power Charges’ | The intent of this CP is to amend DCUSA Schedule 15 to reflect the CDCM tariffs introduced as a result of the approval of DCP 222 ‘Non billing of Excess Reactive Power Charges’. | CDCM | 2 | Dylan Townsend |  | 2017-02-10 | 0 |  | 2017-06-29 | At the February DCUSA Panel meeting, it was determined that this change should proceed to the change report phase. This change report was submitted to the March DCUSA Panel, however after further discussions with the Proposer the Change Report and legal text were amended and the amended Change Report was submitted to the April Panel and issued to Parties to vote upon on 21 April 2017.
STATUS - AWAITING AUTHORITY CONSENT
DCP 282 | Embedded Distribution Network Operator (EDNO) UMSO | This CP seeks to facilitate the management and trading of UMS apparatus connected to EDNO networks via the “host” DNO’s UMSO service on one combined inventory, without the need for additional MPANs, following a request from the customer to the EDNO to do so. | General | 1 | Claire Hynes/ John Lawton | Stephen Perry | 2016-09-14 | 4 |  | First release following approval | The DCP 282 change report was issued to Partes to vote on with a closing date of the 07 April 2017. The outcome of this vote will be issued to Parties on the 11 April 2017
STATUS - AWAITING IMPLEMENTATION
2018-04-01
DCP 161 | Excess Capacity Charges | To improve the cost reflectivity of the excess capacity charge calculation within the CDCM and EDCM by removing the customer contributions and adding in any additional costs that should be attributed to this charge. Also, to consider applying the excess capacity charge on either a monthly, seasonal or time of day basis. | CDCM | 1 | Michael Walls/Chris Ong | Keith Burwell | 2013-02-06 | 12 |  | 2018-04-01 | The Authority directed for DCP 161 to be made and implemented on 1 April 2018.
DCP 222 | Non Billing Of Excess Reactive Power Charges | This CP proposes the removal of the excess reactive power charge when a DNO requests that a generator operates outside of the 0.95 power factor limit. | CDCM | 1 | Fungai Madzivadondo/Dave Wornell | Nisha Doshi | 2014-12-02 | 11 |  | 2018-04-01 | The Authority directed for DCP 222 to be made and implemented on 1 April 2018.
DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | CDCM | 1 | Rosalind Timperley/ Chris Ong | Bethany Hanna | 2015-01-13 | 4 |  | 2018-04-01 | The Authority directed for DCP 228 to be made and implemented on 1 April 2018.
DCP 234 | Merging the PCDM and extended PCDM | The intent of the CP is to replace the Price Control Disaggregation (PCDM) and extended PCDM models with one model.To create a new schedule in DCUSA which contains the legal text that relates to IDNO charging that is currently contained in Schedules 16, 17 and 18. | CDCM and EDCM | 1 | Claire Hynes/ Claire Campbell | Lynda Carroll | 2015-02-27 | 7 |  | 2018-04-01 | The Authority directed for DCP 234 to be made and implemented on 1 April 2018.
DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | The intent of this proposal is to align table 1001 in the CDCM to the current format of table in Schedule 15. | CDCM | 2 | Fungai Madzivadondo/John Lawton | Lynda Carroll | 2016-05-18 | 2 |  | 2018-04-01 | Parties voted to approve the change on the 17 October 2016 for implementation on the 01 April 2018.
DCP 290 | Housekeeping Change to Update PCDM Model References | The intent of this Change Proposal is to facilitate the updating of the title, model number and issue date of the PDCM as referenced in Schedules 16, 17 and 18, which was not correctly applied in the legal text of DCP234. | CDCM/EDCM | 2 | Dan Fittock |  | 2017-01-17 | 0 |  | 2018-04-01 | Parties voted to approve the change on 10 March 2017 for implementation on 01 April 2018.
STATUS - APPEAL
n/a | n/a
STATUS - IMPLEMENTED - Date
STATUS - REJECTED
n/a
STATUS - WITHDRAWN
Change Register - May 2017

## Status Change
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst/WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status changed in the last meeting
STATUS - DEFINITION
DCP 226 | Housekeeping 66/72/73/77/80 | This CP seeks to review and revise the DCUSA document to incorporate housekeeping log items 66/72/73/77/80 | General | 2 | Fungai Madzivadondo/ Rosalind Timperley | Roberta Fernie | 2015-01-05 | 0 |  | Next Release Following Authority Consent | The Working Group invitation closed with only one interested person. It was agreed that in addition to addressing the proposed housekeeping changes DCP 226 would also review the numbering and referencing throughout the DCUSA document. Draft legal text has been provided by the Proposer which has since been reviewed by the DCUSA legal advisor. It is expected that a Change Report will be drafted and presented to the Panel in June | N/A
DCP 243 | Treatment of Customer Contributions in the CDCM | ​This CP seeks to revise DCUSA Schedule 16 to utilise current source data to determine a common industry set of modelling inputs in order to improve clarity in the approach to be used in calculating ‘Customer contribution under the current connection charging policy’ for use in CDCM table 1060. | CDCM | 1 | Dylan Townsend/ Rosalind Timperley | Lynda Carroll | 2015-06-05 | 15 |  | 2018-04-01 | The Working Group issued a RFI in February 2017. The Working Group met on 21 March 2017 to review the responses to the RFI and decide which option to proceed with. The Working Group agreed to proceed to final consultation after deciding on which option to proceed with and are currently drafting the final consultation document. | N/A
DCP 244 | MOP Leaving Site for Cat A Situations | ​This CP seeks to remove the DNO Intervention SLA for attending Category A jobs where the MOP operative will not or has not remained on site and to address housekeeping issues with the DCP 195A legal text | General | 1 | To be progressed by the Interventions Working Group | Angela Picciarello | 2015-06-19 | 2 |  | Next Release Following Authority Consent | The Working Group is waiting for Operational Delivery Group (ODG) to develop MOP guidance on leaving site where there is a category A situation. The CP has been placed on hold whilst this progressed.The Interventions Working Group are considering offline the prospects of a ‘Cat A made safe code’ and DCP 244 will be added to the April agenda for discussion. | N/A
DCP 266 | The calculation and application of IDNO discounts | To change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this CP is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | CDCM | 1 | Dylan Townsend/ Rosalind Timperley | Donald Smith | 2016-03-09 | 6 |  | 2018-04-01 | The Working Group met on 24 January 2017 and were presented with a new model (Method GM) which combines Method M model and the Method G model which was presented to the WG in November. An Impact Assessment request has been sent to the Modelling Consultant in March. The Impact Assessment will be circulated to the Working Group and the next Working Group meeting will be held in June. | N/A
DCP 268 | DUoS Charging Using HH settlement data | The intent of this CP is to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | CDCM | 1 | Claire Hynes / John Lawton | Lynda Carroll | 2016-03-14 | 10 |  | 2019-04-01 | The DCP 268 Working Group met on the 05 April 2017 to review the legal text and modelling support request. The Working Group are in the process of drafting the change report with an aim of submitting it to the June DCUSA Panel. | N/A
DCP 274 | The application of export capacity charges in the EDCM | The intent of this CP is to amend the EDCM methodology to ensure that distributed generation and storage sites do not pay distribution use of system charges for the import and export from a site where the same assets are used. | EDCM | 1 | Dan Fittock/ Claire Hynes | Keith Burwell | 2016-06-10 | 4 |  | 2019-04-01 | The DCP 274 Working Group last met on 9 May to discuss the gathered evidence in support of the CPs intent. The Working Group agreed that there was still currently insufficient evidence to support the CPs intent and actions were taken by WG members to review the historic Ofgem communications for background information on why this was not implemented previously, in order to guide the WG to a decision on whether the CP should progress. | N/A
DCP 283 | The calculation of generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators | CDCM | 1 | Dylan Townsend / John Lawton | Edda Dirks | 2016-10-12 | 6 |  | 2019-04-01 | The Working Group issued a Consultation on 14 March 2017 which closed on 04 April 2017. The Working Group met on 7 April 2017 to review the consultation responses. The Working Group have met on 4 May 2017 and have agreed to proceed with a second consultation to parties and will include legal text and impacts. | N/A
DCP 287 | Generation credits in the EDCM | The intent of this Change Proposal is to amend the calculation of credits for embedded generation in the EDCM to take account of potential cost savings for DNOs that can be attributed to embedded generation in the areas of transmission exit charges, direct costs, indirect costs and network rates. | EDCM | 1 | Dylan Townsend/ Dan Fittock | Edda Dirks | 2016-12-07 | 2 |  | 2020-04-01 | The DCP 287 Working Group is due to meet on 12 May to review the gathered evidence to support the intent of the CP and to review the draft consultation document. | N/A
DCP 288 & DCP 288A | Introduction of the Electricity Theft Detection Incentive Scheme | The intent of this Change Proposal (CP) is to introduce an Electricity Theft Detection Incentive Scheme in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014 | TRAS | 1 | Fungai Madzivadondo/Rachel Collis | Jon Dixon | 2016-12-12 | 0 |  | TBD | The TIG review the DCP 288 consultation on 29 March. The group further discussed the principles of the CP at their meeting on 10 April noting that Ofgem had confirmed they are happy for the group to revise the originally proposed volume, costs and implementation timescales. An Alternative CP was also raised at the meeting. The TIG will discuss the preferred solution at the May TIG meeting taking into account responses from the TRAS Theft Target consultation. The legal text for both the original and alternate CP will be discussed at the May TIG meeting. | N/A
DCP 291 | Application of Generation Credits to EDCM Customers | The intent of this Change Proposal is to apply EDCM generation credits to all generators whether intermittent or non-intermittent, on the basis that a LRIC/FCP charge 1 exists. | EDCM | 1 | Dylan Townsend/ Dan Fittock | Edda Dirks | 2017-02-10 | 1 |  | 2019-04-01 | The DCP 291 Working Group met on 05 May to discuss the previous Ofgem decision on Decision on F Factor setting for Intermittent Generators and to review the draft consultation document. The Working Group will next meet on 5 June to discuss the RFI results from DNOs to find out what, if any, impacts could be on providing credits to intermittent generators. | N/A
DCP 293 | Charging methodology cut-off date | This change looks to establish a cut-off date for the finalisation of the charging methodologies at 17 months prior to the date that the methodology would become effective. Establishing this cut-off date will provide a 2-month time window for DCUSA to provide charging models and DNOs to test the new charging models and then to calculate, test and approve revised charges. | General | 1 | Angie Castillo/ Claire Hynes | Lynda Carroll | 2017-02-14 | 1 |  | First release following approval | The Working Group met on the 21 March 2017 to analyse the CP and the outcome of the DCP 164 Authority Decision. The Working Group are in the process of drafting a consultation for issue to Parties. | N/A
DCP 294 | Capacity Management Following Acceptance of Connection Offer | This CP seeks to put arrangements in place that set out the principles under which the unutilised maximum capacity specified in connection offers or in bilateral connection agreements with IDNOs can be managed in an economic and efficient manner whilst protecting the legitimate requirements of parties requiring Capacity which was agreed in connection offers. | CCCM | 1 | Dan Fitock/ Claire Hynes |  | 2017-03-01 | 0 |  | First release following approval | The first Working Group meeting took place on the 20 April 2017 and it was agreed that legal advice was required before a solution could be progressed on this CP. The Working Group are in the process of finalising the legal advice questions for submission to the DCUSA Panel for approval. | N/A
DCP 295 | CVA Registrants acceding to the DCUSA | This change is to facilitate BSC Modification PXXX which is to oblige CVA Registrants connecting to a Distribution System to accede to the DCUSA which will negate the need for a bilateral Use of System Agreements between the LDSO and the CVA Registrants saving administrative cost and effort and promoting efficiency and consistency. The effect of this change will be to modify the legal text to include CVA Registrants in addition to Distributed Generation Parties mainly in Section 2A but also in Sections 1A, 1B, 1C, 2B, 2C and 3 and Schedules 9, 11, 19 and 21. | General | 1 | Dylan Townsend/ Dan Fittock |  | 2017-03-07 | 0 |  | First release following approval | A Working Group invitation was issued to Parties and the first Working Group meeting is in the process of being set up. | N/A
DCP 297 | Network Interventions SLA Enhancement | This CP seeks to change the mechanism whereby DNO’s are released from their obligations to meet the intervention SLA to one which is solely based on the accuracy of Suppliers smart meter roll-out forecasts. The DCUSA Panel has directed that this change be considered by the Interventions Working Group. | General | 1 |  |  | 2017-04-07 | 0 |  | First release following approval | At the April DCUSA Panel meeting the Panel directed that this change be progressed by the Interventions Working Group. | DEFINITION
STATUS - CHANGE REPORT
DCP 251 | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | The intent of this proposal is to correct drafting errors in the specification of the distribution systems that are eligible for LDNO tariffs under the CDCM and under the EDCM and ensure that there the charging methodologies do not impose undue discrimination between licensed and licence-exempt distribution systems and restore the 50 per cent LDNO discount on indirect costs which was removed by the approved legal text for DCP 185 in cases where the fixed adder is negative.​ | CDCM | 1 | Dan Fittock/John Lawton | Keith Burwell | 2015-10-15 | 18 |  | Next release date after approval | The DCP 251 and DCP 252 Working Group last met on 13 April 2017 and finalised the Change Reports. These have now been submitted with the meeting papers for the May Panel meeting. | CHANGE REPORT
DCP 252 | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | The intent of this proposal is to correct drafting errors and inconsistencies in the specification of the distribution systems that are eligible for Portfolio tariffs under the EDCM (schedules 17 and 18) and establish arrangements that ensure that methodologies in Schedules 17 and 18 do not impose undue discrimination between licensed and licence exempt distribution systems.​ | EDCM | 1 | Dan Fittock/John Lawton | Keith Burwell | 2015-10-15 | 18 |  | Next release date after approval | The DCP 251 and DCP 252 Working Group last met on 13 April 2017 and finalised the Change Reports. These have now been submitted with the meeting papers for the May Panel meeting. | CHANGE REPORT
DCP 289 | Creation of Distribution Charging Methodology Development Group | The intent of this CP is to formalise the creation of a new single Standing Issues Working Group for the Use of System charging methodologies and related topics within DCUSA. | General/ Urgent | 1 | Da n Fittock/ Claire Hynes | Vivian Marangoni | 2016-12-16 | 2 |  | Within 5 Working Days of Approval or next DCUSA release following Authority consent | The Working Group met on the 07 April 2017 to consider the consultation responses. The Working Group have agreed to take three solutions forward to the change report stage. This change report has been submitted with the meeting papers for the May Panel meeting. | CHANGE REPORT
DCP 296 | Notification Process for Remedied DCUSA Payment Default(s) | This CP seeks to amend the DCUSA drafting to obligate the DCUSA Panel to notify DNOs and IDNOs to cease suspension of registration services where the Party has remedied a DCUSA Payment Default. | General | 2 | Dylan Townsend |  | 2017-04-07 | 0 |  | 2017-06-29 | At the April DCUSA Panel meeting, it was determined that this change should proceed to the change report phase. The DCP 296 Change Report has been submitted with the meeting papers for the May Panel meeting. | CHANGE REPORT
STATUS - VOTING
DCP 292 | Align DCUSA Schedule 15 table 3 to the CDCM tariff structure following the approval DCP 222 ‘Non billing of Excess Reactive Power Charges’ | The intent of this CP is to amend DCUSA Schedule 15 to reflect the CDCM tariffs introduced as a result of the approval of DCP 222 ‘Non billing of Excess Reactive Power Charges’. | CDCM | 2 | Dylan Townsend |  | 2017-02-10 | 0 |  | 2017-06-29 | At the February DCUSA Panel meeting, it was determined that this change should proceed to the change report phase. This change report was submitted to the March DCUSA Panel, however after further discussions with the Proposer the Change Report and legal text were amended and the amended Change Report was submitted to the April Panel and issued to Parties to vote upon on 21 April 2017. | VOTING
STATUS - AWAITING AUTHORITY CONSENT
DCP 282 | Embedded Distribution Network Operator (EDNO) UMSO | This CP seeks to facilitate the management and trading of UMS apparatus connected to EDNO networks via the “host” DNO’s UMSO service on one combined inventory, without the need for additional MPANs, following a request from the customer to the EDNO to do so. | General | 1 | Claire Hynes/ John Lawton | Stephen Perry | 2016-09-14 | 4 |  | First release following approval | The DCP 282 change report was issued to Partes to vote on with a closing date of the 07 April 2017. The outcome of this vote will be issued to Parties on the 11 April 2017 | AWAITING CONSENT
STATUS - AWAITING IMPLEMENTATION
2018-04-01
DCP 161 | Excess Capacity Charges | To improve the cost reflectivity of the excess capacity charge calculation within the CDCM and EDCM by removing the customer contributions and adding in any additional costs that should be attributed to this charge. Also, to consider applying the excess capacity charge on either a monthly, seasonal or time of day basis. | CDCM | 1 | Michael Walls/Chris Ong | Keith Burwell | 2013-02-06 | 12 |  | 2018-04-01 | The Authority directed for DCP 161 to be made and implemented on 1 April 2018. | N/A
DCP 222 | Non Billing Of Excess Reactive Power Charges | This CP proposes the removal of the excess reactive power charge when a DNO requests that a generator operates outside of the 0.95 power factor limit. | CDCM | 1 | Fungai Madzivadondo/Dave Wornell | Nisha Doshi | 2014-12-02 | 11 |  | 2018-04-01 | The Authority directed for DCP 222 to be made and implemented on 1 April 2018. | N/A
DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | CDCM | 1 | Rosalind Timperley/ Chris Ong | Bethany Hanna | 2015-01-13 | 4 |  | 2018-04-01 | The Authority directed for DCP 228 to be made and implemented on 1 April 2018. | N/A
DCP 234 | Merging the PCDM and extended PCDM | The intent of the CP is to replace the Price Control Disaggregation (PCDM) and extended PCDM models with one model.To create a new schedule in DCUSA which contains the legal text that relates to IDNO charging that is currently contained in Schedules 16, 17 and 18. | CDCM and EDCM | 1 | Claire Hynes/ Claire Campbell | Lynda Carroll | 2015-02-27 | 7 |  | 2018-04-01 | The Authority directed for DCP 234 to be made and implemented on 1 April 2018. | N/A
DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | The intent of this proposal is to align table 1001 in the CDCM to the current format of table in Schedule 15. | CDCM | 2 | Fungai Madzivadondo/John Lawton | Lynda Carroll | 2016-05-18 | 2 |  | 2018-04-01 | Parties voted to approve the change on the 17 October 2016 for implementation on the 01 April 2018. | N/A
DCP 290 | Housekeeping Change to Update PCDM Model References | The intent of this Change Proposal is to facilitate the updating of the title, model number and issue date of the PDCM as referenced in Schedules 16, 17 and 18, which was not correctly applied in the legal text of DCP234. | CDCM/EDCM | 2 | Dan Fittock |  | 2017-01-17 | 0 |  | 2018-04-01 | Parties voted to approve the change on 10 March 2017 for implementation on 01 April 2018. | N/A
STATUS - APPEAL
N/A
STATUS - IMPLEMENTED - Date
N/A
STATUS - REJECTED
N/A
STATUS - WITHDRAWN
N/A
Change Register - May 2017

## CP Work Plans
The DCUSA Panel is invited to:
Change Proposal | Secretariat | CP Title | Change Report Due Date | Status | Date of Last Agreed Work Plans | Note the Change Proposal Status
DCP 226 | Fungai | Housekeeping 66/72/73/77/80 | On hold |  |  | Approve the Extensions to the Change Proposal Assessment Process
DCP 243 | Dylan | Treatment of Customer Contributions in the CDCM | 2017-06-14 |  | 2017-02-15 | Approve the DCP 268, 289 and 294 Work Plans
DCP 244 | Roz | MOP Leaving Site for Cat A Situations | CP on hold. First Work Plan to be submitted
DCP 251 | Dan | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | 2017-05-10 | Change Report Due | 2017-04-19
DCP 252 | Dan | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | 2017-05-10 | Change Report Due | 2017-04-19
DCP 266 | Dylan | The calculation and application of IDNO discounts | 2017-06-14 |  | 2017-02-15
DCP 268 | Claire | DUoS Charging Using HH settlement data | 2017-05-10 | Work Plan Due | 2017-03-15
DCP 274 | Dan | The application of export capacity charges in the EDCM | 2017-08-18 |  | 2017-02-15
DCP 283 | Dylan | The calculation of generation credits in the CDCM | 2017-08-18 |  | 2016-12-21
DCP 287 | Dan | Generation credits in the EDCM | 2018-01-10 |  | 2017-04-25
DCP 288 | Fungai | Introduction of the Electricity Theft Detection Incentive Scheme | 2017-06-14 |  | 2017-04-19
DCP 289 | Claire | Creation of Distribution Charging Methodology Development Group | 2017-05-10 | Change Report Due | 2017-03-15
DCP 291 | Dylan | Application of Generation Credits to EDCM Customers | 2017-09-13 |  | 2017-04-19
DCP 293 | Claire | Charging methodology cut-off date | 2017-07-12 |  | 2017-04-19
DCP 294 | Claire | Capacity Management Following Acceptance of Connection Offer |  | First Work Plan due
DCP 295 | Dylan | CVA Registrants acceding to the DCUSA |  | First Work Plan due (after first meeting)
DCP 297 |  | Network Interventions SLA Enhancement |  | First Work Plan due (after first meeting)
CP Work Plans

## Legal Text Overlap
February 2016
Awaiting Implementation
CP Number | DCP 293 | DCP 291 | DCP 287 | DCP 283 | DCP 274 | DCP 268 | DCP 266 | DCP 252 | DCP 251 | DCP 243 | DCP 273 | DCP 161 | DCP 228 | DCP 222 | DCP 234
Implementation Date | [10 empty] | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01
Status | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Under Development | Developed | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation
DCUSA Schedule 15
Impacted Paragraphs | [5 empty] | Table 3 | [5 empty] | Table 3 (para 4.1)
DCUSA Schedule 16 | Prior to Introduction |  |  |  |  | para 3 |  |  |  |  | para 3
Impacted Paragraphs | [11 empty] | 3a
| para 3 |  |  |  |  | 12 | [5 empty] | 12
14
40,42,42A,43
45,52A,
68,72,72A,74
[6 empty] | 80,81,83,84 | [8 empty] | 3(b)
97
98 and 99
100 to 120 (including the tables and headings)
124 and 125
[12 empty] | 81 |  |  | Glossary
92 to 95
126,127,128,
129130
[6 empty] | 131,132, | 109,111 to 113A & 113D,118 to 124
132A,132B
135,135A
135B,136
[6 empty] | 140A-140E | [5 empty] | 131
[6 empty] | 141 table 4 &5 | [5 empty] | 136
141 (table 5)
[6 empty] | 142143 | [7 empty] | 146 (table 7)
[6 empty] | 144,145, | [5 empty] | 147 (table 8 & 9)
146 table 6& 7
[6 empty] | 147 table 8& 9 | [5 empty] | 153
157 - deleted
173
177 (originally 176)
DCUSA Schedule 17 | Prior to Introduction
Impacted Paragraphs | [11 empty] | 1.3 |  |  | 25
| para 1.3 (a) | [13 empty] | 25.1
|  | 6.3 | 9.2, 9.3, 16.7 | [11 empty] | 25.2
25.3 to 25.18 (including the tables and headings).
25.19
DCUSA Schedule 18 | Prior to Introduction
Impacted Paragraphs | [11 empty] | 1.3 |  |  | 25
| para 1.3 (a) | 6.5 | 9.2, 9.3, 16.7 | [11 empty] | 25.1
25.2
25.3 to 25.18 (including the tables and headings).
25.19
DCUSA Schedule 20 | Prior to Introduction
Impacted Paragraphs | [5 empty] | 1.1 | [5 empty] | 1.1
DCUSA Schedule xx | Prior to Introduction
Impacted Paragraphs
| Clause 1 | [6 empty] | Clause 1 | Clause 1
[8 empty] | Title | Title
Charging Methodology CPs Legal Text Overlap Tracker
Colour Code
Red Text = Legal text close to being completed but not yet finalised
Black Text = Finalised Legal text that will not change further (i.e. version to be included in Change Report)
Yellow Highlight = Paragraph changed by more than one CP