## CPs
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst/WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status July 2016
STATUS - DEFINITION
DCP 169 | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | This Change Proposal (CP) seeks remove the restriction in paragraph 135 of Schedule 16 of DCUSA in order to allow the use of Seasonal Time of Day (SToD) tariffs to be calculated and applied. | CDCM | 1 | Claire Hynes/Rosalind Timperley | Keith Burwell | 2013-03-13 | 8 |  | On Hold | The Working Group is waiting for the Ofgem decision on DCP 228 before deciding on how to proceed with DCP 169.
DCP 226 | Housekeeping 66/72/73/77/80 | This CP seeks to review and revise the DCUSA document to incorporate housekeeping log items 66/72/73/77/80 | General | 2 | Fungai Madzivadondo/ Rosalind Timperley | Roberta Fernie | 2015-01-05 | 0 |  | Next Release Following Authority Consent | The Working Group invitation closed with only one interested person. It was agreed that that in addition to addressing the proposed housekeeping changes DCP 226 would also review the numbering and referencing throughout the DCUSA document.
DCP 243 | Treatment of Customer Contributions in the CDCM | ​This CP seeks to revise DCUSA Schedule 16 to utilise current source data to determine a common industry set of modelling inputs in order to improve clarity in the approach to be used in calculating ‘Customer contribution under the current connection charging policy’ for use in CDCM table 1060. | CDCM | 1 | Fungai Madzivadondo/Rosalind Timperley | Lynda Carroll | 2015-06-05 | 11 |  | 2018-04-01 | The third DCP 243 Consultation will be issued on 09 November 2016 with deadline of 30 November 2016.
DCP 244 | MOP Leaving Site for Cat A Situations | ​This CP seeks to remove the DNO Intervention SLA for attending Category A jobs where the MOP operative will not or has not remained on site and to address housekeeping issues with the DCP 195A legal text | General | 1 | To be progressed by the Interventions Working Group | Angela Picciarello | 2015-06-19 | 2 |  | Next Release Following Authority Consent | The Working Group is waiting for Operational Delivery Group (ODG) to develop MOP guidance on leaving site where there is a category A situation. The CP has been placed on hold whilst this progressed.
DCP 251 | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | The intent of this proposal is to correct drafting errors in the specification of the distribution systems that are eligible for LDNO tariffs under the CDCM and under the EDCM and ensure that there the charging methodologies do not impose undue discrimination between licensed and licence-exempt distribution systems and restore the 50 per cent LDNO discount on indirect costs which was removed by the approved legal text for DCP 185 in cases where the fixed adder is negative.​ | CDCM | 1 | Dan Fittock/John Lawton | Keith Burwell | 2015-10-15 | 10 |  | Next release date after approval | The DCP 251 and DCP 252 consultation was issued for Working Group review by the 11 November 2016.
DCP 252 | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | The intent of this proposal is to correct drafting errors and inconsistencies in the specification of the distribution systems that are eligible for Portfolio tariffs under the EDCM (schedules 17 and 18) and establish arrangements that ensure that methodologies in Schedules 17 and 18 do not impose undue discrimination between licensed and licence exempt distribution systems.​ | EDCM | 1 | Dan Fittock/John Lawton | Keith Burwell | 2015-10-15 | 10 |  | Next release date after approval | The DCP 251 and DCP 252 consultation was issued for Working Group review by the 11 November 2016.
DCP 255 | Changes to Electricity (Connection Charges) Regulations 2002 | ​This CP seeks to incorporate changes in the CCCM as a result of changes to the Electricity (Connection Charges) Regulations 2002​. | CCCM | 2 | Dan Fittock/Claire Hynes/ | Lesley Ferrando | 2015-11-06 | 3 | On-hold until the Department of Business, Innovation and Skills finalise the ECCR 2016 legal text. | First practicable release after approval | The Working Group are awaiting the receipt of the final ECCR 2016 legal text from BEIS (formally DECC) before progressing this change.
DCP 266 | The calculation and application of IDNO discounts | To change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this CP is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | CDCM | 1 | Fungai Madzivadondo/ Roz Timperley | Donald Smith | 2016-03-09 | 4 |  | 2018-04-01 | The Working Group has received the updated modelling documents and requested that the modelling consultant attend their next meeting discusss the modelling documents provided. The next DCP 266 meeting is scheduled for 30 November 2016.
DCP 268 | DUoS Charging Using HH settlement data | The intent of this CP is to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | CDCM | 1 | Claire Hynes / John Lawton | Lynda Carroll | 2016-03-14 | 6 |  | 2019-04-01 | The DCP 268 Working Group are in the process of drafting consultation two on the draft legal text and the proposed model for submission to Parties for a period of three weeks.
DCP 274 | The application of export capacity charges in the EDCM | The intent of this CP is to amend the EDCM methodology to ensure that distributed generation and storage sites do not pay distribution use of system charges for the import and export from a site where the same assets are used. | EDCM | 1 | Dan Fittock/ Claire Hynes | Keith Burwell | 2016-06-10 | 2 |  | 2018-04-01 | The DCP 274 Working Group are carrying out an informal RFI with DNO parties to determine the number of sites affected by this issue. The Working Group will meet on the 21 October 2016 to consider the responses.
DCP 281 | Changes to Schedule 19 – Portfolio Billing | This CP seeks to ensure that HH Portfolio data is reported to DNOs in a consistent manner by all embedded LDSOs and to define how revised data must be reported. | EDCM | 2 | Dan Fittock/ Claire Hynes | Lynda Carroll | 2016-09-14 | 0 |  | Next release date after approval | The Working Group have issued a consultation to Parties for a period of three weeks with a closing date of the 18 November 2016. The Working Group will meet in early December to consider the consultation responses.
DCP 282 | Embedded Distribution Network Operator (EDNO) UMSO | This CP seeks to facilitate the management and trading of UMS apparatus connected to EDNO networks via the “host” DNO’s UMSO service on one combined inventory, without the need for additional MPANs, following a request from the customer to the EDNO to do so. | General | 1 | Claire Hynes/ John Lawton | Stephen Perry | 2016-09-14 | 0 |  | First release following approval | The Working Group are in the process of drafting a consultation for issue to Parties..
DCP 283 | The calculation of generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators | CDCM | 1 | Claire Hynes/ John Lawton |  | 2016-10-12 | 0 |  | 2019-04-01 | A Working Group invitation has been issued to Parties. The first Working Group meeting is expected to be scheduled in mid- November.
DCP 284 | The application of scaling to generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators by including an element of scaling. | CDCM |  | Claire Hynes/ John Lawton |  | 2016-10-12 | 0 |  | 2019-04-01 | A Working Group invitation has been issued to Parties. The first Working Group meeting is expected to be scheduled in mid- November.
DCP 285 | Schedule 23, Appendix 1 SLC References | The intent of this change is to remove references to Supply Licence Condition (SLC) 12.16 in Schedule 23, Appendix 1 and replace them with the updated SLC references. | General |  | Fungai Madzivadondo/Sarah Jones |  | 2016-10-12 | 0 |  | First release following approval | The DCP 285 Change Report and legal text is being finalised and will be submitted to the December Panel meeting
STATUS - CHANGE REPORT
DCP 263 | NTC DEH Gap | This CP seeks to amend the NTC so that they cater for DNOs’ connections to non-metered DEH networks.There should be no impact from this change on the applicability of the NTC to boundary metered DEHs or on the contractual terms suppliers put in place by virtue of Schedule 2A of DCUSA. | General | 1 | Dan Fittock/Claire Hynes | Lesley Ferrando | 2016-01-22 | 3 |  | First practicable release after approval | The DCP 263 Change Report has been submitted to the November DCUSA Panel.
DCP 278 | Allocation of Users to the ETTOS Secure Email Service | This CP seeks to include the rules for allocation of user accounts for the ETTOS secure email service in the DCUSA | ETTOS | 2 | Fungai Madzivadondo/Sarah Jones | Jon Dixon | 2016-07-13 | 2 |  | Next release date after approval | The DCP 278 Change Report has been submitted to the November DCUSA Panel.
DCP 279 | Linking Credit Cover to the Annual Iteration Process | This change proposal has been submitted in order to update those clauses in DCUSA Schedule 1 (Credit Cover) that refer to the ‘Regulatory Asset Value (RAV)’ as the new price control, RIIO-ED1, redefines the calculation of a DNO’s Regulatory Asset Value. | General | 2 | Claire Hynes |  | 2016-07-29 | 1 |  | November 2016 Release | The DCP 279 Change Report has been submitted to the November DCUSA Panel.
DCP 280 | Clarification of TRAS Accession Process | This CP proposes to amend the TRAS Schedules to clarify the TRAS accession process. It has been assessed that there is a three-month time lag between a new Supplier starting to register metering systems and actually submitting data into TRAS. This time lag has not been reflected within the current TRAS Schedule and a change is required to explicitly reference the time lag so new parties are clear when they need to provide their initial data submission. The three-month time lag will also ensure that the new Supplier has time to work with the Service Provider to start submitting data. | TRAS | 2 | Fungai Madzivadondo/Sarah Jones | Jon Dixon | 2016-08-18 | 2 |  | Next release date after approval | The DCP 280 Change Report has been submitted to the November DCUSA Panel.
STATUS - VOTING
DCP 275 | Code Governance Review 3 & SLC 22 | The CP seeks to implement the distribution licence changes arising from Ofgem’s Code Governance Review Phase 3 Final Proposals impacting DCUSA governance. | General | 1 | Fungai Madzivadondo/ Peter Waymont |  | 2016-06-10 | 0 |  | 2017-02-23 | The DCP 275 Change Report has issued to Parties to vote upon by the 11 November 2016.
DCP 277 | Schedule 25 – Amendment to Appendix 2 - Conditionality | Following on from the changes in DCP 272, the TRAS Expert Group has reviewed the conditionality for data items within the TRAS Service Providers Programming Manual and seeks to update some of the data items conditional/mandatory status because the current conditionality cannot be always met. Additionally, some JCode/RGMA Codes also require back population as they were missed on the original drafting. | TRAS | 2 | Keavy Larkin/Sarah Jones | Jon Dixon | 2016-07-11 | 1 |  | Next release date after approval | The DCP 277 Change Report has been issued to Parties to vote upon by the 15 November 2016.
STATUS - AWAITING AUTHORITY CONSENT
DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | CDCM | 1 | Rosalind Timperley/ Chris Ong | Bethany Hanna | 2015-01-13 | 4 |  | TBC | The DCP 228 Implementation Date vote was issued to Ofgem with a recommendation to reject the proposed implementation date of 1 April 2018.
DCP 270 | Removal of HV Medium tariff from CDCM | This CP seeks for the removal of the HV Medium Non-domestic tariff and consideration of the removal of both the LV and LV Sub Medium Non Domestic tariffs from the CDCM. | CDCM | 1 | Dan Fittock/Claire Hynes | Lynda Carroll | 2016-04-28 | 1 |  | 2018-04-01 | The DCP 270 Change Report has been issued to Parties to vote upon by the 17 October 2016.
STATUS - AWAITING IMPLEMENTATION
2017-04-01
DCP 138 | Implementation of alternative network use factor (NUF) calculation method in EDCM | This CP seeks to amend the method of calculating Network Use Factors for EDCM demand customers as defined within DCUSA to address the concerns raised by Ofgem in Condition 3 of the Ofgem decision document on EDCM import charges published in September 2011. | EDCM | 1 | Fungai Madzivadondo/Simon Yeo | Keith Burwell | 2012-06-18 | 9 |  | 2017-04-01 | The Authority directs that modification DCP 138 be made. The CP will be implemented on 1 April 2017.
DCP 227 | Removing the inconsistency in the application of Peaking Probabilities in the CDCM | ​The proposal changes the way that peaking probabilities are applied in the CDCM and therefore affects CDCM tariffs. | CDCM | 1 | Rosalind Timperley /George Moran |  | 2015-01-13 | 4 |  | 2017-04-01 | The Authority directed for DCP 227 to be made and implemented on 1 April 2017.
2018-04-01
DCP 161 | Excess Capacity Charges | To improve the cost reflectivity of the excess capacity charge calculation within the CDCM and EDCM by removing the customer contributions and adding in any additional costs that should be attributed to this charge. Also, to consider applying the excess capacity charge on either a monthly, seasonal or time of day basis. | CDCM | 1 | Michael Walls/Chris Ong | Keith Burwell | 2013-02-06 | 12 |  | 2018-04-01 | The Authority directed for DCP 161 to be made and implemented on 1 April 2018.
DCP 222 | Non Billing Of Excess Reactive Power Charges | This CP proposes the removal of the excess reactive power charge when a DNO requests that a generator operates outside of the 0.95 power factor limit. | CDCM | 1 | Fungai Madzivadondo/Dave Wornell | Nisha Doshi | 2014-12-02 | 11 |  | 2018-04-01 | The Authority directed for DCP 222 to be made and implemented on 1 April 2018.
DCP 234 | Merging the PCDM and extended PCDM | The intent of the CP is to replace the Price Control Disaggregation (PCDM) and extended PCDM models with one model.To create a new schedule in DCUSA which contains the legal text that relates to IDNO charging that is currently contained in Schedules 16, 17 and 18. | CDCM and EDCM | 1 | Claire Hynes/ Claire Campbell | Lynda Carroll | 2015-02-27 | 7 |  | 2018-04-01 | The Authority directed for DCP 234 to be made and implemented on 1 April 2018.
DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | The intent of this proposal is to align table 1001 in the CDCM to the current format of table in Schedule 15. | CDCM | 2 | Fungai Madzivadondo/John Lawton | Lynda Carroll | 2016-05-18 | 2 |  | 2018-04-01 | Parties voted to approve the change on the 17 October 2016 for implementation on the 01 April 2018.
STATUS - TO BE CONFIRMED
DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | CDCM | 1 | Rosalind Timperley/ Chris Ong | Bethany Hanna | 2015-01-13 | 4 |  | TBC | The Authority directed for DCP 228 to be made and an alternative implementation date be considered and submitted in accordance with clause 14.2 of Part 1C of DCUSA. As suggested by Ofgem in their decision letter the DCUSA Panel will consider the implementation of DCP 228 and submit an alternative implementation date to the previously proposed 1 April 2016 date.
STATUS - APPEAL
n/a | n/a
STATUS - IMPLEMENTED
DCP 267 | Introduction of a new definition for 'Confirmed Theft' | To introduce a definition for Confirmed Theft under DCUSA to ensure consistency across Suppliers in submitting confirmed theft detections under TRAS. | TRAS | 2 | Dan Fittock/Claire Hynes | Jon Dixon | 2016-03-09 | 1 |  | Next release date after approval | DCUSA Parties voted to approve DCP 267. The CP was implemented on 03 November 2016.
DCP 271 | Process and Costs of Providing Additional Hunter Facilities | This change seeks to introduce a process for Suppliers who wish to procure additional Hunter facilities from the TRAS Service Provider and to make those costs transparent to the Supplier community | TRAS | 2 | Keavy Larkin/Sarah Jones | Jon Dixon | 2016-05-11 | 3 |  | 2016-11-03 | DCUSA Parties voted to approve DCP 271. The CP was implemented on 03 November 2016.
DCP 272 | TRAS – Amendment of Schedule 25 Appendix 2 | This CP seeks to introduce a clear data item list in DCUSA for delivery of the TRAS solution. | TRAS | 2 | Keavy Larkin/Sarah Jones | Jon Dixon | 2016-05-11 | 3 |  | 2016-11-03 | DCUSA Parties voted to approve DCP 272. The CP was implemented on 03 November 2016.
STATUS - REJECTED
DCP 160 | Non-Half Hourly (NHH) Notional Capacity | This CP seeks to revise Schedule 16 (along with appropriate CDCM and ARP Modelling changes) to introduce a notional spare capacity requirement to be applied to the average maximum demand when calculating NHH tariffs. The notional spare capacity should align with the same proportions which are calculated and allocated to Half Hourly (HH) tariffs. | CDCM | 1 | Claire Hynes / George Moran | Keith Burwell | 2013-01-08 | 12 |  | 2018-04-01 | The Authority directed that DCP 160 not be made on the 18 October 2016.
STATUS - WITHDRAWN
n/a | n/a
Change Register - November

## Status Change
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst/WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status July 2016 | Status Changed in the last Month
STATUS - DEFINITION
DCP 169 | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | This Change Proposal (CP) seeks remove the restriction in paragraph 135 of Schedule 16 of DCUSA in order to allow the use of Seasonal Time of Day (SToD) tariffs to be calculated and applied. | CDCM | 1 | Claire Hynes/Rosalind Timperley | Keith Burwell | 2013-03-13 | 8 |  | On Hold | The Working Group is waiting for the Ofgem decision on DCP 228 before deciding on how to proceed with DCP 169. | n/a
DCP 226 | Housekeeping 66/72/73/77/80 | This CP seeks to review and revise the DCUSA document to incorporate housekeeping log items 66/72/73/77/80 | General | 2 | Fungai Madzivadondo/ Rosalind Timperley | Roberta Fernie | 2015-01-05 | 0 |  | Next Release Following Authority Consent | The Working Group invitation closed with only one interested person. It was agreed that that in addition to addressing the proposed housekeeping changes DCP 226 would also review the numbering and referencing throughout the DCUSA document. | n/a
DCP 243 | Treatment of Customer Contributions in the CDCM | ​This CP seeks to revise DCUSA Schedule 16 to utilise current source data to determine a common industry set of modelling inputs in order to improve clarity in the approach to be used in calculating ‘Customer contribution under the current connection charging policy’ for use in CDCM table 1060. | CDCM | 1 | Fungai Madzivadondo/Rosalind Timperley | Lynda Carroll | 2015-06-05 | 11 |  | 2018-04-01 | The third DCP 243 Consultation will be issued on 09 November 2016 with deadline of 30 November 2016. | Consultation
DCP 244 | MOP Leaving Site for Cat A Situations | ​This CP seeks to remove the DNO Intervention SLA for attending Category A jobs where the MOP operative will not or has not remained on site and to address housekeeping issues with the DCP 195A legal text | General | 1 | To be progressed by the Interventions Working Group | Angela Picciarello | 2015-06-19 | 2 |  | Next Release Following Authority Consent | The Working Group is waiting for Operational Delivery Group (ODG) to develop MOP guidance on leaving site where there is a category A situation. The CP has been placed on hold whilst this progressed. | n/a
DCP 251 | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | The intent of this proposal is to correct drafting errors in the specification of the distribution systems that are eligible for LDNO tariffs under the CDCM and under the EDCM and ensure that there the charging methodologies do not impose undue discrimination between licensed and licence-exempt distribution systems and restore the 50 per cent LDNO discount on indirect costs which was removed by the approved legal text for DCP 185 in cases where the fixed adder is negative.​ | CDCM | 1 | Dan Fittock/John Lawton | Keith Burwell | 2015-10-15 | 10 |  | Next release date after approval | The DCP 251 and DCP 252 consultation was issued for Working Group review by the 11 November 2016. | n/a
DCP 252 | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | The intent of this proposal is to correct drafting errors and inconsistencies in the specification of the distribution systems that are eligible for Portfolio tariffs under the EDCM (schedules 17 and 18) and establish arrangements that ensure that methodologies in Schedules 17 and 18 do not impose undue discrimination between licensed and licence exempt distribution systems.​ | EDCM | 1 | Dan Fittock/John Lawton | Keith Burwell | 2015-10-15 | 10 |  | Next release date after approval | The DCP 251 and DCP 252 consultation was issued for Working Group review by the 11 November 2016. | n/a
DCP 255 | Changes to Electricity (Connection Charges) Regulations 2002 | ​This CP seeks to incorporate changes in the CCCM as a result of changes to the Electricity (Connection Charges) Regulations 2002​. | CCCM | 2 | Dan Fittock/Claire Hynes/ | Lesley Ferrando | 2015-11-06 | 3 | On-hold until the Department of Business, Innovation and Skills finalise the ECCR 2016 legal text. | First practicable release after approval | The Working Group are awaiting the receipt of the final ECCR 2016 legal text from BEIS (formally DECC) before progressing this change. | n/a
DCP 266 | The calculation and application of IDNO discounts | To change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this CP is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | CDCM | 1 | Fungai Madzivadondo/ Roz Timperley | Donald Smith | 2016-03-09 | 4 |  | 2018-04-01 | The Working Group has received the updated modelling documents and requested that the modelling consultant attend their next meeting discusss the modelling documents provided. The next DCP 266 meeting is scheduled for 30 November 2016. | n/a
DCP 268 | DUoS Charging Using HH settlement data | The intent of this CP is to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | CDCM | 1 | Claire Hynes / John Lawton | Lynda Carroll | 2016-03-14 | 6 |  | 2019-04-01 | The DCP 268 Working Group are in the process of drafting consultation two on the draft legal text and the proposed model for submission to Parties for a period of three weeks. | n/a
DCP 274 | The application of export capacity charges in the EDCM | The intent of this CP is to amend the EDCM methodology to ensure that distributed generation and storage sites do not pay distribution use of system charges for the import and export from a site where the same assets are used. | EDCM | 1 | Dan Fittock/ Claire Hynes | Keith Burwell | 2016-06-10 | 2 |  | 2018-04-01 | The DCP 274 Working Group are carrying out an informal RFI with DNO parties to determine the number of sites affected by this issue. The Working Group will meet on the 21 October 2016 to consider the responses. | n/a
DCP 281 | Changes to Schedule 19 – Portfolio Billing | This CP seeks to ensure that HH Portfolio data is reported to DNOs in a consistent manner by all embedded LDSOs and to define how revised data must be reported. | EDCM | 2 | Dan Fittock/ Claire Hynes | Lynda Carroll | 2016-09-14 | 0 |  | Next release date after approval | The Working Group have issued a consultation to Parties for a period of three weeks with a closing date of the 18 November 2016. The Working Group will meet in early December to consider the consultation responses. | Consultation
DCP 282 | Embedded Distribution Network Operator (EDNO) UMSO | This CP seeks to facilitate the management and trading of UMS apparatus connected to EDNO networks via the “host” DNO’s UMSO service on one combined inventory, without the need for additional MPANs, following a request from the customer to the EDNO to do so. | General | 1 | Claire Hynes/ John Lawton | Stephen Perry | 2016-09-14 | 0 |  | First release following approval | The Working Group are in the process of drafting a consultation for issue to Parties.. | n/a
DCP 283 | The calculation of generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators | CDCM | 1 | Claire Hynes/ John Lawton |  | 2016-10-12 | 0 |  | 2019-04-01 | A Working Group invitation has been issued to Parties. The first Working Group meeting is expected to be scheduled in mid- November. | Definition
DCP 284 | The application of scaling to generation credits in the CDCM | This CP seeks to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators by including an element of scaling. | CDCM |  | Claire Hynes/ John Lawton |  | 2016-10-12 | 0 |  | 2019-04-01 | A Working Group invitation has been issued to Parties. The first Working Group meeting is expected to be scheduled in mid- November. | Definition
DCP 285 | Schedule 23, Appendix 1 SLC References | The intent of this change is to remove references to Supply Licence Condition (SLC) 12.16 in Schedule 23, Appendix 1 and replace them with the updated SLC references. | General |  | Fungai Madzivadondo/Sarah Jones |  | 2016-10-12 | 0 |  | First release following approval | The DCP 285 Change Report and legal text is being finalised and will be submitted to the December Panel meeting | Definition
STATUS - CHANGE REPORT
DCP 263 | NTC DEH Gap | This CP seeks to amend the NTC so that they cater for DNOs’ connections to non-metered DEH networks.There should be no impact from this change on the applicability of the NTC to boundary metered DEHs or on the contractual terms suppliers put in place by virtue of Schedule 2A of DCUSA. | General | 1 | Dan Fittock/Claire Hynes | Lesley Ferrando | 2016-01-22 | 3 |  | First practicable release after approval | The DCP 263 Change Report has been submitted to the November DCUSA Panel. | Change Report
DCP 278 | Allocation of Users to the ETTOS Secure Email Service | This CP seeks to include the rules for allocation of user accounts for the ETTOS secure email service in the DCUSA | ETTOS | 2 | Fungai Madzivadondo/Sarah Jones | Jon Dixon | 2016-07-13 | 2 |  | Next release date after approval | The DCP 278 Change Report has been submitted to the November DCUSA Panel. | Change Report
DCP 279 | Linking Credit Cover to the Annual Iteration Process | This change proposal has been submitted in order to update those clauses in DCUSA Schedule 1 (Credit Cover) that refer to the ‘Regulatory Asset Value (RAV)’ as the new price control, RIIO-ED1, redefines the calculation of a DNO’s Regulatory Asset Value. | General | 2 | Claire Hynes |  | 2016-07-29 | 1 |  | November 2016 Release | The DCP 279 Change Report has been submitted to the November DCUSA Panel. | Change Report
DCP 280 | Clarification of TRAS Accession Process | This CP proposes to amend the TRAS Schedules to clarify the TRAS accession process. It has been assessed that there is a three-month time lag between a new Supplier starting to register metering systems and actually submitting data into TRAS. This time lag has not been reflected within the current TRAS Schedule and a change is required to explicitly reference the time lag so new parties are clear when they need to provide their initial data submission. The three-month time lag will also ensure that the new Supplier has time to work with the Service Provider to start submitting data. | TRAS | 2 | Fungai Madzivadondo/Sarah Jones | Jon Dixon | 2016-08-18 | 2 |  | Next release date after approval | The DCP 280 Change Report has been submitted to the November DCUSA Panel. | Change Report
STATUS - VOTING
DCP 275 | Code Governance Review 3 & SLC 22 | The CP seeks to implement the distribution licence changes arising from Ofgem’s Code Governance Review Phase 3 Final Proposals impacting DCUSA governance. | General | 1 | Fungai Madzivadondo/ Peter Waymont |  | 2016-06-10 | 0 |  | 2017-02-23 | The DCP 275 Change Report has issued to Parties to vote upon by the 11 November 2016. | Voting
DCP 277 | Schedule 25 – Amendment to Appendix 2 - Conditionality | Following on from the changes in DCP 272, the TRAS Expert Group has reviewed the conditionality for data items within the TRAS Service Providers Programming Manual and seeks to update some of the data items conditional/mandatory status because the current conditionality cannot be always met. Additionally, some JCode/RGMA Codes also require back population as they were missed on the original drafting. | TRAS | 2 | Keavy Larkin/Sarah Jones | Jon Dixon | 2016-07-11 | 1 |  | Next release date after approval | The DCP 277 Change Report has been issued to Parties to vote upon by the 15 November 2016. | Voting
STATUS - AWAITING AUTHORITY CONSENT
DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | CDCM | 1 | Rosalind Timperley/ Chris Ong | Bethany Hanna | 2015-01-13 | 4 |  | TBC | The DCP 228 Implementation Date vote was issued to Ofgem with a recommendation to reject the proposed implementation date of 1 April 2018. | Awaiting Authority Consent
DCP 270 | Removal of HV Medium tariff from CDCM | This CP seeks for the removal of the HV Medium Non-domestic tariff and consideration of the removal of both the LV and LV Sub Medium Non Domestic tariffs from the CDCM. | CDCM | 1 | Dan Fittock/Claire Hynes | Lynda Carroll | 2016-04-28 | 1 |  | 2018-04-01 | The DCP 270 Change Report has been issued to Parties to vote upon by the 17 October 2016. | Awaiting Authority Consent
STATUS - AWAITING IMPLEMENTATION
[5 empty] | 2017-04-01 | [6 empty] | n/a
DCP 138 | Implementation of alternative network use factor (NUF) calculation method in EDCM | This CP seeks to amend the method of calculating Network Use Factors for EDCM demand customers as defined within DCUSA to address the concerns raised by Ofgem in Condition 3 of the Ofgem decision document on EDCM import charges published in September 2011. | EDCM | 1 | Fungai Madzivadondo/Simon Yeo | Keith Burwell | 2012-06-18 | 9 |  | 2017-04-01 | The Authority directs that modification DCP 138 be made. The CP will be implemented on 1 April 2017. | n/a
DCP 227 | Removing the inconsistency in the application of Peaking Probabilities in the CDCM | ​The proposal changes the way that peaking probabilities are applied in the CDCM and therefore affects CDCM tariffs. | CDCM | 1 | Rosalind Timperley /George Moran |  | 2015-01-13 | 4 |  | 2017-04-01 | The Authority directed for DCP 227 to be made and implemented on 1 April 2017. | n/a
2018-04-01
DCP 161 | Excess Capacity Charges | To improve the cost reflectivity of the excess capacity charge calculation within the CDCM and EDCM by removing the customer contributions and adding in any additional costs that should be attributed to this charge. Also, to consider applying the excess capacity charge on either a monthly, seasonal or time of day basis. | CDCM | 1 | Michael Walls/Chris Ong | Keith Burwell | 2013-02-06 | 12 |  | 2018-04-01 | The Authority directed for DCP 161 to be made and implemented on 1 April 2018. | n/a
DCP 222 | Non Billing Of Excess Reactive Power Charges | This CP proposes the removal of the excess reactive power charge when a DNO requests that a generator operates outside of the 0.95 power factor limit. | CDCM | 1 | Fungai Madzivadondo/Dave Wornell | Nisha Doshi | 2014-12-02 | 11 |  | 2018-04-01 | The Authority directed for DCP 222 to be made and implemented on 1 April 2018. | n/a
DCP 234 | Merging the PCDM and extended PCDM | The intent of the CP is to replace the Price Control Disaggregation (PCDM) and extended PCDM models with one model.To create a new schedule in DCUSA which contains the legal text that relates to IDNO charging that is currently contained in Schedules 16, 17 and 18. | CDCM and EDCM | 1 | Claire Hynes/ Claire Campbell | Lynda Carroll | 2015-02-27 | 7 |  | 2018-04-01 | The Authority directed for DCP 234 to be made and implemented on 1 April 2018. | n/a
DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | The intent of this proposal is to align table 1001 in the CDCM to the current format of table in Schedule 15. | CDCM | 2 | Fungai Madzivadondo/John Lawton | Lynda Carroll | 2016-05-18 | 2 |  | 2018-04-01 | Parties voted to approve the change on the 17 October 2016 for implementation on the 01 April 2018. | Awaiting Implementation
STATUS - TO BE CONFIRMED | [11 empty] | n/a
DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | CDCM | 1 | Rosalind Timperley/ Chris Ong | Bethany Hanna | 2015-01-13 | 4 |  | TBC | The Authority directed for DCP 228 to be made and an alternative implementation date be considered and submitted in accordance with clause 14.2 of Part 1C of DCUSA. As suggested by Ofgem in their decision letter the DCUSA Panel will consider the implementation of DCP 228 and submit an alternative implementation date to the previously proposed 1 April 2016 date. | n/a
STATUS - APPEAL | [11 empty] | n/a
n/a | n/a | [10 empty] | n/a
STATUS - IMPLEMENTED
DCP 267 | Introduction of a new definition for 'Confirmed Theft' | To introduce a definition for Confirmed Theft under DCUSA to ensure consistency across Suppliers in submitting confirmed theft detections under TRAS. | TRAS | 2 | Dan Fittock/Claire Hynes | Jon Dixon | 2016-03-09 | 1 |  | Next release date after approval | DCUSA Parties voted to approve DCP 267. The CP was implemented on 03 November 2016. | Implemented
DCP 271 | Process and Costs of Providing Additional Hunter Facilities | This change seeks to introduce a process for Suppliers who wish to procure additional Hunter facilities from the TRAS Service Provider and to make those costs transparent to the Supplier community | TRAS | 2 | Keavy Larkin/Sarah Jones | Jon Dixon | 2016-05-11 | 3 |  | 2016-11-03 | DCUSA Parties voted to approve DCP 271. The CP was implemented on 03 November 2016. | Implemented
DCP 272 | TRAS – Amendment of Schedule 25 Appendix 2 | This CP seeks to introduce a clear data item list in DCUSA for delivery of the TRAS solution. | TRAS | 2 | Keavy Larkin/Sarah Jones | Jon Dixon | 2016-05-11 | 3 |  | 2016-11-03 | DCUSA Parties voted to approve DCP 272. The CP was implemented on 03 November 2016. | Implemented
STATUS - REJECTED
DCP 160 | Non-Half Hourly (NHH) Notional Capacity | This CP seeks to revise Schedule 16 (along with appropriate CDCM and ARP Modelling changes) to introduce a notional spare capacity requirement to be applied to the average maximum demand when calculating NHH tariffs. The notional spare capacity should align with the same proportions which are calculated and allocated to Half Hourly (HH) tariffs. | CDCM | 1 | Claire Hynes / George Moran | Keith Burwell | 2013-01-08 | 12 |  | 2018-04-01 | The Authority directed that DCP 160 not be made on the 18 October 2016. | Rejected
STATUS - WITHDRAWN | [11 empty] | n/a
n/a | n/a | [10 empty] | n/a
Change Register - November

## CP Work Plans
Change Proposal | Secretariat | CP Title | Change Report Due | Status | Update Change Report Due date
DCP 169 | Roz | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | On hold
DCP 226 | Fungai | Housekeeping 66/72/73/77/80 | On hold
DCP 243 | Fungai | Treatment of Customer Contributions in the CDCM | 2017-01-11
DCP 244 | Roz | MOP Leaving Site for Cat A Situations | CP on hold. First Work Plan to be submitted
DCP 251 | Lauren | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | 2016-12-14
DCP 252 | Lauren | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | 2016-12-14
DCP 255 | Claire | Changes to Electricity (Connection Charges) Regulations 2002 | On hold
DCP 263 | Claire | NTC DEH gap | 2016-11-09 | Change Report Due
DCP 266 | Fungai | The calculation and application of IDNO discounts | 2016-11-09 | Change Report Due
DCP 268 | Claire | DUoS Charging Using HH settlement data | 2016-12-08
DCP 274 | Claire | The application of export capacity charges in the EDCM | 2017-01-11
DCP 278 | Fungai | Allocation of Users to the ETTOS Secure Email Service | 2016-10-19 | Change Report Due
DCP 279 | Claire | Linking Credit Cover to the Annual Iteration Process | 2016-11-09 | Change Report Due
DCP 280 | Keavy | Clarification of TRAS Accession Process | 2016-11-16 | Change Report Due
DCP 281 | Dan | Changes to Schedule 19 – Portfolio Billing | 2017-01-18 | First Workplan Due
DCP 282 | Claire | EDNO UMSO | 2017-01-18 | First Workplan Due
DCP 283 | Claire | The calculation of generation credits in the CDCM | 2017-02-08 | First Workplan (following first meeting)
DCP 284 | Claire | The application of scaling to generation credits in the CDCM | 2017-02-08 | First Workplan (following first meeting)
DCP 285 | Fungai | Schedule 23, Appendix 1 SLC References | 2016-11-09 | First Workplan (following first meeting)
CP Work Plans

## Legal Text Overlap
Colour Code
February 2016 | Red Text = Legal text close to being completed but not yet finalised
Black Text = Finalised Legal text that will not change further (i.e. version to be included in Change Report)
Yellow Highlight = Paragraph changed by more than one CP
|  | Awaiting Decision | [6 empty] | Awaiting Implementation
CP Number | DCP 274 | DCP 270 | DCP 268 | DCP 266 | DCP 252 | DCP 251 | DCP 243 | DCP 169 | DCP 273 | DCP 227 | DCP 138 | DCP 161 | DCP 228 | DCP 222 | DCP 234
Implementation Date | [8 empty] | 2018-04-01 | 2017-04-01 | 2017-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01
Status | Under Development | Developed | Under Development | Under Development | Under Development | Under Development | Under Development | on Hold | Developed | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation | Awaiting Implementation
DCUSA Schedule 15
Impacted Paragraphs | [11 empty] | Table 3 (para 4.1)
DCUSA Schedule 16 | [8 empty] | para 3
Impacted Paragraphs | [11 empty] | 3a
12
14
3(b)
97
98 and 99
[10 empty] | 67 to 72 |  |  |  |  | 100 to 120 (including the tables and headings)
|  | 84 | [12 empty] | 124 and 125
[12 empty] | 81 |  |  | Glossary
92 to 95
109,111 to 113A & 113D,118 to 124
131
136
|  | 141 | [9 empty] | 141 (table 5)
146 (table 7)
147 (table 8 & 9)
153
157 - deleted
173
177 (originally 176)
DCUSA Schedule 17
Impacted Paragraphs | [11 empty] | 1.3 |  |  | 25
25.1
25.2
[11 empty] | 18.6 to 18.8 |  |  |  | 25.3 to 25.18 (including the tables and headings).
25.19
30.6
DCUSA Schedule 18
Impacted Paragraphs | [11 empty] | 1.3 |  |  | 25
25.1
25.2
25.3 to 25.18 (including the tables and headings).
[11 empty] | 18.7 to 18.8 |  |  |  | 25.19
30.6
DCUSA Schedule 20
Impacted Paragraphs | [11 empty] | 1.1
Charging Methodology CPs Legal Text Overlap Tracker