## CPs
Change Proposals Register - December 2014
DCP No | CP Title | CP Type | Part 1 / 2 Matter | Lead Analyst/WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status December 2014
STATUS - DEFINITION
DCP 114 | NTC Amendments - Capacity Management (Over Utilisation) | General | 1 | Katherine Rushton/Peter Waymont | Lesley Ferrando | 2011-12-07 | 8 |  | Next Release Following Authority Consent | Definition - The Working Group is considering the legal text.
DCP 115 | NTC Amendments - Capacity Management (Under Utilisation) | General | 1 | Katherine Rushton/Peter Waymont | Lesley Ferrando | 2011-12-07 | 8 |  | Next Release Following Authority Consent | Definition - The Working Group is considering the legal text.
DCP 117 | Treatment of ‘Load related new connections & reinforcement (net of contributions)’ in the Price Control | CDCM | 1 | Michael Walls/Neil Fitzsimons | Bethany Hanna | 2011-11-13 | 14 |  | Next Release Following Authority Consent | Definition -The Working Group has sent through the model specification document to the DCUSA modelling consultant. The Working Group will next meet on 13 October and plans to draft a consultation at that point to be issued to Parties.
DCP 138 | Implementation of alternative network use factor (NUF) calculation method in EDCM | EDCM | 1 | Katherine Rushton/Simon Yeo | Bethany Hanna | 2012-06-18 | 3 |  | 2014-04-01 | Definition - A decision from Ofgem on the DNOs proposals for Network Use Factors has been received, therefore, the DCP 138 Working Group will be coming off hold.
DCP 160 | Non-Half Hourly (NHH) Notional Capacity | CDCM | 1 | Claire Hynes / George Moran | Bethany Hanna | 2013-01-08 | 3 |  | 2014-04-01 | Definition - The Working Group are reviewing the background of the CP and the current arrangements for HH and NHH before deciding on a way forward. The next meeting is scheduled for the 22 January 2014.
DCP 169 | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | CDCM | 1 | Rosalind Timperley/Jonathan Wisdom | Bethany Hanna | 2013-03-13 | 5 |  | 2015-04-01 | Definition -The Working Group is considering the Ofgem decision on DCP 123 in deciding how it should proceed
DCP 172 | Clarification of way in which voltage rise is used in determining the New Network Capacity | CCCM | 1 | Claire Hynes/ Neil Magrath | Arun Pontin | 2013-04-30 | 6 |  | Next Release Following Authority Consent | The Working Group is considering whether to issue a second consultation on a new option which has been raised or to request legal review of the legal text on the Working Groups preferred solution for this CP.
DCP 180 | Further reduction in the volatility of Use of System Charges | CDCM | 1 | Rosalind Timperley/ Helen Inwood | Bethany Hanna | 2013-06-12 | 7 | Waiting for DCP 178 to progress first. | 2014-04-01 | Definition -The Working Group is waiting for DCP 178 to progress first.
DCP 181 | Previous Connection Terms Enduring | General | 1 | Claire Hynes/ Peter Waymont | James Goldsack | 2013-06-17 | 2 |  | Next Release Following Authority Consent | Definition - The Working Group is reviewing the change report and draft legal text.
DCP 182 | Removal of Disconnection Notice | General | 1 | Katherine Rushton/ Gillian Millar | Stacy Feldmann | 2013-06-24 | 3 |  | Next Release Following Authority Consent | The Working Group is reviewing the legal text.
DCP 183 | To Convert the super red KWH to KVA when calculating the EDCM tariffs | EDCM | 1 | Rosalind Timperley/ Wendy Mantle | Bethany Hanna | 2013-08-12 | 11 |  | 2015-04-01 | The Working Group has issued an RFI seeking supporting information from DNOs.
DCP 190 | Credit for equipment recovery associated with temporary connections | CCCM | 1 | Claire Hynes/ David Ball | Clothilde Cantegreil | 2013-09-18 | 4 |  | Next Release Following Authority Consent | The DCP 190 and DCP 190A Change Report has been sent back to the DCP 190 Working Group to consider the DCP 190 legal text reference to Section 6.
DCP 203 | The Rationalisation Of Discount Factors Used To Determine LDNO Use Of System Tariffs Relating To UMS Connections On Embedded Distribution Networks And The Associated LDNO Tariffs | CDCM & EDCM | 1 | Michael Walls/Neil Fitzsimons | Stacy Feldmann | 2014-02-12 | 5 |  | 2015-04-01 | The Working Group is drafting the second consultation. The next meeting will take place in early November following the consultation.
DCP 204 | Smart Metering Related Amendments to Schedule 8 | General | 1 | Rosalind Timperley/ David Brogden | Rory McCarthy | 2014-02-27 | 8 |  | 2015-04-01 | Definition - The Working Group is in the process of drafting a Change Report
DCP 205 | Recovery of Costs Due To Load And Generation Increases From Existing Customers In RIIO-ED1 | CCCM | 1 | Claire Hynes/ Catherine Falconer | Neil Copeland | 2014-03-12 | 6 |  | 2015-04-01 | Definition - The DCP 205 Working Group is meeting on the 22 December to review the Wragge & Co. reviewed legal text and andf the draft DCP 205 Change Report.
DCP 206 | EDCM Customers And Their Suppliers; EDCM Generators With Import Facilities; DNOs; IDNOs | EDCM | 1 | Michael Walls/Franck Latremolier | Keith Burwell | 2014-03-13 | 3 |  | 2015-04-01 | The DCP 206 Change Report is being finalised by the Working Group
DCP 209 | Resolving Unregistered Customers | General | 1 | Claire Hynes/ Chris Allanson | Rhianne Ogilvie | 08/05.2014 | 2 |  | 2015-04-01 | The DCP 209 letter requesting advice from Wragge & Co. on the powers of a DNO to disconnect a premise in order to draft the letter templates for the CP was issued with a deadline date of the 09 December 2014. The DCP 209 Working Group will meet to discuss the legal advice received.
DCP 210 | The Assessment Timetable | General | 1 | Katherine Rushton/ John Lawton | Amanda Rooney | 08/05.2014 | 0 |  | Next Release Following Authority Consent | Definition - The Working Group is in the process of drafting a Change Report
DCP 211 | Enhance Transparency Of DCUSA Change Management | General | 1 | Katherine Rushton/ Tony Savka | Amanda Rooney | 2014-05-20 | 1 |  | Next Release Following Authority Consent | Definition - The Working Group is in the process of drafting a Change Report
DCP 214 | Voting | General | 1 | Katherine Rushton/ | Amanda Rooney | 2014-07-09 | 1 |  | Next Release Following Authority Consent | The Working Group has reviewed the consultation responses and is meeting to discuss the way forward.
DCP 216 | Amending the EDCM Model Format | EDCM | 1 | Claire Hynes/ Andrew Pace | Keith Burwell and Bethany Hanna | 2014-09-10 | 1 |  | Next Release Following Authority Consent | The Working Group is currently reviewing the draft consultation one document ex-committee and seeking modelling support.
DCP 220 | Correction Of Paragraphs 17 And 18 In Schedule 16 (CDCM) To Accurately Reflect Network Levels In The Network Model | CDCM | 2 | Claire Hynes/ |  | 2014-11-19 | 0 |  | Next Release Following Authority Consent | The DCUSA Panel agreed ex-committee for this change to go straight to report.
STATUS - CHANGE REPORT
DCP 178 | Notification period for change to use of system charges | CDCM | 1 | Rosalind Timperley/Chris Ong | Bethany Hanna | 2013-06-11 | 10 |  | 01/12/2013 or 01/12/2014 | The Authority sent back the change report to be further refined. The revised DCP 178 Change Report is planned to be presented at the December DCUSA Panel meeting.
DCP 198 | Align the PCDM Model with the legal text | CDCM | 1 | Michael Walls/Chris Ong | Bethany Hanna | 2013-12-10 | 3 |  | 2015-04-01 | The DCP 198 Change Report is planned to be presented at the December DCUSA Panel meeting.
DCP 212 | Align The Extended PCDM Model With The Legal Text | EDCM | 1 | Michael Walls/ | Bethany Hanna | 2014-05-22 | 1 |  | 2015-04-01 | The DCP 212 Change Report is planned to be presented at the December DCUSA Panel meeting.
STATUS - VOTING
n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
STATUS - AWAITING AUTHORITY CONSENT
DCP 137 | Introduction of locational tariffs for the export from HV generators in areas identified as generation dominated. | CDCM | 1 | Rosalind Timperley/ Oliver Day | Bethany Hanna | 2012-06-13 | 6 |  | 2014-04-01 | The Change declaration was issued to Ofgem on the 10 Sepember 2014 with the recommendation to accept the solution and reject the implementation date. The indicative decision date is the 15 October 2014.
STATUS - AWAITING IMPLEMENTATION
DCP 161 | Excess Capacity Charges | CDCM | 1 | Michael Walls/Chris Ong | Keith Burwell | 2013-02-06 | 12 |  | Next Release Following Authority Consent | The Authority directed for DCP 161 to be made and implemented on the 01 April 2016.
DCP 179 | Amending the CDCM tariff structure | CDCM | 1 | Rosalind Timperley/ Andy Pace | Bethany Hanna | 2013-06-12 | 9 |  | 2015-04-01 | The Authority directed for DCP 179 to be made and implemented on the 01 April 2015.
DCP 185 | LDNO discount on 20% of residual revenue | EDCM | 1 | Rosalind Timperley/ Rob Garner | James Goldsack | 2013-07-19 | 6 |  | 2015-04-01 | The Authority directed for DCP 185 to be made and implemented in the 01 April 2015 DCUSA Release.
DCP 189 | Un-expired capitalised O&M | EDCM | 1 | Rosalind Timperley/ Pat Wormald | Iain Morgan | 2013-08-12 | 11 |  | 2015-04-01 | The Authority directed for DCP 189 to be made and implemented in the 01 April 2015 DCUSA Release.
DCP 195/ 195A | Service Level Agreement for Resolving Network Operational Issues | General | 1 | Rosalind Timperley/ Kevin Woollard | Neil Copeland/ | 2013-11-14 | 5 |  | 2015-02-12 | The Authority rejected the DCP 195 change and directed for the DCP 195A change to be made and be implemented in an extraordinary DCUSA release on 12 February 2015.
DCP 217 | Rate of Return | CDCM & EDCM |  | Michael Walls |  | 2014-09-10 | 0 |  | 2015-04-01 | The Authority directed for DCP 217 to be made and implemented in the 01 April 2015 DCUSA Release.
DCP 218 | Licence Derogation Notification | General | 2 | Rosalind Timperley |  | 2014-10-07 |  |  | Next Release Following Authority Consent | The Part 2 Matter DCP 218 change was approved by Parties for implementation in the next DCUSA release on the 12 February 2014.
DCP 219 | DCUSA Housekeeping Changes | General | 2 | Rosalind Timperley |  | 07/102014 |  |  | Next Release Following Authority Consent | The Part 2 Matter DCP 219 change was approved by Parties for implementation in the next DCUSA release on the 12 February 2014.
STATUS - IMPLEMENTED
n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
STATUS - REJECTED
n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
STATUS - WITHDRAWN
DCP 221 | Model version | CDCM |  | Claire Hynes | n/a | 2014-11-18 | n/a | n/a | 2014-04-01 | A withdrawal notification e-mail was issued for this CP to DCUSA Contract Managers with a closing date of the 10 December 2014 should any Contract Manager wish to adopt this CP.