###### DCP 325 'Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20’ Work Plan

| No. | Event | Target Date |
| --- | --- | --- |
|  | First Working Group meeting | - 04 September 2018 |
|  | Electralink to draft a consultation document based on Working Group comments at the meeting and circulate to Working Group members for review. | - 18 September 2018 |
|  | Working Group meeting to review the draft consultation | - 27 September 2018 |
|  | ElectraLink updates consultation document and circulates to group for final sign off | - 28 September 2018 |
|  | Consultation Document issued for a period of four weeks | - 08 October 2018 |
|  | Consultation Responses due | - 05 November 2018 |
|  | Electralink collates consultation responses and circulates to Working Group members | - 13 November 2018 |
|  | Working Group meeting to review the consultation responses and develop the solution and legal text | - 20 November 2018 |
|  | Working Group meeting to decide next steps for the change | - 06 December 2018 |
|  | The Secretariat to pull together a Considerations Log from the collated consultation responses and circulate to Working Group Members | - 13 December 2018 |
|  | Working Group meeting to review Considerations Log and develop the solution | - 11 January 2019 |
|  | ElectraLink to draft a further consultation document | - January 2019 |
|  | Working Group members to complete actions from 11 January 2019 Working Group meeting | - January 2019 |
|  | AE and KB to produce options for CEPA/TNEI to consider for the solution of this change | - January 2019 |
|  | Working Group meeting to discuss the CEPA/TNEI options | - 24 January 2019 |
|  | Requirements to be developed further and circulated to Working Group members | - 31 January 2019 |
|  | Working Group members to review the requirements and circulate any comments | - 07 February 2019 |
|  | Official request sent to CEPA/TNEI | - w/c 11 February 2019 |
|  | Working Group meeting to review the CEPA/TNEI proposals | - 17 May 2019 |
|  | Update to the Illustrative Forecast Model completed by the Proposer | - 22 May 2019 |
|  | Further Working Group meeting to discuss the updated IFM, considerations log and draft legal text | - 17 June 2019 |
|  | Drafting of the second consultation document | - June 2019 |
|  | Consultation document issued for a period of three weeks | - June/July 2019 |
|  | Consultation Responses due | - July 2019 |
|  | ElectraLink collates consultation responses and circulates to Working Group members | - August 2019 |
|  | Working Group meeting to review the consultation responses | - August 2019 |
|  | ElectraLink to draft third consultation | - August/September 2019 |
|  | Working Group meeting to review the draft third consultation | - September 2019 |
|  | ElectraLink to update consultation document and circulate to industry for a period of three-weeks. | - September 2019 |
|  | Consultation responses due | - October 2019 |
|  | ElectraLink collates consultation responses and circulates to Working Group members | - October 2019 |
|  | Working Group meeting to review the consultation responses and finalise the legal text | - October 2019 |
|  | Implement changes to legal text in light of consultation responses | - October 2019 |
|  | Legal text issued to the DCUSA legal consultant for review | - October 2019 |
|  | Electralink to draft Change Report and circulate to Working Group | - October 2019 |
|  | ElectraLink to circulate draft legal text to Working Group members once received from legal advisor | - October/November 2019 |
|  | Meeting to review draft Change Report and DCUSA legal consultant comments on the legal text | - November 2019 |
|  | Change Report submitted to DCUSA Panel (Panel paper day) | - 13 November 2019 |
|  | DCUSA Panel approves Change Report | - 20 November 2019 |
|  | Change Report issued for voting | - 22 November 2019 |
|  | Voting Closes (three weeks) | - 13 December 2019 |
|  | Change Declaration issued | - 17 December 2019 |
|  | Implementation Date | - First Release following Party Approval |