JOINT WORK PLAN:

DCP 319 - Removal of residual charging for embedded generators in the CDCM

DCP 321 - Removal of residual charging for embedded generators in the EDCM

| No. | Event | Target Date |
| --- | --- | --- |
|  | First Working Group meeting | - 25 July 2018 |
|  | ElectraLink to draft straw man consultation document and circulate to Working Group members for review. | - 25 July 2018 |
|  | Working Group meeting to discuss Ofgem views on progressing CPs and to start to develop potential solutions | - 20 August 2018 |
|  | Working Group meeting to discuss/develop potential solutions | - 20 September 2018 |
|  | ElectraLink to amend draft consultation document in line with discussions held during meeting and circulate to Working Group members for review. | - 27 September 2018 |
|  | Working Group meeting to review draft consultation document and to finalise any potential solutions | - October 2018 |
|  | Allowance made for Modelling / Impact Assessment request (if needed) – 20 Working Day turn-around | - October/November 2018 |  |
|  | ElectraLink to amend draft consultation document in line with discussions held during meeting and circulate to Working Group members for review/sign-off. | - November 2018 |
|  | Consultation issued to Parties / Industry | - November 2018 |
|  | Consultation Responses due [based on three-week consultation period] | - December 2018 |
|  | ElectraLink collates consultation responses and circulates to Working Group members | - December 2018 |
|  | Meeting to review consultation responses | - January 2019 |
|  | Implement changes to legal text in light of consultation responses | - January 2019 |
|  | Legal text issued to the DCUSA legal consultant for review | - January 2019 |
|  | ElectraLink to draft Change Report and circulate to Working Group | - January 2019 |
|  | ElectraLink to circulate draft legal text to Working Group members once received from legal advisor | - February 2019 |
|  | Meeting to review draft Change Report and DCUSA legal consultant comments on the legal text | - February 2019 |
|  | Change Report submitted to DCUSA Panel (Panel paper day) | - 13 March 2019 |
|  | DCUSA Panel approves Change Report | - 20 March 2019 |
|  | Change Report issued for voting | - 22 March 2019 |
|  | Voting Closes | - 12 April 2019 |
|  | Change Declaration issued | - 16 April 2019 |
|  | Ofgem Decision | - 21 May 2019 |
|  | Implementation Date | - 01 April 2021 |