###### DCP 314 ‘Appropriate treatment of Bad Debt following appointment of Supplier of Last Resort’ Work Plan

| No. | Event | Target Date |
| --- | --- | --- |
|  | First Working Group meeting | - 23 March 2018 |
|  | Electralink to draft a consultation document based on Working Group comments at the meeting and circulate to Working Group members for review. | - 20 April 2018 |
|  | Second Working Group meeting | - 14 May 2018 |
|  | Third Working Group meeting | - 05 June 2018 |
|  | Fourth Working Group meeting | - 02 July 2018 |
|  | Produce draft consultation and circulate to Working Group members | - 16 July 2018 |
|  | Working Group meeting to review the consultation document | - 03 August 2018 |
|  | ElectraLink updates consultation document and circulates to group for final sign off | - 10 August 2018 |
|  | Consultation Document issued for a period of three weeks | - 14 August 2018 |
|  | Consultation Responses due [based on three-week consultation period] | - 05 September 2018 |
|  | Electralink collates consultation responses and circulates to Working Group members | - 07 September 2018 |
|  | Meeting to review consultation responses | - September 2018 |
|  | Implement changes to legal text in light of consultation responses | - September 2018 |
|  | Legal text issued to the DCUSA legal consultant for review | - September 2018 |
|  | Electralink to draft Change Report and circulate to Working Group | - September 2018 |
|  | ElectraLink to circulate draft legal text to Working Group members once received from legal advisor | - September/October 2018 |
|  | Meeting to review draft Change Report and DCUSA legal consultant comments on the legal text | - October 2018 |
|  | Change Report submitted to DCUSA Panel | - 10 October 2018 |
|  | DCUSA Panel approves Change Report | - 17 October 2018 |
|  | Change Report issued for voting | - 19 October 2018 |
|  | Voting Closes (three weeks) | - 09 November 2018 |
|  | Change Declaration issued | - 13 November 2018 |
|  | Ofgem Decision | - 18 December 2018 |
|  | Implementation Date | - First Scheduled DCUSA Release following approval |