###### DCP 307 ‘Requiring IDNOs to comply with D2021 billing’ Work Plan

| No. | Event | Target Date |
| --- | --- | --- |
|  | First Working Group meeting | - 01 November 2017 |
|  | Electralink to draft a consultation document based on Working Group comments at the meeting and circulate to Working Group members for review. | - 29 November 2017 |
|  | Working Group to review the consultation document and submit comments to ElectraLink | - W/C 11 December 2017 |
|  | ElectraLink updates consultation document and circulates to group for final sign off | - 20 December 2017 |
|  | Working Group to review the draft Consultation document | - W/C 08 January 2018 |
|  | Consultation Document issued for a period of three weeks | - 15 January 2018 |
|  | Consultation Responses due [based on three-week consultation period] | - 5 February 2018 |
|  | Electralink collates consultation responses and circulates to Working Group members | - 9 February 2018 |
|  | Meeting to review consultation responses | - 16 February 2018 |
|  | Implement changes to legal text in light of consultation responses | - 23 February 2018 |
|  | Legal text issued to the DCUSA legal consultant for review | - W/C 26 February 2018 |
|  | Electralink to draft Change Report and circulate to Working Group | - W/C 26 March 2018 |
|  | ElectraLink to circulate draft legal text to Working Group members once received from legal advisor | - W/C 16 April 2018 |
|  | Meeting to review draft Change Report and DCUSA legal consultant comments on the legal text | - W/C 23 April 2018 |
|  | Change Report submitted to DCUSA Panel (Panel paper day) | - 9 May 2018 |
|  | DCUSA Panel approves Change Report | - 16 May 2018 |
|  | Change Report issued for voting | - 18 May 2018 |
|  | Voting Closes (three weeks) | - 8 June 2018 |
|  | Change Declaration issued | - 12 June 2018 |
|  | Ofgem Decision | - 17 July 2018 |
|  | Implementation Date | - TBC |