###### DCP 293 'Charging Methodology Cut-off Date’ Work Plan

|  |  |  |
| --- | --- | --- |
| **No.** | **Event** | **Target Date** |
|  | First Working Group meeting | 21 March 2017 |
|  | Electralink to draft a consultation document based on Working Group comments at the meeting and circulate to Working Group members for review. | 28 March 2017 |
|  | Working Group to review the consultation document and submit comments to ElectraLink | 28 March – 04 April 2017 |
|  | ElectraLink updates consultation document and circulates to group for final sign off | 06 April 2017 |
|  | Consultation Document issued for a period of three weeks | 26 June 2017 |
|  | Consultation Responses due [based on two week consultation period] | 10 July 2017 |
|  | Electralink collates consultation responses and circulates to Working Group members | 12 July 2017 |
|  | Meeting to review consultation responses | 14 July 2017 |
|  | Implement changes to legal text in light of consultation responses | 2017 |
|  | Legal text issued to the DCUSA legal consultant for review | July 2017 |
|  | Electralink to draft Change Report and circulate to Working Group | 12 July 2017 |
|  | ElectraLink to circulate draft legal text to Working Group members once received from legal advisor | July 2017 |
|  | Meeting to review draft Change Report and DCUSA legal consultant comments on the legal text | July/August 2017 |
|  | Change Report submitted to DCUSA Panel (Panel paper day) | 13 September 2017 |
|  | DCUSA Panel approves Change Report | 20 September 2017 |
|  | Change Report issued for voting | 22 September 2017 |
|  | Voting Closes (three weeks) | 13 October 2017 |
|  | Change Declaration issued | 17 October 2017 |
|  | Ofgem Decision | 21 November 2017 |
|  | Implementation Date | Next Scheduled DCUSA release |