###### DCP 287 'Generation Credits in the EDCM’ Work Plan

|  |  |  |
| --- | --- | --- |
| **No.** | **Event** | **Target Date** |
|  | First Working Group meeting – review CP, including modelling specifications and discussion of proposed legal text. | 13 March 2017 |
|  | Working Group members to complete Action Items and submit to ElectraLink for inclusion into Draft Consultation. | 27 March 2017 |
|  | ElectraLink to draft a consultation document based on Working Group comments at the meeting and circulate to Working Group members for review. | 28 March 2017 |
|  | Meeting of Working Group to review consultation document. | 04 April 2017 |
|  | Working Group to complete actions as per last meeting and include updates in consultation document submit to ElectraLink to circulate to group for review | April 2017 |
|  | Meeting of Working Group to review consultation document. | 12 May 2017 |
|  | Working Group to complete actions | 31 May 2017 |
|  | Update consultation document | 14 June 2017 |
|  | Meeting of Working Group to review consultation document. | 21 July 2017 |
|  | Further meeting to review the consultation document | 15 August 2017 |
|  | Complete outstanding actions | 22 August 2017 |
|  | Meeting to review of the Consultation document | 7 September 2017 |
|  | Meeting to review the final Consultation document | 26 September 2017 |
|  | ElectraLink to circulate consultation document to group for final review | 03 October 2017 |
|  | Consultation Document issued to parties for a period of 3 weeks | 06 October 2017 |
|  | Consultation Responses due back | 27 October 2017 |
|  | ElectraLink collates consultation responses and circulates to Working Group members | 03 November 2017 |
|  | Meeting for Working Group to review the Consultation responses. Proposed face to face meeting. | 10 November 2017 |
|  | ElectraLink issues the RFI to DNOs | 22 November 2017 |
|  | RFI Responses due | 29 November 2017 |
|  | Meeting to review the RFI responses | 11 December 2017 |
|  | ElectraLink updates legal text and starts second consultation document. | W/C 08 January 2018 |
|  | Working Group meeting to review draft second consultation and agree the legal text. | 23 January 2018 |
|  | Outstanding actions completed | 05 February 2018 |
|  | Working Group Teleconference to review and finalise the Legal Text ahead of sending to the Modeller | 07 February 2018 |
|  | Modelling support request made to Reckon for three weeks (if available otherwise there may be a delay in the work plan) | 08 February 2018 |
|  | Circulate updated second consultation document to Working Group members | 08 February 2018 |
|  | Teleconference to review and finalise Consultation ahead of receiving the Models | 27 February 2018 |
|  | Model received from Reckon | 01 March 2018 |
|  | Request an anonymised Impact Assessment from DNOs | 05 March 2018 |
|  | Teleconference meeting to review modelling issues/questions and legal text | 14 March 2018 |
|  | Meeting to review outcomes from modelling request / advice and to continue drafting the consultation document | 17 July 2018 |
|  | ElectraLink to issue the draft legal text to the Working Group | 24 July 2018 |
|  | Working Group to review legal text (Demand and LRIC) | 31 July 2018 |
|  | Working Group to review legal text (FCP) | 07 August 2018 |
|  | ElectraLink to issue modelling request to CEPA/TNEI | 08 August 2018 |
|  | Working Group meeting to review consultation document and discuss forward looking charges and access consultation (possible face to face) to be agreed. | 21 August 2018 |
|  | Meeting for FCP DNO meeting with CEPA/TNEI |  |
|  |  |  |
|  | ElectraLink updates second consultation document in line with comments made by Working Group and circulates for review | 28 August 2018 |
|  | Updated models received | 5 September2018 |
|  | impact Assessment to be carried out by DNOs (1 week) | 5 - 12 September 2018 |
|  | ElectraLink updates second consultation document to include results of modelling and impact assessment and circulates to Working Group for final review / sign-off. | w/c 17 September 2018 |
|  | Second Consultation Document issued for a period of [three weeks] | w/c 24 September 2018 |
|  | Second Consultation Responses due [based on three-week consultation period] | w/c 15 October 2018 |
|  | ElectraLink collates second consultation responses and circulates to Working Group members | w/c 15 October 2018 |
|  | Meeting to review second consultation responses | w/c 22 October 2018 |
|  | Amend the legal text based on feedback from the second consultation as required. | November 2018 |
|  | Legal text issued to the DCUSA legal consultant for review | November 2018 |
|  | ElectraLink to draft Change Report and circulate to Working Group | November 2018 |
|  | ElectraLink to circulate draft legal text to Working Group members once received from legal advisor | November 2018 |
|  | Meeting to review draft Change Report and DCUSA legal consultant comments on the legal text | November 2018 |
|  | Change Report submitted to DCUSA Panel (Panel paper day) | 14 December 2018 |
|  | DCUSA Panel approves Change Report | 19 December 2018 |
|  | Change Report issued for voting | 02 January 2019[[1]](#footnote-1) |
|  | Voting Closes (three weeks) | 23 January 2019 |
|  | Change Declaration issued | 25 January 2019 |
|  | Ofgem Decision | 1 March 2019 |
|  | Implementation Date | 01 April 2021 |

1. Suggested date to issue for voting as a result of Christmas and New Year. Alternatively it could be issued for 4 weeks instead of 3. [↑](#footnote-ref-1)