###### DCP 283 'The calculation of generation credits in the CDCM’ Work Plan

|  |  |  |
| --- | --- | --- |
| **No.** | **Event** | **Target Date** |
|  | First Working Group meeting – review CP, including modelling specifications and discussion of proposed legal text. | 28 November 2016 |
|  | ElectraLink to draft a RFI document based on Working Group comments at the meeting and circulate to Working Group members for review. | 5 December 2016 |
|  | Working Group to review the draft RFI document and submit comments to ElectraLink | 12 December 2016 |
|  | ElectraLink updates RFI document based on comments received. | 12 December 2016 |
|  | RFI Document issued to parties for a period of [13 December – 13 January] | 13 December 2016 |
|  | RFI Responses due back. | 13 January 2017 |
|  | ElectraLink collates RFI responses and circulates to Working Group members | 16 January 2017 |
|  | Meeting for Working Group to review the RFI responses. Proposed face to face meeting. | 23 January 2017 |
|  | ElectraLink to draft a consultation document based on principals and Working Group comments at the meeting and circulate to Working Group members for review. | 13 February 2017 |
|  | Working Group to review the consultation document and submit comments to ElectraLink. | 20 February 2017 |
|  | Meeting for Working Group to review consultation document. Meeting to be via Teleconference. | 21 February 2017 |
|  | Secretariat to provide clean version of draft consultation document to AP. | 22 February 2017 |
|  | Additional text to be included into draft consultation document by AP. | 24 February 2017 |
|  | Secretariat to circulate the amended draft consultation document to Working Group for review and comment. | 3 March 2017 |
|  | Working Group to meet to review draft consultation document. | 10 March 2017 |
|  | ElectraLink to submit clean version of document to WG by COP 10 March | 10 March 2017 |
|  | Working Group to review and provide final comment on draft consultation by noon on 15 March | 15 March 2017 |
|  | Consultation issued to parties for a period of [three weeks] | 14 March 2017 |
|  | Consultation Responses due [based on three-week consultation period] | 4 April 2017 |
|  | Working Group to meet to review the consultation responses. (face to face) | 7 April 2017 |
|  | Actions from last meeting to be completed by this date so any relevant information can be circulated to Working Group members | 28 April 2017 |
|  | Working Group meeting to discuss actions from last meeting and second consultation including modelling spec and legal text (face to face) | 4 May 2017 |
|  | ElectraLink to provide agreed actions to Working Group members | 11 May 2017 |
|  | Working Group to complete allocated actions | 16 May 2017 |
|  | Meeting date for teleconference with DNO engineers to discuss LV network design. (11am) | 16 May 2017 |
|  | ElectraLink produces second consultation document including legal text and modelling specification document. | 18 May 2017 |
|  | Working Group to meet via teleconference to review consultation document and discuss sharing factor (subject to meeting held on 16 May 2017) (9am-1pm) | 25 May 2017 |
|  | ElectraLink updates consultation document to include model (dependent upon outcome of sharing factor discussion) and circulates to Working Group for review | 15 June2017 |
|  | Working Group to meet via teleconference to review consultation document and discuss sharing factor. | 22 June 2017 |
|  | ElectraLink updates consultation document based on comments | 29 June 2017 |
|  | Modelling support request made to Reckon for three weeks (double KPIs) model updated and Impact Assessment | 31 July 2017 |
|  | Working Group members to complete actions | 16 August 2017 |
|  | Model received from Reckon | 11 August 2017 |
|  | Working Group DNO members to sense check the model on receipt. | 18 August 2017 |
|  | ElectraLink updates consultation document with agreed actions and modelling spec and Impact Assessment and circulate to Working Group | 18 August 2017 |
|  | Working Group to review the consultation, updated modelling and impact assessment and submit final comments to ElectraLink | 25 August 2017 |
|  | Consultation Document issued for a period of [three weeks] | 1 September 2017 |
|  | Consultation Responses due [based on three-week consultation period] | 22 September 2017 |
|  | ElectraLink collates consultation responses and circulates to Working Group members. | W/C 25 September 2017 |
|  | Meeting to review consultation responses. | 3 October 2017 |
|  | Legal text issued to the DCUSA legal consultant for review | 3 October 2017 |
|  | ElectraLink to draft Change Report and circulate to Working Group | 15 November 2017 |
|  | ElectraLink to circulate draft legal text to Working Group members once received from legal advisor | 15 November 2017 |
|  | Meeting to review and finalise Change Report and including legal text. | 22 November 2017 |
|  | ElectraLink to amend Change Report as agreed at meeting and circulate to Working Group for final sign-off. | 29 November 2017 |
|  | Change Report submitted to DCUSA Panel (Panel paper day) | 13 December 2017 |
|  | DCUSA Panel approves Change Report | 20 December 2017 |
|  | Change Report issued for voting | 22 December 2017 |
|  | Voting Closes (three weeks) | 18 January 2018 |
|  | Change Declaration issued | 22 January 2018 |
|  | Ofgem Decision (date dependent on if Ofgem issues a notification on activities over the festive season) | 26 February 2018 |
|  | Implementation Date | 01 April 2020 |