| DCP 235 Proposed Timetable/ Work Plan |  |
| --- | --- |
| - Working Group First Meeting | - Wednesday, 22nd April 2015 |
| - Proposer and Chair Review and Update the Consultation | - 30 April 2015 – 06 May 2015 |
| - Working Group Review | - 07 May 2015 – 13 May 2015 |
| - Consultation | - 15 May 2015 – 05 June 2015 |
| - Collate Consultation responses and circulate to Working Group members | - 12 June 2015 |
| - Working Group Second Meeting - to review the consultation responses | - 19 June 2015 |
| Legal Text Review By the DCUSA Legal Advisor | 26 June 2015 – 10 July 2015 |
| - Draft the Change Report | - 17 July 2015 |
| - Working Group Third Meeting – Review the Change Report | - 24 July 2015 |
| - DCUSA Panel Meeting - Submit the final Change Report to the DCUSA Panel for consideration | - Change Report Submission Date – 12 August 2015 - DCUSA Panel Meeting Date - 19 August 2015 |
| - Change Report Issued to Parties to Vote For A Period Of Three Weeks | - 21 August 2015 – 11 September 2015 |
| - Collate Votes and Issue the Change Declaration to the Authority (Ofgem) for decision | - 15 September 2015 |
| - Indicative Ofgem Decision Date based on Ofgem’s 25 Working Day KPI | - 20 October 2015 |
| - DCUSA Release | - 05 November 2015 |