## DCP 234 Working Group Work Plan

| No. | Event | Target Date |
| --- | --- | --- |
|  | Working Group to review Consultation and its associated documentation by the 03 March 2016. | - 03 March 2016 |
|  | Update consultation based on Working Group comments | - 04 March 2016 |
|  | DCP 234 Consultation on the proposed changes to the CDCM model issued to Parties for a period of 4 weeks | - 18 March – 08 April 2016 |
|  | Working Group meet to review the consultation responses | - w/c 21 April 2016 |
|  | Working Group review the draft legal text | - 21 -25 April 2016 |
|  | Legal text issued to the DCUSA legal consultant for review for a period of two weeks | - 25 April – 06 May 2016 |
|  | Electralink to draft Change Report and circulate to proposer to review for one week | - 09 - 14 May 2016 |
|  | Circulate the Wragge & Co. reviewed legal text to Working Group members to review on receipt | - 10 May 2016 2016 |
|  | Working Group meet to review draft Change Report and DCUSA legal consultant comments on the legal text | - w/c 16 May 2016 |
|  | Update the Change Report pack based on the comments at the DCP 234 Working Group meeting. | - 23 - 27 May 2016 |
|  | Circulate the Change Report to the Working Group for final review | - 30 May - 03 June 2016 |
|  | Change Report submitted to DCUSA Panel (Panel paper day) | - 08 June 2016 |
|  | DCUSA Panel approves Change Report | - 15 June 2016 |
|  | Change Report issued for voting | - 17 June 2016 |
|  | Voting Closes | - 08 July 2016 |
|  | Change Declaration issued | - 12 July 2016 |
|  | Ofgem Decision (Key Performance Indicator -25 Days) | - 23 August 2016 |
|  | Implementation Date | - First Release Following Consent |