## DCP 231 Work Plan/Timetable

|  |  |  |
| --- | --- | --- |
| **No.** | **Event** | **Target Date** |
|  | First Working Group meeting | 9 April 2015 |
|  | Working Group instructed ElectraLink to prepare and submit a consultancy request for modelling support | 9 April 20105 |
|  | ElectraLink to circulate modelling documentation and plan next meeting | Upon receipt of modelling documentation |
|  | Electralink to draft consultation document and circulate to Working Group members for review. Working Group Chair to prepare draft legal text for inclusion in the consultation document | 10 June 2015 |
|  | Working Group to review the consultation document and submit comments to ElectraLink | 10 June 2015 |
|  | Working Group meeting to discuss consultation document | 10 June 2015 |
|  | ElectraLink updates consultation document and circulates to group for final sign off | 11 June 2015 |
|  | Consultation Document issued for a period of two weeks | 12 June 2015 |
|  | Consultation Responses due [based on two week consultation period] | 26 June 2015 |
|  | Electralink collates consultation responses and circulates to Working Group members | 29 June 2015 |
|  | Meeting to review consultation responses | 30 June 2015 |
|  | Implement changes to legal text in light of consultation responses | 30 June 2015/if needed |
|  | Legal text issued to the DCUSA legal consultant for review | 1 July 2015 |
|  | Electralink to draft Change Report and circulate to Working Group | 1 July 2015 |
|  | ElectraLink to circulate draft legal text to Working Group members once received from legal advisor | 7 July 2015 |
|  | Meeting to review draft Change Report and DCUSA legal consultant comments on the legal text | Planning to do this via email, unless something is identified by Wragges |
|  | Change Report submitted to DCUSA Panel (Panel paper day) | 8 July 2015 |
|  | DCUSA Panel approves Change Report | 15 July 2015 |
|  | Change Report issued for voting | 17 July 2015 |
|  | Voting Closes | 7 August 2015 |
|  | Change Declaration issued | 11 August 2015 |
|  | Ofgem Decision | Mid September |
|  | Implementation Date | 1 April 2016 |