## DCP 222 ‘Non billing of excess Reactive Power charges’ Work Plan

| No. | Event | Target Date |
| --- | --- | --- |
|  | Meeting to review consultation responses | - Past |
|  | Meeting to discuss feedback on CP and decide whether to progress with the CP | - 23 June 2015 |
|  | ElectraLink to send legal text to the DCUSA legal advisor | - 17 July - 31 July 2015 |
|  | Meeting to review discuss National Grid views on the CP and Legal text once received from the DCUSA Legal advisor | - 3 August 2015(2pm) |
|  | Meeting to review Change Report | - 18 September 2015 (10am) |
|  | Electralink to update Change Report and circulate to the WG to review for one week | - w/c 21 September 2015 |
|  | Circulate the Change Report to the Working Group for final review | - 28 September – 2 October |
|  | Working Group meeting to review Change Report and Legal Text | - 8 January 2016 |
|  | Circulate the Change Report to the Working Group for review | - 8 January – 25 January 2016 |
|  | Working Group member to draft specification document for modelling support | - w/c 11 January 2016 |
|  | Working Group to review specification | - w/c 11 January 2016 |
|  | Electralink to seek approval for modelling support request | - w/c 18 January 2016 |
|  | Modelling support request made to Reckon | - 25 January 2016 |
|  | Model received from Reckon | - w/c 1 February 2016 |
|  | Modelling Support tested by all DNOs | - w/c 1 February 2016 – 12 February |
|  | Next Working Group meeting | - 5 February 2016 |
|  | Change Report submitted to DCUSA Panel (Panel paper day) | - 09 March 2016 |
|  | DCUSA Panel approves Change Report | - 16 March 2016 |
|  | Change Report issued for voting | - 18 March 2016 |
|  | Voting Closes | - 12 April 2016 |
|  | Change Declaration issued | - 14 April 2016 |
|  | Authority Decision | - 20 May 2016 |
|  | Implementation Date | - 01 April 2018 |