## CPs
Change Proposals Register - September 2014
DCP No | CP Title | CP Type | Part 1 / 2 Matter | Lead Analyst/WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status September 2014
STATUS - DEFINITION
DCP 114 | NTC Amendments - Capacity Management (Over Utilisation) | General | 1 | Michael Walls/Peter Waymont | Lesley Ferrando | 2011-12-07 | 8 |  | Next Release Following Authority Consent | Definition - The Working Group is seeking to meet in late-September 2014.
DCP 115 | NTC Amendments - Capacity Management (Under Utilisation) | General | 1 | Michael Walls/Peter Waymont | Lesley Ferrando | 2011-12-07 | 8 |  | Next Release Following Authority Consent | Definition - The Working Group is seeking to meet in late-September 2014.
DCP 117 | Treatment of ‘Load related new connections & reinforcement (net of contributions)’ in the Price Control | CDCM | 1 | Michael Walls/Neil Fitzsimons | Bethany Hanna | 2011-11-13 | 14 |  | Next Release Following Authority Consent | Definition -The Working Group has sent through the model specification document to the DCUSA modelling consultant, once it is completed, the Working Group will issue a consultation.
DCP 138 | Implementation of alternative network use factor (NUF) calculation method in EDCM | EDCM | 1 | Rosalind Timperley/Simon Yeo | Bethany Hanna | 2012-06-18 | 3 | Awaiting decision from Ofgem on Network Use Factor proposals | 2014-04-01 | Definition - Awaiting decision from Ofgem on Network Use Factor proposals
DCP 160 | Non-Half Hourly (NHH) Notional Capacity | CDCM | 1 | Rosalind Timperley/ George Moran | Bethany Hanna | 2013-01-08 | 1 | On-hold - Waiting for DCP 179 to progress | 2014-04-01 | Definition - This CP is on hold, and being reviewed by the DCP 179 Working Group alongside its proposals
DCP 169 | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | CDCM | 1 | Rosalind Timperley/Jonathan Wisdom | Bethany Hanna | 2013-03-13 | 5 |  | 2015-04-01 | Definition -The Working Group is considering the Ofgem decision on DCP 123 in deciding how it should proceed
DCP 172 | Clarification of way in which voltage rise is used in determining the New Network Capacity | CCCM | 1 | Claire Hynes/ Neil Magrath | Arun Pontin | 2013-04-30 | 4 |  | Next Release Following Authority Consent | Definition -The Working Group is meeting to finalise the DCP 172 consultation document on the 11 September 2014.
DCP 180 | Further reduction in the volatility of Use of System Charges | CDCM | 1 | Rosalind Timperley/ Helen Inwood | Bethany Hanna | 2013-06-12 | 7 | Waiting for DCP 178 to progress first. | 2014-04-01 | Definition -The Working Group is waiting for DCP 178 to progress first.
DCP 181 | Previous Connection Terms Enduring | General | 1 | Claire Hynes/ Peter Waymont | James Goldsack | 2013-06-17 | 2 |  | Next Release Following Authority Consent | Definition - The proposer is drafting legal text for the consideration of the Working Group at its next meeting.
DCP 182 | Removal of Disconnection Notice | General | 1 | Delveer Johal/ | Stacy Feldmann | 2013-06-24 | 2 |  | Next Release Following Authority Consent | The Working Group is in the process of drafting a consultation document and meeting in late September
DCP 183 | To Convert the super red KWH to KVA when calculating the EDCM tariffs | EDCM | 1 | Delveer Johal/ Wendy Mantle | Bethany Hanna | 2013-08-12 | 10 |  | 2015-04-01 | The Working Group is in the process of drafting a consultation document.
DCP 190 | Credit for equipment recovery associated with temporary connections | CCCM | 1 | Claire Hynes/ David Ball | Stacy Feldmann | 2013-09-18 | 2 |  | Next Release Following Authority Consent | Definition - DCP 190 consultation two was issued on the 20 August with a closing date of the 12 September 2014. The Working Group will meet on the 18 September 2014 to review the responses.
DCP 198 | Align the PCDM Model with the legal text | CDCM | 1 | Michael Walls/Chris Ong | Bethany Hanna | 2013-12-10 | 3 |  | 2015-04-01 | The Working Group is seeking to meet to discuss the draft legal text on the 28 August 2014.
DCP 203 | The Rationalisation Of Discount Factors Used To Determine LDNO Use Of System Tariffs Relating To UMS Connections On Embedded Distribution Networks And The Associated LDNO Tariffs | CDCM & EDCM | 1 | Michael Walls/Neil Fitzsimons | Stacy Feldmann | 2014-02-12 | 5 |  | 2015-04-01 | The Working Group next meets on 25 September 2014
DCP 204 | Smart Metering Related Amendments to Schedule 8 | General | 1 | Delveer Johal/ |  | 2014-02-27 | 5 |  | 2015-04-01 | Definition - The Working Group issued consultation one which closes on the 05 September 2014, and are meeting mid September
DCP 205 | Recovery of Costs Due To Load And Generation Increases From Existing Customers In RIIO-ED1 | CCCM | 1 | Claire Hynes/ Catherine Falconer | Neil Copeland | 2014-03-12 | 4 |  | 2015-04-01 | Definition - The Working Group has reviewed the consultation responses and are drafting a further consultation based on the solution identified.
DCP 206 | EDCM Customers And Their Suppliers; EDCM Generators With Import Facilities; DNOs; IDNOs | EDCM | 1 | Michael Walls/Franck Latremolier | Keith Burwell | 2014-03-13 | 3 |  | 2015-04-01 | The Working Group is preparing the Change Report to be issued to the October Panel
DCP 209 | Resolving Unregistered Customers | General | 1 | Claire Hynes/ Chris Allanson | Rhianne Ogilvie | 08/05.2014 | 2 |  | 2015-04-01 | The Working Group are reviewing a letter requesting legal advice from Wragge& Co. on the powers of a DNO to disconnect a premise in oorder to draft the letter templates for the CP.
DCP 210 | The Assessment Timetable | General | 1 | Delveer Johal/ |  | 08/05.2014 | 0 |  | Next Release Following Authority Consent | The Working Group are scheduling their first meeting in late September.
DCP 211 | Enhance Transparency Of DCUSA Change Management | General | 1 | Delveer Johal/ |  | 2014-05-20 | 1 |  | Next Release Following Authority Consent | The Working Group is in the process of drafting a consultation document
DCP 212 | Align The Extended PCDM Model With The Legal Text | EDCM | 1 | Michael Walls/ | Bethany Hanna | 2014-05-22 | 1 |  | 2015-04-01 | The Working Group is drafting the consultancy support modelling specification and will meet at the end of August 2014.
DCP 213 | Providing Clarity on Late Payment of DCUSA Invoices being considered in Breach of DCUSA. | General | 1 | Delveer Johal/ |  | 2014-07-07 | 0 |  | Next Release Following Authority Consent | The Working Group will meet in September 2014.
DCP 214 | Voting | General | 1 | Michael Walls/ |  | 2014-07-09 | 1 |  | Next Release Following Authority Consent | The Working Group next meets on 16 September 2014
STATUS - CHANGE REPORT
DCP 189 | Un-expired capitalised O&M | EDCM | 1 | Rosalind Timperley/ Pat Wormald | Iain Morgan | 2013-08-12 | 11 |  | 2015-04-01 | Change Report to the September DCUSA Panel.
STATUS - VOTING
N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STATUS - AWAITING AUTHORITY CONSENT
DCP 137 | Introduction of locational tariffs for the export from HV generators in areas identified as generation dominated. | CDCM | 1 | Rosalind Timperley/ Oliver Day | Bethany Hanna | 2012-06-13 | 6 |  | 2014-04-01 | The Change declaration was issued to Ofgem on the 10 Sepember 2014 with the recommendation to accept the solution and reject the implementation date.
DCP 161 | Excess Capacity Charges | CDCM | 1 | Michael Walls/Chris Ong | Keith Burwell | 2013-02-06 | 12 |  | Next Release Following Authority Consent | The Change declaration was issued to Ofgem on the 10 Sepember 2014 with the recommendation to reject the change.
DCP 162 | Non-Secure Connections in the Common Connections Charging Methodology | CCCM | 1 | Claire Hynes/ Neil Magrath | Clothilde Cantegreil | 2013-02-07 | 8 |  | Next Release Following Authority Consent | The Change declaration was issued to Ofgem on the 10 Sepember 2014 with the recommendation to accept DCP 162 and reject DCP 162A.
DCP 167 | Additional examples for the Common Connection Charging Methodology to illustrate ‘remote reinforcement and remote reconfiguration’ | CCCM | 1 | Claire Hynes/Neil Magrath | Clothilde Cantegreil | 2013-02-13 | 5 |  | Next Release Following Authority Consent | The Change declaration was issued to Ofgem on the 10 Sepember 2014 with the recommendation to accept DCP 167 and reject DCP 167A.
DCP 178 | Notification period for change to use of system charges | CDCM | 1 | Rosalind Timperley/Chris Ong | Bethany Hanna | 2013-06-11 | 10 |  | 01/12/2013 or 01/12/2014 | Awaiting Authority consent. The Authority have issued a ' Consultation On A Proposal To Increase Significantly The Notification Period For ChangesTo Distribution Use Of System Charges' on the 8 August 2014 closing on the 19 September 2014.
DCP 179 | Amending the CDCM tariff structure | CDCM | 1 | Rosalind Timperley/ Andy Pace | Bethany Hanna | 2013-06-12 | 9 |  | 2015-04-01 | The Change declaration was issued to Ofgem on the 10 Sepember 2014 with the recommendation to accept the solution and reject the implementation date.
DCP 196 | Panel Ability To Refer A Change Proposal To The DCUSA Standing Issues Group For Pre-assessment. | General | 1 | Claire Hynes/ Tony Savka | Amanda Rooney | 2013-11-26 | 2 |  | Next Release Following Authority Consent | The Change declaration was issued to Ofgem on the 10 Sepember 2014 with the recommendation to accept the change.
DCP 200 | ‘Unmetered Supplies’ – Revision To Schedule 22 Of The DCUSA (the Common Connection Charging Methodology) | CCCM | 1 | Claire Hynes/Tim Huges | Rory McCarthy | 2014-01-01 | 2 |  | Next Release Following Authority Consent | The Change declaration was issued to Ofgem on the 10 Sepember 2014 with the recommendation to accept the change.
DCP 215 | The Inclusion of a Theft Assessment Calculator within DCUSA | General | 1 | Claire Hynes/ |  | 2014-07-09 | 0 |  | Next Release Following Authority Consent | The Change declaration was issued to Ofgem on the 10 Sepember 2014 with the recommendation to accept the change.
STATUS - AWAITING IMPLEMENTATION
DCP 185 | LDNO discount on 20% of residual revenue | EDCM | 1 | Rosalind Timperley/ Rob Garner | James Goldsack | 2013-07-19 | 6 |  | 2015-04-01 | The Authority directed for DCP 185 to be made and implemented in the 1 April 2015 DCUSA Release
DCP 195/ 195A | Service Level Agreement for Resolving Network Operational Issues | General | 1 | Rosalind Timperley/ Kevin Woollard | Neil Copeland/ | 2013-11-14 | 5 |  | 2015-02-12 | The Authority rejected the DCP 195 change and directed for the DCP 195A change to be made and be implemented in an extraordinary DCUSA release on 12 February 2015.
DCP 207 | Amending Licence & DCUSA Derogation Scope | General | 1 | Delveer Johal/ | Amanda Rooney | 2014-03-24 | 1 |  | Next Release Following Authority Consent | The Authority directed for DCP 207 to be made and implemented in the next DCUSA Release
DCP 208 | Non-veto Of Derogations | General | 2 | Delveer Johal/ |  | 2014-04-23 | 0 |  | Next Release Following Authority Consent | The Authority directed for DCP 208 to be made and implemented in the next DCUSA Release
STATUS - IMPLEMENTED
N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STATUS - REJECTED
DCP 133 | 500 MW network common model for CDCM input | CDCM | 1 | Delveer Johal/ Glenn Sheern | Bethany Hanna | 2012-05-10 | 27 |  | 2015-04-01 | The Authority rejected DCP 133, directing tha the modification not be made.
STATUS - WITHDRAWN
N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A