## Appendix 1 – DCP 209 Working Group Work Plan

| No. | Event | Target Date |
| --- | --- | --- |
|  | Working Group to meet to review the DCP 209 Change Report | - 11 August 2015 |
|  | Submit the draft new Schedule to the DCUSA legal advisor for review | - w/c 10 August 2015 |
|  | Working Group meet to review the DCUSA legal advisors comments on the legal text | - w/c 24 August 2015 |
|  | Update the Change Report pack based on the comments at the DCP 209 Working Group meeting. | - 28 August - 04 September 2015 |
|  | Circulate the Change Report pack to the Working Group for final review | - 04 – 08 September 2015 |
|  | Change Report submitted to DCUSA Panel (Panel paper day) | - 09 September 2015 |
|  | DCUSA Panel approves Change Report | - 16 September 2015 |
|  | Change Report issued for voting | - 18 September 2015 |
|  | Voting Closes | - 09 October 2015 |
|  | Change Declaration issued | - 13 October 2015 |
|  | Ofgem Decision (Key Performance Indicator -25 Days) | - 22 December 2015 |
|  | Implementation Date | - 04 January 2016 |