## Appendix 1 – DCP 160 Working Group Work Plan

| No. | Event | Target Date |
| --- | --- | --- |
|  | The Chair and the Secretariat to draft consultation two for the review of the Working Group on 14 March 2016 | - 14 March 2016 |
|  | Working Group meet to review Consultation two | - 14 March 2016 |
|  | Update consultation two based on Working Group comments | - 17 March 2016 |
|  | DCP 160 Consultation two on the proposed changes to the CDCM model issued to Parties | - 18 March – 08 April 2016 |
|  | Secretariat to collate the consultation responses | - 08 - 16 April 2016 |
|  | Working Group meet to review the consultation responses | - w/c 21 April 2016 |
|  | Working Group review the draft legal text | - 25 – 28 April 2016 |
|  | Legal text issued to the DCUSA legal consultant for review for a period of two weeks | - 29 April – 13 May 2016 |
|  | Electralink to draft Change Report and circulate to proposer to review for one week | - 09 - 14 May 2016 |
|  | Circulate the Wragge & Co. reviewed legal text to Working Group members to review on receipt | - 14 May 2016 |
|  | Working Group meet to review draft Change Report and DCUSA legal consultant comments on the legal text | - w/c 16 May 2016 |
|  | Update the Change Report pack based on the comments at the DCP 160 Working Group meeting. | - 23 - 27 May 2016 |
|  | Circulate the Change Report to the Working Group for final review | - 30 May - 03 June 2016 |
|  | Change Report submitted to DCUSA Panel (Panel paper day) | - 08 June 2016 |
|  | DCUSA Panel approves Change Report | - 15 June 2016 |
|  | Change Report issued for voting | - 17 June 2016 |
|  | Voting Closes | - 08 July 2016 |
|  | Change Declaration issued | - 12 July 2016 |
|  | Ofgem Decision (Key Performance Indicator -25 Days) | - 23 August 2016 |
|  | Implementation Date | - 01 April 2018 |