## Open
CACoP Actions Log
Action Ref. | Action | Owner | Notes | Update
01/01 | All CACoP members to review the contacts section of the CACoP and provide feedback to DCode for them to update | All CACoP members | Open | Not all members had updated DCode on this. Action needs to be completed by Wednesday 04 April 2018.
01/07 | All CACoP members to review the Central Modification Register and ensure that the most recent information has been included. Any amendments should be sent to MRASCo | All CACoP members | Open | The Group agreed that this would need to be an ongoing action
02/01 | Ofgem to update the cover note and draft Principle to reflect the discussions at the meeting. | Ofgem | Open
02/02 | All Code Administrators to present the draft Principle to their respective Code Panels for comment | All CACoP members | Open
02/03 | UNC to lead on the CACoP sub-group to review the reporting template | UNC | Open
02/04 | All CACoP members to present the updated CACoP document to their Code Panels following revisions to Principle 12. | All CACoP members | Open
02/05 | DCUSA to consider the development of a wider communication plan, potentially to include a website | DCUSA | Open
02/06 | CUSC/Grid Code to review the structure and layout of the horizon scan document in advance of the next meeting | CUSC/Grid Code | Open
02/07 | All CACoP members to send any relevant information regarding Panel governance procedures to the UNC | All CACoP members | Open
02/08 | The Secretariat to circulate a work plan for the group | All CACoP members | Open
02/09 | Ofgem to obtain timescales from Future Thinking and let Code Administrators know the final date to submit their contacts for the Customer Survey | Ofgem | Open
02/10 | All CACoP members to feedback their scheduled Release dates and times to allow a common picture to be formed by the MRA. | All CACoP members | Open
02C/01 | SPAA to speak with all CACoP members to compile a list of questions that need answers from the Ofgem EU Exit Group | SPAA | Open

## Closed
CACoP Actions Log
Action Ref. | Action | Owner | Notes | Update
01/02 | Dcode administrator to update the CACoP document to reflect the discussions held and to obtain background information where requested. | DCode | Closed
01/03 | CUSC to chase a query dating back to October on DCP 295 | Mike Oxenham | Closed
01/04 | SEC to share information on SECMP 0041 to all Code Administrators | Talia Addy | Closed
01/05 | All CACoP members to disseminate the information on SECMP 0041 to contract managers | All CACoP members | Closed
01/06 | National Grid to update the horizon scanning document once it has been reviewed by CACoP members | National Grid | Closed
01/08 | DCUSA to produce a proposal for a centralised CACoP website and present it at the next CACoP meeting | Dan Fittock | Closed
01/09 | The BSC representative to contact the Chair if they would like further information on the MAMCoP Change Process under SPAA | Chris Wood | Closed