## Sheet1
DCP 403 Actions Log
Action Ref. | Action | Owner | Notes | Update
1.1 | Working Group to review comments highlighted by SSEG, specific to paragraph 9 and subsection 10 of Ofgems TCR decision document. | All | Open.
1.2 | The working Group will review 389 to see what potential impacts the legal text has. | All | Open.
1.3 | Working Group to review legal text to check if its broad enough to cover DNO/IDNO situations. | All | Open.
1.4 | find the text around the Ofgem TCR decision regarding redundant capacity and respond to the arguemtns made by SSEG in question 3. Also also included responses in the TCR document relating to private networks. | Andy Pace | Open.
1.5 | Working Group will review both DCP 389 and 328 and respond accordingly to the comments made in Q9 of the consulation by ENW | All | Open.
1.6 | Secretairiate to review BEIS licence exception to identify if any impacts after comments made by OPN in Q9 | All | Open.
1.7 | Contact Gowlings abd agree date for them to attend the next WG session | Andy Gree | Clsoed | Gus Wood has confimred he can attend 5th October at 10am. Invite issued.
1.8 | Secretairiate to review BEIS licence exception to identify if any impacts after comments made by OPN in Q9 | John Lawton | Open.