## Sheet1
DCP 403 Actions Log
Action Ref. | Issue Identified | Action | Consultaiton question | Owner | Notes | Update
1.1 | What does paragraph 9 subsection 10 of Ofgems TCR document mean? | Working Group to review comments highlighted by SSEG, specific to paragraph 9 and subsection 10 of Ofgems TCR decision document. | 2 | All | Open. | 05-10-22 SM to clarify paragragp 3,57 (10) SM to also clarify the use of the word ''consumption' in paragraph 3.57 (9) and what this means.
1.2 | Does this change impact DCP 389 or vice versa? | The working Group will review 389 to see what potential impacts the legal text has. | 9 | All | Closed. | Working Group review DCP 389 and believe it does not impact DCP 403
1.3 | Is the legal text broad enough to cover DNO/IDNO situations. | Working Group to review legal text to check if its broad enough to cover DNO/IDNO situations. | 3 | All | Closed. | The residual charge is applied to the DNOs boundry charge for IDNO connections at EHV so will still be built into the end customers charge. For LV and HV customers the IDNO replicates the DNOs charges including the residual. The legal text will indicte sufficeient evidance will be provided and where such instences occur disccusion between the DNO and INDO will need to take place as one will be charging and the other not.
1.5 | Does this change impact DCP328 or 389? | Working Group will review both DCP 389 and 328 and respond accordingly to the comments made in Q9 of the consulation by ENW | 3 | All | Closed. | The Working Group do not believe there is an impact on DCP 389 and DCP 328 after reviewing the legal text.
1.6+A7:G9 | Review BEIS licence exception to identify if any impacts. | Secretairiate to review BEIS licence exception to identify if any impacts after comments made by OPN in Q9 | 9 | All | Closed. | Based on what the BEIS licence exemption is reviewing (insert link) the Working Group concluded that it will not impact this change.
1.7 | Invite legal rep to next call | Contact Gowlings abd agree date for them to attend the next WG session | N/A | Andy Green | Clsoed | Gus Wood has confimred he can attend 5th October at 10am. Invite issued.
1.8 | GW to redraft legal text and secretatirat to share | Gus to redraft the legal text and Andy to share woith the Working Group | N/A | Andy Green | Clsoed | Gus has provided and Andy Shared