## JL Status Report
Programme reference number | Title | Process change | Status | Legal text Delivery to the Programme | Comment
DCUSA Panel Meeting
CCIAG-CCT-32 | Demand Control | Schedule 8 | Red | Unknown. | Solution not yet known. Discussions have been held with the REC over SSC and TPR ownership and whether DCUSA could benefit.
Next Stakeholder meeting 11/07/23
CCIAG-CCT-33 | Charging Methodology | Schedule 16 | Green | Draft to be merged with the Housekeeping changes prior to DCUSA Ltd sign off | Additional requirement identified relating to energised sites and to determine the MPAN count (15/06/23). Legal text agreed and document updated.
CCIAG-CCT-34 | Residual Charges | Schedule 32 | Green | Draft to be merged with the Housekeeping changes prior to DCUSA Ltd sign off
CCIAG-CCT-35 | Remove legal text owned by another code | Clause 25 | N/A | This is not required. Using the programme design artifacts since the clauses are affected by both. | closed
CCIAG-CCT-36 | Billing and Invoicing DCP415 | Definitions | Green | Programme CR 19 approved for DCP415. | Design artifacts to be release on 02 August 2023.
Clause 19
|  | Clause 21 |  | Once design released legal text can be updated if needed and merged with the housekeeping changes prior to DCUSA Ltd sign off.
Schedule 16
Schedule 19
Schedule 21
| Billing and Invoicing | Clause 20 | Amber | Solution developed; Programme change raised (CR29); | October release by the Programme at the latest see note 3 below.
CCIAG-CCT-36 | DCP416 | Clause 21 |  | Discussed at the Programme Change Board on the 11/07/23. Next step is the DAG later this month.
Clause 22
CCIAG-CCT-37 | Transitional protection for CT customers transitioning to HH settlement (DCP414) | Clause 19 | N/A | To be delivered under DCUSA. No impact on the MHHS design. | Housekeeping Changes will need to be made to the schedule Part 4 if the Authority have not determined the outcome of the change by the time the legal text needs to be delivered to the Programme in October.
|  | Schedule 16 |  | Part vote to accept. Awaiting Authority approval
It is hoped that a decision is made alongside BSC P432 at the end of July 2023.
Note:
1) I am classifying the DCUSA changes under two types:
· Housekeeping changes due to the e.g. removal of text no longer valid line Data Collector and replace with Data Services
· Consequential changes i.e. changes that need to be considered where there in no replacement and the ownership is with DCUSA e.g. a decision to create a new flow since the format of the of the old flow no longer fit for purpose.
2) The Panel agreed at their June meeting that they would prefer all impacted changes due to the MHHS SCR to be in one document i.e both Housekeeping and Consequential changes.
3) Current plan is to aim for the Transition tranche. The risks to this are the delivery of CR29 and the limited time to check impact from the interface trance which is to be delivered at the same time.

## Timetable
DCUSA Consequential Code Drafting Plan |  |  | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-28 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30
DCUSA Panel Meetings |  |  | 2023-07-24: 19th; 2023-08-14: 16th; 2023-09-18: 2023-09-20; 2023-10-16: 18th
DCUSA Next Stakeholder Meetings |  |  | 2023-07-10: 11th
CCIAG-CT-32 - Demand Control | bar: 2023-07-03 to 2023-07-31; 2023-08-14
CCIAG-CT-33 - Charging Methodology |  |  | 2023-07-03: completed
CCIAG-CT-34 - Residual Charges |  |  | 2023-07-03: completed
CCIAG-CT-35 - legal text owned by another code - Not required | bar: 2023-08-14
CCIAG-CT-36 |  | Two Programme CRs required | bar: 2023-08-14
| DCP415 | CR19 - DIN release August | 2023-08-14: 2nd
| DCP416 | CR27 - | 2023-07-10: 12th DAG; 2023-07-24: 27th - IA; 2023-10-02: 4th?
CR27 - DIN Release Oct? | bar: 2023-08-14
CCIAG-CT-37 - (DCP414 has no impact on design) - Not required | bar: 2023-08-14
DCP414 Authority Approval Decision |  |  | 2023-07-31: End of July
DIN Interim Releases |  |  | 2023-08-14: 2nd; 2023-08-28: 30th; 2023-10-02: 4th
DCUSA Legal Text | bar: 2023-08-14
Programme Housekeeping impact | bar: 2023-07-03 to 2023-08-14
Consequential change impact | bar: 2023-07-03 to 2023-08-14
DCUSA Stakeholder review | bar: 2023-07-31; 2023-08-14
DCUSA Panel sign off |  |  | 2023-08-14: 16th; 2023-08-28: special Panel meeting
Release to programme |  |  | 2023-09-11: 12th
CDWG legal text and slide pack |  |  | 2023-09-18: 19th CDWG
Programme consultation | bar: 2023-08-14
MHHS Programme Release Tranches | bar: 2023-08-14
CDWG metings |  |  | 2023-07-10: 11th; 2023-07-17: 19th; 2023-08-07: 8th; 2023-08-14: 15th
Governance, Qualiifcation and Migration Consultations |  |  | 2023-08-14: 18th
Interface and Transitional Text Consultations |  |  | 2023-10-09: 11th
Consquential Code Drop |  |  | 2023-10-16: 16th