## CPs
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status Changed in the last month | Date Issued to Ofgem | Original Expected Decision Date | Latest Expected Decision Date
STATUS - INITIAL ASSESSMENT
No
STATUS - DEFINITION
DCP 325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20. | The intent of this Change Proposal is to combine, review and if appropriate, amend the requirements of Section 35A, Section 35B, Schedule 15 and Schedule 20 to improve transparency and efficiency in the data published by DNOs | General | 2 | Richard Colwill / Melissa Kendal | N/A | 2018-11-07 | 11 | No | Next scheduled release following approval | The Working Group is currently developing a consultation to be issued in August. | N/A
DCP 371 | Last resort arrangements for Distributors to manage specific consumer connected devices | The intent of this Change Proposal seeks to provide the governance arrangements regarding Distributors ability to manage consumer devices (such as EV chargers) connected to Smart Meter infrastructure to prevent network overloads in emergency scenarios as a last resort measure | General | 1 | Richard Colwill / George Dawson | N/A | 2020-07-15 | 3 | No | First release following approval | The proposer has been in contact and it is very likely this CP will be withdrawn. They are just waiting for formal cofirmation internally. | N/A
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | The intent of this modification is to define “Mixed Demand” Sites and apply a proportionate Residual charge where a Site meets the mixed demand definition. | General | 1 | John Lawton / Andy Green | Marlon Mcdonald | 2021-04-14 | 15 | No | TBC | The Working Group met on 13 July and agreed a final set of actions to be completed by 24 July so the consultation could be sent. The Working Group agreed to issue the 2nd consultation to industry on 02 August with a closing date of 31 August | CONSULTATION
DCP 412 | Discounts from TCR charges for ‘peaky’ final demand customers | This Change Proposal aims to create a discount against the residual charge for ‘peaky’ customers, removing the disproportionate impact of allocating residual charges on the basis of the Agreed Supply Capacity. | CDCM / EDCM | 1 | Andy Green / Craig Booth | Marlon McDonald | 2022-10-11 | 17 | No | TBC | The Working Group has issued the first of two consultations, after agreeing by majority vote that a single consultation would have been overly complex. Work on the second consultation continues whilst the first consultation is with industry. | CONSULTATION
DCP 415 | Replacement of D0242/D0315 for MHHS | To create a new DCUSA owned DIP data message for supercustomer billing statements using MHHS data. | Billing | 2 | Hannah Proffitt / Craig Booth | N/A | 10/22/2022 | 3 | No | TBC (dependent on date required for DIP testing) | The Change Report was submitted to the Panel for review in the February Panel meeting. The Panel agreed that it would not progress to Party voting and that it should be sent back to the Working Group but that the Working Group won’t need to meet until the MHHS Programme have been able to carry out an Impact Assessment for the solution they developed. It was noted that even then, no further work may be required but that it was too early to know that for sure. | N/A
DCP 416 | Electronic Invoicing Post MHHS | To create a new DCUSA owned DIP data message for electronic Distributor billing post MHHS. | Billing | 2 | Melissa Kendal / Andy Green | N/A | 2022-11-14 | 5 | No | TBC (dependent on date required for DIP testing) | The Working Group have reviewed the consultation responses and met on 23 June 2023 to finalise the conclusions to the second consultation. A decision on whether or not a Change Report is to be produced is to be made by the Panel but the Proposer has initated a MHHS Change Request for the CP to be impact assessed and so it is expected that DCP 416 will be put on hold, pending outcome of the MHHS Change Request. | N/A
DCP 417 | Ability for the DCUSA Secretariat to Raise Change Proposals | This change seeks to grant the ability to the Secretariat to raise Change Proposals where it identifies a change that would better facilitate the DCUSA Objectives and to introduce an obligation for the Secretariat to raise Change Proposals in certain circumstances, such as at the direction of the Authority. | General | 1 | Melissa Kendal / Richard Colwill | Nadir Hafeez | 2022-12-14 | 6 | No | Next scheduled release following approval | The Working Group issued a consultation on 05 May to seek feedback on their proposed solution. DCP 417 WG 11 was held on 13 June 2023 to review and discuss the Consultation responses – based on the responses, the Working Group agreed that an alternate solution was needed and agreed for a second Consultation to be issued shortly. | N/A
DCP 419 | Pre-Notifications of Planned Supply De-Energisations | This change seeks to ensure that all DCUSA Parties, that de-energise metering equipment as part of any planned work, provide the Distributor with advance notification of the supply interruption. | General | 1 | Alysson Pena / | TBC | 2023-03-06 | 4 | No | Next scheduled release following approval | The Working Group issued a consultation on 28 June with responses due by 19 July. A meeting was held on 08 August to review resposnes and a further meeting has been scheduled for 22 August to continue review of the consultation responses and to determine next steps. | N/A
DCP 420 | Include Car Charging Stations In The Definition For Non Final Demand | This change proposal aims to expand the definition of Non Final Demand to include Non Domestic sites which are solely for the use of charging vehicles where electricity is sold with a commercial transaction to a private user. These are to include e.g. Council run services, electric charging stations at car parks and service stations or petrol forecourts but are not to include private fleet charging stations. This is a temporary fix to be put in place until the charging stations included are commercially viable. | General | 1 | Craig Booth / Richard Colwill | TBC | 2023-03-29 | 2 | No | - | The Working Group is to issue an RFI shortly to further explore the issue being raised. The next meeting is scheduled for 14 September. | N/A
DCP 421 | Update the Tables in schedule 15 of DCUSA | To amend the current tables within Schedule 15 of DCUSA to correctly represent ED2 revenue. | General | 2 | Craig Booth / Andy Green | N/A | 2023-04-12 | 2 | No | Next scheduled release following approval | The Working Group have met twice since the last panel meeting. A consultation has been drafted with the intention of issuing to industry on 11 August 2023 | N/A
DCP 423 | LDNO Discounts for negative scaling | The purpose of this change proposal is to set a floor on the LDNO discount applied to negative tariff components, after scaling, for demand tariffs. The intent of this change proposal is to seek to remedy what the proposer believes is an unintended outcome of the implementation of Ofgem’s Targeted Charging Review where LDNO tariffs can be higher than the equivalent all-the-way tariff i.e. the LDNO margin is negative for that component. | CDCM | 1 | Melissa Kendal / Andy Green | TBC | 2023-05-09 | 1 | No | 2025-04-01 | The initial meeting for the Working Group took place on 02 August. A series of consultation questions were agreed. A new meeting will be agreed by Doodle Poll once the agreed actions have been completed by the Working Group | N/A
DCP 424 | Use of System charging for complex sites | This change proposal enables the correct DUoS to be paid by meters that are class F or G within a Class 5 or Class 6 Complex Site as described in BSC Modification P441 (where netting of Import and Export takes place for BSC Settlement purposes) in a practical manner. Under p441 where generation and demand are netted before settlement, the gross values must be added to the D0036 or D0275 to ensure the correct DUoS is charged. However, for class F and G the MPAN counts are included on the D0030 data flows but the volumes are zero. In order for the volumes to be correctly charged DUoS it is proposed that these volumes are included in the D0036 or D0275 using a pseudo MPAN for the gross value. | CDCM | 1 | Andy Green / Craig Booth | TBC | 2023-05-10 | 2 | No | Aligned to BSC Mod P441 Implementation Date | The Working Group have meet twice since the last panel session and a 3rd meeting has been agreed to take place on 11 August where it is hoped the solution can be agreed upon and a consultation drafted | N/A
STATUS - CHANGE REPORT
N/A | N/A | [7 empty] | No |  |  | N/A
STATUS - VOTING
N/A | N/A | [7 empty] | No |  |  | N/A
STATUS - AWAITING AUTHORITY CONSENT
DCP 343 | Use of a nominated calculation agent for the calculation of the LV mains split | This CP seeks to remove the need for the procurement of a nominated calculation agent for the purpose of calculating the ‘LV mains split’ and to make minor associated housekeeping changes. | General | 2 | Hollie Nicholls / Angelo Fitzhenry | Ankita Mehra | 2019-12-02 | 3 | No | First release following approval | A Working Group was formed to develop DCP 343 and following a consultation a final solution was agreed. The Working Group submitted their Change Report to the August Panel meeting, where it was approved to be issued for voting. The Change Report was issued for voting on 23 August 2019 with voting ending on 16 September 2019. A Change Declaration has been submitted to the Authority with a recommendation from Parties to reject the change on 18 September 2019. | N/A | 2019-09-18 | 2019-10-23 | 2023-07-31
DCP 392 | Charging of Third Party DNO works to transmission connection users. | To apply the common connection charging method (CCCM) to all electricity connections in respect of DNO works, regardless of whether they are directly connected to a distribution system or not, and to apply the equivalent of the Electricity (Connection Charges) Regulations (ECCR) for reimbursement to the transmission-connected customer where cost apportionment factor (CAF) rules do not apply so that full charge for works is initially made to the transmission connected customer. | CCCM | 1 | Hannah Proffitt / John Lawton | Dafydd Burton | 2021-12-07 | 16 | No | Next scheduled release or within one month of Authority Consent | Voting closed on 14 November 2022 and a Change Declaration was issued to the Authority on 18 November 2022 with a recommendation from Parties to reject DCP 392. | N/A | 18 November 2022 | 2023-04-01 | 2023-07-27
DCP 413 | Value of a User’s Credit Allowance in Schedule 1 | To ensure the User’s Credit Allowance better reflects the risk. | Cover | 1 | Hannah Proffitt / Andy Green | TBC | 2022-09-27 | 5 | No | 2023-03-01 | The DCP 413 consultation was issued to industry on 09 December. The Working Group met on 01 February to review responses and a number of actions were taken away to fully understand how independent credit assessments work across other codes and the Working Group agreed to meet on 22 February 2023 to review the findings from these actions and to finalise the Change Report and legal drafting. The Change Report was issued to the April Panel meeting, where the Panel approved for the Change Report to be issued for voting. A Change Declaration was issued on 19 May confirming that for DCP 413, DCUSA Parties’ have voted and recommend to the Authority to determine that the proposed solution is rejected, and the proposed implementation date is accepted. | N/A | 2023-05-19 | TBC | TBC
DCP 411 | Charging De-energised sites | To remove the different treatment of DUoS with respect to de-energised sites | CDCM | 1 | Andy Green / Craig Booth | TBC | 2022-07-13 | 11 | No | 2025-04-01 | The Change Report was issued following approval during the May Panel meeting. Voting has concluded, with the change declaration issued to Ofgem on 14/06/2023. | N/A | 2023-06-14 | 2023-11-30 | 2023-11-30
STATUS - AWAITING IMPLEMENTATION
2024-04-01
DCP 395 | Allocation of Smart Meter Communication Licence costs within LDNO Tariffs | To increase the cost reflectivity of LDNO tariffs by appropriately allocating costs associated with the smart meter communication licence to LDNO tariffs | General | 1 | John Lawton / George Dawson |  | 2021-05-10 | 3 | No | 2024-04-01 | The DCP 395 Working Group issued a consultation to industry in March 2022, with responses due by 12 April. The Working Group met on 25 April to review the consultation responses and agreed the final solution. The Change Report was presented to the Panel during the May Panel meeting, where it was approved to be issued for Party voting. | N/A
DCP 414 | Transitional Protection for NHH CT Customers affected by regulatory change | This change proposal seeks to provide transitional protection for Non Half-Hourly Current Transformer customers moving to Half-Hourly settlement & prevent penal excess capacity charges being applied to customers in any instance that the Maximum Import Capacity is a zero value because there is no site-specific connection agreement in place between users & Distribution Network Operators. | General | 1 | Andy Green / John Lawton | Danielle Walton | 2022-10-18 | 8 | No | 29 June 2023 or April 2024 | The Change Report was issued following last month’s Panel meeting and voting has concluded, with the change declaration issued on 14/06/2023. | AWAITING IMPLEMENTATION | 2023-06-14 | 2023-07-31 | 2023-07-31
STATUS - SENT BACK
N/A | N/A | [7 empty] | No |  |  | N/A
STATUS - IMPLEMENTED
DCP 422 | Access SCR clarifications and corrections | To make clarifications and corrections to the legal text developed to implement Ofgem’s Access SCR direction | CCCM | 2 | Melissa Kendal / Richard Colwill | N/A | 2023-05-05 | 1 | No | 2023-08-01 | DCP 422 was submitted to the Panel in May for initial assessment. The Panel agreed for the CP to enter the change process and a Working Group was set up to revuew the proposed solution. The Change Report was presented to the Panel during the June meeting, where it was agreed to be issued for Party voting. The result of the Party vote was that DCP 422 be implemented. | IMPLEMENTED
STATUS - REJECTED
DCP 328 | Use of system charging for private networks with competition in supply | The intent of this change is to ensure that use of system charging remains cost-reflective when competition in supply on a private network is in place. | CDCM / EDCM | 1 | Richard Colwill / John Lawton | Olivia Powis | 2018-08-15 | 39 | No | Next scheduled release following approval | The DCP 328 Change Report was issued to DCUSA Parties for voting on 10 October 2022 for a period of 15 Working Days. DCUSA Parties have voted on DCP 328 and the overall recommendation, in accordance with Clause 13.5 of the DCUSA, is that the Change Proposal be rejected. As DCP 328 was raised as a Part 1 Matter, it was subsequently issued to the Authority for their decision. | REJECTED | 01 November 2022 | 2023-03-21 | 2023-07-11
STATUS - WITHDRAWN
N/A | N/A | [7 empty] | No |  |  | N/A
Change Register - August 2023

## Status Change
AWAITING IMPLEMENTATION
IMPLEMENTED
REJECTED
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status Changed in the last month | DEFINITION
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | The intent of this modification is to define “Mixed Demand” Sites and apply a proportionate Residual charge where a Site meets the mixed demand definition. | General | 1 | John Lawton / Andy Green | Marlon Mcdonald | 2021-04-14 | 15 | No | TBC | The Working Group met on 13 July and agreed a final set of actions to be completed by 24 July so the consultation could be sent. The Working Group agreed to issue the 2nd consultation to industry on 02 August with a closing date of 31 August | CONSULTATION | CONSULTATION
DCP 412 | Discounts from TCR charges for ‘peaky’ final demand customers | This Change Proposal aims to create a discount against the residual charge for ‘peaky’ customers, removing the disproportionate impact of allocating residual charges on the basis of the Agreed Supply Capacity. | CDCM / EDCM | 1 | Andy Green / Craig Booth | Marlon McDonald | 2022-10-11 | 17 | No | TBC | The Working Group has issued the first of two consultations, after agreeing by majority vote that a single consultation would have been overly complex. Work on the second consultation continues whilst the first consultation is with industry. | CONSULTATION | AWAITING AUTHORITY CONSENT
DCP 414 | Transitional Protection for NHH CT Customers affected by regulatory change | This change proposal seeks to provide transitional protection for Non Half-Hourly Current Transformer customers moving to Half-Hourly settlement & prevent penal excess capacity charges being applied to customers in any instance that the Maximum Import Capacity is a zero value because there is no site-specific connection agreement in place between users & Distribution Network Operators. | General | 1 | Andy Green / John Lawton | Danielle Walton | 2022-10-18 | 8 | No | 29 June 2023 or April 2024 | The Change Report was issued following last month’s Panel meeting and voting has concluded, with the change declaration issued on 14/06/2023. | AWAITING IMPLEMENTATION | AWAITING IMPLEMENTATION
DCP 422 | Access SCR clarifications and corrections | To make clarifications and corrections to the legal text developed to implement Ofgem’s Access SCR direction | CCCM | 2 | Melissa Kendal / Richard Colwill | N/A | 2023-05-05 | 1 | No | 2023-08-01 | DCP 422 was submitted to the Panel in May for initial assessment. The Panel agreed for the CP to enter the change process and a Working Group was set up to revuew the proposed solution. The Change Report was presented to the Panel during the June meeting, where it was agreed to be issued for Party voting. The result of the Party vote was that DCP 422 be implemented. | IMPLEMENTED | VOTING
DCP 328 | Use of system charging for private networks with competition in supply | The intent of this change is to ensure that use of system charging remains cost-reflective when competition in supply on a private network is in place. | CDCM / EDCM | 1 | Richard Colwill / John Lawton | Olivia Powis | 2018-08-15 | 39 | No | Next scheduled release following approval | The DCP 328 Change Report was issued to DCUSA Parties for voting on 10 October 2022 for a period of 15 Working Days. DCUSA Parties have voted on DCP 328 and the overall recommendation, in accordance with Clause 13.5 of the DCUSA, is that the Change Proposal be rejected. As DCP 328 was raised as a Part 1 Matter, it was subsequently issued to the Authority for their decision. | REJECTED | CHANGE REPORT
Status Change - August 2023

## Timetables
DCP | Title | Part 1/ Part 2 Matter | Standard/ Urgent | Proposer | Party | Technical Secretariat | Chair | Timetable Change | [6 empty] | 2024 | [11 empty] | Notes
[9 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
424 | Use of System charging for complex sites | Part 1 | Standard | Mary Gillie | NPg | Andy Green | Craig Booth | No | Jul: Def; Aug: CON; Sep: Def; Oct: CR; Nov: CD; Dec: WO
423 | LDNO Discounts for negative scaling | Part 1 | Standard | Tom Cadge | ENC | Melissa Kendall | Andy Green | No | Jul: Def; Aug: CON; Sep: Def; Oct: CR; Nov: CD; Dec: WO
421 | Update the Tables in schedule 15 of DCUSA | Part 1 | Standard | Dave Wornell | NGED | Craig Booth | Andy Green | No | Jul: Def; Aug: CON; Sep: Def; Oct: CR; Nov: CD; Dec: WO
420 | Include Car Charging Stations In The Definition For Non Final Demand | Part 1 | Standard | Dave Wornell | NGED | Craig Booth | Richard Colwill | No | Def | RFI | CON | Def | CR | CD | WO
419 | Pre-notification of Planned Supply De-energisations | Part 1 | Standard | Nikhel Jethwa | SSEN | Alysson Pena | Richard Colwill | No | Def | Def | CR | CD | WO
417 | Ability for the DCUSA Secretariat to Raise Change Proposals | Part 1 | Standard | Simon Yeo | NGED | Melissa Kendall | Richard Colwill | No | Def | CON | Def | CR | CD | WO
416 | Electronic Invoicing Post MHHS | Part 2 | Standard | Peter Waymont | UKPN | Craig Booth | Andy Green | No: No; Def: O/H
415 | Replacement of D0242/D0315 for MHHS | Part 2 | Standard | Peter Waymont | UKPN | Melissa Kendall | Craig Booth | No: No; Def: O/H
412 | Discounts from TCR charges for ‘peaky’ final demand customers | Part 1 | Standard | Lee Stone | E.ON | Andy Green | Craig Booth | No | Def | CON | Def | CR | CD | WO
Proposed new timetable for DCP 412 'Discounts from TCR charges for ‘peaky’ final demand customers' | [8 empty] | Def | CON | CON | Def | CR | CD | WO | [11 empty] | The Working Group has issued the first of two consultations, after agreeing by majority vote that a single consultation would have been overly complex. Work on the second consultation continues whilst the first consultation is with industry.
388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | Part 1 | Standard | Lee Stone | E.on | Andy Green | John Lawton | No | CON | Def | CR | CD | WO
Proposed new timetable for DCP 388 'Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand' | [8 empty] | Def | CON | Def | CR | CD | WO | [12 empty] | The aim was to issue out on consultaion in July but due to being more complex than expected and to provide time to review the timetable has been moved back a month.
371 | Last resort arrangements for Distributors to manage specific consumer connected devices | Part 1 | Standard | Tom Cadge | SSEN |  | Richard Colwill | No: No; Def: O/H
325 | Reviewing the requirements of Sections 35A (‘Provision of Cost Information’), 35B (‘Production of the Annual Review Pack’), Schedule 15 (‘Cost Information Table’) and Schedule 20 (‘Production of the Annual Review Pack’) | Part 1 | Standard | Kara Burke | NPg | Melissa Kendall | Richard Colwill | No | CON | Def | CR | CD | WO
Proposed new timetable 'Table’) and Schedule 20 (‘Production of the Annual Review Pack’)' | [8 empty] | Def | CON | Def | CR | CD | WO | [12 empty] | DCP 421 is looking at something similar and we believe it is best to wait until the consultations for DCP 421 is completed before issuing out DCP 388 consultation.
Key
Definition | Def
RFI | RFI
Consultation | CON
Change Report | CR
Voting/ Change Declaration | CD
With Ofgem | WO
Implementation | Imp
Decision | Dec
Withdrwan | Wd

## Legal Text Overlap Tracker
YES
|  | MHHS | DCP 343 | DCP 424 | DCP 325 | DCP 421 | DCP 423 | DCP 395 | DCP 414
|  | Unknown | Next Scheduled | 2024-04-01 | Next Scheduled | Next Scheduled | 2025-04-01 | 2024-04-01 | 2024-04-01 |  | NOTES TO ASSIST
Schedules | Paragraph Number |  | Awaiting Authority Consent | Definition | Definition | Definition | Definition | Awaiting Implementation | Awaiting Implementation | Number of CPs Impacting Paragraph
Schedule 15 | Table 1 |  |  |  | YES | YES |  |  |  | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 2 |  |  |  | YES | YES |  |  |  | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 3 |  |  |  | YES |  |  |  |  | 1
0
Schedule 16 | Introduction | [8 empty] | 0
Schedule 16 | 1 | [8 empty] | 0
Schedule 16 | 2 | [8 empty] | 0
Schedule 16 | 3 | [8 empty] | 0 | Model reference number and date
Schedule 16 | 4 | [8 empty] | 0
Schedule 16 | 5 | [8 empty] | 0
Schedule 16 | 6 | [8 empty] | 0
Schedule 16 | 7 | [8 empty] | 0
Schedule 16 | 7A | [8 empty] | 0
Schedule 16 | 8 | [8 empty] | 0
Schedule 16 | 9 | [8 empty] | 0
Schedule 16 | 10 | [8 empty] | 0
Schedule 16 | 10A | [8 empty] | 0
Schedule 16 | 11 | [8 empty] | 0
Schedule 16 | 12 | [8 empty] | 0
Schedule 16 | 13 | [8 empty] | 0
Schedule 16 | 14 | [8 empty] | 0
Schedule 16 | 15 | [8 empty] | 0
Schedule 16 | 16 | [8 empty] | 0
Schedule 16 | 17 | [8 empty] | 0
Schedule 16 | 18 | [8 empty] | 0
Schedule 16 | 19 | [8 empty] | 0
Schedule 16 | 20 | [8 empty] | 0
Schedule 16 | 21 | [8 empty] | 0
Schedule 16 | 22 | [8 empty] | 0
Schedule 16 | 23 | [8 empty] | 0
Schedule 16 | 24 | [8 empty] | 0
Schedule 16 | 25 | [8 empty] | 0
Schedule 16 | 26 | [8 empty] | 0
Schedule 16 | 27 | [8 empty] | 0
Schedule 16 | 28 | [8 empty] | 0
Schedule 16 | 29 | [8 empty] | 0
Schedule 16 | 30 | [8 empty] | 0
Schedule 16 | 31 | [8 empty] | 0
Schedule 16 | 32 | [8 empty] | 0
Schedule 16 | 33 | [8 empty] | 0
Schedule 16 | 34 | [8 empty] | 0
Schedule 16 | 35 | [8 empty] | 0
Schedule 16 | 36 | [8 empty] | 0
Schedule 16 | 37 | [8 empty] | 0
Schedule 16 | 38 | [8 empty] | 0
Schedule 16 | 39 | [8 empty] | 0
Schedule 16 | 40 | [8 empty] | 0
Schedule 16 | 41 | [8 empty] | 0
Schedule 16 | 41A | [8 empty] | 0
Schedule 16 | 41B | [8 empty] | 0
Schedule 16 | 42 | [8 empty] | 0
Schedule 16 | 42A | YES | [7 empty] | 1
Schedule 16 | 43 | [8 empty] | 0
Schedule 16 | 44 | YES | [7 empty] | 1
Schedule 16 | 45 | [8 empty] | 0
Schedule 16 | 46 | [8 empty] | 0
Schedule 16 | 47 | [8 empty] | 0
Schedule 16 | 48 | [8 empty] | 0
Schedule 16 | 49 | [8 empty] | 0
Schedule 16 | 50 | [8 empty] | 0
Schedule 16 | 51 | [8 empty] | 0
Schedule 16 | 52 | [7 empty] | YES | 1
Schedule 16 | 52A | [7 empty] | YES | 1
Schedule 16 | 53 | [8 empty] | 0
Schedule 16 | 54 | [8 empty] | 0
Schedule 16 | 55 | [8 empty] | 0
Schedule 16 | 56 | [8 empty] | 0
Schedule 16 | 57 | [8 empty] | 0
Schedule 16 | 58 | [8 empty] | 0
Schedule 16 | 59 | [8 empty] | 0
Schedule 16 | 60 | [8 empty] | 0
Schedule 16 | 61 | [8 empty] | 0
Schedule 16 | 62 | [8 empty] | 0
Schedule 16 | 63 | [8 empty] | 0
Schedule 16 | 64 | [8 empty] | 0
Schedule 16 | 65 | [8 empty] | 0
Schedule 16 | 66 | [8 empty] | 0
Schedule 16 | 67 | [8 empty] | 0
Schedule 16 | 68 | [8 empty] | 0
Schedule 16 | 69 | [8 empty] | 0
Schedule 16 | 70 | YES | [7 empty] | 1
Schedule 16 | 71 | [8 empty] | 0
Schedule 16 | 72 | [8 empty] | 0
Schedule 16 | 72A | [8 empty] | 0
Schedule 16 | 73 | [8 empty] | 0
Schedule 16 | 74 | [7 empty] | YES | 1
Schedule 16 | 75 | [8 empty] | 0
Schedule 16 | 76 | [8 empty] | 0
Schedule 16 | 77 | [8 empty] | 0
Schedule 16 | 78 | [8 empty] | 0
Schedule 16 | 79 | [8 empty] | 0
Schedule 16 | 80 | YES | [6 empty] | YES | 2
Schedule 16 | 81 | [8 empty] | 0
Schedule 16 | 82 | [8 empty] | 0
Schedule 16 | 83 | [7 empty] | YES | 1
Schedule 16 | 84 | [8 empty] | 0
Schedule 16 | 85 | [8 empty] | 0
Schedule 16 | 86 | [8 empty] | 0
Schedule 16 | 87 | [8 empty] | 0
Schedule 16 | 88 | [8 empty] | 0
Schedule 16 | 89 | [8 empty] | 0
Schedule 16 | 90 | [8 empty] | 0
Schedule 16 | 91 | [8 empty] | 0
Schedule 16 | 92 | [8 empty] | 0
Schedule 16 | 92A | [8 empty] | 0
Schedule 16 | 92B | [8 empty] | 0
Schedule 16 | 92C | [8 empty] | 0
Schedule 16 | 93 | [8 empty] | 0
Schedule 16 | 94 | [8 empty] | 0
Schedule 16 | 95 | [8 empty] | 0
Schedule 16 | 96 | [8 empty] | 0
Schedule 16 | 97 | [8 empty] | 0
Schedule 16 | 98 | [5 empty] | YES |  |  | 1
Schedule 16 | 99 | [8 empty] | 0
Schedule 16 | 100 | [8 empty] | 0
Schedule 16 | 101 | [7 empty] | YES | 1
Schedule 16 | 102 | [8 empty] | 0
Schedule 16 | 102A | [8 empty] | 0
Schedule 16 | 102B | [8 empty] | 0
Schedule 16 | 103 | [8 empty] | 0
Schedule 16 | 104 | [8 empty] | 0
Schedule 16 | 105 | [8 empty] | 0
Schedule 16 | 106 | [8 empty] | 0
Schedule 16 | 107 | [8 empty] | 0
Schedule 16 | 108 | [8 empty] | 0
Schedule 16 | 108A | [8 empty] | 0
Schedule 16 | 109 | [8 empty] | 0
Schedule 16 | 110 | [8 empty] | 0
Schedule 16 | 111 | [8 empty] | 0
Schedule 16 | 112 | [8 empty] | 0
Schedule 16 | 112A | [8 empty] | 0
Schedule 16 | 113 | [8 empty] | 0
Schedule 16 | 113A | [8 empty] | 0
Schedule 16 | 113B | [8 empty] | 0
Schedule 16 | 113C | [8 empty] | 0
Schedule 16 | 113D | [8 empty] | 0
Schedule 16 | 113E | [8 empty] | 0
Schedule 16 | 114 | [8 empty] | 0
Schedule 16 | 115 | [8 empty] | 0
Schedule 16 | 116 | [8 empty] | 0
Schedule 16 | 117 | [8 empty] | 0
Schedule 16 | 118 | [8 empty] | 0
Schedule 16 | 119 | [8 empty] | 0
Schedule 16 | 120 | [8 empty] | 0
Schedule 16 | 121 | [8 empty] | 0
Schedule 16 | 122 | [8 empty] | 0
Schedule 16 | 123 | [8 empty] | 0
Schedule 16 | 124 | [8 empty] | 0
Schedule 16 | 125 | [8 empty] | 0
Schedule 16 | 126 | [8 empty] | 0
Schedule 16 | 127 | [8 empty] | 0
Schedule 16 | 127A | [8 empty] | 0
Schedule 16 | 128 | YES |  | YES | [5 empty] | 2
Schedule 16 | 129 | YES | [7 empty] | 1
Schedule 16 | 130 | YES | [7 empty] | 1
Schedule 16 | 131 | [8 empty] | 0
Schedule 16 | 132 | YES | [7 empty] | 1
Schedule 16 | 132A | [8 empty] | 0
Schedule 16 | 132B | [8 empty] | 0
Schedule 16 | 132C | YES | [6 empty] | YES | 2
Schedule 16 | 132D | [8 empty] | 0
Schedule 16 | 133 | YES | [7 empty] | 1
Schedule 16 | 134 | [7 empty] | YES | 1
Schedule 16 | 135 | [8 empty] | 0
Schedule 16 | 135A | YES | [6 empty] | YES | 2 | DCP 414 adds two new rows to table for tariffs named 'Domestic Aggregated or CT' and 'Non-Domestic Aggregated or CT' whereas, for MHHS it is proposed to remove the last column containing applicable MC
Schedule 16 | 135B | [8 empty] | 0
Schedule 16 | 136 | [7 empty] | YES | 1
Schedule 16 | 137 | [8 empty] | 0
Schedule 16 | 138 | [8 empty] | 0
Schedule 16 | 139 | [8 empty] | 0
Schedule 16 | 140 | [8 empty] | 0
Schedule 16 | 140A | YES | [7 empty] | 1
Schedule 16 | 140B | YES | [7 empty] | 1
Schedule 16 | 140C | YES | [7 empty] | 1
Schedule 16 | 140D | [8 empty] | 0
Schedule 16 | 140E | [8 empty] | 0
Schedule 16 | 141 | [7 empty] | YES | 1
Schedule 16 | 142 | YES | [7 empty] | 1
Schedule 16 | 143 | YES | [7 empty] | 1
Schedule 16 | 144 | YES | [7 empty] | 1
Schedule 16 | 145 | [8 empty] | 0
Schedule 16 | 146 | [8 empty] | 0
Schedule 16 | 147 | [7 empty] | YES | 1
Schedule 16 | 148 | [8 empty] | 0
Schedule 16 | 149 | [8 empty] | 0
Schedule 16 | 150 | [8 empty] | 0
Schedule 16 | 151 | [8 empty] | 0
Schedule 16 | 152 | [8 empty] | 0
Schedule 16 | 153 | [8 empty] | 0
Schedule 16 | 154 | [8 empty] | 0
Schedule 16 | 155 | [8 empty] | 0
Schedule 16 | 156 | [8 empty] | 0
Schedule 16 | 157 | [8 empty] | 0
Schedule 16 | 158 | [8 empty] | 0
Schedule 16 | 159 | [8 empty] | 0
Schedule 16 | 160 | [8 empty] | 0
Schedule 16 | 161 | [8 empty] | 0
Schedule 16 | 162 | [8 empty] | 0
Schedule 16 | 163 | [8 empty] | 0
Schedule 16 | 164 | [8 empty] | 0
Schedule 16 | 165 | [8 empty] | 0
Schedule 16 | 166 | [8 empty] | 0
Schedule 16 | 167 | [8 empty] | 0
Schedule 16 | 168 | [8 empty] | 0
Schedule 16 | 169 | [8 empty] | 0
Schedule 16 | 170 | [8 empty] | 0
Schedule 16 | 171 | [8 empty] | 0
Schedule 16 | 172 | [8 empty] | 0
Schedule 16 | 173 | [8 empty] | 0
Schedule 16 | 174 | [8 empty] | 0
Schedule 16 | 175 | [8 empty] | 0
Schedule 16 | 176 | [8 empty] | 0
Schedule 16 | 177 | [8 empty] | 0
Schedule 16 | 178 | [8 empty] | 0
Schedule 16 | 179 | [7 empty] | YES | 1
Schedule 16 | 180 | [8 empty] | 0
Schedule 16 | 181 | [7 empty] | YES | 1
Schedule 16 | 182 | [7 empty] | YES | 1
Schedule 16 | 183 | [7 empty] | YES | 1
Schedule 16 | 184 | [7 empty] | YES | 1
Schedule 16 | Glossary | YES | [7 empty] | 1
0
Schedule 17 | Introduction | [8 empty] | 0
Schedule 17 | 1 | [8 empty] | 0
Schedule 17 | 1.1 | [8 empty] | 0
Schedule 17 | 1.2 | [8 empty] | 0
Schedule 17 | 1.3 | [8 empty] | 0 | Model reference number and date
Schedule 17 | 1.3A | [8 empty] | 0
Schedule 17 | 1.4 | [8 empty] | 0
Schedule 17 | 1.5 | [8 empty] | 0
Schedule 17 | 1.6 | [8 empty] | 0
Schedule 17 | 1.7 | [8 empty] | 0
Schedule 17 | 1.8 | [8 empty] | 0
Schedule 17 | 1.9 | [8 empty] | 0
Schedule 17 | 2 | [8 empty] | 0
Schedule 17 | 2.1 | [8 empty] | 0
Schedule 17 | 2.2 | [8 empty] | 0
Schedule 17 | 2.3 | [8 empty] | 0
Schedule 17 | 2.4 | [8 empty] | 0
Schedule 17 | 2.5 | [8 empty] | 0
Schedule 17 | 2.6 | [8 empty] | 0
Schedule 17 | 2.7 | [8 empty] | 0
Schedule 17 | 2.8 | [8 empty] | 0
Schedule 17 | 2.9 | [8 empty] | 0
Schedule 17 | 2.1 | [8 empty] | 0
Schedule 17 | 2.11 | [8 empty] | 0
Schedule 17 | 2.12 | [8 empty] | 0
Schedule 17 | 2.13 | [8 empty] | 0
Schedule 17 | 2.14 | [8 empty] | 0
Schedule 17 | 2.15 | [8 empty] | 0
Schedule 17 | 2.16 | [8 empty] | 0
Schedule 17 | 2.17 | [8 empty] | 0
Schedule 17 | 2.18 | [8 empty] | 0
Schedule 17 | 2.19 | [8 empty] | 0
Schedule 17 | 3 | [8 empty] | 0
Schedule 17 | 3.1 | [8 empty] | 0
Schedule 17 | 3.2 | [8 empty] | 0
Schedule 17 | 3.3 | [8 empty] | 0
Schedule 17 | 3.4 | [8 empty] | 0
Schedule 17 | 3.5 | [8 empty] | 0
Schedule 17 | 3.6 | [8 empty] | 0
Schedule 17 | 3.7 | [8 empty] | 0
Schedule 17 | 4 | [8 empty] | 0
Schedule 17 | 4.1 | [8 empty] | 0
Schedule 17 | 5 | [8 empty] | 0
Schedule 17 | 5.1 | [8 empty] | 0
Schedule 17 | 6 | [8 empty] | 0
Schedule 17 | 6.1 | [8 empty] | 0
Schedule 17 | 6.2 | [8 empty] | 0
Schedule 17 | 6.3 | [8 empty] | 0
Schedule 17 | 7 | [8 empty] | 0
Schedule 17 | 7.1 | [8 empty] | 0
Schedule 17 | 8 | [8 empty] | 0
Schedule 17 | 8.1 | [8 empty] | 0
Schedule 17 | 8.2 | [8 empty] | 0
Schedule 17 | 8.3 | [8 empty] | 0
Schedule 17 | 8.4 | [8 empty] | 0
Schedule 17 | 9 | [8 empty] | 0
Schedule 17 | 9.1 | [8 empty] | 0
Schedule 17 | 9.2 | [8 empty] | 0
Schedule 17 | 9.3 | [8 empty] | 0
Schedule 17 | 10 | [8 empty] | 0
Schedule 17 | 10.1 | [8 empty] | 0
Schedule 17 | 10.2 | [8 empty] | 0
Schedule 17 | 10.3 | [8 empty] | 0
Schedule 17 | 10.4 | [8 empty] | 0
Schedule 17 | 11 | [8 empty] | 0
Schedule 17 | 11.1 | [8 empty] | 0
Schedule 17 | 12 | [8 empty] | 0
Schedule 17 | 12.1 | [8 empty] | 0
Schedule 17 | 12.2 | [8 empty] | 0
Schedule 17 | 12.3 | [8 empty] | 0
Schedule 17 | 13 | [8 empty] | 0
Schedule 17 | 13.1 | [8 empty] | 0
Schedule 17 | 13.2 | [8 empty] | 0
Schedule 17 | 13.3 | [8 empty] | 0
Schedule 17 | 13.4 | [8 empty] | 0
Schedule 17 | 14 | [8 empty] | 0
Schedule 17 | 14.1 | [8 empty] | 0
Schedule 17 | 14.2 | [8 empty] | 0
Schedule 17 | 14.3 | [8 empty] | 0
Schedule 17 | 14.4 | [8 empty] | 0
Schedule 17 | 14.5 | [8 empty] | 0
Schedule 17 | 15 | [8 empty] | 0
Schedule 17 | 15.1 | [8 empty] | 0
Schedule 17 | 15.2 | [8 empty] | 0
Schedule 17 | 15.3 | [8 empty] | 0
Schedule 17 | 15.4 | [8 empty] | 0
Schedule 17 | 15.5 | [8 empty] | 0
Schedule 17 | 15.6 | [8 empty] | 0
Schedule 17 | 15.7 | [8 empty] | 0
Schedule 17 | 15.8 | [8 empty] | 0
Schedule 17 | 15.9 | [8 empty] | 0
Schedule 17 | 15.1 | [8 empty] | 0
Schedule 17 | 15.11 | [8 empty] | 0
Schedule 17 | 15.12 | [8 empty] | 0
Schedule 17 | 15.15 | [8 empty] | 0
Schedule 17 | 16 | [8 empty] | 0
Schedule 17 | 16.1 | [8 empty] | 0
Schedule 17 | 16.2 | [8 empty] | 0
Schedule 17 | 16.3 | [8 empty] | 0
Schedule 17 | 16.4 | [8 empty] | 0
Schedule 17 | 16.5 | [8 empty] | 0
Schedule 17 | 16.6 | [8 empty] | 0
Schedule 17 | 16.7 | [8 empty] | 0
Schedule 17 | 16.8 | [8 empty] | 0
Schedule 17 | 16.9 | [8 empty] | 0
Schedule 17 | 16.1 | [8 empty] | 0
Schedule 17 | 17 | [8 empty] | 0
Schedule 17 | 17.1 | [8 empty] | 0
Schedule 17 | 17.2 | [8 empty] | 0
Schedule 17 | 17.3 | [8 empty] | 0
Schedule 17 | 18 | [8 empty] | 0
Schedule 17 | 18.1 | [8 empty] | 0
Schedule 17 | 18.2 | [8 empty] | 0
Schedule 17 | 18.3 | [8 empty] | 0
Schedule 17 | 18.4 | [8 empty] | 0
Schedule 17 | 18.5 | [8 empty] | 0
Schedule 17 | 18.6 | [8 empty] | 0
Schedule 17 | 18.7 | [8 empty] | 0
Schedule 17 | 18.8 | [8 empty] | 0
Schedule 17 | 18.9 | [8 empty] | 0
Schedule 17 | 18.1 | [8 empty] | 0
Schedule 17 | 18.11 | [8 empty] | 0
Schedule 17 | 18.12 | [8 empty] | 0
Schedule 17 | 18.13 | [8 empty] | 0
Schedule 17 | 18.14 | [8 empty] | 0
Schedule 17 | 18.15 | [8 empty] | 0
Schedule 17 | 18.16 | [8 empty] | 0
Schedule 17 | 18.17 | [8 empty] | 0
Schedule 17 | 18.18 | [8 empty] | 0
Schedule 17 | 18.19 | [8 empty] | 0
Schedule 17 | 18.2 | [8 empty] | 0
Schedule 17 | 18.21 | [8 empty] | 0
Schedule 17 | 19 | [8 empty] | 0
Schedule 17 | 19.1 | [8 empty] | 0
Schedule 17 | 19.2 | [8 empty] | 0
Schedule 17 | 19.3 | [8 empty] | 0
Schedule 17 | 19.4 | [8 empty] | 0
Schedule 17 | 19.5 | [8 empty] | 0
Schedule 17 | 19.6 | [8 empty] | 0
Schedule 17 | 19.7 | [8 empty] | 0
Schedule 17 | 19.8 | [8 empty] | 0
Schedule 17 | 19.9 | [8 empty] | 0
Schedule 17 | 19.1 | [8 empty] | 0
Schedule 17 | 19.11 | [8 empty] | 0
Schedule 17 | 20 | [8 empty] | 0
Schedule 17 | 20.1 | [8 empty] | 0
Schedule 17 | 20.2 | [8 empty] | 0
Schedule 17 | 20.3 | [8 empty] | 0
Schedule 17 | 20.4 | [8 empty] | 0
Schedule 17 | 20.5 | [8 empty] | 0
Schedule 17 | 20.6 | [8 empty] | 0
Schedule 17 | 20.7 | [8 empty] | 0
Schedule 17 | 20.8 | [8 empty] | 0
Schedule 17 | 20.9 | [8 empty] | 0
Schedule 17 | 21 | [8 empty] | 0
Schedule 17 | 21.1 | [8 empty] | 0
Schedule 17 | 21.2 | [8 empty] | 0
Schedule 17 | 22 | [8 empty] | 0
Schedule 17 | 22.1 | [8 empty] | 0
Schedule 17 | 22.2 | [8 empty] | 0
Schedule 17 | 22.3 | [8 empty] | 0
Schedule 17 | 22.4 | [8 empty] | 0
Schedule 17 | 23 | [8 empty] | 0
Schedule 17 | 23.1 | [8 empty] | 0
Schedule 17 | 23.2 | [8 empty] | 0
Schedule 17 | 23.3 | [8 empty] | 0
Schedule 17 | 23.4 | [8 empty] | 0
Schedule 17 | 23.5 | [8 empty] | 0
Schedule 17 | 24 | [8 empty] | 0
Schedule 17 | 24.1 | [8 empty] | 0
Schedule 17 | 24.2 | [8 empty] | 0
Schedule 17 | 24.3 | [8 empty] | 0
Schedule 17 | 24.4 | [8 empty] | 0
Schedule 17 | 24.5 | [8 empty] | 0
Schedule 17 | 24.6 | [8 empty] | 0
Schedule 17 | 24.7 | [8 empty] | 0
Schedule 17 | 24.8 | [8 empty] | 0
Schedule 17 | 24.9 | [8 empty] | 0
Schedule 17 | 25 | [8 empty] | 0
Schedule 17 | 25.1 | [8 empty] | 0
Schedule 17 | 25.2 | [8 empty] | 0
Schedule 17 | 25.3 | [7 empty] | YES | 1
Schedule 17 | 25.4 | [8 empty] | 0
Schedule 17 | 25.5 | [8 empty] | 0
Schedule 17 | 25.6 | [8 empty] | 0
Schedule 17 | 25.7 | [8 empty] | 0
Schedule 17 | 25.8 | [8 empty] | 0
Schedule 17 | 25.9 | [8 empty] | 0
Schedule 17 | 25.1 | [8 empty] | 0
Schedule 17 | 25.11 | [8 empty] | 0
Schedule 17 | 25.12 | [8 empty] | 0
Schedule 17 | 25.13 | [8 empty] | 0
Schedule 17 | 25.14 | [8 empty] | 0
Schedule 17 | 25.15 | [8 empty] | 0
Schedule 17 | 25.16 | [8 empty] | 0
Schedule 17 | 25.17 | [8 empty] | 0
Schedule 17 | 25.18 | [8 empty] | 0
Schedule 17 | 25.19 | [8 empty] | 0
Schedule 17 | 26 | [8 empty] | 0
Schedule 17 | 26.1 | [8 empty] | 0
Schedule 17 | 26.2 | [8 empty] | 0
Schedule 17 | 26.3 | [8 empty] | 0
Schedule 17 | 26.4 | [8 empty] | 0
Schedule 17 | 26.5 | [8 empty] | 0
Schedule 17 | 26.6 | [8 empty] | 0
Schedule 17 | 26.7 | [8 empty] | 0
Schedule 17 | 26.8 | [8 empty] | 0
Schedule 17 | 26.9 | [8 empty] | 0
Schedule 17 | 26.1 | [8 empty] | 0
Schedule 17 | 26.11 | [8 empty] | 0
Schedule 17 | 27 | [8 empty] | 0
Schedule 17 | 27.1 | [8 empty] | 0
Schedule 17 | 27.2 | [8 empty] | 0
Schedule 17 | 27.3 | [8 empty] | 0
Schedule 17 | 27.4 | [8 empty] | 0
Schedule 17 | 28 | [8 empty] | 0
Schedule 17 | 28.1 | [8 empty] | 0
Schedule 17 | 28.2 | [8 empty] | 0
Schedule 17 | 29 | [8 empty] | 0
Schedule 17 | 29.1 | [8 empty] | 0
Schedule 17 | 29.2 | [8 empty] | 0
Schedule 17 | 29.3 | [8 empty] | 0
Schedule 17 | 29.4 | [8 empty] | 0
Schedule 17 | 30 | [8 empty] | 0
Schedule 17 | 30.1 | [8 empty] | 0
Schedule 17 | 30.2 | [8 empty] | 0
Schedule 17 | 30.3 | [8 empty] | 0
Schedule 17 | 30.4 | [8 empty] | 0
Schedule 17 | 30.5 | [8 empty] | 0
Schedule 17 | 30.6 | [8 empty] | 0
Schedule 17 | 30.7 | [8 empty] | 0
Schedule 17 | 30.8 | [8 empty] | 0
Schedule 17 | 30.9 | [8 empty] | 0
Schedule 17 | 30.1 | [8 empty] | 0
Schedule 17 | 30.11 | [8 empty] | 0
Schedule 17: Annex 1 | 1 | [8 empty] | 0
Schedule 17: Annex 1 | 2 | [8 empty] | 0
Schedule 17: Annex 1 | 2.1 | [8 empty] | 0
Schedule 17: Annex 1 | 2.2 | [8 empty] | 0
Schedule 17: Annex 1 | 2.3 | [8 empty] | 0
Schedule 17: Annex 1 | 2.4 | [8 empty] | 0
Schedule 17: Annex 1 | 2.5 | [8 empty] | 0
Schedule 17: Annex 1 | 3 | [8 empty] | 0
Schedule 17: Annex 1 | Definitions | [8 empty] | 0
Schedule 17: Annex 1 | 4 | [8 empty] | 0
Schedule 17: Annex 1 | 4.1 | [8 empty] | 0
Schedule 17: Annex 1 | 4.2 | [8 empty] | 0
Schedule 17: Annex 1 | 4.3 | [8 empty] | 0
Schedule 17: Annex 1 | 4.4 | [8 empty] | 0
Schedule 17: Annex 1 | 4.5 | [8 empty] | 0
Schedule 17: Annex 1 | 4.6 | [8 empty] | 0
Schedule 17: Annex 1 | 4.7 | [8 empty] | 0
Schedule 17: Annex 1 | 4.8 | [8 empty] | 0
Schedule 17: Annex 1 | 4.9 | [8 empty] | 0
Schedule 17: Annex 1 | 4.1 | [8 empty] | 0
Schedule 17: Annex 1 | 5 | [8 empty] | 0
Schedule 17: Annex 1 | 5.1 | [8 empty] | 0
Schedule 17: Annex 1 | 5.2 | [8 empty] | 0
Schedule 17: Annex 1 | 5.3 | [8 empty] | 0
Schedule 17: Annex 1 | 5.4 | [8 empty] | 0
Schedule 17: Annex 1 | 5.5 | [8 empty] | 0
Schedule 17: Annex 1 | 5.6 | [8 empty] | 0
Schedule 17: Annex 1 | 5.7 | [8 empty] | 0
Schedule 17: Annex 1 | 5.8 | [8 empty] | 0
Schedule 17: Annex 1 | 5.9 | [8 empty] | 0
Schedule 17: Annex 1 | 5.1 | [8 empty] | 0
Schedule 17: Annex 1 | 5.11 | [8 empty] | 0
Schedule 17: Annex 1 | 5.12 | [8 empty] | 0
Schedule 17: Annex 1 | 5.13 | [8 empty] | 0
Schedule 17: Annex 1 | 5.14 | [8 empty] | 0
Schedule 17: Annex 1 | 5.15 | [8 empty] | 0
Schedule 17: Annex 1 | 5.16 | [8 empty] | 0
Schedule 17: Annex 1 | 5.17 | [8 empty] | 0
Schedule 17: Annex 1 | 5.18 | [8 empty] | 0
Schedule 17: Annex 1 | 5.19 | [8 empty] | 0
Schedule 17: Annex 1 | 5.2 | [8 empty] | 0
Schedule 17: Annex 1 | 5.21 | [8 empty] | 0
Schedule 17: Annex 1 | 5.22 | [8 empty] | 0
Schedule 17: Annex 1 | 5.23 | [8 empty] | 0
Schedule 17: Annex 1 | 5.24 | [8 empty] | 0
Schedule 17: Annex 1 | 5.25 | [8 empty] | 0
Schedule 17: Annex 1 | 5.26 | [8 empty] | 0
Schedule 17: Annex 1 | 5.27 | [8 empty] | 0
Schedule 17: Annex 1 | 5.28 | [8 empty] | 0
Schedule 17: Annex 1 | 5.29 | [8 empty] | 0
Schedule 17: Annex 1 | 5.3 | [8 empty] | 0
Schedule 17: Annex 1 | 5.31 | [8 empty] | 0
Schedule 17: Annex 1 | 5.32 | [8 empty] | 0
Schedule 17: Annex 1 | 5.33 | [8 empty] | 0
Schedule 17: Annex 1 | 5.34 | [8 empty] | 0
Schedule 17: Annex 1 | 5.35 | [8 empty] | 0
Schedule 17: Annex 1 | 5.36 | [8 empty] | 0
Schedule 17: Annex 1 | 5.37 | [8 empty] | 0
Schedule 17: Annex 1 | 5.38 | [8 empty] | 0
Schedule 17: Annex 1 | 5.39 | [8 empty] | 0
Schedule 17: Annex 1 | 5.4 | [8 empty] | 0
Schedule 17: Annex 1 | 5.41 | [8 empty] | 0
Schedule 17: Annex 1 | 5.42 | [8 empty] | 0
Schedule 17: Annex 1 | 5.43 | [8 empty] | 0
Schedule 17: Annex 1 | 5.44 | [8 empty] | 0
Schedule 17: Annex 1 | 5.45 | [8 empty] | 0
Schedule 17: Annex 1 | 6 | [8 empty] | 0
Schedule 17: Annex 1 | 6.1 | [8 empty] | 0
Schedule 17: Annex 1 | 6.2 | [8 empty] | 0
Schedule 17: Annex 1 | 6.3 | [8 empty] | 0
Schedule 17: Annex 1 | 6.4 | [8 empty] | 0
Schedule 17: Annex 1 | 6.5 | [8 empty] | 0
Schedule 17: Annex 1 | 6.6 | [8 empty] | 0
Schedule 17: Annex 1 | 6.7 | [8 empty] | 0
Schedule 17: Annex 1 | 6.8 | [8 empty] | 0
Schedule 17: Annex 1 | 7 | [8 empty] | 0
Schedule 17: Annex 1 | 7.1 | [8 empty] | 0
Schedule 17: Annex 1 | 7.2 | [8 empty] | 0
Schedule 17: Annex 1 | 7.3 | [8 empty] | 0
Schedule 17: Annex 1 | 7.4 | [8 empty] | 0
Schedule 17: Annex 1 | 7.5 | [8 empty] | 0
Schedule 17: Annex 1 | 7.6 | [8 empty] | 0
Schedule 17: Annex 1 | 7.7 | [8 empty] | 0
Schedule 17: Annex 1 | 7.8 | [8 empty] | 0
Schedule 17: Annex 1 | 8 | [8 empty] | 0
Schedule 17: Annex 1 | 8.1 | [8 empty] | 0
Schedule 17: Annex 1 | 8.2 | [8 empty] | 0
Schedule 17: Annex 1 | 8.3 | [8 empty] | 0
Schedule 17: Annex 1 | 8.4 | [8 empty] | 0
Schedule 17: Annex 1 | 9 | [8 empty] | 0
Schedule 17: Annex 1 | 9.1 | [8 empty] | 0
Schedule 17: Annex 1 | 9.2 | [8 empty] | 0
Schedule 17: Annex 1 | 9.3 | [8 empty] | 0
Schedule 17: Annex 1 | 9.4 | [8 empty] | 0
Schedule 17: Annex 1 | 9.5 | [8 empty] | 0
Schedule 17: Annex 1 | 9.6 | [8 empty] | 0
Schedule 17: Annex 1 | 9.7 | [8 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [8 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [8 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [8 empty] | 0
Schedule 17: Annex 1 | Attachment 3 | [8 empty] | 0
Schedule 17: Annex 2 | Annex 2 | [8 empty] | 0
0
Schedule 18 | Introduction | [8 empty] | 0
Schedule 18 | 1 | [8 empty] | 0
Schedule 18 | 1.1 | [8 empty] | 0
Schedule 18 | 1.2 | [8 empty] | 0
Schedule 18 | 1.3 | [8 empty] | 0 | Model reference number and date
Schedule 18 | 1.3A | [8 empty] | 0
Schedule 18 | 1.4 | [8 empty] | 0
Schedule 18 | 1.5 | [8 empty] | 0
Schedule 18 | 1.6 | [8 empty] | 0
Schedule 18 | 1.7 | [8 empty] | 0
Schedule 18 | 1.8 | [8 empty] | 0
Schedule 18 | 1.9 | [8 empty] | 0
Schedule 18 | 2 | [8 empty] | 0
Schedule 18 | 2.1 | [8 empty] | 0
Schedule 18 | 2.2 | [8 empty] | 0
Schedule 18 | 2.3 | [8 empty] | 0
Schedule 18 | 2.4 | [8 empty] | 0
Schedule 18 | 2.5 | [8 empty] | 0
Schedule 18 | 2.6 | [8 empty] | 0
Schedule 18 | 2.7 | [8 empty] | 0
Schedule 18 | 2.8 | [8 empty] | 0
Schedule 18 | 2.9 | [8 empty] | 0
Schedule 18 | 2.1 | [8 empty] | 0
Schedule 18 | 2.11 | [8 empty] | 0
Schedule 18 | 2.12 | [8 empty] | 0
Schedule 18 | 2.13 | [8 empty] | 0
Schedule 18 | 2.14 | [8 empty] | 0
Schedule 18 | 2.15 | [8 empty] | 0
Schedule 18 | 2.16 | [8 empty] | 0
Schedule 18 | 2.17 | [8 empty] | 0
Schedule 18 | 2.18 | [8 empty] | 0
Schedule 18 | 2.19 | [8 empty] | 0
Schedule 18 | 2.2 | [8 empty] | 0
Schedule 18 | 2.21 | [8 empty] | 0
Schedule 18 | 2.22 | [8 empty] | 0
Schedule 18 | 2.23 | [8 empty] | 0
Schedule 18 | 2.24 | [8 empty] | 0
Schedule 18 | 2.25 | [8 empty] | 0
Schedule 18 | 2.26 | [8 empty] | 0
Schedule 18 | 2.27 | [8 empty] | 0
Schedule 18 | 2.28 | [8 empty] | 0
Schedule 18 | 2.29 | [8 empty] | 0
Schedule 18 | 2.3 | [8 empty] | 0
Schedule 18 | 3 | [8 empty] | 0
Schedule 18 | 3.1 | [8 empty] | 0
Schedule 18 | 3.2 | [8 empty] | 0
Schedule 18 | 3.3 | [8 empty] | 0
Schedule 18 | 3.4 | [8 empty] | 0
Schedule 18 | 3.5 | [8 empty] | 0
Schedule 18 | 3.6 | [8 empty] | 0
Schedule 18 | 3.7 | [8 empty] | 0
Schedule 18 | 4 | [8 empty] | 0
Schedule 18 | 4.1 | [8 empty] | 0
Schedule 18 | 5 | [8 empty] | 0
Schedule 18 | 5.1 | [8 empty] | 0
Schedule 18 | 6 | [8 empty] | 0
Schedule 18 | 6.1 | [8 empty] | 0
Schedule 18 | 6.2 | [8 empty] | 0
Schedule 18 | 6.3 | [8 empty] | 0
Schedule 18 | 6.4 | [8 empty] | 0
Schedule 18 | 6.5 | [8 empty] | 0
Schedule 18 | 7 | [8 empty] | 0
Schedule 18 | 7.1 | [8 empty] | 0
Schedule 18 | 8 | [8 empty] | 0
Schedule 18 | 8.1 | [8 empty] | 0
Schedule 18 | 8.2 | [8 empty] | 0
Schedule 18 | 8.3 | [8 empty] | 0
Schedule 18 | 8.4 | [8 empty] | 0
Schedule 18 | 9 | [8 empty] | 0
Schedule 18 | 9.1 | [8 empty] | 0
Schedule 18 | 9.2 | [8 empty] | 0
Schedule 18 | 10 | [8 empty] | 0
Schedule 18 | 10.1 | [8 empty] | 0
Schedule 18 | 10.2 | [8 empty] | 0
Schedule 18 | 10.3 | [8 empty] | 0
Schedule 18 | 10.4 | [8 empty] | 0
Schedule 18 | 10.5 | [8 empty] | 0
Schedule 18 | 11 | [8 empty] | 0
Schedule 18 | 11.1 | [8 empty] | 0
Schedule 18 | 12 | [8 empty] | 0
Schedule 18 | 12.1 | [8 empty] | 0
Schedule 18 | 12.2 | [8 empty] | 0
Schedule 18 | 12.3 | [8 empty] | 0
Schedule 18 | 12.4 | [8 empty] | 0
Schedule 18 | 12.5 | [8 empty] | 0
Schedule 18 | 12.6 | [8 empty] | 0
Schedule 18 | 13 | [8 empty] | 0
Schedule 18 | 13.1 | [8 empty] | 0
Schedule 18 | 13.2 | [8 empty] | 0
Schedule 18 | 13.3 | [8 empty] | 0
Schedule 18 | 13.4 | [8 empty] | 0
Schedule 18 | 14 | [8 empty] | 0
Schedule 18 | 14.1 | [8 empty] | 0
Schedule 18 | 14.2 | [8 empty] | 0
Schedule 18 | 14.3 | [8 empty] | 0
Schedule 18 | 14.4 | [8 empty] | 0
Schedule 18 | 14.5 | [8 empty] | 0
Schedule 18 | 15 | [8 empty] | 0
Schedule 18 | 15.1 | [8 empty] | 0
Schedule 18 | 15.2 | [8 empty] | 0
Schedule 18 | 15.3 | [8 empty] | 0
Schedule 18 | 15.4 | [8 empty] | 0
Schedule 18 | 15.5 | [8 empty] | 0
Schedule 18 | 15.6 | [8 empty] | 0
Schedule 18 | 15.7 | [8 empty] | 0
Schedule 18 | 15.8 | [8 empty] | 0
Schedule 18 | 15.9 | [8 empty] | 0
Schedule 18 | 15.1 | [8 empty] | 0
Schedule 18 | 15.11 | [8 empty] | 0
Schedule 18 | 15.12 | [8 empty] | 0
Schedule 18 | 15.15 | [8 empty] | 0
Schedule 18 | 16 | [8 empty] | 0
Schedule 18 | 16.1 | [8 empty] | 0
Schedule 18 | 16.2 | [8 empty] | 0
Schedule 18 | 16.3 | [8 empty] | 0
Schedule 18 | 16.4 | [8 empty] | 0
Schedule 18 | 16.5 | [8 empty] | 0
Schedule 18 | 16.6 | [8 empty] | 0
Schedule 18 | 16.7 | [8 empty] | 0
Schedule 18 | 16.8 | [8 empty] | 0
Schedule 18 | 16.9 | [8 empty] | 0
Schedule 18 | 16.1 | [8 empty] | 0
Schedule 18 | 17 | [8 empty] | 0
Schedule 18 | 17.1 | [8 empty] | 0
Schedule 18 | 17.2 | [8 empty] | 0
Schedule 18 | 17.3 | [8 empty] | 0
Schedule 18 | 18 | [8 empty] | 0
Schedule 18 | 18.1 | [8 empty] | 0
Schedule 18 | 18.2 | [8 empty] | 0
Schedule 18 | 18.3 | [8 empty] | 0
Schedule 18 | 18.4 | [8 empty] | 0
Schedule 18 | 18.5 | [8 empty] | 0
Schedule 18 | 18.6 | [8 empty] | 0
Schedule 18 | 18.7 | [8 empty] | 0
Schedule 18 | 18.8 | [8 empty] | 0
Schedule 18 | 18.9 | [8 empty] | 0
Schedule 18 | 18.1 | [8 empty] | 0
Schedule 18 | 18.11 | [8 empty] | 0
Schedule 18 | 18.12 | [8 empty] | 0
Schedule 18 | 18.13 | [8 empty] | 0
Schedule 18 | 18.14 | [8 empty] | 0
Schedule 18 | 18.15 | [8 empty] | 0
Schedule 18 | 18.16 | [8 empty] | 0
Schedule 18 | 18.17 | [8 empty] | 0
Schedule 18 | 18.18 | [8 empty] | 0
Schedule 18 | 18.19 | [8 empty] | 0
Schedule 18 | 18.2 | [8 empty] | 0
Schedule 18 | 18.21 | [8 empty] | 0
Schedule 18 | 19 | [8 empty] | 0
Schedule 18 | 19.1 | [8 empty] | 0
Schedule 18 | 19.2 | [8 empty] | 0
Schedule 18 | 19.3 | [8 empty] | 0
Schedule 18 | 19.4 | [8 empty] | 0
Schedule 18 | 19.5 | [8 empty] | 0
Schedule 18 | 19.6 | [8 empty] | 0
Schedule 18 | 19.7 | [8 empty] | 0
Schedule 18 | 19.8 | [8 empty] | 0
Schedule 18 | 19.9 | [8 empty] | 0
Schedule 18 | 19.1 | [8 empty] | 0
Schedule 18 | 19.11 | [8 empty] | 0
Schedule 18 | 20 | [8 empty] | 0
Schedule 18 | 20.1 | [8 empty] | 0
Schedule 18 | 20.2 | [8 empty] | 0
Schedule 18 | 20.3 | [8 empty] | 0
Schedule 18 | 20.4 | [8 empty] | 0
Schedule 18 | 20.5 | [8 empty] | 0
Schedule 18 | 20.6 | [8 empty] | 0
Schedule 18 | 20.7 | [8 empty] | 0
Schedule 18 | 20.8 | [8 empty] | 0
Schedule 18 | 20.9 | [8 empty] | 0
Schedule 18 | 21 | [8 empty] | 0
Schedule 18 | 21.1 | [8 empty] | 0
Schedule 18 | 21.2 | [8 empty] | 0
Schedule 18 | 22 | [8 empty] | 0
Schedule 18 | 22.1 | [8 empty] | 0
Schedule 18 | 22.2 | [8 empty] | 0
Schedule 18 | 22.3 | [8 empty] | 0
Schedule 18 | 22.4 | [8 empty] | 0
Schedule 18 | 23 | [8 empty] | 0
Schedule 18 | 23.1 | [8 empty] | 0
Schedule 18 | 23.2 | [8 empty] | 0
Schedule 18 | 23.3 | [8 empty] | 0
Schedule 18 | 23.4 | [8 empty] | 0
Schedule 18 | 23.5 | [8 empty] | 0
Schedule 18 | 24 | [8 empty] | 0
Schedule 18 | 24.1 | [8 empty] | 0
Schedule 18 | 24.2 | [8 empty] | 0
Schedule 18 | 24.3 | [8 empty] | 0
Schedule 18 | 24.4 | [8 empty] | 0
Schedule 18 | 24.5 | [8 empty] | 0
Schedule 18 | 24.6 | [8 empty] | 0
Schedule 18 | 24.7 | [8 empty] | 0
Schedule 18 | 24.8 | [8 empty] | 0
Schedule 18 | 24.9 | [8 empty] | 0
Schedule 18 | 25 | [8 empty] | 0
Schedule 18 | 25.1 | [8 empty] | 0
Schedule 18 | 25.2 | [8 empty] | 0
Schedule 18 | 25.3 | [7 empty] | YES | 1
Schedule 18 | 25.4 | [8 empty] | 0
Schedule 18 | 25.5 | [8 empty] | 0
Schedule 18 | 25.6 | [8 empty] | 0
Schedule 18 | 25.7 | [8 empty] | 0
Schedule 18 | 25.8 | [8 empty] | 0
Schedule 18 | 25.9 | [8 empty] | 0
Schedule 18 | 25.1 | [8 empty] | 0
Schedule 18 | 25.11 | [8 empty] | 0
Schedule 18 | 25.12 | [8 empty] | 0
Schedule 18 | 25.13 | [8 empty] | 0
Schedule 18 | 25.14 | [8 empty] | 0
Schedule 18 | 25.15 | [8 empty] | 0
Schedule 18 | 25.16 | [8 empty] | 0
Schedule 18 | 25.17 | [8 empty] | 0
Schedule 18 | 25.18 | [8 empty] | 0
Schedule 18 | 25.19 | [8 empty] | 0
Schedule 18 | 26 | [8 empty] | 0
Schedule 18 | 26.1 | [8 empty] | 0
Schedule 18 | 26.2 | [8 empty] | 0
Schedule 18 | 26.3 | [8 empty] | 0
Schedule 18 | 26.4 | [8 empty] | 0
Schedule 18 | 26.5 | [8 empty] | 0
Schedule 18 | 26.6 | [8 empty] | 0
Schedule 18 | 26.7 | [8 empty] | 0
Schedule 18 | 26.8 | [8 empty] | 0
Schedule 18 | 26.9 | [8 empty] | 0
Schedule 18 | 26.1 | [8 empty] | 0
Schedule 18 | 26.11 | [8 empty] | 0
Schedule 18 | 27 | [8 empty] | 0
Schedule 18 | 27.1 | [8 empty] | 0
Schedule 18 | 27.2 | [8 empty] | 0
Schedule 18 | 27.3 | [8 empty] | 0
Schedule 18 | 27.4 | [8 empty] | 0
Schedule 18 | 28 | [8 empty] | 0
Schedule 18 | 28.1 | [8 empty] | 0
Schedule 18 | 28.2 | [8 empty] | 0
Schedule 18 | 29 | [8 empty] | 0
Schedule 18 | 29.1 | [8 empty] | 0
Schedule 18 | 29.2 | [8 empty] | 0
Schedule 18 | 29.3 | [8 empty] | 0
Schedule 18 | 29.4 | [8 empty] | 0
Schedule 18 | 30 | [8 empty] | 0
Schedule 18 | 30.1 | [8 empty] | 0
Schedule 18 | 30.2 | [8 empty] | 0
Schedule 18 | 30.3 | [8 empty] | 0
Schedule 18 | 30.4 | [8 empty] | 0
Schedule 18 | 30.5 | [8 empty] | 0
Schedule 18 | 30.6 | [8 empty] | 0
Schedule 18 | 30.7 | [8 empty] | 0
Schedule 18 | 30.8 | [8 empty] | 0
Schedule 18 | 30.9 | [8 empty] | 0
Schedule 18 | 30.1 | [8 empty] | 0
Schedule 18 | 30.11 | [8 empty] | 0
Schedule 18: Annex 1 | 1 | [8 empty] | 0
Schedule 18: Annex 1 | 1.1 | [8 empty] | 0
Schedule 18: Annex 1 | 2 | [8 empty] | 0
Schedule 18: Annex 1 | 2.1 | [8 empty] | 0
Schedule 18: Annex 1 | 2.2 | [8 empty] | 0
Schedule 18: Annex 1 | 2.3 | [8 empty] | 0
Schedule 18: Annex 1 | 2.4 | [8 empty] | 0
Schedule 18: Annex 1 | 2.5 | [8 empty] | 0
Schedule 18: Annex 1 | 3 | [8 empty] | 0
Schedule 18: Annex 1 | Definitions | [8 empty] | 0
Schedule 18: Annex 1 | 4 | [8 empty] | 0
Schedule 18: Annex 1 | 4.1 | [8 empty] | 0
Schedule 18: Annex 1 | 4.2 | [8 empty] | 0
Schedule 18: Annex 1 | 4.3 | [8 empty] | 0
Schedule 18: Annex 1 | 4.4 | [8 empty] | 0
Schedule 18: Annex 1 | 4.5 | [8 empty] | 0
Schedule 18: Annex 1 | 4.6 | [8 empty] | 0
Schedule 18: Annex 1 | 4.7 | [8 empty] | 0
Schedule 18: Annex 1 | 4.8 | [8 empty] | 0
Schedule 18: Annex 1 | 4.9 | [8 empty] | 0
Schedule 18: Annex 1 | 5 | [8 empty] | 0
Schedule 18: Annex 1 | 5.1 | [8 empty] | 0
Schedule 18: Annex 1 | 5.2 | [8 empty] | 0
Schedule 18: Annex 1 | 5.3 | [8 empty] | 0
Schedule 18: Annex 1 | 5.4 | [8 empty] | 0
Schedule 18: Annex 1 | 5.5 | [8 empty] | 0
Schedule 18: Annex 1 | 5.6 | [8 empty] | 0
Schedule 18: Annex 1 | 5.7 | [8 empty] | 0
Schedule 18: Annex 1 | 5.8 | [8 empty] | 0
Schedule 18: Annex 1 | 5.9 | [8 empty] | 0
Schedule 18: Annex 1 | 5.1 | [8 empty] | 0
Schedule 18: Annex 1 | 5.11 | [8 empty] | 0
Schedule 18: Annex 1 | 5.12 | [8 empty] | 0
Schedule 18: Annex 1 | 5.13 | [8 empty] | 0
Schedule 18: Annex 1 | 5.14 | [8 empty] | 0
Schedule 18: Annex 1 | 5.15 | [8 empty] | 0
Schedule 18: Annex 1 | 5.16 | [8 empty] | 0
Schedule 18: Annex 1 | 5.17 | [8 empty] | 0
Schedule 18: Annex 1 | 5.18 | [8 empty] | 0
Schedule 18: Annex 1 | 5.19 | [8 empty] | 0
Schedule 18: Annex 1 | 5.2 | [8 empty] | 0
Schedule 18: Annex 1 | 5.21 | [8 empty] | 0
Schedule 18: Annex 1 | 5.22 | [8 empty] | 0
Schedule 18: Annex 1 | 5.23 | [8 empty] | 0
Schedule 18: Annex 1 | 5.24 | [8 empty] | 0
Schedule 18: Annex 1 | 5.25 | [8 empty] | 0
Schedule 18: Annex 1 | 5.26 | [8 empty] | 0
Schedule 18: Annex 1 | 5.27 | [8 empty] | 0
Schedule 18: Annex 1 | 5.28 | [8 empty] | 0
Schedule 18: Annex 1 | 5.29 | [8 empty] | 0
Schedule 18: Annex 1 | 5.3 | [8 empty] | 0
Schedule 18: Annex 1 | 5.31 | [8 empty] | 0
Schedule 18: Annex 1 | 5.32 | [8 empty] | 0
Schedule 18: Annex 1 | 5.33 | [8 empty] | 0
Schedule 18: Annex 1 | 5.34 | [8 empty] | 0
Schedule 18: Annex 1 | 5.35 | [8 empty] | 0
Schedule 18: Annex 1 | 5.36 | [8 empty] | 0
Schedule 18: Annex 1 | 5.37 | [8 empty] | 0
Schedule 18: Annex 1 | 5.38 | [8 empty] | 0
Schedule 18: Annex 1 | 5.39 | [8 empty] | 0
Schedule 18: Annex 1 | 5.4 | [8 empty] | 0
Schedule 18: Annex 1 | 5.41 | [8 empty] | 0
Schedule 18: Annex 1 | 5.42 | [8 empty] | 0
Schedule 18: Annex 1 | 6 | [8 empty] | 0
Schedule 18: Annex 1 | 6.1 | [8 empty] | 0
Schedule 18: Annex 1 | 6.2 | [8 empty] | 0
Schedule 18: Annex 1 | 6.3 | [8 empty] | 0
Schedule 18: Annex 1 | 6.4 | [8 empty] | 0
Schedule 18: Annex 1 | 6.5 | [8 empty] | 0
Schedule 18: Annex 1 | 6.6 | [8 empty] | 0
Schedule 18: Annex 1 | 6.7 | [8 empty] | 0
Schedule 18: Annex 1 | 6.8 | [8 empty] | 0
Schedule 18: Annex 1 | 6.9 | [8 empty] | 0
Schedule 18: Annex 1 | 6.1 | [8 empty] | 0
Schedule 18: Annex 1 | 6.11 | [8 empty] | 0
Schedule 18: Annex 1 | 6.12 | [8 empty] | 0
Schedule 18: Annex 1 | 6.13 | [8 empty] | 0
Schedule 18: Annex 1 | 6.14 | [8 empty] | 0
Schedule 18: Annex 1 | 6.15 | [8 empty] | 0
Schedule 18: Annex 1 | 6.16 | [8 empty] | 0
Schedule 18: Annex 1 | 6.17 | [8 empty] | 0
Schedule 18: Annex 1 | 6.18 | [8 empty] | 0
Schedule 18: Annex 1 | 6.19 | [8 empty] | 0
Schedule 18: Annex 1 | 6.2 | [8 empty] | 0
Schedule 18: Annex 1 | 6.21 | [8 empty] | 0
Schedule 18: Annex 1 | 6.22 | [8 empty] | 0
Schedule 18: Annex 1 | 6.23 | [8 empty] | 0
Schedule 18: Annex 1 | 6.24 | [8 empty] | 0
Schedule 18: Annex 1 | 6.25 | [8 empty] | 0
Schedule 18: Annex 1 | 6.26 | [8 empty] | 0
Schedule 18: Annex 1 | 6.27 | [8 empty] | 0
Schedule 18: Annex 1 | 6.28 | [8 empty] | 0
Schedule 18: Annex 1 | 6.29 | [8 empty] | 0
Schedule 18: Annex 1 | 6.3 | [8 empty] | 0
Schedule 18: Annex 1 | 6.31 | [8 empty] | 0
Schedule 18: Annex 1 | 6.32 | [8 empty] | 0
Schedule 18: Annex 1 | 6.33 | [8 empty] | 0
Schedule 18: Annex 1 | 6.34 | [8 empty] | 0
Schedule 18: Annex 1 | 7 | [8 empty] | 0
Schedule 18: Annex 1 | 7.1 | [8 empty] | 0
Schedule 18: Annex 1 | 7.2 | [8 empty] | 0
Schedule 18: Annex 1 | 7.3 | [8 empty] | 0
Schedule 18: Annex 1 | 7.4 | [8 empty] | 0
Schedule 18: Annex 1 | 7.5 | [8 empty] | 0
Schedule 18: Annex 1 | 8 | [8 empty] | 0
Schedule 18: Annex 1 | 8.1 | [8 empty] | 0
Schedule 18: Annex 1 | 8.2 | [8 empty] | 0
Schedule 18: Annex 1 | 8.3 | [8 empty] | 0
Schedule 18: Annex 1 | 8.4 | [8 empty] | 0
Schedule 18: Annex 1 | 8.5 | [8 empty] | 0
Schedule 18: Annex 1 | 8.6 | [8 empty] | 0
Schedule 18: Annex 1 | 8.7 | [8 empty] | 0
Schedule 18: Annex 1 | 8.8 | [8 empty] | 0
Schedule 18: Annex 1 | 8.9 | [8 empty] | 0
Schedule 18: Annex 1 | 8.1 | [8 empty] | 0
Schedule 18: Annex 1 | 8.11 | [8 empty] | 0
Schedule 18: Annex 1 | 8.12 | [8 empty] | 0
Schedule 18: Annex 1 | 8.13 | [8 empty] | 0
Schedule 18: Annex 1 | 8.14 | [8 empty] | 0
Schedule 18: Annex 1 | 8.15 | [8 empty] | 0
Schedule 18: Annex 1 | 8.16 | [8 empty] | 0
Schedule 18: Annex 1 | 8.17 | [8 empty] | 0
Schedule 18: Annex 1 | 8.18 | [8 empty] | 0
Schedule 18: Annex 1 | 8.19 | [8 empty] | 0
Schedule 18: Annex 1 | 8.2 | [8 empty] | 0
Schedule 18: Annex 1 | 8.21 | [8 empty] | 0
Schedule 18: Annex 1 | Attachment 1 | [8 empty] | 0
Schedule 18: Annex 1 | Attachment 2 | [8 empty] | 0
Schedule 18: Annex 1 | Attachment 3 | [8 empty] | 0
Schedule 18: Annex 2 | Annex 2 | [8 empty] | 0
0
Schedule 20 | Introduction |  |  |  | YES |  |  |  |  | 1
Schedule 20 | 1.1 |  |  |  | YES |  |  |  |  | 1
Schedule 20 | 2.1 |  |  |  | YES |  |  |  |  | 1
Schedule 20 | 3.1 |  |  |  | YES |  |  |  |  | 1
Schedule 20 | 3.2 |  |  |  | YES |  |  |  |  | 1
0
Schedule 29 | Introduction | [6 empty] | YES |  | 1
Schedule 29 | 1 | [8 empty] | 0
Schedule 29 | 1A | [8 empty] | 0
Schedule 29 | 2 | [8 empty] | 0
Schedule 29 | 3 | [8 empty] | 0
Schedule 29 | 4 | [6 empty] | YES |  | 1
Schedule 29 | 5 | [6 empty] | YES |  | 1
Schedule 29 | 6 | [6 empty] | YES |  | 1
Schedule 29 | 7 | [8 empty] | 0
Schedule 29 | 8 | [8 empty] | 0
Schedule 29 | 9 | [8 empty] | 0
Schedule 29 | 10 | [8 empty] | 0
Schedule 29 | 11 | [8 empty] | 0
Schedule 29 | 11A | [8 empty] | 0
Schedule 29 | 12 | [8 empty] | 0
Schedule 29 | 13 | [8 empty] | 0
Schedule 29 | 14 | [8 empty] | 0
Schedule 29 | 15 | [8 empty] | 0
Schedule 29 | 16 | [8 empty] | 0
Schedule 29 | 17 | [8 empty] | 0
Schedule 29 | 18 | [8 empty] | 0
Schedule 29 | 19 | [8 empty] | 0
Schedule 29 | 20 | [8 empty] | 0
Schedule 29 | 21 | [8 empty] | 0
Schedule 29 | 22 | [8 empty] | 0
Schedule 29 | 23 | [8 empty] | 0
Schedule 29 | 24 | [8 empty] | 0
Schedule 29 | 25 | [8 empty] | 0
Schedule 29 | 26 | [8 empty] | 0
Schedule 29 | 27 | [8 empty] | 0
Schedule 29 | 28 | [8 empty] | 0
Schedule 29 | 29 | [6 empty] | YES |  | 1
Schedule 29 | 30 | [8 empty] | 0
Schedule 29 | 31 | [8 empty] | 0
Schedule 29 | 32 | [8 empty] | 0
Schedule 29 | 33 |  | YES | [6 empty] | 1
Schedule 29 | 34 |  | YES | [6 empty] | 1
Schedule 29 | 35 | [8 empty] | 0
Schedule 29 | 36 | [8 empty] | 0
Schedule 29 | 37 | [8 empty] | 0
Schedule 29 | 38 | [8 empty] | 0
Schedule 29 | 39 | [8 empty] | 0
Schedule 29 | 40 | [8 empty] | 0
Schedule 29 | 41 | [8 empty] | 0
Schedule 29 | 42 | [8 empty] | 0
Schedule 29 | 43 | [8 empty] | 0
Schedule 29 | 44 | [8 empty] | 0
Schedule 29 | 45 | [8 empty] | 0
Schedule 29 | 46 | [8 empty] | 0
Schedule 29 | 46A | [8 empty] | 0
Schedule 29 | 47 | [8 empty] | 0
Charging Methodology CPs Legal Text Overlap Tracker