## Sheet1
ID | Task Owner | Task | Relating To | Date Assigned | Date Due | Notes | Date Completed
01_01 | Lee Wells | Set out examples of £200K and £300K in a simpler format to show how it is being proposed to do this under option 3 and how this gives the same answer as the originally proposed option 5. | N/A | 2023-10-24 | 2023-11-06
01_02 | Lee Wells | For the examples in the spreadsheet which result in a negative charge, show this in simpler terms and illustrate why it would be necessary to take the other approach anyway. | N/A | 2023-10-24 | 2023-11-06
01_03 | Lee Wells | Write an explanation as to why the Proposer's preferred option changed from option 5 to option 3. | N/A | 2023-10-24 | 2023-11-06
01_04 | Lee Wells | Show the difference between the 6 options (using a single scenario) and why it may defer to option 3 in any case. | N/A | 2023-10-24 | 2023-11-06 | This will covered under action 01_02.
01_05 | Tech Sec | Pull together a consulation draft for Lee to put his text into. | N/A | 2023-10-24 | 2023-10-24 | Include with the Final Agenda of the next meeting.
01_06 | Chair | Check with the Panel around including both DNOs and IDNOs voting on DCP 425. | N/A | 2023-10-24 | 2023-11-15 | This will be raised at the next Panel meeting.