## Tranche 4 Int, DS and Trans Txt
INTERNAL Tranche 4 Interfaces/Data Specifications and Transition Text Consultation Consolidated Comments Log
Comment ID | Code Artefact Name | Document Section | Comments | Comment Theme | Related Design Artefact | Related Design Artefact Section/Step | Suggested Change e.g. proposed wording | Comment Owner | Organisation | Constituency | Submitted | Triage Status | Drafting change? | Triage Response Reason | Programme Response e.g.clarification or update on the change
CD4-079 | DCUSA MHHS Transitional Text | Clause 1 Definitions and Interpretation | Typo - 'Smart Data Service Agent' – Replace ‘Agent’ with ‘Agent’ | Minor Drafting Error(s) |  |  | Replace ‘Agent’ with ‘Agent’ | Andrew Sherry | Electricity North West Limited | Network Operator | 2023-10-27 | Accepted | Yes | Minor Change relating to code ​ | the suggested change is the same as written in the legal text although having checked with the MP the response was related to a 't' missing at the end of Agent. Agreed that this should be added (same response as CD4-163)
CD4-080 | DCUSA MHHS Transitional Text | Glossary of terms used in Schedule 16 | Definition - Domestic Premise Indicator has the meaning given to the term in the Energy Data Market Specification | Minor Drafting Error(s) |  |  | Amend Definition to Domestic Premises Indicator has the meaning given to the term in the Energy Market Data Market Specification | Andrew Sherry | Electricity North West Limited | Network Operator | 2023-10-27 | Accepted | Yes | Minor Change relating to code ​ | agree with the suggested change (same as CD4- 167)
CD4-081 | DCUSA MHHS Transitional Text | 132C | The document refers to the Connection Type as determining if an MPAN is billed via aggregated billing or not. Should this be Market Segment? | General Drafting Comment |  |  | replace connection type with Market Segment | Tracey Dunne | Electricity North West Limited | Network Operator | 2023-10-27 | Rejected | No | Out of Design Scope ​ | Within a Market Segment you can have MPANs settled on an aggregated basis and a site specific basis. The differentiator is the Connection Type. This is catered for both in different paragraphs within schedule 16; Connection Type that is whole current in 132C and for Connection Type that is 'not whole current' in 135A. No. IF-21 is received for all not-W connection types.
CD4-162 | DCUSA MHHS Transitional Text | Definitions | Some of the new terms (such as Industry Standing Data) refer to the Balancing and Settlement Code and others (such as Market-wide Data Service) refer to the BSC - should these references be consistent across this section? Suggest always using Balancing and Settlement Code. | General Drafting Comment |  |  | Amend references to the BSC to refer to the Balancing and Settlement Code. | Paul Saker | EDF | Large Supplier | 2023-11-01 | Rejected | No | Minor Change relating to code ​ | I agree that consistency would be helpful, but to do so would mean amending definitions not impacted by the MHHS Programme. This suggestion can be raised with the DCUSA Panel as a potential housekeeing change.
CD4-163 | DCUSA MHHS Transitional Text | Definitions | Typo - 'Smart Data Service Agen' should be 'Smart Data Service Agent' | Minor Drafting Error(s) |  |  | Correct typo | Paul Saker | EDF | Large Supplier | 2023-11-01 | Accepted | Yes | Minor Change relating to code ​ | Agreed that this should be amended (same response as CD4-79)
CD4-164 | DCUSA MHHS Transitional Text | Definitions | Typo - in the defintion of Supercustomer DUoS Report, 'Energy Data Market Specification' should be 'Energy Market Data Specification' | Minor Drafting Error(s) |  |  | Correct typo | Paul Saker | EDF | Large Supplier | 2023-11-01 | Accepted | Yes | Minor Change relating to code ​ | agree with the suggested change
CD4-165 | DCUSA MHHS Transitional Text | Definitions | Unmetered Supply Certificate - I am not sure why this defintion has been amended as it would seem to be equally applicable to the MHHS arrangements. | General Drafting Comment |  |  | Explain why this has been amended. | Paul Saker | EDF | Large Supplier | 2023-11-01 | Rejected | No | Minor Change relating to code ​ | The certificate is still applicable to both the existing arrangements and the MHHS arrangments. The suggested deletion is to simplfy the text rather than refer to some of the contents and not all contents contained within the Unmetered Supplies Procedure. the contents of the certificate are defined in the unmetered supplies procedure
CD4-166 | DCUSA MHHS Transitional Text | Definitions | Unmetered Supplies Procedure - suggest amending 'or for MHHS' to 'which for MHHS' | General Drafting Comment |  |  | Amend text for clarity | Paul Saker | EDF | Large Supplier | 2023-11-01 |  |  | Minor Change relating to code ​ | 'or' or 'which'? For discussion we have used 'or for MHHS' twenty three times and which for MHHS once (in schedule 16 Para 128)
CD4-167 | DCUSA MHHS Transitional Text | Glossary of Terms used in this Schedule 16 (Page 225) | Typo - in the defintion of Domestic Premise Indicator, 'Energy Data Market Specification' should be 'Energy Market Data Specification' | Minor Drafting Error(s) |  |  | Correct typo | Paul Saker | EDF | Large Supplier | 2023-11-01 | Accepted | Yes | Minor Change relating to code ​ | agree with the suggested change (same as CD4- 080)
CD4-169 | DCUSA MHHS Transitional Text | General | Should the DCUSA drating should reference Line Loss Factor Identifier? We undertand that Line Loss Factor Class ID (LLFC ID) as we know it will change at MHHS to become DUoS Tariff ID and Line Loss Factor Identifier (LLF ID), the document only references to DUoS Tariff ID with no references to Line Loss Factor Identifier. | General Drafting Comment |  |  | Clarify whether Line Loss Factor Identifier should be referenced in the DCUSA text. | Paul Saker | EDF | Large Supplier | 2023-11-01 | Rejected | No | Minor Change relating to code ​ | The LLF ID is not used in DCUSA, only the LLFC ID and the proposed DUoS Tariff ID, so no reference to it is required No. It is not required in DCUSA
CD4-200 | DCUSA MHHS Transitional Text | PG 28 | have not been able to tie bacxk to terms "DUoS Tariff ID" to the BSC or ISD - are these to be definined latterly (section X) | General Drafting Comment | na | na | Clarification | Lee Stone | Npower Commercial Gas Limited (eon I&C). | I&C Supplier | 2023-11-01 | Rejected | No | Out of Code Scope | ISD Entity 17
CD4-201 | DCUSA MHHS Transitional Text | PG 28 | have not been able to tie bacxk to terms "Industry Standing Data" to the BSC or ISD - are these to be definined latterly (section X) | General Drafting Comment | na | na | Clarification | Lee Stone | Npower Commercial Gas Limited (eon I&C). | I&C Supplier | 2023-11-01 | Rejected | No | Out of Code Scope | BSCP707 covers changes to Industry Standing Data with this being capitalised within the document. I suspect that the last act will be to review all the defintions and update Schedule X but from a DCUSA perspective we need to refer to the code that owns the process. may not be defined in a published document yet. Is referred to as such in 3.5.2 of Annex S3 "SVA rules for migrated MHHS metering systems

## Triage and Clarification Status
Triage status | Description​
​
Accepted ​ | Comment has been accepted and change has been made to code drafting.​​
Rejected​ | Comment reject - not consistent with Design. No change will be made to code drafting.​​
Acknowledge​ | Comment is not related to the code artefacts but may be picked up in a later tranche or further clarification, will be provided to the comment raiser.​​
Requires further clarification with PP​ | Comment is not fully understood by the code reviewer and requires clarification with the comment raiser.​​
Clarification Provided​ | No change made - clarification is provided to respond to reviewers comment​
Triage response​ reason | Triage clarification response​
​
Out of Code Scope | Outside of MHHS Code drafting parameters
Out of Design Scope ​ | Outside of current Design parameters
Later Tranche​ | Acknowledge this will be delivered in a later tranche​
Minor Change relating to code ​ | Small change required to the code drafting content
Major Change relating to code ​ | Large change required to the code drafting content
Design Query ​ | Comment is relating to the MHHS Design and not the Code drafting ​​
Comment theme | Reviewer comment theme
Design Translation | Design not correctly translated into Code
Missing Content - Design | Expected content in Design for the Topic Area not documented
Missing Content - Existing Code | Expected content in Code for the Topic Area not documented
Minor Drafting Error(s) | Grammar, punctuation, spelling, formatting and other minor inconsistencies
Document Layout and Structure | Code Artefact could be better or more logically structured (propose alternative)
General Drafting Comment | Any comment on code drafting not covered by the above