## Action Log
DCP 428 ‘Zero REP-002/A Data’ Action Log |  |  | 2023-12-18
I.D | Task Owner | Task | Relating To | Date Assigned | Date Due | Notes | Date Completed
01_01 | Alysson Peña | Draft a DCP 428 consultation | DCP 428 consultation | 2023-11-08 | 2023-11-08 |  | 2023-12-11
01_02 | Alysson Peña | Issue draft consultation to Working Group for review | DCP 428 consultation | 2023-11-08 | 2023-11-08 |  | 2023-12-11
02_01 | Dylan Townsend | Secretariat to draft the RFI and then to issue to the Working Group for review with the intent being that it is issued early January | DCP 428 RFI | 2023-12-11 | 2023-12-18

## Decisions Log
DCP 428 ‘Zero REP-002/A Data’ Decisions Log |  |  |  |  | 2023-12-18
Decision Ref | Date | Minutes # | Paragraph # | Decision Description | Notes / Additional Context (if applicable) | Decision Outcome | Next Steps
01_01 | 2023-11-08 | WG_01 | 4.6 | Working Group members agreed with the proposed DCP 428 solution to be contained in the consultation. |  | Approved (Unanimous) | Draft and issue DCP 428 consultation.
02_01 | 2023-12-11 | WG_02 | 3.4 | Working Group agreed to draft and then issue a short RFI to obtain responses to some questions which fell out of the review of responses to the consultation |  | Approved (Unanimous) | Draft and issue short RFI seeking input on whether it would be accpetable not to issue zero value invoices and to better understand the potential scale of the issue

## Work Plan
DCP 428 ‘Zero REP-002/A Data’ Work Plan |  | 2023-12-18
No. | Event | Target Date
1 | First Working Group meeting | 2023-11-08
2 | Consultation Document Issued | 2023-11-17
3 | Consultation Responses Due [based on three-week consultation period] | 2023-12-08
4 | Second Working Group meeting | 2023-12-11
5 | RFI Document Issued | 2024-01-02
6 | RFI Responses Due [based on two-week RFI period] | 2024-01-16
7 | Third Working Group meeting | 2024-01-22
8 | Legal Text Review by DCUSA Legal Advisers | 2024-01-29
9 | Fourth Working Group meeting | TBC February 2024
10 | Change Report Submitted to DCUSA Panel (paper day) | 2024-03-13
11 | DCUSA Panel Approves Change Report | 2024-03-20
12 | Change Report Issued for Voting | 2024-03-21
13 | Voting Closes [based on three-week voting period] | 2024-04-11
14 | Change Declaration Issued | 2024-04-15
15 | Authority Decision | TBC
16 | Implementation Date | 2025-04-01

## Version Control
DCP 428 ‘Zero REP-002/A Data’ Version Control |  |  |  | 2023-12-18
Purpose
The purpose of this document is to ensure that different drafts and versions of Working Group documents are effectively managed. It will provide an audit trail for the revisions and updates.
Consultation
Author | Owner | Version | Details | Effective Date
Richard Colwill | Richard Colwill | 0.1 | Initial draft as per action from WG 01. | 2023-11-14
Richard Colwill/ Peter Waymont | Richard Colwill | 0.2 | Clarity sought on aspect of solution | 2023-11-14
Richard Colwill | Richard Colwill | 1 | Final Document Issued | 2023-11-17
Legal Text
Author | Owner | Version | Details | Effective Date
Peter Waymont | Richard Colwill | 0.1 | As original Change Proposal | 2023-08-25
Peter Waymont / Dylan Townsend | Richard Colwill | 0.2 | Updated text provided by UKPN as part of consultation response and comments added during WG meeting 02 | 2023-12-11
Change Report
Author | Owner | Version | Details | Effective Date
0.1

## Lists (hidden)
Decision Outcome
Approved (Majority)
Approved (Unanimous)
Rejected (Majority)
Rejected (Unanimous)
No Decision Reached