## CPs
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status Changed in the last month | Date Issued to Ofgem | Original Expected Decision Date | Latest Expected Decision Date
STATUS - INITIAL ASSESSMENT
No
STATUS - DEFINITION
DCP 325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20. | The intent of this Change Proposal is to combine, review and if appropriate, amend the requirements of Section 35A, Section 35B, Schedule 15 and Schedule 20 to improve transparency and efficiency in the data published by DNOs | General | 2 | Richard Colwill / Melissa Kendal | N/A | 2018-11-07 | 11 | No | Next scheduled release following approval | The DCP 325 Working Group is looking to issue a consultation to industry shortly. | N/A
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | The intent of this modification is to define “Mixed Demand” Sites and apply a proportionate Residual charge where a Site meets the mixed demand definition. | General | 1 | John Lawton / Andy Green | Andrew Malley | 2021-04-14 | 17 | No | TBC | The Working Group met on 02 October to review the need for a BSC change. It was agreed that a BSC change was required and that DCP 388 couldn’t be progressed until the BSC change had been defined so DCP 388 has been paused. | N/A
DCP 412 | Discounts from TCR charges for ‘peaky’ final demand customers | This Change Proposal aims to create a discount against the residual charge for ‘peaky’ customers, removing the disproportionate impact of allocating residual charges on the basis of the Agreed Supply Capacity. | CDCM / EDCM | 1 | Andy Green / Craig Booth | Andrew Malley | 2022-10-11 | 29 | No | TBC | The DCP 412 Working Group plan to meet again in January to further develop the second consultation documents. | N/A
DCP 415 | Replacement of D0242/D0315 for MHHS | To create a new DCUSA owned DIP data message for supercustomer billing statements using MHHS data. | Billing | 2 | Hannah Proffitt / Craig Booth | N/A | 10/22/2022 | 3 | No | TBC (dependent on date required for DIP testing) | The Change Report was submitted to the Panel for review in the February Panel meeting. The Panel agreed that it would not progress to Party voting and that it should be sent back to the Working Group but that the Working Group won’t need to meet until the MHHS Programme have been able to carry out an Impact Assessment for the solution they developed. It was noted that even then, no further work may be required but that it was too early to know that for sure. | N/A
DCP 416 | Electronic Invoicing Post MHHS | To create a new DCUSA owned DIP data message for electronic Distributor billing post MHHS. | Billing | 2 | Melissa Kendal / Andy Green | N/A | 2022-11-14 | 5 | No | TBC (dependent on date required for DIP testing) | The Working Group have reviewed the consultation responses and met on 23 June 2023 to finalise the conclusions to the second consultation. A decision on whether or not a Change Report is to be produced is to be made by the Panel but the Proposer has initated a MHHS Change Request for the CP to be impact assessed and so it is expected that DCP 416 will be put on hold, pending outcome of the MHHS Change Request. | N/A
DCP 417 | Ability for the DCUSA Secretariat to Raise Change Proposals | This change seeks to grant the ability to the Secretariat to raise Change Proposals where it identifies a change that would better facilitate the DCUSA Objectives and to introduce an obligation for the Secretariat to raise Change Proposals in certain circumstances, such as at the direction of the Authority. | General | 1 | Melissa Kendal / Richard Colwill | Nadir Hafeez | 2022-12-14 | 8 | No | Next scheduled release following approval | The DCP 417 Working Group is currently developing a Change Report and plan to issue it to the DCUSA Panel for the February meeting scheduled for 21 February 2024. | N/A
DCP 419 | Pre-Notifications of Planned Supply De-Energisations | This change seeks to ensure that all DCUSA Parties, that de-energise metering equipment as part of any planned work, provide the Distributor with advance notification of the supply interruption. | General | 1 | Alysson Pena / | TBC | 2023-03-06 | 8 | No | Next scheduled release following approval | The next DCP 419 Working Group is scheduled for 11 January 2024, where the Working Group will continue to review and refine proposed solution. | N/A
DCP 420 | Include Car Charging Stations In The Definition For Non Final Demand | This change proposal aims to expand the definition of Non Final Demand to include Non Domestic sites which are solely for the use of charging vehicles where electricity is sold with a commercial transaction to a private user. These are to include e.g. Council run services, electric charging stations at car parks and service stations or petrol forecourts but are not to include private fleet charging stations. This is a temporary fix to be put in place until the charging stations included are commercially viable. | General | 1 | Craig Booth / Richard Colwill | TBC | 2023-03-29 | 4 | No | - | The next DCP 420 Working Group is scheduled for 11 January 2024, where the Working Group will continue to consider potential solutions. | N/A
DCP 421 | Update the Tables in schedule 15 of DCUSA | To amend the current tables within Schedule 15 of DCUSA to correctly represent ED2 revenue. | General | 2 | Craig Booth / Andy Green | N/A | 2023-04-12 | 4 | No | Next scheduled release following approval | Modelling work has been completed and has been reviewed by NPg, who confirm it appears to work as required. | N/A
DCP 423 | LDNO Discounts for negative scaling | The purpose of this change proposal is to set a floor on the LDNO discount applied to negative tariff components, after scaling, for demand tariffs. The intent of this change proposal is to seek to remedy what the proposer believes is an unintended outcome of the implementation of Ofgem’s Targeted Charging Review where LDNO tariffs can be higher than the equivalent all-the-way tariff i.e. the LDNO margin is negative for that component. | CDCM | 1 | Melissa Kendal / Andy Green | TBC | 2023-05-09 | 2 | No | 2025-04-01 | The next DCP 423 Working Group is scheduled for 23 January 2024, where they will review the modelling feedback and continue to develop a consultation. | N/A
DCP 424 | Use of System charging for complex sites | This change proposal enables the correct DUoS to be paid by meters that are class F or G within a Class 5 or Class 6 Complex Site as described in BSC Modification P441 (where netting of Import and Export takes place for BSC Settlement purposes) in a practical manner. Under p441 where generation and demand are netted before settlement, the gross values must be added to the D0036 or D0275 to ensure the correct DUoS is charged. However, for class F and G the MPAN counts are included on the D0030 data flows but the volumes are zero. In order for the volumes to be correctly charged DUoS it is proposed that these volumes are included in the D0036 or D0275 using a pseudo MPAN for the gross value. | CDCM | 1 | Andy Green / Craig Booth | TBC | 2023-05-10 | 6 | No | Aligned to BSC Mod P441 Implementation Date | DCP 424 has been delayed due a request by Ofgem for further impact analysis on the proposed BSC solution (P441 - Creation of Complex Site Classes). The DCP 424 consultation is now estimated to be released in Q1 2024. | N/A
DCP 425 | Cost Apportionment Factor “cap” Methodology | The intent of this Change Proposal (“CP”) is to provide further clarification as to how costs of Reinforcement are apportioned between the Company and the Customer (a Generation Connection) when the High-Cost Project Threshold is triggered. | General | 1 | Richard Colwill/ Craig Booth | TBC | 2023-07-13 | 4 | No | 2023-12-19 | The next DCP 425 Working Group is scheduled for 19 January 2024. The aim is to issue the Change Report to the February Panel scheduled for 21 February 2024. | N/A
DCP 428 | Zero REP-002/A Data | To specify how parties should deal with zero or blank data in the supercustomer/aggregated billing messages when sending daily statements or raising invoices. | General | 2 | Richard Colwill/ Alysson Peña | TBC | 2023-07-25 | 2 | No | 2024-04-01 | The DCP 428 Working Group plan to issue an RFI to industry early January and are preparing to issue the Change Report to the February Panel scheduled for 21 February 2024. | N/A
STATUS - CHANGE REPORT
DCP 429 | Obtaining an Independent Credit Assessment | The purpose of this change proposal seeks to update DCUSA Schedule 1 Clause 2.6 that refers to the Company obtaining an Independent Credit Assessment from a recognised Credit Assessment Agency chosen by the User. | General | 2 | Richard Colwill/ Alysson Peña | TBC | 2023-09-12 | 3 | No | 2025-04-01 | The DCP 429 Change Report will be issued to the Panel for review on 17 January 2024, if approved it will be issued for voting on 19 January 2024. | CHANGE REPORT
DCP 432 | Amend the Recognised Credit Assessment Agency table in Schedule 1 | To bring into effect the change from Graydon to Creditsafe ratings and to reflect the fact that Experian no longer provides Bronze, Silver or Gold reports. | General | 2 | Dylan Townsend | N/A | 2023-12-13 | N/A | No | 2024-02-29 | DCP 432 was presented to the DCUSA Panel on 20 December 2023 and was approved to progress to Change Report. The Change Report will be presented at the Panel meeting scheduled for 17 January 2024, with the aim of issuing out to vote on 18 January 2024. | CHANGE REPORT
STATUS - VOTING
DCP 430 | Reducing Good Payment Record | To clarify how Distributors should deal with late payments in considering good payment record reductions. | General | 2 | Alysson Peña | N/A | 2023-10-02 | N/A | No | 2024-02-29 | DCP 430 was presented to the Panel on 18 October 2023 and was approved to progress to Change Report. The Change Report was presented at the DCUSA Panel meeting scheduled for 20 December 2023 and issued for voting on 21 December 2023. The deadline for responses is set at 16 January 2024. | VOTING
DCP 431 | Party Novation Process | The intent of this Change Proposal (“CP”) is to add clarity to the DCUSA for how a Party can transfer its rights and obligations to another Party via a novation agreement. | General | 2 | George Kester | N/A | 2023-10-10 | N/A | No | 2024-02-29 | DCP 431 was presented to the Panel on 18 October 2023 and was approved to progress to Change Report. The Change Report was presented at the DCUSA Panel meeting scheduled for 20 December 2023 and issued for voting on 21 December 2023. The deadline for responses is set at 16 January 2024. | VOTING
STATUS - AWAITING AUTHORITY CONSENT
DCP 392 | Charging of Third Party DNO works to transmission connection users. | To apply the common connection charging method (CCCM) to all electricity connections in respect of DNO works, regardless of whether they are directly connected to a distribution system or not, and to apply the equivalent of the Electricity (Connection Charges) Regulations (ECCR) for reimbursement to the transmission-connected customer where cost apportionment factor (CAF) rules do not apply so that full charge for works is initially made to the transmission connected customer. | CCCM | 1 | Hannah Proffitt / John Lawton | Dafydd Burton | 2021-12-07 | 16 | No | Next scheduled release or within one month of Authority Consent | Voting closed on 14 November 2022 and a Change Declaration was issued to the Authority on 18 November 2022 with a recommendation from Parties to reject DCP 392. | N/A | 18 November 2022 | 2023-04-01 | 2024-01-15
DCP 411 | Charging De-energised sites | To remove the different treatment of DUoS with respect to de-energised sites | CDCM | 1 | Andy Green / Craig Booth | TBC | 2022-07-13 | 11 | No | 2025-04-01 | The Change Report was issued following approval during the May Panel meeting. Voting has concluded, with the change declaration issued to Ofgem on 14/06/2023. | N/A | 2023-06-14 | 2023-11-30 | 2024-01-31
STATUS - AWAITING IMPLEMENTATION
2024-04-01
DCP 395 | Allocation of Smart Meter Communication Licence costs within LDNO Tariffs | To increase the cost reflectivity of LDNO tariffs by appropriately allocating costs associated with the smart meter communication licence to LDNO tariffs | General | 1 | John Lawton / George Dawson |  | 2021-05-10 | 3 | No | 2024-04-01 | The DCP 395 Working Group issued a consultation to industry in March 2022, with responses due by 12 April. The Working Group met on 25 April to review the consultation responses and agreed the final solution. The Change Report was presented to the Panel during the May Panel meeting, where it was approved to be issued for Party voting. | N/A
DCP 414 | Transitional Protection for NHH CT Customers affected by regulatory change | This change proposal seeks to provide transitional protection for Non Half-Hourly Current Transformer customers moving to Half-Hourly settlement & prevent penal excess capacity charges being applied to customers in any instance that the Maximum Import Capacity is a zero value because there is no site-specific connection agreement in place between users & Distribution Network Operators. | General | 1 | Andy Green / John Lawton | Danielle Walton | 2022-10-18 | 8 | No | 29 June 2023 or April 2024 | The Change Report was issued following last month’s Panel meeting and voting has concluded, with the change declaration issued on 14/06/2023. | N/A | 2023-06-14 | 2023-07-31 | 2023-07-31
STATUS - SENT BACK
N/A | N/A | [7 empty] | No |  |  | N/A
STATUS - IMPLEMENTED
N/A | N/A | [7 empty] | No |  |  | N/A
STATUS - REJECTED
N/A | N/A | [7 empty] | No |  |  | N/A
STATUS - WITHDRAWN
N/A | N/A | [7 empty] | No |  |  | N/A
Change Register - January 2024

## Status Change
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status Changed in the last month
DCP 429 | Obtaining an Independent Credit Assessment | The purpose of this change proposal seeks to update DCUSA Schedule 1 Clause 2.6 that refers to the Company obtaining an Independent Credit Assessment from a recognised Credit Assessment Agency chosen by the User. | General | 2 | Richard Colwill/ Alysson Peña | TBC | 2023-09-12 | 2 | No | 2025-04-01 | The DCP 429 Working Group met on 13 November 2023 and then again on 20 November and subsequently issued their consultation to industry on 22 November 2023 with a closing date of 13 December. The next meeting of the Working Group is scheduled for 18 December, where the group will review the consultation responses and determine next steps.. | CHANGE REPORT
DCP 430 | Reducing Good Payment Record | To clarify how Distributors should deal with late payments in considering good payment record reductions. | [5 empty] | N/A | No | 2024-02-29 | DCP 430 was presented to the Panel on 18 October 2023 and was approved to progress to Change Report. The Change Report was presented at the DCUSA Panel meeting scheduled for 20 December 2023 and issued for voting on 21 December 2023. The deadline for responses is set at 16 January 2024. | VOTING
DCP 431 | Party Novation Process | The intent of this Change Proposal (“CP”) is to add clarity to the DCUSA for how a Party can transfer its rights and obligations to another Party via a novation agreement. | [5 empty] | N/A | No | 2024-02-29 | DCP 431 was presented to the Panel on 18 October 2023 and was approved to progress to Change Report. The Change Report was presented at the DCUSA Panel meeting scheduled for 20 December 2023 and issued for voting on 21 December 2023. The deadline for responses is set at 16 January 2024. | VOTING
DCP 432 | Amend the Recognised Credit Assessment Agency table in Schedule 1 | To bring into effect the change from Graydon to Creditsafe ratings and to reflect the fact that Experian no longer provides Bronze, Silver or Gold reports. | [5 empty] | N/A | No | 2024-02-29 | DCP 432 was presented to the DCUSA Panel on 20 December 2023 and was approved to progress to Change Report. The Change Report will be presented at the Panel meeting scheduled for 17 January 2024, with the aim of issuing out to vote on 18 January 2024. | CHANGE REPORT
Status Change - January 2024

## Timetables
DCP | 428 | Part 1/ Part 2 Matter | Standard/ Urgent | Proposer | Party | Technical Secretariat | Chair | Timetable Change |  | 2024 | [11 empty] | Notes
[9 empty] | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
431 | Party Novation Process | Part 2 | Standard | David Ballantyne | UKPN | George Kester |  | No | bar: Dec to 2024 Jan
430 | Reducing Good Payment Record | Part 2 | Standard | Peter Waymont | UKPN | Alysson Peña |  | No | bar: Dec to 2024 Jan
429 | Obtaining an Independent Credit Assessment | Part 2 | Standard | Donna Butcher | UKPN | Alysson Peña | Richard Colwill | No | Dec: Def; 2024 Jan: Def; 2024 Feb: Def; 2024 Mar: CR; 2024 Apr: CD
Propose new time table for DCP 429 | [8 empty] | Dec: Def; 2024 Jan: CR; 2024 Feb: CD | The Working Group has finished its actions early.
428 | Zero REP-002/A Data | Part 2 | Standard | Peter Waymont | UKPN | Alysson Peña | Richard Colwill | No | Dec: Def; 2024 Jan: Def; 2024 Feb: Def; 2024 Mar: CR; 2024 Apr: CD
425 | Cost Apportionment Factor “cap” methodology | Part 1 | Standard | Lee Wells | NPg | Alysson Peña | Richard Colwill | No | Dec: Def; 2024 Jan: CR; 2024 Feb: CD; 2024 Mar: WO
Propose new time table for DCP 425 | [8 empty] | Dec: Def; 2024 Jan: Def; 2024 Feb: CR; 2024 Mar: CD | The Working Group needed more time to finalise the solution.
424 | Use of System charging for complex sites | Part 1 | Standard | Mary Gillie | NPg | Craig Booth | Andy Green | No | Dec: Def; 2024 Jan: CR; 2024 Feb: CD; 2024 Mar: WO
423 | LDNO Discounts for negative scaling | Part 1 | Standard | Tom Cadge | ENC | Melissa Kendall | Andy Green | No | Dec: Def; 2024 Jan: CON; 2024 Feb: Def; 2024 Mar: CR; 2024 Apr: CD; 2024 May: WO
421 | Update the Tables in schedule 15 of DCUSA | Part 1 | Standard | Dave Wornell | NGED | Craig Booth | Andy Green | No | Dec: CR; 2024 Jan: CD; 2024 Feb: WO
Propose new time table for DCP 421 | [8 empty] | Dec: Def; 2024 Jan: Def; 2024 Feb: CR; 2024 Mar: CD; 2024 Apr: WO | The Working Group needed more time to review and test the modelling.
420 | Include Car Charging Stations In The Definition For Non Final Demand | Part 1 | Standard | Dave Wornell | NGED | Craig Booth | Richard Colwill | No | Dec: Def; 2024 Jan: CR; 2024 Feb: CD; 2024 Mar: WO
Propose new time table for DCP 420 | [8 empty] | Dec: Def; 2024 Jan: Def; 2024 Feb: Def; 2024 Mar: Def; 2024 Apr: CR; 2024 May: CD; 2024 Jun: WO | The Working Group needed more time to review and test the modelling.
419 | Pre-notification of Planned Supply De-energisations | Part 1 | Standard | Nikhel Jethwa | SSEN | Alysson Peña | Richard Colwill | No | Dec: Def; 2024 Jan: CR; 2024 Feb: CD; 2024 Mar: WO
Propose new time table for DCP 419 | [8 empty] | Dec: Def; 2024 Jan: Def; 2024 Feb: Def; 2024 Mar: CR; 2024 Apr: CD; 2024 May: WO | Working Group is continuing to review and refine the proposed solution.
417 | Ability for the DCUSA Secretariat to Raise Change Proposals | Part 1 | Standard | Simon Yeo | NGED | Melissa Kendall | Richard Colwill | No | Dec: CR; 2024 Jan: CD; 2024 Feb: WO
Propose new time table for DCP 417 | [8 empty] | Dec: Def; 2024 Jan: Def; 2024 Feb: CR; 2024 Mar: CD; 2024 Apr: WO | With the issuing of a second consultation, the Working Group is still considering and developing the solution and aim to issue the Change Report in February,
416 | Electronic Invoicing Post MHHS | Part 2 | Standard | Peter Waymont | UKPN | Craig Booth | Andy Green | No | Dec: O/H
415 | Replacement of D0242/D0315 for MHHS | Part 2 | Standard | Peter Waymont | UKPN | Melissa Kendall | Craig Booth | No | Dec: O/H
412 | Discounts from TCR charges for ‘peaky’ final demand customers | Part 1 | Standard | Lee Stone | E.ON | Andy Green | Craig Booth | No | Dec: CON 2; 2024 Jan: Def; 2024 Feb: Def; 2024 Mar: CR; 2024 Apr: CD; 2024 May: WO
Propose new time table for DCP 412 | [8 empty] | Dec: Def; 2024 Jan: Def; 2024 Feb: CON 2; 2024 Mar: Def; 2024 Apr: CR; 2024 May: CD; 2024 Jun: WO | The Working Group is still developing the proposed solution.
388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | Part 1 | Standard | Lee Stone | E.on | Andy Green | John Lawton | No | Dec: Def; 2024 Jan: Def; 2024 Feb: CR; 2024 Mar: CD; 2024 Apr: WO | Dependancy on the related BSC mod.
325 | Reviewing the requirements of Sections 35A (‘Provision of Cost Information’), 35B (‘Production of the Annual Review Pack’), Schedule 15 (‘Cost Information Table’) and Schedule 20 (‘Production of the Annual Review Pack’) | Part 1 | Standard | Kara Burke | NPg | Melissa Kendall | Richard Colwill | No | Dec: Def; 2024 Jan: CON 2; 2024 Feb: Def; 2024 Mar: CR; 2024 Apr: CD; 2024 May: WO
Key
Definition | Def
RFI | RFI
Consultation | CON/ CON 2
Change Report | CR
Voting/ Change Declaration | CD
With Ofgem | WO
Implementation | Imp
Decision | Dec
Withdrwan | Wd

## Legal Text Overlap Tracker
YES
|  | MHHS | DCP 424 | DCP 325 | DCP 421 | DCP 423 | DCP 395 | DCP 414 | DCP 388 | DCP 412 | DCP 420
|  | Unknown | 2024-04-01 | Next Scheduled | Next Scheduled | 2025-04-01 | 2024-04-01 | 2024-04-01 | TBC | TBC | TBC |  | NOTES TO ASSIST
Schedules | Paragraph Number |  | Definition | Definition | Definition | Definition | Awaiting Implementation | Awaiting Implementation | Definition | Definition | Definition | Number of CPs Impacting Paragraph
Schedule 15 | Table 1 |  |  | YES | YES | [6 empty] | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 2 |  |  | YES | YES | [6 empty] | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 3 |  |  | YES | YES | [6 empty] | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
0
Schedule 16 | Introduction | [10 empty] | 0
Schedule 16 | 1 | [10 empty] | 0
Schedule 16 | 2 | [10 empty] | 0
Schedule 16 | 3 | [10 empty] | 0 | Model reference number and date
Schedule 16 | 4 | [10 empty] | 0
Schedule 16 | 5 | [10 empty] | 0
Schedule 16 | 6 | [10 empty] | 0
Schedule 16 | 7 | [10 empty] | 0
Schedule 16 | 7A | [10 empty] | 0
Schedule 16 | 8 | [10 empty] | 0
Schedule 16 | 9 | [10 empty] | 0
Schedule 16 | 10 | [10 empty] | 0
Schedule 16 | 10A | [10 empty] | 0
Schedule 16 | 11 | [10 empty] | 0
Schedule 16 | 12 | [10 empty] | 0
Schedule 16 | 13 | [10 empty] | 0
Schedule 16 | 14 | [10 empty] | 0
Schedule 16 | 15 | [10 empty] | 0
Schedule 16 | 16 | [10 empty] | 0
Schedule 16 | 17 | [10 empty] | 0
Schedule 16 | 18 | [10 empty] | 0
Schedule 16 | 19 | [10 empty] | 0
Schedule 16 | 20 | [10 empty] | 0
Schedule 16 | 21 | [10 empty] | 0
Schedule 16 | 22 | [10 empty] | 0
Schedule 16 | 23 | [10 empty] | 0
Schedule 16 | 24 | [10 empty] | 0
Schedule 16 | 25 | [10 empty] | 0
Schedule 16 | 26 | [10 empty] | 0
Schedule 16 | 27 | [10 empty] | 0
Schedule 16 | 28 | [10 empty] | 0
Schedule 16 | 29 | [10 empty] | 0
Schedule 16 | 30 | [10 empty] | 0
Schedule 16 | 31 | [10 empty] | 0
Schedule 16 | 32 | [10 empty] | 0
Schedule 16 | 33 | [10 empty] | 0
Schedule 16 | 34 | [10 empty] | 0
Schedule 16 | 35 | [10 empty] | 0
Schedule 16 | 36 | [10 empty] | 0
Schedule 16 | 37 | [10 empty] | 0
Schedule 16 | 38 | [10 empty] | 0
Schedule 16 | 39 | [10 empty] | 0
Schedule 16 | 40 | [10 empty] | 0
Schedule 16 | 41 | [10 empty] | 0
Schedule 16 | 41A | [10 empty] | 0
Schedule 16 | 41B | [10 empty] | 0
Schedule 16 | 42 | [10 empty] | 0
Schedule 16 | 42A | YES | [9 empty] | 1
Schedule 16 | 43 | [10 empty] | 0
Schedule 16 | 44 | YES | [9 empty] | 1
Schedule 16 | 45 | [10 empty] | 0
Schedule 16 | 46 | [10 empty] | 0
Schedule 16 | 47 | [10 empty] | 0
Schedule 16 | 48 | [10 empty] | 0
Schedule 16 | 49 | [10 empty] | 0
Schedule 16 | 50 | [10 empty] | 0
Schedule 16 | 51 | [10 empty] | 0
Schedule 16 | 52 | [6 empty] | YES |  |  |  | 1
Schedule 16 | 52A | [6 empty] | YES |  |  |  | 1
Schedule 16 | 53 | [10 empty] | 0
Schedule 16 | 54 | [10 empty] | 0
Schedule 16 | 55 | [10 empty] | 0
Schedule 16 | 56 | [10 empty] | 0
Schedule 16 | 57 | [10 empty] | 0
Schedule 16 | 58 | [10 empty] | 0
Schedule 16 | 59 | [10 empty] | 0
Schedule 16 | 60 | [10 empty] | 0
Schedule 16 | 61 | [10 empty] | 0
Schedule 16 | 62 | [10 empty] | 0
Schedule 16 | 63 | [10 empty] | 0
Schedule 16 | 64 | [10 empty] | 0
Schedule 16 | 65 | [10 empty] | 0
Schedule 16 | 66 | [10 empty] | 0
Schedule 16 | 67 | [10 empty] | 0
Schedule 16 | 68 | [10 empty] | 0
Schedule 16 | 69 | [10 empty] | 0
Schedule 16 | 70 | YES | [9 empty] | 1
Schedule 16 | 71 | [10 empty] | 0
Schedule 16 | 72 | [10 empty] | 0
Schedule 16 | 72A | [10 empty] | 0
Schedule 16 | 73 | [10 empty] | 0
Schedule 16 | 74 | [6 empty] | YES |  |  |  | 1
Schedule 16 | 75 | [10 empty] | 0
Schedule 16 | 76 | [10 empty] | 0
Schedule 16 | 77 | [10 empty] | 0
Schedule 16 | 78 | [10 empty] | 0
Schedule 16 | 79 | [10 empty] | 0
Schedule 16 | 80 | YES | [5 empty] | YES |  |  |  | 2
Schedule 16 | 81 | [10 empty] | 0
Schedule 16 | 82 | [10 empty] | 0
Schedule 16 | 83 | [6 empty] | YES |  |  |  | 1
Schedule 16 | 84 | [10 empty] | 0
Schedule 16 | 85 | [10 empty] | 0
Schedule 16 | 86 | [10 empty] | 0
Schedule 16 | 87 | [10 empty] | 0
Schedule 16 | 88 | [10 empty] | 0
Schedule 16 | 89 | [10 empty] | 0
Schedule 16 | 90 | [10 empty] | 0
Schedule 16 | 91 | [10 empty] | 0
Schedule 16 | 92 | [10 empty] | 0
Schedule 16 | 92A | [10 empty] | 0
Schedule 16 | 92B | [10 empty] | 0
Schedule 16 | 92C | [10 empty] | 0
Schedule 16 | 93 | [10 empty] | 0
Schedule 16 | 94 | [10 empty] | 0
Schedule 16 | 95 | [10 empty] | 0
Schedule 16 | 96 | [10 empty] | 0
Schedule 16 | 97 | [10 empty] | 0
Schedule 16 | 98 |  |  |  |  | YES | [5 empty] | 1
Schedule 16 | 99 | [10 empty] | 0
Schedule 16 | 100 | [10 empty] | 0
Schedule 16 | 101 | [6 empty] | YES |  |  |  | 1
Schedule 16 | 102 | [10 empty] | 0
Schedule 16 | 102A | [10 empty] | 0
Schedule 16 | 102B | [10 empty] | 0
Schedule 16 | 103 | [10 empty] | 0
Schedule 16 | 104 | [10 empty] | 0
Schedule 16 | 105 | [10 empty] | 0
Schedule 16 | 106 | [10 empty] | 0
Schedule 16 | 107 | [10 empty] | 0
Schedule 16 | 108 | [10 empty] | 0
Schedule 16 | 108A | [10 empty] | 0
Schedule 16 | 109 | [10 empty] | 0
Schedule 16 | 110 | [10 empty] | 0
Schedule 16 | 111 | [10 empty] | 0
Schedule 16 | 112 | [10 empty] | 0
Schedule 16 | 112A | [10 empty] | 0
Schedule 16 | 113 | [10 empty] | 0
Schedule 16 | 113A | [10 empty] | 0
Schedule 16 | 113B | [10 empty] | 0
Schedule 16 | 113C | [10 empty] | 0
Schedule 16 | 113D | [10 empty] | 0
Schedule 16 | 113E | [10 empty] | 0
Schedule 16 | 114 | [10 empty] | 0
Schedule 16 | 115 | [10 empty] | 0
Schedule 16 | 116 | [10 empty] | 0
Schedule 16 | 117 | [10 empty] | 0
Schedule 16 | 118 | [10 empty] | 0
Schedule 16 | 119 | [10 empty] | 0
Schedule 16 | 120 | [10 empty] | 0
Schedule 16 | 121 | [10 empty] | 0
Schedule 16 | 122 | [10 empty] | 0
Schedule 16 | 123 | [10 empty] | 0
Schedule 16 | 124 | [10 empty] | 0
Schedule 16 | 125 | [10 empty] | 0
Schedule 16 | 126 | [10 empty] | 0
Schedule 16 | 127 | [10 empty] | 0
Schedule 16 | 127A | [10 empty] | 0
Schedule 16 | 128 | YES | YES | [8 empty] | 2
Schedule 16 | 129 | YES | [9 empty] | 1
Schedule 16 | 130 | YES | [9 empty] | 1
Schedule 16 | 131 | [10 empty] | 0
Schedule 16 | 132 | YES | [9 empty] | 1
Schedule 16 | 132A | [10 empty] | 0
Schedule 16 | 132B | [10 empty] | 0
Schedule 16 | 132C | YES | [5 empty] | YES |  |  |  | 2
Schedule 16 | 132D | [10 empty] | 0
Schedule 16 | 133 | YES | [9 empty] | 1
Schedule 16 | 134 | [6 empty] | YES |  |  |  | 1
Schedule 16 | 135 | [10 empty] | 0
Schedule 16 | 135A | YES | [5 empty] | YES |  |  |  | 2 | DCP 414 adds two new rows to table for tariffs named 'Domestic Aggregated or CT' and 'Non-Domestic Aggregated or CT' whereas, for MHHS it is proposed to remove the last column containing applicable MC
Schedule 16 | 135B | [10 empty] | 0
Schedule 16 | 136 | [6 empty] | YES |  |  |  | 1
Schedule 16 | 137 | [10 empty] | 0
Schedule 16 | 138 | [10 empty] | 0
Schedule 16 | 139 | [10 empty] | 0
Schedule 16 | 140 | [10 empty] | 0
Schedule 16 | 140A | YES | [9 empty] | 1
Schedule 16 | 140B | YES | [9 empty] | 1
Schedule 16 | 140C | YES | [9 empty] | 1
Schedule 16 | 140D | [10 empty] | 0
Schedule 16 | 140E | [10 empty] | 0
Schedule 16 | 141 | [6 empty] | YES |  |  |  | 1
Schedule 16 | 142 | YES | [9 empty] | 1
Schedule 16 | 143 | YES | [9 empty] | 1
Schedule 16 | 144 | YES | [9 empty] | 1
Schedule 16 | 145 | [10 empty] | 0
Schedule 16 | 146 | [10 empty] | 0
Schedule 16 | 147 | [6 empty] | YES |  |  |  | 1
Schedule 16 | 148 | [10 empty] | 0
Schedule 16 | 149 | [10 empty] | 0
Schedule 16 | 150 | [10 empty] | 0
Schedule 16 | 151 | [10 empty] | 0
Schedule 16 | 152 | [10 empty] | 0
Schedule 16 | 153 | [10 empty] | 0
Schedule 16 | 154 | [10 empty] | 0
Schedule 16 | 155 | [10 empty] | 0
Schedule 16 | 156 | [10 empty] | 0
Schedule 16 | 157 | [10 empty] | 0
Schedule 16 | 158 | [10 empty] | 0
Schedule 16 | 159 | [10 empty] | 0
Schedule 16 | 160 | [10 empty] | 0
Schedule 16 | 161 | [10 empty] | 0
Schedule 16 | 162 | [10 empty] | 0
Schedule 16 | 163 | [10 empty] | 0
Schedule 16 | 164 | [10 empty] | 0
Schedule 16 | 165 | [10 empty] | 0
Schedule 16 | 166 | [10 empty] | 0
Schedule 16 | 167 | [10 empty] | 0
Schedule 16 | 168 | [10 empty] | 0
Schedule 16 | 169 | [10 empty] | 0
Schedule 16 | 170 | [10 empty] | 0
Schedule 16 | 171 | [10 empty] | 0
Schedule 16 | 172 | [10 empty] | 0
Schedule 16 | 173 | [10 empty] | 0
Schedule 16 | 174 | [10 empty] | 0
Schedule 16 | 175 | [10 empty] | 0
Schedule 16 | 176 | [10 empty] | 0
Schedule 16 | 177 | [10 empty] | 0
Schedule 16 | 178 | [10 empty] | 0
Schedule 16 | 179 | [6 empty] | YES |  |  |  | 1
Schedule 16 | 180 | [10 empty] | 0
Schedule 16 | 181 | [6 empty] | YES |  |  |  | 1
Schedule 16 | 182 | [6 empty] | YES |  |  |  | 1
Schedule 16 | 183 | [6 empty] | YES |  |  |  | 1
Schedule 16 | 184 | [6 empty] | YES |  |  |  | 1
Schedule 16 | Glossary | YES | [9 empty] | 1
0
Schedule 17 | Introduction | [10 empty] | 0
Schedule 17 | 1 | [10 empty] | 0
Schedule 17 | 1.1 | [10 empty] | 0
Schedule 17 | 1.2 | [10 empty] | 0
Schedule 17 | 1.3 | [10 empty] | 0 | Model reference number and date
Schedule 17 | 1.3A | [10 empty] | 0
Schedule 17 | 1.4 | [10 empty] | 0
Schedule 17 | 1.5 | [10 empty] | 0
Schedule 17 | 1.6 | [10 empty] | 0
Schedule 17 | 1.7 | [10 empty] | 0
Schedule 17 | 1.8 | [10 empty] | 0
Schedule 17 | 1.9 | [10 empty] | 0
Schedule 17 | 2 | [10 empty] | 0
Schedule 17 | 2.1 | [10 empty] | 0
Schedule 17 | 2.2 | [10 empty] | 0
Schedule 17 | 2.3 | [10 empty] | 0
Schedule 17 | 2.4 | [10 empty] | 0
Schedule 17 | 2.5 | [10 empty] | 0
Schedule 17 | 2.6 | [10 empty] | 0
Schedule 17 | 2.7 | [10 empty] | 0
Schedule 17 | 2.8 | [10 empty] | 0
Schedule 17 | 2.9 | [10 empty] | 0
Schedule 17 | 2.1 | [10 empty] | 0
Schedule 17 | 2.11 | [10 empty] | 0
Schedule 17 | 2.12 | [10 empty] | 0
Schedule 17 | 2.13 | [10 empty] | 0
Schedule 17 | 2.14 | [10 empty] | 0
Schedule 17 | 2.15 | [10 empty] | 0
Schedule 17 | 2.16 | [10 empty] | 0
Schedule 17 | 2.17 | [10 empty] | 0
Schedule 17 | 2.18 | [10 empty] | 0
Schedule 17 | 2.19 | [10 empty] | 0
Schedule 17 | 3 | [10 empty] | 0
Schedule 17 | 3.1 | [10 empty] | 0
Schedule 17 | 3.2 | [10 empty] | 0
Schedule 17 | 3.3 | [10 empty] | 0
Schedule 17 | 3.4 | [10 empty] | 0
Schedule 17 | 3.5 | [10 empty] | 0
Schedule 17 | 3.6 | [10 empty] | 0
Schedule 17 | 3.7 | [10 empty] | 0
Schedule 17 | 4 | [10 empty] | 0
Schedule 17 | 4.1 | [10 empty] | 0
Schedule 17 | 5 | [10 empty] | 0
Schedule 17 | 5.1 | [10 empty] | 0
Schedule 17 | 6 | [10 empty] | 0
Schedule 17 | 6.1 | [10 empty] | 0
Schedule 17 | 6.2 | [10 empty] | 0
Schedule 17 | 6.3 | [10 empty] | 0
Schedule 17 | 7 | [10 empty] | 0
Schedule 17 | 7.1 | [10 empty] | 0
Schedule 17 | 8 | [10 empty] | 0
Schedule 17 | 8.1 | [10 empty] | 0
Schedule 17 | 8.2 | [10 empty] | 0
Schedule 17 | 8.3 | [10 empty] | 0
Schedule 17 | 8.4 | [10 empty] | 0
Schedule 17 | 9 | [10 empty] | 0
Schedule 17 | 9.1 | [10 empty] | 0
Schedule 17 | 9.2 | [10 empty] | 0
Schedule 17 | 9.3 | [10 empty] | 0
Schedule 17 | 10 | [10 empty] | 0
Schedule 17 | 10.1 | [10 empty] | 0
Schedule 17 | 10.2 | [10 empty] | 0
Schedule 17 | 10.3 | [10 empty] | 0
Schedule 17 | 10.4 | [10 empty] | 0
Schedule 17 | 11 | [10 empty] | 0
Schedule 17 | 11.1 | [10 empty] | 0
Schedule 17 | 12 | [10 empty] | 0
Schedule 17 | 12.1 | [10 empty] | 0
Schedule 17 | 12.2 | [10 empty] | 0
Schedule 17 | 12.3 | [10 empty] | 0
Schedule 17 | 13 | [10 empty] | 0
Schedule 17 | 13.1 | [10 empty] | 0
Schedule 17 | 13.2 | [10 empty] | 0
Schedule 17 | 13.3 | [10 empty] | 0
Schedule 17 | 13.4 | [10 empty] | 0
Schedule 17 | 14 | [10 empty] | 0
Schedule 17 | 14.1 | [10 empty] | 0
Schedule 17 | 14.2 | [10 empty] | 0
Schedule 17 | 14.3 | [10 empty] | 0
Schedule 17 | 14.4 | [10 empty] | 0
Schedule 17 | 14.5 | [10 empty] | 0
Schedule 17 | 15 | [10 empty] | 0
Schedule 17 | 15.1 | [10 empty] | 0
Schedule 17 | 15.2 | [10 empty] | 0
Schedule 17 | 15.3 | [10 empty] | 0
Schedule 17 | 15.4 | [10 empty] | 0
Schedule 17 | 15.5 | [10 empty] | 0
Schedule 17 | 15.6 | [10 empty] | 0
Schedule 17 | 15.7 | [10 empty] | 0
Schedule 17 | 15.8 | [10 empty] | 0
Schedule 17 | 15.9 | [10 empty] | 0
Schedule 17 | 15.1 | [10 empty] | 0
Schedule 17 | 15.11 | [10 empty] | 0
Schedule 17 | 15.12 | [10 empty] | 0
Schedule 17 | 15.15 | [10 empty] | 0
Schedule 17 | 16 | [10 empty] | 0
Schedule 17 | 16.1 | [10 empty] | 0
Schedule 17 | 16.2 | [10 empty] | 0
Schedule 17 | 16.3 | [10 empty] | 0
Schedule 17 | 16.4 | [10 empty] | 0
Schedule 17 | 16.5 | [10 empty] | 0
Schedule 17 | 16.6 | [10 empty] | 0
Schedule 17 | 16.7 | [10 empty] | 0
Schedule 17 | 16.8 | [10 empty] | 0
Schedule 17 | 16.9 | [10 empty] | 0
Schedule 17 | 16.1 | [10 empty] | 0
Schedule 17 | 17 | [10 empty] | 0
Schedule 17 | 17.1 | [10 empty] | 0
Schedule 17 | 17.2 | [10 empty] | 0
Schedule 17 | 17.3 | [10 empty] | 0
Schedule 17 | 18 | [10 empty] | 0
Schedule 17 | 18.1 | [10 empty] | 0
Schedule 17 | 18.2 | [10 empty] | 0
Schedule 17 | 18.3 | [10 empty] | 0
Schedule 17 | 18.4 | [10 empty] | 0
Schedule 17 | 18.5 | [10 empty] | 0
Schedule 17 | 18.6 | [10 empty] | 0
Schedule 17 | 18.7 | [10 empty] | 0
Schedule 17 | 18.8 | [10 empty] | 0
Schedule 17 | 18.9 | [10 empty] | 0
Schedule 17 | 18.1 | [10 empty] | 0
Schedule 17 | 18.11 | [10 empty] | 0
Schedule 17 | 18.12 | [10 empty] | 0
Schedule 17 | 18.13 | [10 empty] | 0
Schedule 17 | 18.14 | [10 empty] | 0
Schedule 17 | 18.15 | [10 empty] | 0
Schedule 17 | 18.16 | [10 empty] | 0
Schedule 17 | 18.17 | [10 empty] | 0
Schedule 17 | 18.18 | [10 empty] | 0
Schedule 17 | 18.19 | [10 empty] | 0
Schedule 17 | 18.2 | [10 empty] | 0
Schedule 17 | 18.21 | [10 empty] | 0
Schedule 17 | 19 | [10 empty] | 0
Schedule 17 | 19.1 | [10 empty] | 0
Schedule 17 | 19.2 | [10 empty] | 0
Schedule 17 | 19.3 | [10 empty] | 0
Schedule 17 | 19.4 | [10 empty] | 0
Schedule 17 | 19.5 | [10 empty] | 0
Schedule 17 | 19.6 | [10 empty] | 0
Schedule 17 | 19.7 | [10 empty] | 0
Schedule 17 | 19.8 | [10 empty] | 0
Schedule 17 | 19.9 | [10 empty] | 0
Schedule 17 | 19.1 | [10 empty] | 0
Schedule 17 | 19.11 | [10 empty] | 0
Schedule 17 | 20 | [10 empty] | 0
Schedule 17 | 20.1 | [10 empty] | 0
Schedule 17 | 20.2 | [10 empty] | 0
Schedule 17 | 20.3 | [10 empty] | 0
Schedule 17 | 20.4 | [10 empty] | 0
Schedule 17 | 20.5 | [10 empty] | 0
Schedule 17 | 20.6 | [10 empty] | 0
Schedule 17 | 20.7 | [10 empty] | 0
Schedule 17 | 20.8 | [10 empty] | 0
Schedule 17 | 20.9 | [10 empty] | 0
Schedule 17 | 21 | [10 empty] | 0
Schedule 17 | 21.1 | [10 empty] | 0
Schedule 17 | 21.2 | [10 empty] | 0
Schedule 17 | 22 | [10 empty] | 0
Schedule 17 | 22.1 | [10 empty] | 0
Schedule 17 | 22.2 | [10 empty] | 0
Schedule 17 | 22.3 | [10 empty] | 0
Schedule 17 | 22.4 | [10 empty] | 0
Schedule 17 | 23 | [10 empty] | 0
Schedule 17 | 23.1 | [10 empty] | 0
Schedule 17 | 23.2 | [10 empty] | 0
Schedule 17 | 23.3 | [10 empty] | 0
Schedule 17 | 23.4 | [10 empty] | 0
Schedule 17 | 23.5 | [10 empty] | 0
Schedule 17 | 24 | [10 empty] | 0
Schedule 17 | 24.1 | [10 empty] | 0
Schedule 17 | 24.2 | [10 empty] | 0
Schedule 17 | 24.3 | [10 empty] | 0
Schedule 17 | 24.4 | [10 empty] | 0
Schedule 17 | 24.5 | [10 empty] | 0
Schedule 17 | 24.6 | [10 empty] | 0
Schedule 17 | 24.7 | [10 empty] | 0
Schedule 17 | 24.8 | [10 empty] | 0
Schedule 17 | 24.9 | [10 empty] | 0
Schedule 17 | 25 | [10 empty] | 0
Schedule 17 | 25.1 | [10 empty] | 0
Schedule 17 | 25.2 | [10 empty] | 0
Schedule 17 | 25.3 | [6 empty] | YES |  |  |  | 1
Schedule 17 | 25.4 | [10 empty] | 0
Schedule 17 | 25.5 | [10 empty] | 0
Schedule 17 | 25.6 | [10 empty] | 0
Schedule 17 | 25.7 | [10 empty] | 0
Schedule 17 | 25.8 | [10 empty] | 0
Schedule 17 | 25.9 | [10 empty] | 0
Schedule 17 | 25.1 | [10 empty] | 0
Schedule 17 | 25.11 | [10 empty] | 0
Schedule 17 | 25.12 | [10 empty] | 0
Schedule 17 | 25.13 | [10 empty] | 0
Schedule 17 | 25.14 | [10 empty] | 0
Schedule 17 | 25.15 | [10 empty] | 0
Schedule 17 | 25.16 | [10 empty] | 0
Schedule 17 | 25.17 | [10 empty] | 0
Schedule 17 | 25.18 | [10 empty] | 0
Schedule 17 | 25.19 | [10 empty] | 0
Schedule 17 | 26 | [10 empty] | 0
Schedule 17 | 26.1 | [10 empty] | 0
Schedule 17 | 26.2 | [10 empty] | 0
Schedule 17 | 26.3 | [10 empty] | 0
Schedule 17 | 26.4 | [10 empty] | 0
Schedule 17 | 26.5 | [10 empty] | 0
Schedule 17 | 26.6 | [10 empty] | 0
Schedule 17 | 26.7 | [10 empty] | 0
Schedule 17 | 26.8 | [10 empty] | 0
Schedule 17 | 26.9 | [10 empty] | 0
Schedule 17 | 26.1 | [10 empty] | 0
Schedule 17 | 26.11 | [10 empty] | 0
Schedule 17 | 27 | [10 empty] | 0
Schedule 17 | 27.1 | [10 empty] | 0
Schedule 17 | 27.2 | [10 empty] | 0
Schedule 17 | 27.3 | [10 empty] | 0
Schedule 17 | 27.4 | [10 empty] | 0
Schedule 17 | 28 | [10 empty] | 0
Schedule 17 | 28.1 | [10 empty] | 0
Schedule 17 | 28.2 | [10 empty] | 0
Schedule 17 | 29 | [10 empty] | 0
Schedule 17 | 29.1 | [10 empty] | 0
Schedule 17 | 29.2 | [10 empty] | 0
Schedule 17 | 29.3 | [10 empty] | 0
Schedule 17 | 29.4 | [10 empty] | 0
Schedule 17 | 30 | [10 empty] | 0
Schedule 17 | 30.1 | [10 empty] | 0
Schedule 17 | 30.2 | [10 empty] | 0
Schedule 17 | 30.3 | [10 empty] | 0
Schedule 17 | 30.4 | [10 empty] | 0
Schedule 17 | 30.5 | [10 empty] | 0
Schedule 17 | 30.6 | [10 empty] | 0
Schedule 17 | 30.7 | [10 empty] | 0
Schedule 17 | 30.8 | [10 empty] | 0
Schedule 17 | 30.9 | [10 empty] | 0
Schedule 17 | 30.1 | [10 empty] | 0
Schedule 17 | 30.11 | [10 empty] | 0
Schedule 17: Annex 1 | 1 | [10 empty] | 0
Schedule 17: Annex 1 | 2 | [10 empty] | 0
Schedule 17: Annex 1 | 2.1 | [10 empty] | 0
Schedule 17: Annex 1 | 2.2 | [10 empty] | 0
Schedule 17: Annex 1 | 2.3 | [10 empty] | 0
Schedule 17: Annex 1 | 2.4 | [10 empty] | 0
Schedule 17: Annex 1 | 2.5 | [10 empty] | 0
Schedule 17: Annex 1 | 3 | [10 empty] | 0
Schedule 17: Annex 1 | Definitions | [10 empty] | 0
Schedule 17: Annex 1 | 4 | [10 empty] | 0
Schedule 17: Annex 1 | 4.1 | [10 empty] | 0
Schedule 17: Annex 1 | 4.2 | [10 empty] | 0
Schedule 17: Annex 1 | 4.3 | [10 empty] | 0
Schedule 17: Annex 1 | 4.4 | [10 empty] | 0
Schedule 17: Annex 1 | 4.5 | [10 empty] | 0
Schedule 17: Annex 1 | 4.6 | [10 empty] | 0
Schedule 17: Annex 1 | 4.7 | [10 empty] | 0
Schedule 17: Annex 1 | 4.8 | [10 empty] | 0
Schedule 17: Annex 1 | 4.9 | [10 empty] | 0
Schedule 17: Annex 1 | 4.1 | [10 empty] | 0
Schedule 17: Annex 1 | 5 | [10 empty] | 0
Schedule 17: Annex 1 | 5.1 | [10 empty] | 0
Schedule 17: Annex 1 | 5.2 | [10 empty] | 0
Schedule 17: Annex 1 | 5.3 | [10 empty] | 0
Schedule 17: Annex 1 | 5.4 | [10 empty] | 0
Schedule 17: Annex 1 | 5.5 | [10 empty] | 0
Schedule 17: Annex 1 | 5.6 | [10 empty] | 0
Schedule 17: Annex 1 | 5.7 | [10 empty] | 0
Schedule 17: Annex 1 | 5.8 | [10 empty] | 0
Schedule 17: Annex 1 | 5.9 | [10 empty] | 0
Schedule 17: Annex 1 | 5.1 | [10 empty] | 0
Schedule 17: Annex 1 | 5.11 | [10 empty] | 0
Schedule 17: Annex 1 | 5.12 | [10 empty] | 0
Schedule 17: Annex 1 | 5.13 | [10 empty] | 0
Schedule 17: Annex 1 | 5.14 | [10 empty] | 0
Schedule 17: Annex 1 | 5.15 | [10 empty] | 0
Schedule 17: Annex 1 | 5.16 | [10 empty] | 0
Schedule 17: Annex 1 | 5.17 | [10 empty] | 0
Schedule 17: Annex 1 | 5.18 | [10 empty] | 0
Schedule 17: Annex 1 | 5.19 | [10 empty] | 0
Schedule 17: Annex 1 | 5.2 | [10 empty] | 0
Schedule 17: Annex 1 | 5.21 | [10 empty] | 0
Schedule 17: Annex 1 | 5.22 | [10 empty] | 0
Schedule 17: Annex 1 | 5.23 | [10 empty] | 0
Schedule 17: Annex 1 | 5.24 | [10 empty] | 0
Schedule 17: Annex 1 | 5.25 | [10 empty] | 0
Schedule 17: Annex 1 | 5.26 | [10 empty] | 0
Schedule 17: Annex 1 | 5.27 | [10 empty] | 0
Schedule 17: Annex 1 | 5.28 | [10 empty] | 0
Schedule 17: Annex 1 | 5.29 | [10 empty] | 0
Schedule 17: Annex 1 | 5.3 | [10 empty] | 0
Schedule 17: Annex 1 | 5.31 | [10 empty] | 0
Schedule 17: Annex 1 | 5.32 | [10 empty] | 0
Schedule 17: Annex 1 | 5.33 | [10 empty] | 0
Schedule 17: Annex 1 | 5.34 | [10 empty] | 0
Schedule 17: Annex 1 | 5.35 | [10 empty] | 0
Schedule 17: Annex 1 | 5.36 | [10 empty] | 0
Schedule 17: Annex 1 | 5.37 | [10 empty] | 0
Schedule 17: Annex 1 | 5.38 | [10 empty] | 0
Schedule 17: Annex 1 | 5.39 | [10 empty] | 0
Schedule 17: Annex 1 | 5.4 | [10 empty] | 0
Schedule 17: Annex 1 | 5.41 | [10 empty] | 0
Schedule 17: Annex 1 | 5.42 | [10 empty] | 0
Schedule 17: Annex 1 | 5.43 | [10 empty] | 0
Schedule 17: Annex 1 | 5.44 | [10 empty] | 0
Schedule 17: Annex 1 | 5.45 | [10 empty] | 0
Schedule 17: Annex 1 | 6 | [10 empty] | 0
Schedule 17: Annex 1 | 6.1 | [10 empty] | 0
Schedule 17: Annex 1 | 6.2 | [10 empty] | 0
Schedule 17: Annex 1 | 6.3 | [10 empty] | 0
Schedule 17: Annex 1 | 6.4 | [10 empty] | 0
Schedule 17: Annex 1 | 6.5 | [10 empty] | 0
Schedule 17: Annex 1 | 6.6 | [10 empty] | 0
Schedule 17: Annex 1 | 6.7 | [10 empty] | 0
Schedule 17: Annex 1 | 6.8 | [10 empty] | 0
Schedule 17: Annex 1 | 7 | [10 empty] | 0
Schedule 17: Annex 1 | 7.1 | [10 empty] | 0
Schedule 17: Annex 1 | 7.2 | [10 empty] | 0
Schedule 17: Annex 1 | 7.3 | [10 empty] | 0
Schedule 17: Annex 1 | 7.4 | [10 empty] | 0
Schedule 17: Annex 1 | 7.5 | [10 empty] | 0
Schedule 17: Annex 1 | 7.6 | [10 empty] | 0
Schedule 17: Annex 1 | 7.7 | [10 empty] | 0
Schedule 17: Annex 1 | 7.8 | [10 empty] | 0
Schedule 17: Annex 1 | 8 | [10 empty] | 0
Schedule 17: Annex 1 | 8.1 | [10 empty] | 0
Schedule 17: Annex 1 | 8.2 | [10 empty] | 0
Schedule 17: Annex 1 | 8.3 | [10 empty] | 0
Schedule 17: Annex 1 | 8.4 | [10 empty] | 0
Schedule 17: Annex 1 | 9 | [10 empty] | 0
Schedule 17: Annex 1 | 9.1 | [10 empty] | 0
Schedule 17: Annex 1 | 9.2 | [10 empty] | 0
Schedule 17: Annex 1 | 9.3 | [10 empty] | 0
Schedule 17: Annex 1 | 9.4 | [10 empty] | 0
Schedule 17: Annex 1 | 9.5 | [10 empty] | 0
Schedule 17: Annex 1 | 9.6 | [10 empty] | 0
Schedule 17: Annex 1 | 9.7 | [10 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [10 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [10 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [10 empty] | 0
Schedule 17: Annex 1 | Attachment 3 | [10 empty] | 0
Schedule 17: Annex 2 | Annex 2 | [10 empty] | 0
0
Schedule 18 | Introduction | [10 empty] | 0
Schedule 18 | 1 | [10 empty] | 0
Schedule 18 | 1.1 | [10 empty] | 0
Schedule 18 | 1.2 | [10 empty] | 0
Schedule 18 | 1.3 | [10 empty] | 0 | Model reference number and date
Schedule 18 | 1.3A | [10 empty] | 0
Schedule 18 | 1.4 | [10 empty] | 0
Schedule 18 | 1.5 | [10 empty] | 0
Schedule 18 | 1.6 | [10 empty] | 0
Schedule 18 | 1.7 | [10 empty] | 0
Schedule 18 | 1.8 | [10 empty] | 0
Schedule 18 | 1.9 | [10 empty] | 0
Schedule 18 | 2 | [10 empty] | 0
Schedule 18 | 2.1 | [10 empty] | 0
Schedule 18 | 2.2 | [10 empty] | 0
Schedule 18 | 2.3 | [10 empty] | 0
Schedule 18 | 2.4 | [10 empty] | 0
Schedule 18 | 2.5 | [10 empty] | 0
Schedule 18 | 2.6 | [10 empty] | 0
Schedule 18 | 2.7 | [10 empty] | 0
Schedule 18 | 2.8 | [10 empty] | 0
Schedule 18 | 2.9 | [10 empty] | 0
Schedule 18 | 2.1 | [10 empty] | 0
Schedule 18 | 2.11 | [10 empty] | 0
Schedule 18 | 2.12 | [10 empty] | 0
Schedule 18 | 2.13 | [10 empty] | 0
Schedule 18 | 2.14 | [10 empty] | 0
Schedule 18 | 2.15 | [10 empty] | 0
Schedule 18 | 2.16 | [10 empty] | 0
Schedule 18 | 2.17 | [10 empty] | 0
Schedule 18 | 2.18 | [10 empty] | 0
Schedule 18 | 2.19 | [10 empty] | 0
Schedule 18 | 2.2 | [10 empty] | 0
Schedule 18 | 2.21 | [10 empty] | 0
Schedule 18 | 2.22 | [10 empty] | 0
Schedule 18 | 2.23 | [10 empty] | 0
Schedule 18 | 2.24 | [10 empty] | 0
Schedule 18 | 2.25 | [10 empty] | 0
Schedule 18 | 2.26 | [10 empty] | 0
Schedule 18 | 2.27 | [10 empty] | 0
Schedule 18 | 2.28 | [10 empty] | 0
Schedule 18 | 2.29 | [10 empty] | 0
Schedule 18 | 2.3 | [10 empty] | 0
Schedule 18 | 3 | [10 empty] | 0
Schedule 18 | 3.1 | [10 empty] | 0
Schedule 18 | 3.2 | [10 empty] | 0
Schedule 18 | 3.3 | [10 empty] | 0
Schedule 18 | 3.4 | [10 empty] | 0
Schedule 18 | 3.5 | [10 empty] | 0
Schedule 18 | 3.6 | [10 empty] | 0
Schedule 18 | 3.7 | [10 empty] | 0
Schedule 18 | 4 | [10 empty] | 0
Schedule 18 | 4.1 | [10 empty] | 0
Schedule 18 | 5 | [10 empty] | 0
Schedule 18 | 5.1 | [10 empty] | 0
Schedule 18 | 6 | [10 empty] | 0
Schedule 18 | 6.1 | [10 empty] | 0
Schedule 18 | 6.2 | [10 empty] | 0
Schedule 18 | 6.3 | [10 empty] | 0
Schedule 18 | 6.4 | [10 empty] | 0
Schedule 18 | 6.5 | [10 empty] | 0
Schedule 18 | 7 | [10 empty] | 0
Schedule 18 | 7.1 | [10 empty] | 0
Schedule 18 | 8 | [10 empty] | 0
Schedule 18 | 8.1 | [10 empty] | 0
Schedule 18 | 8.2 | [10 empty] | 0
Schedule 18 | 8.3 | [10 empty] | 0
Schedule 18 | 8.4 | [10 empty] | 0
Schedule 18 | 9 | [10 empty] | 0
Schedule 18 | 9.1 | [10 empty] | 0
Schedule 18 | 9.2 | [10 empty] | 0
Schedule 18 | 10 | [10 empty] | 0
Schedule 18 | 10.1 | [10 empty] | 0
Schedule 18 | 10.2 | [10 empty] | 0
Schedule 18 | 10.3 | [10 empty] | 0
Schedule 18 | 10.4 | [10 empty] | 0
Schedule 18 | 10.5 | [10 empty] | 0
Schedule 18 | 11 | [10 empty] | 0
Schedule 18 | 11.1 | [10 empty] | 0
Schedule 18 | 12 | [10 empty] | 0
Schedule 18 | 12.1 | [10 empty] | 0
Schedule 18 | 12.2 | [10 empty] | 0
Schedule 18 | 12.3 | [10 empty] | 0
Schedule 18 | 12.4 | [10 empty] | 0
Schedule 18 | 12.5 | [10 empty] | 0
Schedule 18 | 12.6 | [10 empty] | 0
Schedule 18 | 13 | [10 empty] | 0
Schedule 18 | 13.1 | [10 empty] | 0
Schedule 18 | 13.2 | [10 empty] | 0
Schedule 18 | 13.3 | [10 empty] | 0
Schedule 18 | 13.4 | [10 empty] | 0
Schedule 18 | 14 | [10 empty] | 0
Schedule 18 | 14.1 | [10 empty] | 0
Schedule 18 | 14.2 | [10 empty] | 0
Schedule 18 | 14.3 | [10 empty] | 0
Schedule 18 | 14.4 | [10 empty] | 0
Schedule 18 | 14.5 | [10 empty] | 0
Schedule 18 | 15 | [10 empty] | 0
Schedule 18 | 15.1 | [10 empty] | 0
Schedule 18 | 15.2 | [10 empty] | 0
Schedule 18 | 15.3 | [10 empty] | 0
Schedule 18 | 15.4 | [10 empty] | 0
Schedule 18 | 15.5 | [10 empty] | 0
Schedule 18 | 15.6 | [10 empty] | 0
Schedule 18 | 15.7 | [10 empty] | 0
Schedule 18 | 15.8 | [10 empty] | 0
Schedule 18 | 15.9 | [10 empty] | 0
Schedule 18 | 15.1 | [10 empty] | 0
Schedule 18 | 15.11 | [10 empty] | 0
Schedule 18 | 15.12 | [10 empty] | 0
Schedule 18 | 15.15 | [10 empty] | 0
Schedule 18 | 16 | [10 empty] | 0
Schedule 18 | 16.1 | [10 empty] | 0
Schedule 18 | 16.2 | [10 empty] | 0
Schedule 18 | 16.3 | [10 empty] | 0
Schedule 18 | 16.4 | [10 empty] | 0
Schedule 18 | 16.5 | [10 empty] | 0
Schedule 18 | 16.6 | [10 empty] | 0
Schedule 18 | 16.7 | [10 empty] | 0
Schedule 18 | 16.8 | [10 empty] | 0
Schedule 18 | 16.9 | [10 empty] | 0
Schedule 18 | 16.1 | [10 empty] | 0
Schedule 18 | 17 | [10 empty] | 0
Schedule 18 | 17.1 | [10 empty] | 0
Schedule 18 | 17.2 | [10 empty] | 0
Schedule 18 | 17.3 | [10 empty] | 0
Schedule 18 | 18 | [10 empty] | 0
Schedule 18 | 18.1 | [10 empty] | 0
Schedule 18 | 18.2 | [10 empty] | 0
Schedule 18 | 18.3 | [10 empty] | 0
Schedule 18 | 18.4 | [10 empty] | 0
Schedule 18 | 18.5 | [10 empty] | 0
Schedule 18 | 18.6 | [10 empty] | 0
Schedule 18 | 18.7 | [10 empty] | 0
Schedule 18 | 18.8 | [10 empty] | 0
Schedule 18 | 18.9 | [10 empty] | 0
Schedule 18 | 18.1 | [10 empty] | 0
Schedule 18 | 18.11 | [10 empty] | 0
Schedule 18 | 18.12 | [10 empty] | 0
Schedule 18 | 18.13 | [10 empty] | 0
Schedule 18 | 18.14 | [10 empty] | 0
Schedule 18 | 18.15 | [10 empty] | 0
Schedule 18 | 18.16 | [10 empty] | 0
Schedule 18 | 18.17 | [10 empty] | 0
Schedule 18 | 18.18 | [10 empty] | 0
Schedule 18 | 18.19 | [10 empty] | 0
Schedule 18 | 18.2 | [10 empty] | 0
Schedule 18 | 18.21 | [10 empty] | 0
Schedule 18 | 19 | [10 empty] | 0
Schedule 18 | 19.1 | [10 empty] | 0
Schedule 18 | 19.2 | [10 empty] | 0
Schedule 18 | 19.3 | [10 empty] | 0
Schedule 18 | 19.4 | [10 empty] | 0
Schedule 18 | 19.5 | [10 empty] | 0
Schedule 18 | 19.6 | [10 empty] | 0
Schedule 18 | 19.7 | [10 empty] | 0
Schedule 18 | 19.8 | [10 empty] | 0
Schedule 18 | 19.9 | [10 empty] | 0
Schedule 18 | 19.1 | [10 empty] | 0
Schedule 18 | 19.11 | [10 empty] | 0
Schedule 18 | 20 | [10 empty] | 0
Schedule 18 | 20.1 | [10 empty] | 0
Schedule 18 | 20.2 | [10 empty] | 0
Schedule 18 | 20.3 | [10 empty] | 0
Schedule 18 | 20.4 | [10 empty] | 0
Schedule 18 | 20.5 | [10 empty] | 0
Schedule 18 | 20.6 | [10 empty] | 0
Schedule 18 | 20.7 | [10 empty] | 0
Schedule 18 | 20.8 | [10 empty] | 0
Schedule 18 | 20.9 | [10 empty] | 0
Schedule 18 | 21 | [10 empty] | 0
Schedule 18 | 21.1 | [10 empty] | 0
Schedule 18 | 21.2 | [10 empty] | 0
Schedule 18 | 22 | [10 empty] | 0
Schedule 18 | 22.1 | [10 empty] | 0
Schedule 18 | 22.2 | [10 empty] | 0
Schedule 18 | 22.3 | [10 empty] | 0
Schedule 18 | 22.4 | [10 empty] | 0
Schedule 18 | 23 | [10 empty] | 0
Schedule 18 | 23.1 | [10 empty] | 0
Schedule 18 | 23.2 | [10 empty] | 0
Schedule 18 | 23.3 | [10 empty] | 0
Schedule 18 | 23.4 | [10 empty] | 0
Schedule 18 | 23.5 | [10 empty] | 0
Schedule 18 | 24 | [10 empty] | 0
Schedule 18 | 24.1 | [10 empty] | 0
Schedule 18 | 24.2 | [10 empty] | 0
Schedule 18 | 24.3 | [10 empty] | 0
Schedule 18 | 24.4 | [10 empty] | 0
Schedule 18 | 24.5 | [10 empty] | 0
Schedule 18 | 24.6 | [10 empty] | 0
Schedule 18 | 24.7 | [10 empty] | 0
Schedule 18 | 24.8 | [10 empty] | 0
Schedule 18 | 24.9 | [10 empty] | 0
Schedule 18 | 25 | [10 empty] | 0
Schedule 18 | 25.1 | [10 empty] | 0
Schedule 18 | 25.2 | [10 empty] | 0
Schedule 18 | 25.3 | [6 empty] | YES |  |  |  | 1
Schedule 18 | 25.4 | [10 empty] | 0
Schedule 18 | 25.5 | [10 empty] | 0
Schedule 18 | 25.6 | [10 empty] | 0
Schedule 18 | 25.7 | [10 empty] | 0
Schedule 18 | 25.8 | [10 empty] | 0
Schedule 18 | 25.9 | [10 empty] | 0
Schedule 18 | 25.1 | [10 empty] | 0
Schedule 18 | 25.11 | [10 empty] | 0
Schedule 18 | 25.12 | [10 empty] | 0
Schedule 18 | 25.13 | [10 empty] | 0
Schedule 18 | 25.14 | [10 empty] | 0
Schedule 18 | 25.15 | [10 empty] | 0
Schedule 18 | 25.16 | [10 empty] | 0
Schedule 18 | 25.17 | [10 empty] | 0
Schedule 18 | 25.18 | [10 empty] | 0
Schedule 18 | 25.19 | [10 empty] | 0
Schedule 18 | 26 | [10 empty] | 0
Schedule 18 | 26.1 | [10 empty] | 0
Schedule 18 | 26.2 | [10 empty] | 0
Schedule 18 | 26.3 | [10 empty] | 0
Schedule 18 | 26.4 | [10 empty] | 0
Schedule 18 | 26.5 | [10 empty] | 0
Schedule 18 | 26.6 | [10 empty] | 0
Schedule 18 | 26.7 | [10 empty] | 0
Schedule 18 | 26.8 | [10 empty] | 0
Schedule 18 | 26.9 | [10 empty] | 0
Schedule 18 | 26.1 | [10 empty] | 0
Schedule 18 | 26.11 | [10 empty] | 0
Schedule 18 | 27 | [10 empty] | 0
Schedule 18 | 27.1 | [10 empty] | 0
Schedule 18 | 27.2 | [10 empty] | 0
Schedule 18 | 27.3 | [10 empty] | 0
Schedule 18 | 27.4 | [10 empty] | 0
Schedule 18 | 28 | [10 empty] | 0
Schedule 18 | 28.1 | [10 empty] | 0
Schedule 18 | 28.2 | [10 empty] | 0
Schedule 18 | 29 | [10 empty] | 0
Schedule 18 | 29.1 | [10 empty] | 0
Schedule 18 | 29.2 | [10 empty] | 0
Schedule 18 | 29.3 | [10 empty] | 0
Schedule 18 | 29.4 | [10 empty] | 0
Schedule 18 | 30 | [10 empty] | 0
Schedule 18 | 30.1 | [10 empty] | 0
Schedule 18 | 30.2 | [10 empty] | 0
Schedule 18 | 30.3 | [10 empty] | 0
Schedule 18 | 30.4 | [10 empty] | 0
Schedule 18 | 30.5 | [10 empty] | 0
Schedule 18 | 30.6 | [10 empty] | 0
Schedule 18 | 30.7 | [10 empty] | 0
Schedule 18 | 30.8 | [10 empty] | 0
Schedule 18 | 30.9 | [10 empty] | 0
Schedule 18 | 30.1 | [10 empty] | 0
Schedule 18 | 30.11 | [10 empty] | 0
Schedule 18: Annex 1 | 1 | [10 empty] | 0
Schedule 18: Annex 1 | 1.1 | [10 empty] | 0
Schedule 18: Annex 1 | 2 | [10 empty] | 0
Schedule 18: Annex 1 | 2.1 | [10 empty] | 0
Schedule 18: Annex 1 | 2.2 | [10 empty] | 0
Schedule 18: Annex 1 | 2.3 | [10 empty] | 0
Schedule 18: Annex 1 | 2.4 | [10 empty] | 0
Schedule 18: Annex 1 | 2.5 | [10 empty] | 0
Schedule 18: Annex 1 | 3 | [10 empty] | 0
Schedule 18: Annex 1 | Definitions | [10 empty] | 0
Schedule 18: Annex 1 | 4 | [10 empty] | 0
Schedule 18: Annex 1 | 4.1 | [10 empty] | 0
Schedule 18: Annex 1 | 4.2 | [10 empty] | 0
Schedule 18: Annex 1 | 4.3 | [10 empty] | 0
Schedule 18: Annex 1 | 4.4 | [10 empty] | 0
Schedule 18: Annex 1 | 4.5 | [10 empty] | 0
Schedule 18: Annex 1 | 4.6 | [10 empty] | 0
Schedule 18: Annex 1 | 4.7 | [10 empty] | 0
Schedule 18: Annex 1 | 4.8 | [10 empty] | 0
Schedule 18: Annex 1 | 4.9 | [10 empty] | 0
Schedule 18: Annex 1 | 5 | [10 empty] | 0
Schedule 18: Annex 1 | 5.1 | [10 empty] | 0
Schedule 18: Annex 1 | 5.2 | [10 empty] | 0
Schedule 18: Annex 1 | 5.3 | [10 empty] | 0
Schedule 18: Annex 1 | 5.4 | [10 empty] | 0
Schedule 18: Annex 1 | 5.5 | [10 empty] | 0
Schedule 18: Annex 1 | 5.6 | [10 empty] | 0
Schedule 18: Annex 1 | 5.7 | [10 empty] | 0
Schedule 18: Annex 1 | 5.8 | [10 empty] | 0
Schedule 18: Annex 1 | 5.9 | [10 empty] | 0
Schedule 18: Annex 1 | 5.1 | [10 empty] | 0
Schedule 18: Annex 1 | 5.11 | [10 empty] | 0
Schedule 18: Annex 1 | 5.12 | [10 empty] | 0
Schedule 18: Annex 1 | 5.13 | [10 empty] | 0
Schedule 18: Annex 1 | 5.14 | [10 empty] | 0
Schedule 18: Annex 1 | 5.15 | [10 empty] | 0
Schedule 18: Annex 1 | 5.16 | [10 empty] | 0
Schedule 18: Annex 1 | 5.17 | [10 empty] | 0
Schedule 18: Annex 1 | 5.18 | [10 empty] | 0
Schedule 18: Annex 1 | 5.19 | [10 empty] | 0
Schedule 18: Annex 1 | 5.2 | [10 empty] | 0
Schedule 18: Annex 1 | 5.21 | [10 empty] | 0
Schedule 18: Annex 1 | 5.22 | [10 empty] | 0
Schedule 18: Annex 1 | 5.23 | [10 empty] | 0
Schedule 18: Annex 1 | 5.24 | [10 empty] | 0
Schedule 18: Annex 1 | 5.25 | [10 empty] | 0
Schedule 18: Annex 1 | 5.26 | [10 empty] | 0
Schedule 18: Annex 1 | 5.27 | [10 empty] | 0
Schedule 18: Annex 1 | 5.28 | [10 empty] | 0
Schedule 18: Annex 1 | 5.29 | [10 empty] | 0
Schedule 18: Annex 1 | 5.3 | [10 empty] | 0
Schedule 18: Annex 1 | 5.31 | [10 empty] | 0
Schedule 18: Annex 1 | 5.32 | [10 empty] | 0
Schedule 18: Annex 1 | 5.33 | [10 empty] | 0
Schedule 18: Annex 1 | 5.34 | [10 empty] | 0
Schedule 18: Annex 1 | 5.35 | [10 empty] | 0
Schedule 18: Annex 1 | 5.36 | [10 empty] | 0
Schedule 18: Annex 1 | 5.37 | [10 empty] | 0
Schedule 18: Annex 1 | 5.38 | [10 empty] | 0
Schedule 18: Annex 1 | 5.39 | [10 empty] | 0
Schedule 18: Annex 1 | 5.4 | [10 empty] | 0
Schedule 18: Annex 1 | 5.41 | [10 empty] | 0
Schedule 18: Annex 1 | 5.42 | [10 empty] | 0
Schedule 18: Annex 1 | 6 | [10 empty] | 0
Schedule 18: Annex 1 | 6.1 | [10 empty] | 0
Schedule 18: Annex 1 | 6.2 | [10 empty] | 0
Schedule 18: Annex 1 | 6.3 | [10 empty] | 0
Schedule 18: Annex 1 | 6.4 | [10 empty] | 0
Schedule 18: Annex 1 | 6.5 | [10 empty] | 0
Schedule 18: Annex 1 | 6.6 | [10 empty] | 0
Schedule 18: Annex 1 | 6.7 | [10 empty] | 0
Schedule 18: Annex 1 | 6.8 | [10 empty] | 0
Schedule 18: Annex 1 | 6.9 | [10 empty] | 0
Schedule 18: Annex 1 | 6.1 | [10 empty] | 0
Schedule 18: Annex 1 | 6.11 | [10 empty] | 0
Schedule 18: Annex 1 | 6.12 | [10 empty] | 0
Schedule 18: Annex 1 | 6.13 | [10 empty] | 0
Schedule 18: Annex 1 | 6.14 | [10 empty] | 0
Schedule 18: Annex 1 | 6.15 | [10 empty] | 0
Schedule 18: Annex 1 | 6.16 | [10 empty] | 0
Schedule 18: Annex 1 | 6.17 | [10 empty] | 0
Schedule 18: Annex 1 | 6.18 | [10 empty] | 0
Schedule 18: Annex 1 | 6.19 | [10 empty] | 0
Schedule 18: Annex 1 | 6.2 | [10 empty] | 0
Schedule 18: Annex 1 | 6.21 | [10 empty] | 0
Schedule 18: Annex 1 | 6.22 | [10 empty] | 0
Schedule 18: Annex 1 | 6.23 | [10 empty] | 0
Schedule 18: Annex 1 | 6.24 | [10 empty] | 0
Schedule 18: Annex 1 | 6.25 | [10 empty] | 0
Schedule 18: Annex 1 | 6.26 | [10 empty] | 0
Schedule 18: Annex 1 | 6.27 | [10 empty] | 0
Schedule 18: Annex 1 | 6.28 | [10 empty] | 0
Schedule 18: Annex 1 | 6.29 | [10 empty] | 0
Schedule 18: Annex 1 | 6.3 | [10 empty] | 0
Schedule 18: Annex 1 | 6.31 | [10 empty] | 0
Schedule 18: Annex 1 | 6.32 | [10 empty] | 0
Schedule 18: Annex 1 | 6.33 | [10 empty] | 0
Schedule 18: Annex 1 | 6.34 | [10 empty] | 0
Schedule 18: Annex 1 | 7 | [10 empty] | 0
Schedule 18: Annex 1 | 7.1 | [10 empty] | 0
Schedule 18: Annex 1 | 7.2 | [10 empty] | 0
Schedule 18: Annex 1 | 7.3 | [10 empty] | 0
Schedule 18: Annex 1 | 7.4 | [10 empty] | 0
Schedule 18: Annex 1 | 7.5 | [10 empty] | 0
Schedule 18: Annex 1 | 8 | [10 empty] | 0
Schedule 18: Annex 1 | 8.1 | [10 empty] | 0
Schedule 18: Annex 1 | 8.2 | [10 empty] | 0
Schedule 18: Annex 1 | 8.3 | [10 empty] | 0
Schedule 18: Annex 1 | 8.4 | [10 empty] | 0
Schedule 18: Annex 1 | 8.5 | [10 empty] | 0
Schedule 18: Annex 1 | 8.6 | [10 empty] | 0
Schedule 18: Annex 1 | 8.7 | [10 empty] | 0
Schedule 18: Annex 1 | 8.8 | [10 empty] | 0
Schedule 18: Annex 1 | 8.9 | [10 empty] | 0
Schedule 18: Annex 1 | 8.1 | [10 empty] | 0
Schedule 18: Annex 1 | 8.11 | [10 empty] | 0
Schedule 18: Annex 1 | 8.12 | [10 empty] | 0
Schedule 18: Annex 1 | 8.13 | [10 empty] | 0
Schedule 18: Annex 1 | 8.14 | [10 empty] | 0
Schedule 18: Annex 1 | 8.15 | [10 empty] | 0
Schedule 18: Annex 1 | 8.16 | [10 empty] | 0
Schedule 18: Annex 1 | 8.17 | [10 empty] | 0
Schedule 18: Annex 1 | 8.18 | [10 empty] | 0
Schedule 18: Annex 1 | 8.19 | [10 empty] | 0
Schedule 18: Annex 1 | 8.2 | [10 empty] | 0
Schedule 18: Annex 1 | 8.21 | [10 empty] | 0
Schedule 18: Annex 1 | Attachment 1 | [10 empty] | 0
Schedule 18: Annex 1 | Attachment 2 | [10 empty] | 0
Schedule 18: Annex 1 | Attachment 3 | [10 empty] | 0
Schedule 18: Annex 2 | Annex 2 | [10 empty] | 0
0
Schedule 20 | Introduction |  |  | YES | [7 empty] | 1
Schedule 20 | 1.1 |  |  | YES | [7 empty] | 1
Schedule 20 | 2.1 |  |  | YES | [7 empty] | 1
Schedule 20 | 3.1 |  |  | YES | [7 empty] | 1
Schedule 20 | 3.2 |  |  | YES | [7 empty] | 1
0
Schedule 29 | Introduction | [5 empty] | YES |  |  |  |  | 1
Schedule 29 | 1 | [10 empty] | 0
Schedule 29 | 1A | [10 empty] | 0
Schedule 29 | 2 | [10 empty] | 0
Schedule 29 | 3 | [10 empty] | 0
Schedule 29 | 4 | [5 empty] | YES |  |  |  |  | 1
Schedule 29 | 5 | [5 empty] | YES |  |  |  |  | 1
Schedule 29 | 6 | [5 empty] | YES |  |  |  |  | 1
Schedule 29 | 7 | [10 empty] | 0
Schedule 29 | 8 | [10 empty] | 0
Schedule 29 | 9 | [10 empty] | 0
Schedule 29 | 10 | [10 empty] | 0
Schedule 29 | 11 | [10 empty] | 0
Schedule 29 | 11A | [10 empty] | 0
Schedule 29 | 12 | [10 empty] | 0
Schedule 29 | 13 | [10 empty] | 0
Schedule 29 | 14 | [10 empty] | 0
Schedule 29 | 15 | [10 empty] | 0
Schedule 29 | 16 | [10 empty] | 0
Schedule 29 | 17 | [10 empty] | 0
Schedule 29 | 18 | [10 empty] | 0
Schedule 29 | 19 | [10 empty] | 0
Schedule 29 | 20 | [10 empty] | 0
Schedule 29 | 21 | [10 empty] | 0
Schedule 29 | 22 | [10 empty] | 0
Schedule 29 | 23 | [10 empty] | 0
Schedule 29 | 24 | [10 empty] | 0
Schedule 29 | 25 | [10 empty] | 0
Schedule 29 | 26 | [10 empty] | 0
Schedule 29 | 27 | [10 empty] | 0
Schedule 29 | 28 | [10 empty] | 0
Schedule 29 | 29 | [5 empty] | YES |  |  |  |  | 1
Schedule 29 | 30 | [10 empty] | 0
Schedule 29 | 31 | [10 empty] | 0
Schedule 29 | 32 | [10 empty] | 0
Schedule 29 | 33 | [10 empty] | 0
Schedule 29 | 34 | [10 empty] | 0
Schedule 29 | 35 | [10 empty] | 0
Schedule 29 | 36 | [10 empty] | 0
Schedule 29 | 37 | [10 empty] | 0
Schedule 29 | 38 | [10 empty] | 0
Schedule 29 | 39 | [10 empty] | 0
Schedule 29 | 40 | [10 empty] | 0
Schedule 29 | 41 | [10 empty] | 0
Schedule 29 | 42 | [10 empty] | 0
Schedule 29 | 43 | [10 empty] | 0
Schedule 29 | 44 | [10 empty] | 0
Schedule 29 | 45 | [10 empty] | 0
Schedule 29 | 46 | [10 empty] | 0
Schedule 29 | 46A | [10 empty] | 0
Schedule 29 | 47 | [10 empty] | 0
0
Schedule 32 | 1 | [10 empty] | 0
Schedule 32 | 1.1 | [10 empty] | 0
Schedule 32 | 1.2 | [10 empty] | 0
Schedule 32 | 1.2A | [10 empty] | 0
Schedule 32 | 1.3 | [10 empty] | 0
Schedule 32 | 1.4 | [10 empty] | 0
Schedule 32 | 1.5 | [10 empty] | 0
Schedule 32 | 1.6 | [10 empty] | 0
Schedule 32 | 1.7 | [10 empty] | 0
Schedule 32 | 1.8 | [7 empty] | YES |  |  | 1
Schedule 32 | 1.9 | [10 empty] | 0
Schedule 32 | 1.10 | [7 empty] | YES |  |  | 1
Schedule 32 | 2 | [10 empty] | 0
Schedule 32 | 2.1 | [10 empty] | 0
Schedule 32 | 2.2 | [10 empty] | 0
Schedule 32 | 2.3 | [10 empty] | 0
Schedule 32 | 2.4 | [10 empty] | 0
Schedule 32 | 2.5 | [10 empty] | 0
Schedule 32 | 3 | [10 empty] | 0
Schedule 32 | 3.1 | [7 empty] | YES |  |  | 1
Schedule 32 | 3.2 | [10 empty] | 0
Schedule 32 | 3.3 | [10 empty] | 0
Schedule 32 | 3.4 | [10 empty] | 0
Schedule 32 | 3.5 | [10 empty] | 0
Schedule 32 | 3.6 | [10 empty] | 0
Schedule 32 | 4 | [10 empty] | 0
Schedule 32 | 4.1 | [7 empty] | YES |  |  | 1
Schedule 32 | 4.2 | [7 empty] | YES |  |  | 1
Schedule 32 | 4.2A | [7 empty] | YES |  |  | 1
Schedule 32 | 4.3 | [10 empty] | 0
Schedule 32 | 4.4 | [10 empty] | 0
Schedule 32 | 4.5 | [7 empty] | YES |  |  | 1
Schedule 32 | 4.6 | [10 empty] | 0
Schedule 32 | 5 | [10 empty] | 0
Schedule 32 | 5.1 | [10 empty] | 0
Schedule 32 | 5.2 | [10 empty] | 0
Schedule 32 | 5.3 | [10 empty] | 0
Schedule 32 | 5A. | [7 empty] | YES |  |  | 1
Schedule 32 | 5A.1 | [10 empty] | 0
Schedule 32 | 5A.1A | [10 empty] | 0
Schedule 32 | 5A.2 | [10 empty] | 0
Schedule 32 | 6 | [10 empty] | 0
Schedule 32 | 6.1 | [8 empty] | YES |  | 1
Schedule 32 | 6.2 | [8 empty] | YES |  | 1
Schedule 32 | 6.3 | [7 empty] | YES |  |  | 1
Schedule 32 | 6.4 | [10 empty] | 0
Schedule 32 | 6.4A | [10 empty] | 0
Schedule 32 | 6.5 | [7 empty] | YES |  |  | 1
Schedule 32 | 6.6 | [10 empty] | 0
Schedule 32 | 6.7 | [10 empty] | 0
Schedule 32 | 6.8 | [10 empty] | 0
Schedule 32 | 6.9 | [10 empty] | 0
Schedule 32 | 6.10 | [10 empty] | 0
Schedule 32 | 6.11 | [10 empty] | 0
Schedule 32 | 7 | [10 empty] | 0
Schedule 32 | 7.1 | [10 empty] | 0
Schedule 32 | 7.2 | [10 empty] | 0
Schedule 32 | 7.3 | [10 empty] | 0
Schedule 32 | 7.4 | [10 empty] | 0
Schedule 32 | 7.5 | [10 empty] | 0
Schedule 32 | 7.6 | [10 empty] | 0
Schedule 32 | 7.7 | [10 empty] | 0
Schedule 32 | 7.8 | [10 empty] | 0
Schedule 32 | 7.9 | [10 empty] | 0
Schedule 32 | 7.1 | [10 empty] | 0
Schedule 32 | 7.11 | [10 empty] | 0
Schedule 32 | 7.12 | [10 empty] | 0
Schedule 32 | 7.13 | [10 empty] | 0
Schedule 32 | 7.14 | [10 empty] | 0
Schedule 32 | 7.15 | [10 empty] | 0
Schedule 32 | 7.16 | [10 empty] | 0
Schedule 32 | 7.17 | [10 empty] | 0
Schedule 32 | 8 | [10 empty] | 0
Schedule 32 | 8.1 | [10 empty] | 0
Schedule 31 | 8.2 | [10 empty] | 0
Schedule 32 | Definitions | [7 empty] | YES | YES |  | 2
Charging Methodology CPs Legal Text Overlap Tracker