## Sheet1
INTERNAL Mop Up 2 Consultation Consolidated Comments Log
Comment ID | Code Artefact Name | Document Section | Comments | Comment Theme | Related Design Artefact | Related Design Artefact Section/Step | Suggested Change e.g. proposed wording | Comment Owner | Organisation | Constituency | Submitted | Triage Status | Drafting change? | Triage Response Reason | Programme Response e.g.clarification or update on the change
CD6-132 | DCUSA MHHS Transition | 132D | The rules for determining which measurement class consumption will move to following the implementation of MHHS is incorrect and do not correspond to what was agreed in CR032. The two attributes that will determine resultant measurement class after migrating to MHHS are domestic indicator and connection type. As we cannot determine whether the meter is 100kw we cannot determine whether consumption should be allocated to measurement class C or E, so all consumption will be allocated to measurement class C. |  |  |  | I suggest using the logic that was agreed in CR032 :- i. Measurement Class A: will not be derived for migrated MPANs, as they will be half-hourly ii. Measurement Class B: will not be derived for migrated MPANs, as they will be half-hourly iii. Measurement Class C: will report the sum of Measurement Classes C and E*, which will be determined as ‘all migrated MPANs with Domestic Indicator = N and Connection Type = L, H or E’ iv. Measurement Class D: will be determined as ‘all migrated MPANs with Domestic Indicator = N and Connection Type = U’ v. Measurement Class E will be set to “0MWh” for migrated MPANs* (see Measurement Class C above) vi. Measurement Class F: will be determined as ‘all migrated MPANs with Domestic = Y and Connection Type ≠ U’ vii. Measurement Class G: will be determined as ‘all migrated MPANs with Domestic = N and Connection Type = W’ | Andrew Dudkowsky | National Grid ESO |  | 2024-03-11
CD6-152 | DCUSA MHHS Transition | Glossary of terms used in Schedule 16 | Defnition - Domestic 'Premise' Indicator has the meaning given to the term in the Energy Market Data Specification. |  |  |  | As noted in Mop up 1 there should be an 's' at the end of 'Premise'. | Andrew Sherry | Electricity North West Limited | Network Operator | 2024-03-11
CD6-381 | DCUSA MHHS Transition |  | 1. further clarification needed around the definition of 'aggregated basis' for charging. This needs clarity as needs to be interpreted the same by all DNO's and IDNO's. - Not changed HB 6/3/24 | [5 empty] | E.ON Next | Large Supplier | 2024-03-11
CD6-382 | DCUSA MHHS Transition | page 107 | 2. Title on page 107 needs changing to 'DIP or DTN'. | [5 empty] | E.ON Next | Large Supplier | 2024-03-11
CD6-383 | DCUSA MHHS Transition | page 50 | 3. Page 50 missing 'T' from Agent. | [5 empty] | E.ON Next | Large Supplier | 2024-03-11
CD6-384 | DCUSA MHHS Transition | Missing | 4. Clarification needed on what will happen to paper billing and if this ceases when this will happen. - No Clarification in this paper | [5 empty] | E.ON Next | Large Supplier | 2024-03-11
CD6-385 | DCUSA MHHS Transition | Missing | 5. The Consultation Paper mentions 'Energy Market Specification' throughout, what is this and can a link be provided. |  |  |  | Please provide the detailed view on the energy market specification document |  | E.ON Next | Large Supplier | 2024-03-11
CD6-386 | DCUSA MHHS Transition | General comment | 6. Inconsistency in the drafting, for example it mentions 'BSC' in some areas and other states 'Balancing and Settlement code'. This is a legal document so there needs to be consistency throughout. - |  |  |  | This has been fed back before but we cannot see this has been addressed |  | E.ON Next | Large Supplier | 2024-03-11
CD6-387 | DCUSA MHHS Transition | 20b | 7. Assumed that DUoS volume will be reported as part of the MHHS-REP-900 message within the 'Quantity' (DI-598) data item. However, in the population notes for that data item it says, 'If Charge type =CAPAC or XSCAP, shows a capacity value'. Therefore, I assume that if a different 'ChargeType' (DI-596) was used such as Red, Amber, Green, etc. then the 'Quantity' data item would refer to a volume? If so, it might be useful to state this as well within the population notes. Can we obtain clarity on how this will work. Reference to section 20b in this area however section 20 is missing from the document. |  |  |  | the whole of section 20 is missing from this version please can you clarify if this is intentional or an oversight and what has happened to the information that we need clarity on that was in the original section 20 |  | E.ON Next | Large Supplier | 2024-03-11
CD6-388 | DCUSA MHHS Transition | various missing items | Sections 9,10, 11,13,14,16,17,22,23,24,36-41 and 43-58 all missing from the document. | [5 empty] | E.ON Next | Large Supplier | 2024-03-11
CD6-389 | DCUSA MHHS Transition | 21.5 | Further clarification needed on when REP900 will be sent instead of D2021. Paper states that the REP900 will be sent using the DIP save that for non-MHHS metering points it will be data flow D2021. is this not also related to billing periods too? can this be amended to be more exact? (page 81. 21.5) | [5 empty] | E.ON Next | Large Supplier | 2024-03-11