## Mop Up 2
INTERNAL Mop Up 2 Consultation Consolidated Comments Log
Comment ID | Code Artefact Name | Document Section | Comments | Comment Theme | Related Design Artefact | Related Design Artefact Section/Step | Suggested Change e.g. proposed wording | Comment Owner | Organisation | Constituency | Submitted | Triage Status | Drafting change? | Triage Response Reason | Programme Response e.g.clarification or update on the change
CD6-132 | DCUSA MHHS Transition | 132D | The rules for determining which measurement class consumption will move to following the implementation of MHHS is incorrect and do not correspond to what was agreed in CR032. The two attributes that will determine resultant measurement class after migrating to MHHS are domestic indicator and connection type. As we cannot determine whether the meter is 100kw we cannot determine whether consumption should be allocated to measurement class C or E, so all consumption will be allocated to measurement class C. | Missing Content - Existing Code |  |  | I suggest using the logic that was agreed in CR032 :- i. Measurement Class A: will not be derived for migrated MPANs, as they will be half-hourly ii. Measurement Class B: will not be derived for migrated MPANs, as they will be half-hourly iii. Measurement Class C: will report the sum of Measurement Classes C and E*, which will be determined as ‘all migrated MPANs with Domestic Indicator = N and Connection Type = L, H or E’ iv. Measurement Class D: will be determined as ‘all migrated MPANs with Domestic Indicator = N and Connection Type = U’ v. Measurement Class E will be set to “0MWh” for migrated MPANs* (see Measurement Class C above) vi. Measurement Class F: will be determined as ‘all migrated MPANs with Domestic = Y and Connection Type ≠ U’ vii. Measurement Class G: will be determined as ‘all migrated MPANs with Domestic = N and Connection Type = W’ | Andrew Dudkowsky | National Grid ESO |  | 2024-03-11 | Accepted ​ | Yes | Minor Change relating to code ​ | I can understand the reason for the comment being raised. This clause is for the current arrangements and was introduced when measurment class F and G was created so it is pre MHHS. It will ultimately be deleted during the housekeeping change post migration. However there may be merit in an amendment to clarify this in the text to insert "For non-MHHS Metering Points" at the begining of the Paragraph. The MHHS amendments do cater for connection type and Domestic indicator which provides the choice of aggregated or site specific tariffs based on whole current (Para 132C) or not whole current (Para 135A).
CD6-152 | DCUSA MHHS Transition | Glossary of terms used in Schedule 16 | Defnition - Domestic 'Premise' Indicator has the meaning given to the term in the Energy Market Data Specification. | Minor Drafting Error(s) |  |  | As noted in Mop up 1 there should be an 's' at the end of 'Premise'. | Andrew Sherry | Electricity North West Limited | Network Operator | 2024-03-11 | Accepted ​ | Yes | Minor Change relating to code ​ | "s" to be added to the end of "Premise"
CD6-326 | DCUSA MHHS Transition |  | 1. further clarification needed around the definition of 'aggregated basis' for charging. This needs clarity as needs to be interpreted the same by all DNO's and IDNO's. - Not changed HB 6/3/24 | General Drafting Comment |  |  |  |  | E.ON Next | Large Supplier | 2024-03-11 |  |  |  | schedule 16 indicates what is to be charged on an aggregated basis and what is charged on a site specific basis. The only changes are to how the data is provided (see DIN-895 for more detail). Can you be more specific since all Distributors have been following this approach since the opening of the competitve market in 1998 and the introduction of DCUSA in 2006.
CD6-327 | DCUSA MHHS Transition | page 107 | 2. Title on page 107 needs changing to 'DIP or DTN'. | Missing Content - Existing Code |  |  |  |  | E.ON Next | Large Supplier | 2024-03-11 | Clarification Provided​ | No |  | There is no reference to such on Page 107. I suspect it is referring to such a reference within Clause 59 on page 98, which says DTN or DIP. The suggestion is more a preference. The Paragraph starts with DTN and was in the document pre the inclusion of the DIP. It does, when reviewing the rest of the comments, seem that the comment relates to the transition document and not the Mop-up 2 document where the omission did exist.
CD6-328 | DCUSA MHHS Transition | page 50 | 3. Page 50 missing 'T' from Agent. | Missing Content - Existing Code |  |  |  |  | E.ON Next | Large Supplier | 2024-03-11 | Clarification Provided​ | No |  | This was responded to in the Transition comments log and was accepted at the time, however in the Mop up 1 consultation, the definition was amended by the Programme (Schedule X-1) to remove Agent. It is not referenced in our Mop-up 2 document on the page you refer. See response to CD6-327 re transistion document review.
CD6-329 | DCUSA MHHS Transition | Missing | 4. Clarification needed on what will happen to paper billing and if this ceases when this will happen. - No Clarification in this paper | General Drafting Comment |  |  |  |  | E.ON Next | Large Supplier | 2024-03-11 | Clarification Provided​ | No |  | No reference point provided so it is assumed it is referring to the MHHS invoices under Clause 21.2B. The new MHHS process is for the Distributor to send and the the supplier to receive the electronic invoice. The use of paper bills is therefore not required. However the distributor may wish to use such a process where the DIP is not available under clause 59.4
CD6-330 | DCUSA MHHS Transition | Missing | 5. The Consultation Paper mentions 'Energy Market Specification' throughout, what is this and can a link be provided. | General Drafting Comment |  |  | Please provide the detailed view on the energy market specification document |  | E.ON Next | Large Supplier | 2024-03-11 | Clarification Provided​ | No |  | The Energy Market Data Specification is a defined term that references a document managed by the Retail Energy Code. It contains the metadata that describes the Data Items and Market Messages that are used by industry parties to send and receive information. The scope of the Data Specification includes the information needed to support the requirements of the REC, BSC, DCUSA, UNC, IGT UNC and parts of the SEC.
CD6-331 | DCUSA MHHS Transition | General comment | 6. Inconsistency in the drafting, for example it mentions 'BSC' in some areas and other states 'Balancing and Settlement code'. This is a legal document so there needs to be consistency throughout. - | General Drafting Comment |  |  | This has been fed back before but we cannot see this has been addressed |  | E.ON Next | Large Supplier | 2024-03-11 | Clarification Provided​ | No |  | This comment was received from another supplier during the transition consultation with the following response: I agree that consistency would be helpful, but to do so would mean amending definitions and clauses throughout DCUSA that are not impacted by the MHHS Programme. This suggestion can be raised by any Party as an housekeeping change.
CD6-332 | DCUSA MHHS Transition | 20b | 7. Assumed that DUoS volume will be reported as part of the MHHS-REP-900 message within the 'Quantity' (DI-598) data item. However, in the population notes for that data item it says, 'If Charge type =CAPAC or XSCAP, shows a capacity value'. Therefore, I assume that if a different 'ChargeType' (DI-596) was used such as Red, Amber, Green, etc. then the 'Quantity' data item would refer to a volume? If so, it might be useful to state this as well within the population notes. Can we obtain clarity on how this will work. Reference to section 20b in this area however section 20 is missing from the document. | General Drafting Comment |  |  | the whole of section 20 is missing from this version please can you clarify if this is intentional or an oversight and what has happened to the information that we need clarity on that was in the original section 20 |  | E.ON Next | Large Supplier | 2024-03-11 | Clarification Provided​ | No |  | It is intentional.The document only shows where changes have been made, and if so the full section is provided. To do otherwise would have resulted in over 1000 pages to trawl through. There are no changes to section 20 due to MHHS. The changes made are to the definition titles used within section 20 such as Supercustomer DUoS Report and Daily Statement which are contained within section 1 of the document. Any changes to the content of the data items/messages should be made to the "ECS Reports - External" design document. For Red/Amber/Green, the interpretation is correct and is expected to be a volume.
CD6-333 | DCUSA MHHS Transition | various missing items | Sections 9,10, 11,13,14,16,17,22,23,24,36-41 and 43-58 all missing from the document. | General Drafting Comment |  |  |  |  | E.ON Next | Large Supplier | 2024-03-11 | Clarification Provided​ | No |  | It is intentional.The document only shows where changes have been made, and if so the full section is provided. To do otherwise would have resulted in over 1000 pages to trawl through.
CD6-334 | DCUSA MHHS Transition | 21.5 | Further clarification needed on when REP900 will be sent instead of D2021. Paper states that the REP900 will be sent using the DIP save that for non-MHHS metering points it will be data flow D2021. is this not also related to billing periods too? can this be amended to be more exact? (page 81. 21.5) | Missing Content - Existing Code |  |  |  |  | E.ON Next | Large Supplier | 2024-03-11 | Clarification Provided​ | No |  | This is already catered for under Clause 15.6 15.6 In this Section 2A, in the Schedules when applied pursuant to this Section 2A, and in the terms defined in Clause 1 when used in this Section 2A or those Schedules, any reference to a “charging period” is, subject to any contrary indication, a reference to the period specified in the Relevant Charging Statement (or, if no period is specified therein, a calendar month Also supported by clause 21.2 and 21.2A For clarity, additional text has been added to recognise the time element: "For MHHS Metering Points, for settlement periods whilst they are under MHHS arrangements, the Company shall submit, and the User agrees to receive, accounts by sending an electronic invoice using the REP-900 for all the User’s accounts (including revised accounts and credit-notes). For non-MHHS Metering Points, and for MHHS Metering Points for settlement periods whilst they are not under MHHS arrangements..."

## Triage and Clarification Status
Triage status | Description​
​
Accepted ​ | Comment has been accepted and change has been made to code drafting.​​
Rejected​ | Comment reject - not consistent with Design. No change will be made to code drafting.​​
Acknowledge​ | Comment is not related to the code artefacts but may be picked up in a later tranche or further clarification, will be provided to the comment raiser.​​
Requires further clarification with PP​ | Comment is not fully understood by the code reviewer and requires clarification with the comment raiser.​​
Clarification Provided​ | No change made - clarification is provided to respond to reviewers comment​
Triage response​ reason | Triage clarification response​
​
Out of Code Scope | Outside of MHHS Code drafting parameters
Out of Design Scope ​ | Outside of current Design parameters
Later Tranche​ | Acknowledge this will be delivered in a later tranche​
Minor Change relating to code ​ | Small change required to the code drafting content
Major Change relating to code ​ | Large change required to the code drafting content
Design Query ​ | Comment is relating to the MHHS Design and not the Code drafting ​​
Comment theme | Reviewer comment theme
Design Translation | Design not correctly translated into Code
Missing Content - Design | Expected content in Design for the Topic Area not documented
Missing Content - Existing Code | Expected content in Code for the Topic Area not documented
Minor Drafting Error(s) | Grammar, punctuation, spelling, formatting and other minor inconsistencies
Document Layout and Structure | Code Artefact could be better or more logically structured (propose alternative)
General Drafting Comment | Any comment on code drafting not covered by the above

## Guidance (hidden)
Guidance Sheet
MHHS-DELXXX Consolidated Code Artefacts Consultation Log

## Control (hidden)
Status
Submitted
Accepted
Rejected
Action
Requires Further Clarification
Provide comment owner with clarification
Cosmetic | Formatting and typos
Minor | Minor change relating to code
Major | Major change relating to code
Change request | change request to MHHS Design
Documents
BSCP700 - Unmetered Suppliers Data Services / UMSDS
BSCP701 - Smart Data Collection / SDS
BSCP702 - Advanced Data Collection / ADS
BSCP70x - Unmetered Supplies Operations (UMSO)
BSCP601
BSC Section K
BSC Section J - Party Agents and Qualification under the Code
BSC Section L - Metering
BSC Code of Practice 1
BSC Code of Practice 2
BSC Code of Practice 3
BSC Code of Practice 4
BSC Code of Practice 5
BSC Code of Practice 6
BSC Code of Practice 7
BSC Code of Practice 8
BSC Code of Practice 9
BSC Code of Practice 10
REC - Schedule 13 Transfer of Consumer Data
REC - Schedule 14 Metering Operations
REC - Consolidated Metering Code of Practice
Constituency
Central Party
Code Body
DNO
I&C Supplier
iDNO
In-House Supplier Agent
Independent Agent
Large Supplier
Medium Supplier
Small Supplier
Other MHHS Participant
Software Provider