## CPs
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status Changed in the last month | Date Issued to Ofgem | Original Expected Decision Date | Latest Expected Decision Date
STATUS - INITIAL ASSESSMENT
No
STATUS - DEFINITION
DCP 325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20. | The intent of this Change Proposal is to combine, review and if appropriate, amend the requirements of Section 35A, Section 35B, Schedule 15 and Schedule 20 to improve transparency and efficiency in the data published by DNOs | General | 2 | Richard Colwill / Melissa Kendal | N/A | 2018-11-07 | 11 | No | Next scheduled release following approval | The DCP 325 Working Group is looking to issue a consultation to industry shortly. | N/A
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | The intent of this modification is to define “Mixed Demand” Sites and apply a proportionate Residual charge where a Site meets the mixed demand definition. | General | 1 | John Lawton / Andy Green | Andrew Malley | 2021-04-14 | 17 | No | TBC | The Working Group met on 02 October to review the need for a BSC change. It was agreed that a BSC change was required and that DCP 388 couldn’t be progressed until the BSC change had been defined so DCP 388 has been paused. | N/A
DCP 412 | Discounts from TCR charges for ‘peaky’ final demand customers | This Change Proposal aims to create a discount against the residual charge for ‘peaky’ customers, removing the disproportionate impact of allocating residual charges on the basis of the Agreed Supply Capacity. | CDCM / EDCM | 1 | Andy Green / Craig Booth | Andrew Malley | 2022-10-11 | 29 | No | TBC | The DCP 412 Working Group plan to meet again in April to further develop the second consultation documents with the aim to issue to send before the end of March. | N/A
DCP 415 | Replacement of D0242/D0315 for MHHS | To create a new DCUSA owned DIP data message for supercustomer billing statements using MHHS data. | Billing | 2 | Hannah Proffitt / Craig Booth | N/A | 10/22/2022 | 3 | No | TBC (dependent on date required for DIP testing) | The Change Report was submitted to the Panel for review in the February Panel meeting. The Panel agreed that it would not progress to Party voting and that it should be sent back to the Working Group but that the Working Group won’t need to meet until the MHHS Programme have been able to carry out an Impact Assessment for the solution they developed. It was noted that even then, no further work may be required but that it was too early to know that for sure. | N/A
DCP 416 | Electronic Invoicing Post MHHS | To create a new DCUSA owned DIP data message for electronic Distributor billing post MHHS. | Billing | 2 | Melissa Kendal / Andy Green | N/A | 2022-11-14 | 5 | No | TBC (dependent on date required for DIP testing) | The Working Group have reviewed the consultation responses and met on 23 June 2023 to finalise the conclusions to the second consultation. A decision on whether or not a Change Report is to be produced is to be made by the Panel but the Proposer has initated a MHHS Change Request for the CP to be impact assessed and so it is expected that DCP 416 will be put on hold, pending outcome of the MHHS Change Request. | N/A
DCP 417 | Ability for the DCUSA Secretariat to Raise Change Proposals | This change seeks to grant the ability to the Secretariat to raise Change Proposals where it identifies a change that would better facilitate the DCUSA Objectives and to introduce an obligation for the Secretariat to raise Change Proposals in certain circumstances, such as at the direction of the Authority. | General | 1 | Melissa Kendal / Richard Colwill | Nadir Hafeez | 2022-12-14 | 8 | No | Next scheduled release following approval | The Working Group have requested a representative from Gowlings attend a Working Group in order to finalise the legal text. Due to availably of the legal advisor this can’t happen until after 11 April 2024. It is expected that the change report will be issued to May’s panel. | N/A
DCP 419 | Pre-Notifications of Planned Supply De-Energisations | This change seeks to ensure that all DCUSA Parties, that de-energise metering equipment as part of any planned work, provide the Distributor with advance notification of the supply interruption. | General | 1 | Alysson Pena / | TBC | 2023-03-06 | 9 | No | Next scheduled release following approval | The next DCP 419 Working Group is to be scheulded later in April, where the Working Group will continue to review and refine proposed solution. | N/A
DCP 420 | Include Car Charging Stations In The Definition For Non Final Demand | This change proposal aims to expand the definition of Non Final Demand to include Non Domestic sites which are solely for the use of charging vehicles where electricity is sold with a commercial transaction to a private user. These are to include e.g. Council run services, electric charging stations at car parks and service stations or petrol forecourts but are not to include private fleet charging stations. This is a temporary fix to be put in place until the charging stations included are commercially viable. | General | 1 | Craig Booth / Richard Colwill | TBC | 2023-03-29 | 5 | No | - | The next Working Group meeting is scheduled for 15 April and Charge UK will be attending this meeting. | N/A
DCP 421 | Update the Tables in schedule 15 of DCUSA | To amend the current tables within Schedule 15 of DCUSA to correctly represent ED2 revenue. | General | 2 | Craig Booth / Andy Green | N/A | 2023-04-12 | 4 | No | Next scheduled release following approval | CEPA have provided updated models, and these have been tested by one DNO, still awaiting testing from others before to confirm the updates are fit for purpose. It is expected that the change report will be issued to May’s panel. | N/A
DCP 423 | LDNO Discounts for negative scaling | The purpose of this change proposal is to set a floor on the LDNO discount applied to negative tariff components, after scaling, for demand tariffs. The intent of this change proposal is to seek to remedy what the proposer believes is an unintended outcome of the implementation of Ofgem’s Targeted Charging Review where LDNO tariffs can be higher than the equivalent all-the-way tariff i.e. the LDNO margin is negative for that component. | CDCM | 1 | Melissa Kendal / Andy Green | TBC | 2023-05-09 | 3 | No | 2025-04-01 | CEPA have provided updated modelling which excludes changes in the EDCM as requested. This has been shared with the working group for testing prior to issuing for consultation. | N/A
DCP 424 | Use of System charging for complex sites | This change proposal enables the correct DUoS to be paid by meters that are class F or G within a Class 5 or Class 6 Complex Site as described in BSC Modification P441 (where netting of Import and Export takes place for BSC Settlement purposes) in a practical manner. Under p441 where generation and demand are netted before settlement, the gross values must be added to the D0036 or D0275 to ensure the correct DUoS is charged. However, for class F and G the MPAN counts are included on the D0030 data flows but the volumes are zero. In order for the volumes to be correctly charged DUoS it is proposed that these volumes are included in the D0036 or D0275 using a pseudo MPAN for the gross value. | CDCM | 1 | Andy Green / Craig Booth | TBC | 2023-05-10 | 6 | No | Aligned to BSC Mod P441 Implementation Date | DCP 424 has been delayed due a request by Ofgem for further impact analysis on the proposed BSC solution (P441 - Creation of Complex Site Classes). The DCP 424 consultation is now estimated to be released in Q3 2024. | N/A
DCP 433 | Limitation for backdating of rebates/charges under Schedule 32 | The intent of this Change Proposal is to amend Schedule 32 to ensure that processes which may result in the backdating of rebates/charges are reflective of the limitations within the current industry arrangements. | General | 1 | Craig Booth | TBC | 2024-01-05 | 3 | No | 2024-06-27 | The Working Group issued a consultation on 18 March 2024 to gather feedback on the proposed solution. The deadline for responses is 10 April 2024. The Working Group plan to meet again on 18 April to review the consultation responses and the draft Change Report. | CONSULTATION
DCP 436 | Date change for the provision of Rota Load Block Alpha Identifiers | The proposal is to change the dates related to the provision of Rota Load Block Alpha Identifiers to later dates. Later dates would ensure that the most up to date Rota Load Block Alpha Identifiers are provided to Customers via Suppliers during the winter when the use of Rota Load Disconnections are most likely to be needed. Without changing the dates, (I)DNOs would need to issue Rota Load Block Alpha Identifiers to Suppliers twice per year to achieve this accuracy during winter, which is disruptive to (I)DNOs and Suppliers. | General | 2 | Craig Booth | TBC | 2024-02-12 | 1 | No | 2024-06-27 | The Working Group issued a consultation on 20 March 2024 to gather feedback on the proposed solution. The deadline for responses is 12 April 2024. The Working Group plan to meet again on 16 April to review the consultation responses. | CONSULTATION
DCP 437 | To Shorten the DUoS Pricing Notice Periods | This change proposal aims to shorten the DUoS Pricing Notice Periods so there is longer period between the publication of the PCFM where OFGEM have the option to make changes to our allowed revenue at short notice and the setting of the prices | CDCM | 1 | Hannah Proffitt / Craig Booth | TBC | 2024-02-13 | 0 | No | 2024-11-07 | DCP 437 was submitted to the Panel for Initial Assessment during their February meeting. The Panel approved for DCP 437 to progress to the Definition Phase and for a Working Groupto be set up in order to refine the proposed solution, however, Ofgem noted that the CP may impact upon their DUoS SCR and so was placed on hold until this impact was assessed. During the March Panel meeting, Ofgem confirmed that whilst they do believe there to be an interaction, that they are happy for DCP 437 to proceed. Invitations to join the Working Group have been issued and the first meeting will be scheduled shortly. | DEFINITION
DCP 438 | Rate of Return Change Proposal | This change proposal aims to update the rate of return as the previous legal text is out of date | CDCM | 1 | Hannah Proffitt / Craig Booth | TBC | 2024-02-27 | 0 | No | 2025-04-01 | DCP 438 was submitted to the Panel for Initial Assessment during their March meeting. The Panel approved for DCP 438 to progress to the Definition Phase and for a Working Groupto be set up in order to refine the proposed solution. The first Working Group meeting is scheduled for 22/04/2024. | DEFINITION
STATUS - CHANGE REPORT
N/A | N/A | [7 empty] | No |  |  | N/A
STATUS - VOTING
DCP 428 | Zero REP-002/A Data | To specify how parties should deal with zero or blank data in the supercustomer/aggregated billing messages when sending daily statements or raising invoices. | General | 2 | Richard Colwill/ Alysson Peña | TBC | 2023-07-25 | 4 | No | 2024-04-01 | The DCP 428 Working Group finalised their review of the legal text to confirm it was fit for purpose and the Change Report was approved by the Panel ex-committee and subsequently issued for voting on 10 April 2024. | VOTING
DCP 425 | Cost Apportionment Factor “cap” Methodology | The intent of this Change Proposal (“CP”) is to provide further clarification as to how costs of Reinforcement are apportioned between the Company and the Customer (a Generation Connection) when the High-Cost Project Threshold is triggered. | General | 1 | Richard Colwill/ Craig Booth | TBC | 2023-07-13 | 4 | No | 2023-12-19 | The Working Group has completed the change report and this will be presented to the March panel. | VOTING
DCP 434 | Credit Cover RAV in ED-2 | The RAV calculation used in Credit Cover needs to be updated to reflect ED-2 | General | 2 | Andy Green | N/A | 2024-02-09 | 0 | No | Next scheduled release | The Change Report has been completed and will be presented to the March Panel. | VOTING
DCP 435 | Party Novation Process | To add a process within DCUSA to enable a Party to transfer its rights and obligations to another Party via a novation agreement. | General | 1 | Craig Booth | N/A | 2024-02-09 | 0 | No | Next release after approval. | The Change Report has been completed and will be presented to the March Panel. | VOTING
STATUS - AWAITING AUTHORITY CONSENT
DCP 411 | Charging De-energised sites | To remove the different treatment of DUoS with respect to de-energised sites | CDCM | 1 | Andy Green / Craig Booth | TBC | 2022-07-13 | 11 | No | 2025-04-01 | The Change Report was issued following approval during the May Panel meeting. Voting has concluded, with the change declaration issued to Ofgem on 14/06/2023. | N/A | 2023-06-14 | 2023-11-30 | 2024-04-08
STATUS - AWAITING IMPLEMENTATION
STATUS - SENT BACK
N/A | N/A | [7 empty] | No |  |  | N/A
STATUS - IMPLEMENTED
DCP 395 | Allocation of Smart Meter Communication Licence costs within LDNO Tariffs | To increase the cost reflectivity of LDNO tariffs by appropriately allocating costs associated with the smart meter communication licence to LDNO tariffs | General | 1 | John Lawton / George Dawson |  | 2021-05-10 | 3 | No | 2024-04-01 | The DCP 395 Working Group issued a consultation to industry in March 2022, with responses due by 12 April. The Working Group met on 25 April to review the consultation responses and agreed the final solution. The Change Report was presented to the Panel during the May Panel meeting, where it was approved to be issued for Party voting. | IMPLEMENTED
DCP 414 | Transitional Protection for NHH CT Customers affected by regulatory change | This change proposal seeks to provide transitional protection for Non Half-Hourly Current Transformer customers moving to Half-Hourly settlement & prevent penal excess capacity charges being applied to customers in any instance that the Maximum Import Capacity is a zero value because there is no site-specific connection agreement in place between users & Distribution Network Operators. | General | 1 | Andy Green / John Lawton | Danielle Walton | 2022-10-18 | 8 | No | 2024-04-01 | The Change Report was issued following last month’s Panel meeting and voting has concluded, with the change declaration issued on 14/06/2023. | IMPLEMENTED | 2023-06-14 | 2023-07-31 | 2023-07-31
STATUS - REJECTED
N/A | N/A | [7 empty] | No |  |  | N/A
STATUS - WITHDRAWN
N/A | N/A | [7 empty] | No |  |  | N/A
Change Register - April 2024

## Status Change
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status Changed in the last month
DCP 433 | Limitation for backdating of rebates/charges under Schedule 32 | The intent of this Change Proposal is to amend Schedule 32 to ensure that processes which may result in the backdating of rebates/charges are reflective of the limitations within the current industry arrangements. | General | 1 | Craig Booth | TBC | 2024-01-05 | 3 | No | 2024-06-27 | The Working Group issued a consultation on 18 March 2024 to gather feedback on the proposed solution. The deadline for responses is 10 April 2024. The Working Group plan to meet again on 18 April to review the consultation responses and the draft Change Report. | CONSULTATION
DCP 436 | Date change for the provision of Rota Load Block Alpha Identifiers | The proposal is to change the dates related to the provision of Rota Load Block Alpha Identifiers to later dates. Later dates would ensure that the most up to date Rota Load Block Alpha Identifiers are provided to Customers via Suppliers during the winter when the use of Rota Load Disconnections are most likely to be needed. Without changing the dates, (I)DNOs would need to issue Rota Load Block Alpha Identifiers to Suppliers twice per year to achieve this accuracy during winter, which is disruptive to (I)DNOs and Suppliers. | General | 2 | Craig Booth | TBC | 2024-02-12 | 1 | No | 2024-06-27 | The Working Group issued a consultation on 20 March 2024 to gather feedback on the proposed solution. The deadline for responses is 12 April 2024. The Working Group plan to meet again on 16 April to review the consultation responses. | CONSULTATION
DCP 437 | To Shorten the DUoS Pricing Notice Periods | This change proposal aims to shorten the DUoS Pricing Notice Periods so there is longer period between the publication of the PCFM where OFGEM have the option to make changes to our allowed revenue at short notice and the setting of the prices | CDCM | 1 | Hannah Proffitt / Craig Booth | TBC | 2024-02-13 | 0 | No | 2024-11-07 | DCP 437 was submitted to the Panel for Initial Assessment during their February meeting. The Panel approved for DCP 437 to progress to the Definition Phase and for a Working Groupto be set up in order to refine the proposed solution, however, Ofgem noted that the CP may impact upon their DUoS SCR and so was placed on hold until this impact was assessed. During the March Panel meeting, Ofgem confirmed that whilst they do believe there to be an interaction, that they are happy for DCP 437 to proceed. Invitations to join the Working Group have been issued and the first meeting will be scheduled shortly. | DEFINITION
DCP 438 | Rate of Return Change Proposal | This change proposal aims to update the rate of return as the previous legal text is out of date | CDCM | 1 | Hannah Proffitt / Craig Booth | TBC | 2024-02-27 | 0 | No | 2025-04-01 | DCP 438 was submitted to the Panel for Initial Assessment during their March meeting. The Panel approved for DCP 438 to progress to the Definition Phase and for a Working Groupto be set up in order to refine the proposed solution. The first Working Group meeting is scheduled for 22/04/2024. | DEFINITION
DCP 428 | Zero REP-002/A Data | To specify how parties should deal with zero or blank data in the supercustomer/aggregated billing messages when sending daily statements or raising invoices. | General | 2 | Richard Colwill/ Alysson Peña | TBC | 2023-07-25 | 4 | No | 2024-04-01 | The DCP 428 Working Group finalised their review of the legal text to confirm it was fit for purpose and the Change Report was approved by the Panel ex-committee and subsequently issued for voting on 10 April 2024. | VOTING
DCP 425 | Cost Apportionment Factor “cap” Methodology | The intent of this Change Proposal (“CP”) is to provide further clarification as to how costs of Reinforcement are apportioned between the Company and the Customer (a Generation Connection) when the High-Cost Project Threshold is triggered. | General | 1 | Richard Colwill/ Craig Booth | TBC | 2023-07-13 | 4 | No | 2023-12-19 | The Working Group has completed the change report and this will be presented to the March panel. | VOTING
DCP 434 | Credit Cover RAV in ED-2 | The RAV calculation used in Credit Cover needs to be updated to reflect ED-2 | General | 2 | Andy Green | N/A | 2024-02-09 | 0 | No | Next scheduled release | The Change Report has been completed and will be presented to the March Panel. | VOTING
DCP 435 | Party Novation Process | To add a process within DCUSA to enable a Party to transfer its rights and obligations to another Party via a novation agreement. | General | 1 | Craig Booth | N/A | 2024-02-09 | 0 | No | Next release after approval. | The Change Report has been completed and will be presented to the March Panel. | VOTING
DCP 395 | Allocation of Smart Meter Communication Licence costs within LDNO Tariffs | To increase the cost reflectivity of LDNO tariffs by appropriately allocating costs associated with the smart meter communication licence to LDNO tariffs | General | 1 | John Lawton / George Dawson |  | 2021-05-10 | 3 | No | 2024-04-01 | The DCP 395 Working Group issued a consultation to industry in March 2022, with responses due by 12 April. The Working Group met on 25 April to review the consultation responses and agreed the final solution. The Change Report was presented to the Panel during the May Panel meeting, where it was approved to be issued for Party voting. | IMPLEMENTED
DCP 414 | Transitional Protection for NHH CT Customers affected by regulatory change | This change proposal seeks to provide transitional protection for Non Half-Hourly Current Transformer customers moving to Half-Hourly settlement & prevent penal excess capacity charges being applied to customers in any instance that the Maximum Import Capacity is a zero value because there is no site-specific connection agreement in place between users & Distribution Network Operators. | General | 1 | Andy Green / John Lawton | Danielle Walton | 2022-10-18 | 8 | No | 2024-04-01 | The Change Report was issued following last month’s Panel meeting and voting has concluded, with the change declaration issued on 14/06/2023. | IMPLEMENTED
Status Change - April 2024

## Timetables
DCP | Title | Part 1/ Part 2 Matter | Standard/ Urgent | Proposer | Party | Technical Secretariat | Chair | Timetable Change | [9 empty] | Notes
[9 empty] | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
438 | Rate of Return Change Proposal | Part 1 | Standard | Babatunde Olukotun | NGED | Craig Booth | Andy Green |  | Def | CON | Def | Def | CR | CD
437 | To Shorten the DUoS Pricing Notice Periods | Part 1 | Standard | Dave Wornell | NGED | Andy Green | Craig Booth |  | Def | CON | Def | CR | CD | CD
436 | Date change for the provision of Rota Load Block Alpha Identifiers | Part 2 | Standard | Paul Nicholson | NPg | Andy Green | Craig Booth | No | Apr: Def; May: CR; Jun: CD
435 | Party Novation Process | Part 1 | Standard | Peter Waymont | UKPN | Craig Booth | Craig Booth | No | bar: Apr to May
434 | Credit Cover RAV in ED-2 | Part 2 | Standard | Peter Waymont | UKPN | Andy Green | Andy Green | No | bar: Apr
433 | Limitation for backdating of rebates/charges under Schedule 32 | Part 1 | Standard | Chris Barker | ENWL |  | Craig Booth | No | Apr: Def; May: CR; Jun: CD; Jul: WO
428 | Zero REP-002/A Data | Part 2 | Standard | Peter Waymont | UKPN | Alysson Peña | Richard Colwill | Yes | bar: Apr to May
425 | Cost Apportionment Factor “cap” methodology | Part 1 | Standard | Lee Wells | NPg | Alysson Peña | Richard Colwill | No | bar: Apr
424 | Use of System charging for complex sites | Part 1 | Standard | Mary Gillie | NPg | Craig Booth | Andy Green | No | Apr: O/H | Dependent on BSC P411
423 | LDNO Discounts for negative scaling | Part 1 | Standard | Tom Cadge | ENC | Melissa Kendall | Andy Green | No | Apr: Def; May: CR; Jun: CD; Jul: WO
New Proposed timetable | [8 empty] | Apr: CON; May: Def; Jun: CR; Jul: CD; Aug: WO | CEPA have provided updated modelling which excludes changes in the EDCM as requested. This has been shared with the working group for testing prior to issuing for consultation.
421 | Update the Tables in schedule 15 of DCUSA | Part 1 | Standard | Dave Wornell | NGED | Craig Booth | Andy Green | No | Apr: CR; May: CD; Jun: WO
New Proposed timetable | [8 empty] | Apr: Def; May: CR; Jun: CD; Jul: WO | CEPA have provided updated models, and these have been tested by one DNO, still awaiting testing from others before to confirm the updates are fit for purpose. It is expected that the change report will be issued to May’s panel.
420 | Include Car Charging Stations In The Definition For Non Final Demand | Part 1 | Standard | Dave Wornell | NGED | Craig Booth | Richard Colwill | No | CON | Def | Def | CR | CD | WO
419 | Pre-notification of Planned Supply De-energisations | Part 1 | Standard | Nikhel Jethwa | SSEN | Alysson Peña | Richard Colwill | No | Apr: Def; May: CR; Jun: CD; Jul: WO
417 | Ability for the DCUSA Secretariat to Raise Change Proposals | Part 1 | Standard | Simon Yeo | NGED | Melissa Kendall | Richard Colwill | No | Apr: CR; May: CD; Jun: WO
New Proposed timetable | [8 empty] | Apr: Def; May: CR; Jun: CD; Jul: WO
416 | Electronic Invoicing Post MHHS | Part 2 | Standard | Peter Waymont | UKPN | Craig Booth | Andy Green | No | Apr: O/H
415 | Replacement of D0242/D0315 for MHHS | Part 2 | Standard | Peter Waymont | UKPN | Melissa Kendall | Craig Booth | No | Apr: O/H
412 | Discounts from TCR charges for ‘peaky’ final demand customers | Part 1 | Standard | Lee Stone | E.ON | Andy Green | Craig Booth | No | Def | CON 2 | Def | CR | CD | WO
388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | Part 1 | Standard | Lee Stone | E.on | Andy Green | John Lawton | No | [9 empty] | Dependancy on the related BSC mod.
325 | Reviewing the requirements of Sections 35A (‘Provision of Cost Information’), 35B (‘Production of the Annual Review Pack’), Schedule 15 (‘Cost Information Table’) and Schedule 20 (‘Production of the Annual Review Pack’) | Part 1 | Standard | Kara Burke | NPg | Melissa Kendall | Richard Colwill | No | Apr: CON 2; May: Def; Jun: CR; Jul: CD; Aug: WO
Key
Definition | Def
RFI | RFI
Consultation | CON/ CON 2
Change Report | CR
Voting/ Change Declaration | CD
With Ofgem | WO
Implementation | Imp
Decision | Dec
Withdrwan | Wd

## Legal Text Overlap Tracker
YES
|  | MHHS | DCP 424 | DCP 325 | DCP 421 | DCP 423 | DCP 388 | DCP 412 | DCP 420
|  | Unknown | 2024-04-01 | Next Scheduled | Next Scheduled | 2025-04-01 | TBC | TBC | TBC |  | NOTES TO ASSIST
Schedules | Paragraph Number |  | Definition | Definition | Definition | Definition | Definition | Definition | Definition | Number of CPs Impacting Paragraph
Schedule 15 | Table 1 |  |  | YES | YES |  |  |  |  | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 2 |  |  | YES | YES |  |  |  |  | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 3 |  |  | YES | YES |  |  |  |  | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
0
Schedule 16 | Introduction | [8 empty] | 0
Schedule 16 | 1 | [8 empty] | 0
Schedule 16 | 2 | [8 empty] | 0
Schedule 16 | 3 | [8 empty] | 0 | Model reference number and date
Schedule 16 | 4 | [8 empty] | 0
Schedule 16 | 5 | [8 empty] | 0
Schedule 16 | 6 | [8 empty] | 0
Schedule 16 | 7 | [8 empty] | 0
Schedule 16 | 7A | [8 empty] | 0
Schedule 16 | 8 | [8 empty] | 0
Schedule 16 | 9 | [8 empty] | 0
Schedule 16 | 10 | [8 empty] | 0
Schedule 16 | 10A | [8 empty] | 0
Schedule 16 | 11 | [8 empty] | 0
Schedule 16 | 12 | [8 empty] | 0
Schedule 16 | 13 | [8 empty] | 0
Schedule 16 | 14 | [8 empty] | 0
Schedule 16 | 15 | [8 empty] | 0
Schedule 16 | 16 | [8 empty] | 0
Schedule 16 | 17 | [8 empty] | 0
Schedule 16 | 18 | [8 empty] | 0
Schedule 16 | 19 | [8 empty] | 0
Schedule 16 | 20 | [8 empty] | 0
Schedule 16 | 21 | [8 empty] | 0
Schedule 16 | 22 | [8 empty] | 0
Schedule 16 | 23 | [8 empty] | 0
Schedule 16 | 24 | [8 empty] | 0
Schedule 16 | 25 | [8 empty] | 0
Schedule 16 | 26 | [8 empty] | 0
Schedule 16 | 27 | [8 empty] | 0
Schedule 16 | 28 | [8 empty] | 0
Schedule 16 | 29 | [8 empty] | 0
Schedule 16 | 30 | [8 empty] | 0
Schedule 16 | 31 | [8 empty] | 0
Schedule 16 | 32 | [8 empty] | 0
Schedule 16 | 33 | [8 empty] | 0
Schedule 16 | 34 | [8 empty] | 0
Schedule 16 | 35 | [8 empty] | 0
Schedule 16 | 36 | [8 empty] | 0
Schedule 16 | 37 | [8 empty] | 0
Schedule 16 | 38 | [8 empty] | 0
Schedule 16 | 39 | [8 empty] | 0
Schedule 16 | 40 | [8 empty] | 0
Schedule 16 | 41 | [8 empty] | 0
Schedule 16 | 41A | [8 empty] | 0
Schedule 16 | 41B | [8 empty] | 0
Schedule 16 | 42 | [8 empty] | 0
Schedule 16 | 42A | YES | [7 empty] | 1
Schedule 16 | 43 | [8 empty] | 0
Schedule 16 | 44 | YES | [7 empty] | 1
Schedule 16 | 45 | [8 empty] | 0
Schedule 16 | 46 | [8 empty] | 0
Schedule 16 | 47 | [8 empty] | 0
Schedule 16 | 48 | [8 empty] | 0
Schedule 16 | 49 | [8 empty] | 0
Schedule 16 | 50 | [8 empty] | 0
Schedule 16 | 51 | [8 empty] | 0
Schedule 16 | 52 | [8 empty] | 0
Schedule 16 | 52A | [8 empty] | 0
Schedule 16 | 53 | [8 empty] | 0
Schedule 16 | 54 | [8 empty] | 0
Schedule 16 | 55 | [8 empty] | 0
Schedule 16 | 56 | [8 empty] | 0
Schedule 16 | 57 | [8 empty] | 0
Schedule 16 | 58 | [8 empty] | 0
Schedule 16 | 59 | [8 empty] | 0
Schedule 16 | 60 | [8 empty] | 0
Schedule 16 | 61 | [8 empty] | 0
Schedule 16 | 62 | [8 empty] | 0
Schedule 16 | 63 | [8 empty] | 0
Schedule 16 | 64 | [8 empty] | 0
Schedule 16 | 65 | [8 empty] | 0
Schedule 16 | 66 | [8 empty] | 0
Schedule 16 | 67 | [8 empty] | 0
Schedule 16 | 68 | [8 empty] | 0
Schedule 16 | 69 | [8 empty] | 0
Schedule 16 | 70 | YES | [7 empty] | 1
Schedule 16 | 71 | [8 empty] | 0
Schedule 16 | 72 | [8 empty] | 0
Schedule 16 | 72A | [8 empty] | 0
Schedule 16 | 73 | [8 empty] | 0
Schedule 16 | 74 | [8 empty] | 0
Schedule 16 | 75 | [8 empty] | 0
Schedule 16 | 76 | [8 empty] | 0
Schedule 16 | 77 | [8 empty] | 0
Schedule 16 | 78 | [8 empty] | 0
Schedule 16 | 79 | [8 empty] | 0
Schedule 16 | 80 | YES | [7 empty] | 1
Schedule 16 | 81 | [8 empty] | 0
Schedule 16 | 82 | [8 empty] | 0
Schedule 16 | 83 | [8 empty] | 0
Schedule 16 | 84 | [8 empty] | 0
Schedule 16 | 85 | [8 empty] | 0
Schedule 16 | 86 | [8 empty] | 0
Schedule 16 | 87 | [8 empty] | 0
Schedule 16 | 88 | [8 empty] | 0
Schedule 16 | 89 | [8 empty] | 0
Schedule 16 | 90 | [8 empty] | 0
Schedule 16 | 91 | [8 empty] | 0
Schedule 16 | 92 | [8 empty] | 0
Schedule 16 | 92A | [8 empty] | 0
Schedule 16 | 92B | [8 empty] | 0
Schedule 16 | 92C | [8 empty] | 0
Schedule 16 | 93 | [8 empty] | 0
Schedule 16 | 94 | [8 empty] | 0
Schedule 16 | 95 | [8 empty] | 0
Schedule 16 | 96 | [8 empty] | 0
Schedule 16 | 97 | [8 empty] | 0
Schedule 16 | 98 |  |  |  |  | YES |  |  |  | 1
Schedule 16 | 99 | [8 empty] | 0
Schedule 16 | 100 | [8 empty] | 0
Schedule 16 | 101 | [8 empty] | 0
Schedule 16 | 102 | [8 empty] | 0
Schedule 16 | 102A | [8 empty] | 0
Schedule 16 | 102B | [8 empty] | 0
Schedule 16 | 103 | [8 empty] | 0
Schedule 16 | 104 | [8 empty] | 0
Schedule 16 | 105 | [8 empty] | 0
Schedule 16 | 106 | [8 empty] | 0
Schedule 16 | 107 | [8 empty] | 0
Schedule 16 | 108 | [8 empty] | 0
Schedule 16 | 108A | [8 empty] | 0
Schedule 16 | 109 | [8 empty] | 0
Schedule 16 | 110 | [8 empty] | 0
Schedule 16 | 111 | [8 empty] | 0
Schedule 16 | 112 | [8 empty] | 0
Schedule 16 | 112A | [8 empty] | 0
Schedule 16 | 113 | [8 empty] | 0
Schedule 16 | 113A | [8 empty] | 0
Schedule 16 | 113B | [8 empty] | 0
Schedule 16 | 113C | [8 empty] | 0
Schedule 16 | 113D | [8 empty] | 0
Schedule 16 | 113E | [8 empty] | 0
Schedule 16 | 114 | [8 empty] | 0
Schedule 16 | 115 | [8 empty] | 0
Schedule 16 | 116 | [8 empty] | 0
Schedule 16 | 117 | [8 empty] | 0
Schedule 16 | 118 | [8 empty] | 0
Schedule 16 | 119 | [8 empty] | 0
Schedule 16 | 120 | [8 empty] | 0
Schedule 16 | 121 | [8 empty] | 0
Schedule 16 | 122 | [8 empty] | 0
Schedule 16 | 123 | [8 empty] | 0
Schedule 16 | 124 | [8 empty] | 0
Schedule 16 | 125 | [8 empty] | 0
Schedule 16 | 126 | [8 empty] | 0
Schedule 16 | 127 | [8 empty] | 0
Schedule 16 | 127A | [8 empty] | 0
Schedule 16 | 128 | YES | YES | [6 empty] | 2
Schedule 16 | 129 | YES | [7 empty] | 1
Schedule 16 | 130 | YES | [7 empty] | 1
Schedule 16 | 131 | [8 empty] | 0
Schedule 16 | 132 | YES | [7 empty] | 1
Schedule 16 | 132A | [8 empty] | 0
Schedule 16 | 132B | [8 empty] | 0
Schedule 16 | 132C | YES | [7 empty] | 1
Schedule 16 | 132D | [8 empty] | 0
Schedule 16 | 133 | YES | [7 empty] | 1
Schedule 16 | 134 | [8 empty] | 0
Schedule 16 | 135 | [8 empty] | 0
Schedule 16 | 135A | YES | [7 empty] | 1 | DCP 414 adds two new rows to table for tariffs named 'Domestic Aggregated or CT' and 'Non-Domestic Aggregated or CT' whereas, for MHHS it is proposed to remove the last column containing applicable MC
Schedule 16 | 135B | [8 empty] | 0
Schedule 16 | 136 | [8 empty] | 0
Schedule 16 | 137 | [8 empty] | 0
Schedule 16 | 138 | [8 empty] | 0
Schedule 16 | 139 | [8 empty] | 0
Schedule 16 | 140 | [8 empty] | 0
Schedule 16 | 140A | YES | [7 empty] | 1
Schedule 16 | 140B | YES | [7 empty] | 1
Schedule 16 | 140C | YES | [7 empty] | 1
Schedule 16 | 140D | [8 empty] | 0
Schedule 16 | 140E | [8 empty] | 0
Schedule 16 | 141 | [8 empty] | 0
Schedule 16 | 142 | YES | [7 empty] | 1
Schedule 16 | 143 | YES | [7 empty] | 1
Schedule 16 | 144 | YES | [7 empty] | 1
Schedule 16 | 145 | [8 empty] | 0
Schedule 16 | 146 | [8 empty] | 0
Schedule 16 | 147 | [8 empty] | 0
Schedule 16 | 148 | [8 empty] | 0
Schedule 16 | 149 | [8 empty] | 0
Schedule 16 | 150 | [8 empty] | 0
Schedule 16 | 151 | [8 empty] | 0
Schedule 16 | 152 | [8 empty] | 0
Schedule 16 | 153 | [8 empty] | 0
Schedule 16 | 154 | [8 empty] | 0
Schedule 16 | 155 | [8 empty] | 0
Schedule 16 | 156 | [8 empty] | 0
Schedule 16 | 157 | [8 empty] | 0
Schedule 16 | 158 | [8 empty] | 0
Schedule 16 | 159 | [8 empty] | 0
Schedule 16 | 160 | [8 empty] | 0
Schedule 16 | 161 | [8 empty] | 0
Schedule 16 | 162 | [8 empty] | 0
Schedule 16 | 163 | [8 empty] | 0
Schedule 16 | 164 | [8 empty] | 0
Schedule 16 | 165 | [8 empty] | 0
Schedule 16 | 166 | [8 empty] | 0
Schedule 16 | 167 | [8 empty] | 0
Schedule 16 | 168 | [8 empty] | 0
Schedule 16 | 169 | [8 empty] | 0
Schedule 16 | 170 | [8 empty] | 0
Schedule 16 | 171 | [8 empty] | 0
Schedule 16 | 172 | [8 empty] | 0
Schedule 16 | 173 | [8 empty] | 0
Schedule 16 | 174 | [8 empty] | 0
Schedule 16 | 175 | [8 empty] | 0
Schedule 16 | 176 | [8 empty] | 0
Schedule 16 | 177 | [8 empty] | 0
Schedule 16 | 178 | [8 empty] | 0
Schedule 16 | 179 | [8 empty] | 0
Schedule 16 | 180 | [8 empty] | 0
Schedule 16 | 181 | [8 empty] | 0
Schedule 16 | 182 | [8 empty] | 0
Schedule 16 | 183 | [8 empty] | 0
Schedule 16 | 184 | [8 empty] | 0
Schedule 16 | Glossary | YES | [7 empty] | 1
0
Schedule 17 | Introduction | [8 empty] | 0
Schedule 17 | 1 | [8 empty] | 0
Schedule 17 | 1.1 | [8 empty] | 0
Schedule 17 | 1.2 | [8 empty] | 0
Schedule 17 | 1.3 | [8 empty] | 0 | Model reference number and date
Schedule 17 | 1.3A | [8 empty] | 0
Schedule 17 | 1.4 | [8 empty] | 0
Schedule 17 | 1.5 | [8 empty] | 0
Schedule 17 | 1.6 | [8 empty] | 0
Schedule 17 | 1.7 | [8 empty] | 0
Schedule 17 | 1.8 | [8 empty] | 0
Schedule 17 | 1.9 | [8 empty] | 0
Schedule 17 | 2 | [8 empty] | 0
Schedule 17 | 2.1 | [8 empty] | 0
Schedule 17 | 2.2 | [8 empty] | 0
Schedule 17 | 2.3 | [8 empty] | 0
Schedule 17 | 2.4 | [8 empty] | 0
Schedule 17 | 2.5 | [8 empty] | 0
Schedule 17 | 2.6 | [8 empty] | 0
Schedule 17 | 2.7 | [8 empty] | 0
Schedule 17 | 2.8 | [8 empty] | 0
Schedule 17 | 2.9 | [8 empty] | 0
Schedule 17 | 2.1 | [8 empty] | 0
Schedule 17 | 2.11 | [8 empty] | 0
Schedule 17 | 2.12 | [8 empty] | 0
Schedule 17 | 2.13 | [8 empty] | 0
Schedule 17 | 2.14 | [8 empty] | 0
Schedule 17 | 2.15 | [8 empty] | 0
Schedule 17 | 2.16 | [8 empty] | 0
Schedule 17 | 2.17 | [8 empty] | 0
Schedule 17 | 2.18 | [8 empty] | 0
Schedule 17 | 2.19 | [8 empty] | 0
Schedule 17 | 3 | [8 empty] | 0
Schedule 17 | 3.1 | [8 empty] | 0
Schedule 17 | 3.2 | [8 empty] | 0
Schedule 17 | 3.3 | [8 empty] | 0
Schedule 17 | 3.4 | [8 empty] | 0
Schedule 17 | 3.5 | [8 empty] | 0
Schedule 17 | 3.6 | [8 empty] | 0
Schedule 17 | 3.7 | [8 empty] | 0
Schedule 17 | 4 | [8 empty] | 0
Schedule 17 | 4.1 | [8 empty] | 0
Schedule 17 | 5 | [8 empty] | 0
Schedule 17 | 5.1 | [8 empty] | 0
Schedule 17 | 6 | [8 empty] | 0
Schedule 17 | 6.1 | [8 empty] | 0
Schedule 17 | 6.2 | [8 empty] | 0
Schedule 17 | 6.3 | [8 empty] | 0
Schedule 17 | 7 | [8 empty] | 0
Schedule 17 | 7.1 | [8 empty] | 0
Schedule 17 | 8 | [8 empty] | 0
Schedule 17 | 8.1 | [8 empty] | 0
Schedule 17 | 8.2 | [8 empty] | 0
Schedule 17 | 8.3 | [8 empty] | 0
Schedule 17 | 8.4 | [8 empty] | 0
Schedule 17 | 9 | [8 empty] | 0
Schedule 17 | 9.1 | [8 empty] | 0
Schedule 17 | 9.2 | [8 empty] | 0
Schedule 17 | 9.3 | [8 empty] | 0
Schedule 17 | 10 | [8 empty] | 0
Schedule 17 | 10.1 | [8 empty] | 0
Schedule 17 | 10.2 | [8 empty] | 0
Schedule 17 | 10.3 | [8 empty] | 0
Schedule 17 | 10.4 | [8 empty] | 0
Schedule 17 | 11 | [8 empty] | 0
Schedule 17 | 11.1 | [8 empty] | 0
Schedule 17 | 12 | [8 empty] | 0
Schedule 17 | 12.1 | [8 empty] | 0
Schedule 17 | 12.2 | [8 empty] | 0
Schedule 17 | 12.3 | [8 empty] | 0
Schedule 17 | 13 | [8 empty] | 0
Schedule 17 | 13.1 | [8 empty] | 0
Schedule 17 | 13.2 | [8 empty] | 0
Schedule 17 | 13.3 | [8 empty] | 0
Schedule 17 | 13.4 | [8 empty] | 0
Schedule 17 | 14 | [8 empty] | 0
Schedule 17 | 14.1 | [8 empty] | 0
Schedule 17 | 14.2 | [8 empty] | 0
Schedule 17 | 14.3 | [8 empty] | 0
Schedule 17 | 14.4 | [8 empty] | 0
Schedule 17 | 14.5 | [8 empty] | 0
Schedule 17 | 15 | [8 empty] | 0
Schedule 17 | 15.1 | [8 empty] | 0
Schedule 17 | 15.2 | [8 empty] | 0
Schedule 17 | 15.3 | [8 empty] | 0
Schedule 17 | 15.4 | [8 empty] | 0
Schedule 17 | 15.5 | [8 empty] | 0
Schedule 17 | 15.6 | [8 empty] | 0
Schedule 17 | 15.7 | [8 empty] | 0
Schedule 17 | 15.8 | [8 empty] | 0
Schedule 17 | 15.9 | [8 empty] | 0
Schedule 17 | 15.1 | [8 empty] | 0
Schedule 17 | 15.11 | [8 empty] | 0
Schedule 17 | 15.12 | [8 empty] | 0
Schedule 17 | 15.15 | [8 empty] | 0
Schedule 17 | 16 | [8 empty] | 0
Schedule 17 | 16.1 | [8 empty] | 0
Schedule 17 | 16.2 | [8 empty] | 0
Schedule 17 | 16.3 | [8 empty] | 0
Schedule 17 | 16.4 | [8 empty] | 0
Schedule 17 | 16.5 | [8 empty] | 0
Schedule 17 | 16.6 | [8 empty] | 0
Schedule 17 | 16.7 | [8 empty] | 0
Schedule 17 | 16.8 | [8 empty] | 0
Schedule 17 | 16.9 | [8 empty] | 0
Schedule 17 | 16.1 | [8 empty] | 0
Schedule 17 | 17 | [8 empty] | 0
Schedule 17 | 17.1 | [8 empty] | 0
Schedule 17 | 17.2 | [8 empty] | 0
Schedule 17 | 17.3 | [8 empty] | 0
Schedule 17 | 18 | [8 empty] | 0
Schedule 17 | 18.1 | [8 empty] | 0
Schedule 17 | 18.2 | [8 empty] | 0
Schedule 17 | 18.3 | [8 empty] | 0
Schedule 17 | 18.4 | [8 empty] | 0
Schedule 17 | 18.5 | [8 empty] | 0
Schedule 17 | 18.6 | [8 empty] | 0
Schedule 17 | 18.7 | [8 empty] | 0
Schedule 17 | 18.8 | [8 empty] | 0
Schedule 17 | 18.9 | [8 empty] | 0
Schedule 17 | 18.1 | [8 empty] | 0
Schedule 17 | 18.11 | [8 empty] | 0
Schedule 17 | 18.12 | [8 empty] | 0
Schedule 17 | 18.13 | [8 empty] | 0
Schedule 17 | 18.14 | [8 empty] | 0
Schedule 17 | 18.15 | [8 empty] | 0
Schedule 17 | 18.16 | [8 empty] | 0
Schedule 17 | 18.17 | [8 empty] | 0
Schedule 17 | 18.18 | [8 empty] | 0
Schedule 17 | 18.19 | [8 empty] | 0
Schedule 17 | 18.2 | [8 empty] | 0
Schedule 17 | 18.21 | [8 empty] | 0
Schedule 17 | 19 | [8 empty] | 0
Schedule 17 | 19.1 | [8 empty] | 0
Schedule 17 | 19.2 | [8 empty] | 0
Schedule 17 | 19.3 | [8 empty] | 0
Schedule 17 | 19.4 | [8 empty] | 0
Schedule 17 | 19.5 | [8 empty] | 0
Schedule 17 | 19.6 | [8 empty] | 0
Schedule 17 | 19.7 | [8 empty] | 0
Schedule 17 | 19.8 | [8 empty] | 0
Schedule 17 | 19.9 | [8 empty] | 0
Schedule 17 | 19.1 | [8 empty] | 0
Schedule 17 | 19.11 | [8 empty] | 0
Schedule 17 | 20 | [8 empty] | 0
Schedule 17 | 20.1 | [8 empty] | 0
Schedule 17 | 20.2 | [8 empty] | 0
Schedule 17 | 20.3 | [8 empty] | 0
Schedule 17 | 20.4 | [8 empty] | 0
Schedule 17 | 20.5 | [8 empty] | 0
Schedule 17 | 20.6 | [8 empty] | 0
Schedule 17 | 20.7 | [8 empty] | 0
Schedule 17 | 20.8 | [8 empty] | 0
Schedule 17 | 20.9 | [8 empty] | 0
Schedule 17 | 21 | [8 empty] | 0
Schedule 17 | 21.1 | [8 empty] | 0
Schedule 17 | 21.2 | [8 empty] | 0
Schedule 17 | 22 | [8 empty] | 0
Schedule 17 | 22.1 | [8 empty] | 0
Schedule 17 | 22.2 | [8 empty] | 0
Schedule 17 | 22.3 | [8 empty] | 0
Schedule 17 | 22.4 | [8 empty] | 0
Schedule 17 | 23 | [8 empty] | 0
Schedule 17 | 23.1 | [8 empty] | 0
Schedule 17 | 23.2 | [8 empty] | 0
Schedule 17 | 23.3 | [8 empty] | 0
Schedule 17 | 23.4 | [8 empty] | 0
Schedule 17 | 23.5 | [8 empty] | 0
Schedule 17 | 24 | [8 empty] | 0
Schedule 17 | 24.1 | [8 empty] | 0
Schedule 17 | 24.2 | [8 empty] | 0
Schedule 17 | 24.3 | [8 empty] | 0
Schedule 17 | 24.4 | [8 empty] | 0
Schedule 17 | 24.5 | [8 empty] | 0
Schedule 17 | 24.6 | [8 empty] | 0
Schedule 17 | 24.7 | [8 empty] | 0
Schedule 17 | 24.8 | [8 empty] | 0
Schedule 17 | 24.9 | [8 empty] | 0
Schedule 17 | 25 | [8 empty] | 0
Schedule 17 | 25.1 | [8 empty] | 0
Schedule 17 | 25.2 | [8 empty] | 0
Schedule 17 | 25.3 | [8 empty] | 0
Schedule 17 | 25.4 | [8 empty] | 0
Schedule 17 | 25.5 | [8 empty] | 0
Schedule 17 | 25.6 | [8 empty] | 0
Schedule 17 | 25.7 | [8 empty] | 0
Schedule 17 | 25.8 | [8 empty] | 0
Schedule 17 | 25.9 | [8 empty] | 0
Schedule 17 | 25.1 | [8 empty] | 0
Schedule 17 | 25.11 | [8 empty] | 0
Schedule 17 | 25.12 | [8 empty] | 0
Schedule 17 | 25.13 | [8 empty] | 0
Schedule 17 | 25.14 | [8 empty] | 0
Schedule 17 | 25.15 | [8 empty] | 0
Schedule 17 | 25.16 | [8 empty] | 0
Schedule 17 | 25.17 | [8 empty] | 0
Schedule 17 | 25.18 | [8 empty] | 0
Schedule 17 | 25.19 | [8 empty] | 0
Schedule 17 | 26 | [8 empty] | 0
Schedule 17 | 26.1 | [8 empty] | 0
Schedule 17 | 26.2 | [8 empty] | 0
Schedule 17 | 26.3 | [8 empty] | 0
Schedule 17 | 26.4 | [8 empty] | 0
Schedule 17 | 26.5 | [8 empty] | 0
Schedule 17 | 26.6 | [8 empty] | 0
Schedule 17 | 26.7 | [8 empty] | 0
Schedule 17 | 26.8 | [8 empty] | 0
Schedule 17 | 26.9 | [8 empty] | 0
Schedule 17 | 26.1 | [8 empty] | 0
Schedule 17 | 26.11 | [8 empty] | 0
Schedule 17 | 27 | [8 empty] | 0
Schedule 17 | 27.1 | [8 empty] | 0
Schedule 17 | 27.2 | [8 empty] | 0
Schedule 17 | 27.3 | [8 empty] | 0
Schedule 17 | 27.4 | [8 empty] | 0
Schedule 17 | 28 | [8 empty] | 0
Schedule 17 | 28.1 | [8 empty] | 0
Schedule 17 | 28.2 | [8 empty] | 0
Schedule 17 | 29 | [8 empty] | 0
Schedule 17 | 29.1 | [8 empty] | 0
Schedule 17 | 29.2 | [8 empty] | 0
Schedule 17 | 29.3 | [8 empty] | 0
Schedule 17 | 29.4 | [8 empty] | 0
Schedule 17 | 30 | [8 empty] | 0
Schedule 17 | 30.1 | [8 empty] | 0
Schedule 17 | 30.2 | [8 empty] | 0
Schedule 17 | 30.3 | [8 empty] | 0
Schedule 17 | 30.4 | [8 empty] | 0
Schedule 17 | 30.5 | [8 empty] | 0
Schedule 17 | 30.6 | [8 empty] | 0
Schedule 17 | 30.7 | [8 empty] | 0
Schedule 17 | 30.8 | [8 empty] | 0
Schedule 17 | 30.9 | [8 empty] | 0
Schedule 17 | 30.1 | [8 empty] | 0
Schedule 17 | 30.11 | [8 empty] | 0
Schedule 17: Annex 1 | 1 | [8 empty] | 0
Schedule 17: Annex 1 | 2 | [8 empty] | 0
Schedule 17: Annex 1 | 2.1 | [8 empty] | 0
Schedule 17: Annex 1 | 2.2 | [8 empty] | 0
Schedule 17: Annex 1 | 2.3 | [8 empty] | 0
Schedule 17: Annex 1 | 2.4 | [8 empty] | 0
Schedule 17: Annex 1 | 2.5 | [8 empty] | 0
Schedule 17: Annex 1 | 3 | [8 empty] | 0
Schedule 17: Annex 1 | Definitions | [8 empty] | 0
Schedule 17: Annex 1 | 4 | [8 empty] | 0
Schedule 17: Annex 1 | 4.1 | [8 empty] | 0
Schedule 17: Annex 1 | 4.2 | [8 empty] | 0
Schedule 17: Annex 1 | 4.3 | [8 empty] | 0
Schedule 17: Annex 1 | 4.4 | [8 empty] | 0
Schedule 17: Annex 1 | 4.5 | [8 empty] | 0
Schedule 17: Annex 1 | 4.6 | [8 empty] | 0
Schedule 17: Annex 1 | 4.7 | [8 empty] | 0
Schedule 17: Annex 1 | 4.8 | [8 empty] | 0
Schedule 17: Annex 1 | 4.9 | [8 empty] | 0
Schedule 17: Annex 1 | 4.1 | [8 empty] | 0
Schedule 17: Annex 1 | 5 | [8 empty] | 0
Schedule 17: Annex 1 | 5.1 | [8 empty] | 0
Schedule 17: Annex 1 | 5.2 | [8 empty] | 0
Schedule 17: Annex 1 | 5.3 | [8 empty] | 0
Schedule 17: Annex 1 | 5.4 | [8 empty] | 0
Schedule 17: Annex 1 | 5.5 | [8 empty] | 0
Schedule 17: Annex 1 | 5.6 | [8 empty] | 0
Schedule 17: Annex 1 | 5.7 | [8 empty] | 0
Schedule 17: Annex 1 | 5.8 | [8 empty] | 0
Schedule 17: Annex 1 | 5.9 | [8 empty] | 0
Schedule 17: Annex 1 | 5.1 | [8 empty] | 0
Schedule 17: Annex 1 | 5.11 | [8 empty] | 0
Schedule 17: Annex 1 | 5.12 | [8 empty] | 0
Schedule 17: Annex 1 | 5.13 | [8 empty] | 0
Schedule 17: Annex 1 | 5.14 | [8 empty] | 0
Schedule 17: Annex 1 | 5.15 | [8 empty] | 0
Schedule 17: Annex 1 | 5.16 | [8 empty] | 0
Schedule 17: Annex 1 | 5.17 | [8 empty] | 0
Schedule 17: Annex 1 | 5.18 | [8 empty] | 0
Schedule 17: Annex 1 | 5.19 | [8 empty] | 0
Schedule 17: Annex 1 | 5.2 | [8 empty] | 0
Schedule 17: Annex 1 | 5.21 | [8 empty] | 0
Schedule 17: Annex 1 | 5.22 | [8 empty] | 0
Schedule 17: Annex 1 | 5.23 | [8 empty] | 0
Schedule 17: Annex 1 | 5.24 | [8 empty] | 0
Schedule 17: Annex 1 | 5.25 | [8 empty] | 0
Schedule 17: Annex 1 | 5.26 | [8 empty] | 0
Schedule 17: Annex 1 | 5.27 | [8 empty] | 0
Schedule 17: Annex 1 | 5.28 | [8 empty] | 0
Schedule 17: Annex 1 | 5.29 | [8 empty] | 0
Schedule 17: Annex 1 | 5.3 | [8 empty] | 0
Schedule 17: Annex 1 | 5.31 | [8 empty] | 0
Schedule 17: Annex 1 | 5.32 | [8 empty] | 0
Schedule 17: Annex 1 | 5.33 | [8 empty] | 0
Schedule 17: Annex 1 | 5.34 | [8 empty] | 0
Schedule 17: Annex 1 | 5.35 | [8 empty] | 0
Schedule 17: Annex 1 | 5.36 | [8 empty] | 0
Schedule 17: Annex 1 | 5.37 | [8 empty] | 0
Schedule 17: Annex 1 | 5.38 | [8 empty] | 0
Schedule 17: Annex 1 | 5.39 | [8 empty] | 0
Schedule 17: Annex 1 | 5.4 | [8 empty] | 0
Schedule 17: Annex 1 | 5.41 | [8 empty] | 0
Schedule 17: Annex 1 | 5.42 | [8 empty] | 0
Schedule 17: Annex 1 | 5.43 | [8 empty] | 0
Schedule 17: Annex 1 | 5.44 | [8 empty] | 0
Schedule 17: Annex 1 | 5.45 | [8 empty] | 0
Schedule 17: Annex 1 | 6 | [8 empty] | 0
Schedule 17: Annex 1 | 6.1 | [8 empty] | 0
Schedule 17: Annex 1 | 6.2 | [8 empty] | 0
Schedule 17: Annex 1 | 6.3 | [8 empty] | 0
Schedule 17: Annex 1 | 6.4 | [8 empty] | 0
Schedule 17: Annex 1 | 6.5 | [8 empty] | 0
Schedule 17: Annex 1 | 6.6 | [8 empty] | 0
Schedule 17: Annex 1 | 6.7 | [8 empty] | 0
Schedule 17: Annex 1 | 6.8 | [8 empty] | 0
Schedule 17: Annex 1 | 7 | [8 empty] | 0
Schedule 17: Annex 1 | 7.1 | [8 empty] | 0
Schedule 17: Annex 1 | 7.2 | [8 empty] | 0
Schedule 17: Annex 1 | 7.3 | [8 empty] | 0
Schedule 17: Annex 1 | 7.4 | [8 empty] | 0
Schedule 17: Annex 1 | 7.5 | [8 empty] | 0
Schedule 17: Annex 1 | 7.6 | [8 empty] | 0
Schedule 17: Annex 1 | 7.7 | [8 empty] | 0
Schedule 17: Annex 1 | 7.8 | [8 empty] | 0
Schedule 17: Annex 1 | 8 | [8 empty] | 0
Schedule 17: Annex 1 | 8.1 | [8 empty] | 0
Schedule 17: Annex 1 | 8.2 | [8 empty] | 0
Schedule 17: Annex 1 | 8.3 | [8 empty] | 0
Schedule 17: Annex 1 | 8.4 | [8 empty] | 0
Schedule 17: Annex 1 | 9 | [8 empty] | 0
Schedule 17: Annex 1 | 9.1 | [8 empty] | 0
Schedule 17: Annex 1 | 9.2 | [8 empty] | 0
Schedule 17: Annex 1 | 9.3 | [8 empty] | 0
Schedule 17: Annex 1 | 9.4 | [8 empty] | 0
Schedule 17: Annex 1 | 9.5 | [8 empty] | 0
Schedule 17: Annex 1 | 9.6 | [8 empty] | 0
Schedule 17: Annex 1 | 9.7 | [8 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [8 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [8 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [8 empty] | 0
Schedule 17: Annex 1 | Attachment 3 | [8 empty] | 0
Schedule 17: Annex 2 | Annex 2 | [8 empty] | 0
0
Schedule 18 | Introduction | [8 empty] | 0
Schedule 18 | 1 | [8 empty] | 0
Schedule 18 | 1.1 | [8 empty] | 0
Schedule 18 | 1.2 | [8 empty] | 0
Schedule 18 | 1.3 | [8 empty] | 0 | Model reference number and date
Schedule 18 | 1.3A | [8 empty] | 0
Schedule 18 | 1.4 | [8 empty] | 0
Schedule 18 | 1.5 | [8 empty] | 0
Schedule 18 | 1.6 | [8 empty] | 0
Schedule 18 | 1.7 | [8 empty] | 0
Schedule 18 | 1.8 | [8 empty] | 0
Schedule 18 | 1.9 | [8 empty] | 0
Schedule 18 | 2 | [8 empty] | 0
Schedule 18 | 2.1 | [8 empty] | 0
Schedule 18 | 2.2 | [8 empty] | 0
Schedule 18 | 2.3 | [8 empty] | 0
Schedule 18 | 2.4 | [8 empty] | 0
Schedule 18 | 2.5 | [8 empty] | 0
Schedule 18 | 2.6 | [8 empty] | 0
Schedule 18 | 2.7 | [8 empty] | 0
Schedule 18 | 2.8 | [8 empty] | 0
Schedule 18 | 2.9 | [8 empty] | 0
Schedule 18 | 2.1 | [8 empty] | 0
Schedule 18 | 2.11 | [8 empty] | 0
Schedule 18 | 2.12 | [8 empty] | 0
Schedule 18 | 2.13 | [8 empty] | 0
Schedule 18 | 2.14 | [8 empty] | 0
Schedule 18 | 2.15 | [8 empty] | 0
Schedule 18 | 2.16 | [8 empty] | 0
Schedule 18 | 2.17 | [8 empty] | 0
Schedule 18 | 2.18 | [8 empty] | 0
Schedule 18 | 2.19 | [8 empty] | 0
Schedule 18 | 2.2 | [8 empty] | 0
Schedule 18 | 2.21 | [8 empty] | 0
Schedule 18 | 2.22 | [8 empty] | 0
Schedule 18 | 2.23 | [8 empty] | 0
Schedule 18 | 2.24 | [8 empty] | 0
Schedule 18 | 2.25 | [8 empty] | 0
Schedule 18 | 2.26 | [8 empty] | 0
Schedule 18 | 2.27 | [8 empty] | 0
Schedule 18 | 2.28 | [8 empty] | 0
Schedule 18 | 2.29 | [8 empty] | 0
Schedule 18 | 2.3 | [8 empty] | 0
Schedule 18 | 3 | [8 empty] | 0
Schedule 18 | 3.1 | [8 empty] | 0
Schedule 18 | 3.2 | [8 empty] | 0
Schedule 18 | 3.3 | [8 empty] | 0
Schedule 18 | 3.4 | [8 empty] | 0
Schedule 18 | 3.5 | [8 empty] | 0
Schedule 18 | 3.6 | [8 empty] | 0
Schedule 18 | 3.7 | [8 empty] | 0
Schedule 18 | 4 | [8 empty] | 0
Schedule 18 | 4.1 | [8 empty] | 0
Schedule 18 | 5 | [8 empty] | 0
Schedule 18 | 5.1 | [8 empty] | 0
Schedule 18 | 6 | [8 empty] | 0
Schedule 18 | 6.1 | [8 empty] | 0
Schedule 18 | 6.2 | [8 empty] | 0
Schedule 18 | 6.3 | [8 empty] | 0
Schedule 18 | 6.4 | [8 empty] | 0
Schedule 18 | 6.5 | [8 empty] | 0
Schedule 18 | 7 | [8 empty] | 0
Schedule 18 | 7.1 | [8 empty] | 0
Schedule 18 | 8 | [8 empty] | 0
Schedule 18 | 8.1 | [8 empty] | 0
Schedule 18 | 8.2 | [8 empty] | 0
Schedule 18 | 8.3 | [8 empty] | 0
Schedule 18 | 8.4 | [8 empty] | 0
Schedule 18 | 9 | [8 empty] | 0
Schedule 18 | 9.1 | [8 empty] | 0
Schedule 18 | 9.2 | [8 empty] | 0
Schedule 18 | 10 | [8 empty] | 0
Schedule 18 | 10.1 | [8 empty] | 0
Schedule 18 | 10.2 | [8 empty] | 0
Schedule 18 | 10.3 | [8 empty] | 0
Schedule 18 | 10.4 | [8 empty] | 0
Schedule 18 | 10.5 | [8 empty] | 0
Schedule 18 | 11 | [8 empty] | 0
Schedule 18 | 11.1 | [8 empty] | 0
Schedule 18 | 12 | [8 empty] | 0
Schedule 18 | 12.1 | [8 empty] | 0
Schedule 18 | 12.2 | [8 empty] | 0
Schedule 18 | 12.3 | [8 empty] | 0
Schedule 18 | 12.4 | [8 empty] | 0
Schedule 18 | 12.5 | [8 empty] | 0
Schedule 18 | 12.6 | [8 empty] | 0
Schedule 18 | 13 | [8 empty] | 0
Schedule 18 | 13.1 | [8 empty] | 0
Schedule 18 | 13.2 | [8 empty] | 0
Schedule 18 | 13.3 | [8 empty] | 0
Schedule 18 | 13.4 | [8 empty] | 0
Schedule 18 | 14 | [8 empty] | 0
Schedule 18 | 14.1 | [8 empty] | 0
Schedule 18 | 14.2 | [8 empty] | 0
Schedule 18 | 14.3 | [8 empty] | 0
Schedule 18 | 14.4 | [8 empty] | 0
Schedule 18 | 14.5 | [8 empty] | 0
Schedule 18 | 15 | [8 empty] | 0
Schedule 18 | 15.1 | [8 empty] | 0
Schedule 18 | 15.2 | [8 empty] | 0
Schedule 18 | 15.3 | [8 empty] | 0
Schedule 18 | 15.4 | [8 empty] | 0
Schedule 18 | 15.5 | [8 empty] | 0
Schedule 18 | 15.6 | [8 empty] | 0
Schedule 18 | 15.7 | [8 empty] | 0
Schedule 18 | 15.8 | [8 empty] | 0
Schedule 18 | 15.9 | [8 empty] | 0
Schedule 18 | 15.1 | [8 empty] | 0
Schedule 18 | 15.11 | [8 empty] | 0
Schedule 18 | 15.12 | [8 empty] | 0
Schedule 18 | 15.15 | [8 empty] | 0
Schedule 18 | 16 | [8 empty] | 0
Schedule 18 | 16.1 | [8 empty] | 0
Schedule 18 | 16.2 | [8 empty] | 0
Schedule 18 | 16.3 | [8 empty] | 0
Schedule 18 | 16.4 | [8 empty] | 0
Schedule 18 | 16.5 | [8 empty] | 0
Schedule 18 | 16.6 | [8 empty] | 0
Schedule 18 | 16.7 | [8 empty] | 0
Schedule 18 | 16.8 | [8 empty] | 0
Schedule 18 | 16.9 | [8 empty] | 0
Schedule 18 | 16.1 | [8 empty] | 0
Schedule 18 | 17 | [8 empty] | 0
Schedule 18 | 17.1 | [8 empty] | 0
Schedule 18 | 17.2 | [8 empty] | 0
Schedule 18 | 17.3 | [8 empty] | 0
Schedule 18 | 18 | [8 empty] | 0
Schedule 18 | 18.1 | [8 empty] | 0
Schedule 18 | 18.2 | [8 empty] | 0
Schedule 18 | 18.3 | [8 empty] | 0
Schedule 18 | 18.4 | [8 empty] | 0
Schedule 18 | 18.5 | [8 empty] | 0
Schedule 18 | 18.6 | [8 empty] | 0
Schedule 18 | 18.7 | [8 empty] | 0
Schedule 18 | 18.8 | [8 empty] | 0
Schedule 18 | 18.9 | [8 empty] | 0
Schedule 18 | 18.1 | [8 empty] | 0
Schedule 18 | 18.11 | [8 empty] | 0
Schedule 18 | 18.12 | [8 empty] | 0
Schedule 18 | 18.13 | [8 empty] | 0
Schedule 18 | 18.14 | [8 empty] | 0
Schedule 18 | 18.15 | [8 empty] | 0
Schedule 18 | 18.16 | [8 empty] | 0
Schedule 18 | 18.17 | [8 empty] | 0
Schedule 18 | 18.18 | [8 empty] | 0
Schedule 18 | 18.19 | [8 empty] | 0
Schedule 18 | 18.2 | [8 empty] | 0
Schedule 18 | 18.21 | [8 empty] | 0
Schedule 18 | 19 | [8 empty] | 0
Schedule 18 | 19.1 | [8 empty] | 0
Schedule 18 | 19.2 | [8 empty] | 0
Schedule 18 | 19.3 | [8 empty] | 0
Schedule 18 | 19.4 | [8 empty] | 0
Schedule 18 | 19.5 | [8 empty] | 0
Schedule 18 | 19.6 | [8 empty] | 0
Schedule 18 | 19.7 | [8 empty] | 0
Schedule 18 | 19.8 | [8 empty] | 0
Schedule 18 | 19.9 | [8 empty] | 0
Schedule 18 | 19.1 | [8 empty] | 0
Schedule 18 | 19.11 | [8 empty] | 0
Schedule 18 | 20 | [8 empty] | 0
Schedule 18 | 20.1 | [8 empty] | 0
Schedule 18 | 20.2 | [8 empty] | 0
Schedule 18 | 20.3 | [8 empty] | 0
Schedule 18 | 20.4 | [8 empty] | 0
Schedule 18 | 20.5 | [8 empty] | 0
Schedule 18 | 20.6 | [8 empty] | 0
Schedule 18 | 20.7 | [8 empty] | 0
Schedule 18 | 20.8 | [8 empty] | 0
Schedule 18 | 20.9 | [8 empty] | 0
Schedule 18 | 21 | [8 empty] | 0
Schedule 18 | 21.1 | [8 empty] | 0
Schedule 18 | 21.2 | [8 empty] | 0
Schedule 18 | 22 | [8 empty] | 0
Schedule 18 | 22.1 | [8 empty] | 0
Schedule 18 | 22.2 | [8 empty] | 0
Schedule 18 | 22.3 | [8 empty] | 0
Schedule 18 | 22.4 | [8 empty] | 0
Schedule 18 | 23 | [8 empty] | 0
Schedule 18 | 23.1 | [8 empty] | 0
Schedule 18 | 23.2 | [8 empty] | 0
Schedule 18 | 23.3 | [8 empty] | 0
Schedule 18 | 23.4 | [8 empty] | 0
Schedule 18 | 23.5 | [8 empty] | 0
Schedule 18 | 24 | [8 empty] | 0
Schedule 18 | 24.1 | [8 empty] | 0
Schedule 18 | 24.2 | [8 empty] | 0
Schedule 18 | 24.3 | [8 empty] | 0
Schedule 18 | 24.4 | [8 empty] | 0
Schedule 18 | 24.5 | [8 empty] | 0
Schedule 18 | 24.6 | [8 empty] | 0
Schedule 18 | 24.7 | [8 empty] | 0
Schedule 18 | 24.8 | [8 empty] | 0
Schedule 18 | 24.9 | [8 empty] | 0
Schedule 18 | 25 | [8 empty] | 0
Schedule 18 | 25.1 | [8 empty] | 0
Schedule 18 | 25.2 | [8 empty] | 0
Schedule 18 | 25.3 | [8 empty] | 0
Schedule 18 | 25.4 | [8 empty] | 0
Schedule 18 | 25.5 | [8 empty] | 0
Schedule 18 | 25.6 | [8 empty] | 0
Schedule 18 | 25.7 | [8 empty] | 0
Schedule 18 | 25.8 | [8 empty] | 0
Schedule 18 | 25.9 | [8 empty] | 0
Schedule 18 | 25.1 | [8 empty] | 0
Schedule 18 | 25.11 | [8 empty] | 0
Schedule 18 | 25.12 | [8 empty] | 0
Schedule 18 | 25.13 | [8 empty] | 0
Schedule 18 | 25.14 | [8 empty] | 0
Schedule 18 | 25.15 | [8 empty] | 0
Schedule 18 | 25.16 | [8 empty] | 0
Schedule 18 | 25.17 | [8 empty] | 0
Schedule 18 | 25.18 | [8 empty] | 0
Schedule 18 | 25.19 | [8 empty] | 0
Schedule 18 | 26 | [8 empty] | 0
Schedule 18 | 26.1 | [8 empty] | 0
Schedule 18 | 26.2 | [8 empty] | 0
Schedule 18 | 26.3 | [8 empty] | 0
Schedule 18 | 26.4 | [8 empty] | 0
Schedule 18 | 26.5 | [8 empty] | 0
Schedule 18 | 26.6 | [8 empty] | 0
Schedule 18 | 26.7 | [8 empty] | 0
Schedule 18 | 26.8 | [8 empty] | 0
Schedule 18 | 26.9 | [8 empty] | 0
Schedule 18 | 26.1 | [8 empty] | 0
Schedule 18 | 26.11 | [8 empty] | 0
Schedule 18 | 27 | [8 empty] | 0
Schedule 18 | 27.1 | [8 empty] | 0
Schedule 18 | 27.2 | [8 empty] | 0
Schedule 18 | 27.3 | [8 empty] | 0
Schedule 18 | 27.4 | [8 empty] | 0
Schedule 18 | 28 | [8 empty] | 0
Schedule 18 | 28.1 | [8 empty] | 0
Schedule 18 | 28.2 | [8 empty] | 0
Schedule 18 | 29 | [8 empty] | 0
Schedule 18 | 29.1 | [8 empty] | 0
Schedule 18 | 29.2 | [8 empty] | 0
Schedule 18 | 29.3 | [8 empty] | 0
Schedule 18 | 29.4 | [8 empty] | 0
Schedule 18 | 30 | [8 empty] | 0
Schedule 18 | 30.1 | [8 empty] | 0
Schedule 18 | 30.2 | [8 empty] | 0
Schedule 18 | 30.3 | [8 empty] | 0
Schedule 18 | 30.4 | [8 empty] | 0
Schedule 18 | 30.5 | [8 empty] | 0
Schedule 18 | 30.6 | [8 empty] | 0
Schedule 18 | 30.7 | [8 empty] | 0
Schedule 18 | 30.8 | [8 empty] | 0
Schedule 18 | 30.9 | [8 empty] | 0
Schedule 18 | 30.1 | [8 empty] | 0
Schedule 18 | 30.11 | [8 empty] | 0
Schedule 18: Annex 1 | 1 | [8 empty] | 0
Schedule 18: Annex 1 | 1.1 | [8 empty] | 0
Schedule 18: Annex 1 | 2 | [8 empty] | 0
Schedule 18: Annex 1 | 2.1 | [8 empty] | 0
Schedule 18: Annex 1 | 2.2 | [8 empty] | 0
Schedule 18: Annex 1 | 2.3 | [8 empty] | 0
Schedule 18: Annex 1 | 2.4 | [8 empty] | 0
Schedule 18: Annex 1 | 2.5 | [8 empty] | 0
Schedule 18: Annex 1 | 3 | [8 empty] | 0
Schedule 18: Annex 1 | Definitions | [8 empty] | 0
Schedule 18: Annex 1 | 4 | [8 empty] | 0
Schedule 18: Annex 1 | 4.1 | [8 empty] | 0
Schedule 18: Annex 1 | 4.2 | [8 empty] | 0
Schedule 18: Annex 1 | 4.3 | [8 empty] | 0
Schedule 18: Annex 1 | 4.4 | [8 empty] | 0
Schedule 18: Annex 1 | 4.5 | [8 empty] | 0
Schedule 18: Annex 1 | 4.6 | [8 empty] | 0
Schedule 18: Annex 1 | 4.7 | [8 empty] | 0
Schedule 18: Annex 1 | 4.8 | [8 empty] | 0
Schedule 18: Annex 1 | 4.9 | [8 empty] | 0
Schedule 18: Annex 1 | 5 | [8 empty] | 0
Schedule 18: Annex 1 | 5.1 | [8 empty] | 0
Schedule 18: Annex 1 | 5.2 | [8 empty] | 0
Schedule 18: Annex 1 | 5.3 | [8 empty] | 0
Schedule 18: Annex 1 | 5.4 | [8 empty] | 0
Schedule 18: Annex 1 | 5.5 | [8 empty] | 0
Schedule 18: Annex 1 | 5.6 | [8 empty] | 0
Schedule 18: Annex 1 | 5.7 | [8 empty] | 0
Schedule 18: Annex 1 | 5.8 | [8 empty] | 0
Schedule 18: Annex 1 | 5.9 | [8 empty] | 0
Schedule 18: Annex 1 | 5.1 | [8 empty] | 0
Schedule 18: Annex 1 | 5.11 | [8 empty] | 0
Schedule 18: Annex 1 | 5.12 | [8 empty] | 0
Schedule 18: Annex 1 | 5.13 | [8 empty] | 0
Schedule 18: Annex 1 | 5.14 | [8 empty] | 0
Schedule 18: Annex 1 | 5.15 | [8 empty] | 0
Schedule 18: Annex 1 | 5.16 | [8 empty] | 0
Schedule 18: Annex 1 | 5.17 | [8 empty] | 0
Schedule 18: Annex 1 | 5.18 | [8 empty] | 0
Schedule 18: Annex 1 | 5.19 | [8 empty] | 0
Schedule 18: Annex 1 | 5.2 | [8 empty] | 0
Schedule 18: Annex 1 | 5.21 | [8 empty] | 0
Schedule 18: Annex 1 | 5.22 | [8 empty] | 0
Schedule 18: Annex 1 | 5.23 | [8 empty] | 0
Schedule 18: Annex 1 | 5.24 | [8 empty] | 0
Schedule 18: Annex 1 | 5.25 | [8 empty] | 0
Schedule 18: Annex 1 | 5.26 | [8 empty] | 0
Schedule 18: Annex 1 | 5.27 | [8 empty] | 0
Schedule 18: Annex 1 | 5.28 | [8 empty] | 0
Schedule 18: Annex 1 | 5.29 | [8 empty] | 0
Schedule 18: Annex 1 | 5.3 | [8 empty] | 0
Schedule 18: Annex 1 | 5.31 | [8 empty] | 0
Schedule 18: Annex 1 | 5.32 | [8 empty] | 0
Schedule 18: Annex 1 | 5.33 | [8 empty] | 0
Schedule 18: Annex 1 | 5.34 | [8 empty] | 0
Schedule 18: Annex 1 | 5.35 | [8 empty] | 0
Schedule 18: Annex 1 | 5.36 | [8 empty] | 0
Schedule 18: Annex 1 | 5.37 | [8 empty] | 0
Schedule 18: Annex 1 | 5.38 | [8 empty] | 0
Schedule 18: Annex 1 | 5.39 | [8 empty] | 0
Schedule 18: Annex 1 | 5.4 | [8 empty] | 0
Schedule 18: Annex 1 | 5.41 | [8 empty] | 0
Schedule 18: Annex 1 | 5.42 | [8 empty] | 0
Schedule 18: Annex 1 | 6 | [8 empty] | 0
Schedule 18: Annex 1 | 6.1 | [8 empty] | 0
Schedule 18: Annex 1 | 6.2 | [8 empty] | 0
Schedule 18: Annex 1 | 6.3 | [8 empty] | 0
Schedule 18: Annex 1 | 6.4 | [8 empty] | 0
Schedule 18: Annex 1 | 6.5 | [8 empty] | 0
Schedule 18: Annex 1 | 6.6 | [8 empty] | 0
Schedule 18: Annex 1 | 6.7 | [8 empty] | 0
Schedule 18: Annex 1 | 6.8 | [8 empty] | 0
Schedule 18: Annex 1 | 6.9 | [8 empty] | 0
Schedule 18: Annex 1 | 6.1 | [8 empty] | 0
Schedule 18: Annex 1 | 6.11 | [8 empty] | 0
Schedule 18: Annex 1 | 6.12 | [8 empty] | 0
Schedule 18: Annex 1 | 6.13 | [8 empty] | 0
Schedule 18: Annex 1 | 6.14 | [8 empty] | 0
Schedule 18: Annex 1 | 6.15 | [8 empty] | 0
Schedule 18: Annex 1 | 6.16 | [8 empty] | 0
Schedule 18: Annex 1 | 6.17 | [8 empty] | 0
Schedule 18: Annex 1 | 6.18 | [8 empty] | 0
Schedule 18: Annex 1 | 6.19 | [8 empty] | 0
Schedule 18: Annex 1 | 6.2 | [8 empty] | 0
Schedule 18: Annex 1 | 6.21 | [8 empty] | 0
Schedule 18: Annex 1 | 6.22 | [8 empty] | 0
Schedule 18: Annex 1 | 6.23 | [8 empty] | 0
Schedule 18: Annex 1 | 6.24 | [8 empty] | 0
Schedule 18: Annex 1 | 6.25 | [8 empty] | 0
Schedule 18: Annex 1 | 6.26 | [8 empty] | 0
Schedule 18: Annex 1 | 6.27 | [8 empty] | 0
Schedule 18: Annex 1 | 6.28 | [8 empty] | 0
Schedule 18: Annex 1 | 6.29 | [8 empty] | 0
Schedule 18: Annex 1 | 6.3 | [8 empty] | 0
Schedule 18: Annex 1 | 6.31 | [8 empty] | 0
Schedule 18: Annex 1 | 6.32 | [8 empty] | 0
Schedule 18: Annex 1 | 6.33 | [8 empty] | 0
Schedule 18: Annex 1 | 6.34 | [8 empty] | 0
Schedule 18: Annex 1 | 7 | [8 empty] | 0
Schedule 18: Annex 1 | 7.1 | [8 empty] | 0
Schedule 18: Annex 1 | 7.2 | [8 empty] | 0
Schedule 18: Annex 1 | 7.3 | [8 empty] | 0
Schedule 18: Annex 1 | 7.4 | [8 empty] | 0
Schedule 18: Annex 1 | 7.5 | [8 empty] | 0
Schedule 18: Annex 1 | 8 | [8 empty] | 0
Schedule 18: Annex 1 | 8.1 | [8 empty] | 0
Schedule 18: Annex 1 | 8.2 | [8 empty] | 0
Schedule 18: Annex 1 | 8.3 | [8 empty] | 0
Schedule 18: Annex 1 | 8.4 | [8 empty] | 0
Schedule 18: Annex 1 | 8.5 | [8 empty] | 0
Schedule 18: Annex 1 | 8.6 | [8 empty] | 0
Schedule 18: Annex 1 | 8.7 | [8 empty] | 0
Schedule 18: Annex 1 | 8.8 | [8 empty] | 0
Schedule 18: Annex 1 | 8.9 | [8 empty] | 0
Schedule 18: Annex 1 | 8.1 | [8 empty] | 0
Schedule 18: Annex 1 | 8.11 | [8 empty] | 0
Schedule 18: Annex 1 | 8.12 | [8 empty] | 0
Schedule 18: Annex 1 | 8.13 | [8 empty] | 0
Schedule 18: Annex 1 | 8.14 | [8 empty] | 0
Schedule 18: Annex 1 | 8.15 | [8 empty] | 0
Schedule 18: Annex 1 | 8.16 | [8 empty] | 0
Schedule 18: Annex 1 | 8.17 | [8 empty] | 0
Schedule 18: Annex 1 | 8.18 | [8 empty] | 0
Schedule 18: Annex 1 | 8.19 | [8 empty] | 0
Schedule 18: Annex 1 | 8.2 | [8 empty] | 0
Schedule 18: Annex 1 | 8.21 | [8 empty] | 0
Schedule 18: Annex 1 | Attachment 1 | [8 empty] | 0
Schedule 18: Annex 1 | Attachment 2 | [8 empty] | 0
Schedule 18: Annex 1 | Attachment 3 | [8 empty] | 0
Schedule 18: Annex 2 | Annex 2 | [8 empty] | 0
0
Schedule 20 | Introduction |  |  | YES | [5 empty] | 1
Schedule 20 | 1.1 |  |  | YES | [5 empty] | 1
Schedule 20 | 2.1 |  |  | YES | [5 empty] | 1
Schedule 20 | 3.1 |  |  | YES | [5 empty] | 1
Schedule 20 | 3.2 |  |  | YES | [5 empty] | 1
0
Schedule 29 | Introduction | [8 empty] | 0
Schedule 29 | 1 | [8 empty] | 0
Schedule 29 | 1A | [8 empty] | 0
Schedule 29 | 2 | [8 empty] | 0
Schedule 29 | 3 | [8 empty] | 0
Schedule 29 | 4 | [8 empty] | 0
Schedule 29 | 5 | [8 empty] | 0
Schedule 29 | 6 | [8 empty] | 0
Schedule 29 | 7 | [8 empty] | 0
Schedule 29 | 8 | [8 empty] | 0
Schedule 29 | 9 | [8 empty] | 0
Schedule 29 | 10 | [8 empty] | 0
Schedule 29 | 11 | [8 empty] | 0
Schedule 29 | 11A | [8 empty] | 0
Schedule 29 | 12 | [8 empty] | 0
Schedule 29 | 13 | [8 empty] | 0
Schedule 29 | 14 | [8 empty] | 0
Schedule 29 | 15 | [8 empty] | 0
Schedule 29 | 16 | [8 empty] | 0
Schedule 29 | 17 | [8 empty] | 0
Schedule 29 | 18 | [8 empty] | 0
Schedule 29 | 19 | [8 empty] | 0
Schedule 29 | 20 | [8 empty] | 0
Schedule 29 | 21 | [8 empty] | 0
Schedule 29 | 22 | [8 empty] | 0
Schedule 29 | 23 | [8 empty] | 0
Schedule 29 | 24 | [8 empty] | 0
Schedule 29 | 25 | [8 empty] | 0
Schedule 29 | 26 | [8 empty] | 0
Schedule 29 | 27 | [8 empty] | 0
Schedule 29 | 28 | [8 empty] | 0
Schedule 29 | 29 | [8 empty] | 0
Schedule 29 | 30 | [8 empty] | 0
Schedule 29 | 31 | [8 empty] | 0
Schedule 29 | 32 | [8 empty] | 0
Schedule 29 | 33 | [8 empty] | 0
Schedule 29 | 34 | [8 empty] | 0
Schedule 29 | 35 | [8 empty] | 0
Schedule 29 | 36 | [8 empty] | 0
Schedule 29 | 37 | [8 empty] | 0
Schedule 29 | 38 | [8 empty] | 0
Schedule 29 | 39 | [8 empty] | 0
Schedule 29 | 40 | [8 empty] | 0
Schedule 29 | 41 | [8 empty] | 0
Schedule 29 | 42 | [8 empty] | 0
Schedule 29 | 43 | [8 empty] | 0
Schedule 29 | 44 | [8 empty] | 0
Schedule 29 | 45 | [8 empty] | 0
Schedule 29 | 46 | [8 empty] | 0
Schedule 29 | 46A | [8 empty] | 0
Schedule 29 | 47 | [8 empty] | 0
0
Schedule 32 | 1 | [8 empty] | 0
Schedule 32 | 1.1 | [8 empty] | 0
Schedule 32 | 1.2 | [8 empty] | 0
Schedule 32 | 1.2A | [8 empty] | 0
Schedule 32 | 1.3 | [8 empty] | 0
Schedule 32 | 1.4 | [8 empty] | 0
Schedule 32 | 1.5 | [8 empty] | 0
Schedule 32 | 1.6 | [8 empty] | 0
Schedule 32 | 1.7 | [8 empty] | 0
Schedule 32 | 1.8 | [5 empty] | YES |  |  | 1
Schedule 32 | 1.9 | [8 empty] | 0
Schedule 32 | 1.10 | [5 empty] | YES |  |  | 1
Schedule 32 | 2 | [8 empty] | 0
Schedule 32 | 2.1 | [8 empty] | 0
Schedule 32 | 2.2 | [8 empty] | 0
Schedule 32 | 2.3 | [8 empty] | 0
Schedule 32 | 2.4 | [8 empty] | 0
Schedule 32 | 2.5 | [8 empty] | 0
Schedule 32 | 3 | [8 empty] | 0
Schedule 32 | 3.1 | [5 empty] | YES |  |  | 1
Schedule 32 | 3.2 | [8 empty] | 0
Schedule 32 | 3.3 | [8 empty] | 0
Schedule 32 | 3.4 | [8 empty] | 0
Schedule 32 | 3.5 | [8 empty] | 0
Schedule 32 | 3.6 | [8 empty] | 0
Schedule 32 | 4 | [8 empty] | 0
Schedule 32 | 4.1 | [5 empty] | YES |  |  | 1
Schedule 32 | 4.2 | [5 empty] | YES |  |  | 1
Schedule 32 | 4.2A | [5 empty] | YES |  |  | 1
Schedule 32 | 4.3 | [8 empty] | 0
Schedule 32 | 4.4 | [8 empty] | 0
Schedule 32 | 4.5 | [5 empty] | YES |  |  | 1
Schedule 32 | 4.6 | [8 empty] | 0
Schedule 32 | 5 | [8 empty] | 0
Schedule 32 | 5.1 | [8 empty] | 0
Schedule 32 | 5.2 | [8 empty] | 0
Schedule 32 | 5.3 | [8 empty] | 0
Schedule 32 | 5A. | [5 empty] | YES |  |  | 1
Schedule 32 | 5A.1 | [8 empty] | 0
Schedule 32 | 5A.1A | [8 empty] | 0
Schedule 32 | 5A.2 | [8 empty] | 0
Schedule 32 | 6 | [8 empty] | 0
Schedule 32 | 6.1 | [6 empty] | YES |  | 1
Schedule 32 | 6.2 | [6 empty] | YES |  | 1
Schedule 32 | 6.3 | [5 empty] | YES |  |  | 1
Schedule 32 | 6.4 | [8 empty] | 0
Schedule 32 | 6.4A | [8 empty] | 0
Schedule 32 | 6.5 | [5 empty] | YES |  |  | 1
Schedule 32 | 6.6 | [8 empty] | 0
Schedule 32 | 6.7 | [8 empty] | 0
Schedule 32 | 6.8 | [8 empty] | 0
Schedule 32 | 6.9 | [8 empty] | 0
Schedule 32 | 6.10 | [8 empty] | 0
Schedule 32 | 6.11 | [8 empty] | 0
Schedule 32 | 7 | [8 empty] | 0
Schedule 32 | 7.1 | [8 empty] | 0
Schedule 32 | 7.2 | [8 empty] | 0
Schedule 32 | 7.3 | [8 empty] | 0
Schedule 32 | 7.4 | [8 empty] | 0
Schedule 32 | 7.5 | [8 empty] | 0
Schedule 32 | 7.6 | [8 empty] | 0
Schedule 32 | 7.7 | [8 empty] | 0
Schedule 32 | 7.8 | [8 empty] | 0
Schedule 32 | 7.9 | [8 empty] | 0
Schedule 32 | 7.1 | [8 empty] | 0
Schedule 32 | 7.11 | [8 empty] | 0
Schedule 32 | 7.12 | [8 empty] | 0
Schedule 32 | 7.13 | [8 empty] | 0
Schedule 32 | 7.14 | [8 empty] | 0
Schedule 32 | 7.15 | [8 empty] | 0
Schedule 32 | 7.16 | [8 empty] | 0
Schedule 32 | 7.17 | [8 empty] | 0
Schedule 32 | 8 | [8 empty] | 0
Schedule 32 | 8.1 | [8 empty] | 0
Schedule 31 | 8.2 | [8 empty] | 0
Schedule 32 | Definitions | [5 empty] | YES | YES |  | 2
Charging Methodology CPs Legal Text Overlap Tracker