## Open
Grade | Party Group (DNO/Supplier/Meter Operator) | Company | Company Representative | High Level Concern Category Examples - SLA/Misreports/MOCOPA | Describe briefly the issue you are highlighting | Describe briefly what you would do to resolve this issue? | Who would benefit? | Forum | Update
G2 | Supplier | British Gas | Kevin Woollard | SLA / Misreports | Performance of DNOs in meeting DCUSA SLAs | Increased resources required by DNOs to meet DCUSA SLAs | Customers and Smart programme | MOCoPA | To check the progress of this.
G2 | DNO | UKPN | Paul Morris | Customer Service | Improving the customer journey | Providing improved data to improve first time installs - pic's of issue great . | All | Workshop | Data Workshop
G1 | DNO | SP Energy Networks | John Gray | Customer Service | Difficulty to make contact with customers for Cat A and B resolution. | Ensure that all MOPS capture the customers mobile phone number | Everybody | MOCoPA | Data Workshop
G1 | DNO | UKPN | Paul Morris | Customer Service | Contact details often not provided or incorrect | Ensure that all MOPS capture the customers mobile phone number | Customer / DNO | MOCoPA | Data Workshop
G1 | DNO | Scottish Power | John Heague | Safety | DNO making Earth changes to services, e.g. SNE service changed to CNE/PME | Whether this is acceptable practice and how should it be reported back to DNOs if necessary. | Customer/ DNO | DCUSA IWG | This issue is currently with MOCOPA to review proposed changes to B07 code.
G1 | Supplier | EDF | Simon Wilson | Safety | Faraday Cages being used to cover Smart Meters. | Conserns that this is blocking the signal to the DCC and potential safety concerns | Everybody | DCUSA IWG | This issue has been raised at the AMO Electricity forum and they are currently reviewing whether there have been any other cases.
G1 | Supplier | Scottish Power | John Heague | Safety | Neutral Current Diversion | In certain scenarios the neutral return current could be returning via the earth conductor and it is not common practice for Meter Operators or DNOs to check for this on standard work. This poses a risk to the employees and the customers. | Everybody | TBC | To raise this issue at the next EMF and members are requested to review this issue and consider next steps.

## Closed
Grade | Party Group (DNO/Supplier/Meter Operator) | Company | Company Representative | High Level Concern Category Examples - SLA/Misreports/MOCOPA | Work Stream | Describe briefly the issue you are highlighting | Describe briefly what you would do to resolve this issue? | Who would benefit? | Forum | Workstream Issue covered under
G2 | DNO | WPD | Richard Brady | SLA / Misreports | 1 | Misreporting of 'Safety Critical' category A interventions by Mops | Training and understanding of MOp staff on new service termination guidance. Thorough training and understanding would improve misreporting levels | All parties | MOCoPA
G1 | DNO | SP Energy Networks | John Gray | SLA / Misreports |  | The volume of A07s reported by a single Supplier is a considerable outlier across the UK. | Joint agreement as to what constitutes a correct A07 report, | Everybody | MOCoPA
G2 | DNO | WPD | Richard Brady | SLA / Misreports | 1 | Reports of B code issues being raised by MOp staff and customers after installation of new meter | Training and understanding of MOp staff on new service termination guidance. Thorough training and understanding would improve misreporting levels. | All parties | MOCoPA
G2 | DNO | ENWL | Jane Eccleston | Voltage Checking A19 | 1 | More a risk of issues between suppliers and DNO over quality of reporting and tools and agreed diagnostics. | Element of monitoring once codes have gone live and a formal review of the data collated. | Suppliers/MOPs/DNO/ Customer | MOCoPA | This is not of great concern at present | Close
G2 | DNO | ENWL | Jane Eccleston | SLA / Misreports | 1 | Receiving Cat B dataflow, DNO makes appointment with the customer to find a meter has already been installed. | Suppliers fully understanding the Cat B processes | Smart Meter Programme/DNO/Supplier | MOCoPA | Not currently causing problems | Close
G2 | DNO | SSEN | D C Brogden | SLA / Misreports | 1 | MOp's reporting high volumes of Category B issues following the successful exchange/ installation of meter. SSEN have reported at previous IWG's that MOps are reporting category B issues even if a meter has been installed. This is clearly in contravention of the DCUSA Legal Text (definition of a category B issue). | Changes will be made to the next revision of the MOCOPA guide. Reporting is by MOp so it is their issue to resolve. SSEN will check to see if a meter has recently been installed (D0150 data flow). If a meter has been installed the job will be closed (as disputed) without a site visit. MOp's to ensure that appropriate training and guidance is provided to ensure that they stop incorrectly reporting issues in these circumstances. SSEN will continue to monitor MOps performance. Charges could be applied when Category B issues are incorrectly reported in this way. | Customers, Suppliers and DNO's. Currently unnecessary costs are borne by the DNO. | DCUSA IWG
G1 | DNO | SP Energy Networks | John Gray | SLA / Misreports |  | When a MOP has made a Cat A safe there is no need to dispatch an Emergency resource | All Cat A made safe will be subject to a SLA similar to that of a Cat B | DNOs and Suppliers | Bilateral
G1 | DNO | UKPN | Paul Morris | SLA / Misreports |  | Faster feedback loop for quality issues | need to challenge how to get information back to the Mop or DNO within the hour | DNOs Meter Operator Suppliers | MOCoPA
G1 | Meter Operator | Eon | D. Brown | SLA / Misreports |  | Specifics on misreports to be detailed to enable learnings / understanding / challenge. | Improves understanding and training material in the field as well as between DB and MO | All parties. | Workshop
G3 | Supplier | Eon | D. Brown | Customer Service | 4 | Customer information from DNO / MO not aligned around service termination issues / rectification. | Standard approach. | Both parties access to complete work. | DCUSA IWG
G3 | DNO | ENWL | Jane Eccleston | Customer Service | 4 | Failure to keep the customer informed of next stepts/contact | Inform customers of the industry process | Customer/Smart Meter Programme/DNO/Supplier | MOCoPA | Not currently causing us problems | Close
G3 | Supplier | British Gas | Kevin Woollard | SLA / Misreports | Sub Group | Mechanism to be used for non-appointed meter operators to report interventions to the DNO | Cat A - report via telephone Cat B and C report via D0135 | Customers and Smart programme | MOCoPA
G1 | Meter Operator | Eon | D Brown | SLA / Misreports | Sub Group | If not the appointed Meter Operator and identify an issue with DB equipment how can we report it? | Need a process to report when not the MOP. | MOp | MOCoPA |  | LI to look at Solutions for this
G1 | DNO | Northern Powergrid | Martin Murphy | DCUSA and MOCoPA |  | Speed of change | Examine processes and procedures under DCUSA and MOCoPA in order to identify potential improvements in timescale and remove unnecessary bureaucracy | All parties | MOCoPA |  | EL to get Senior DCUSA analyst in for June 2019 meeting
G2 | DNO | SSEN | D C Brogden | SLA / Misreports | IWG In a few months time - March 2019 | It appears that an increasing number of MOp's are reluctant to operate metal clad cut-outs. Some have actually "embargoed" the operation of this equipment by their operatives. Meter installation jobs are being unnecessarily aborted and category A and category B issues are being incorrectly reported to SSEN. When a defect is incorrectly reported in this way SSEN will often attend site and find no defect exists. The job will be closed as disputed. SSEN do not change metal clad cut outs as a matter of course, only defective equipment will be replaced. Quite often this is repeated and because SSEN have not changed the cut out (as it is not defective) a second defect is reported by MOp's on follow up visits. In some instances the MOp will also advise the customer to call SSEN. The customer journey is potentially very poor in these situations. | Suppliers/ MOp's need to ensure that they apply the rules regarding reporting of defects in an accurate/ consistent way. The new MOCOPA guidance is an opportunity to change the behaviour of MOp's who currently over report. | Customers, Suppliers and DNO's. Currently unnecessary costs are borne by the DNO. | MOCoPA & IWG |  | Added to mocopa agenda, get update at May meeting
G2 | DNO | SSEN | D C Brogden | SLA / Misreports | IWG In a few months time - March 2019 | In multi occupancy buildings some meters may be remote from the available isolation point, i.e. there is no isolation adjacent to the meter. This is a normal situation that should be managed by the MOp. Usually remote isolation can be safely applied and meters can be safely installed. It has become common practice for some MOp's to abort these jobs without making any attempt to isolate the supply and exchange the meter. They then incorrectly report a category B defect. When a defect is incorrectly reported in this way SSEN will often attend site and find no defect exists. The job will be closed as disputed. Quite often this is repeated and because SSEN have not changed the cut out (as it is not defective) a second defect is reported by MOp's on follow up visits. The customer journey is potentially very poor in these situations. | MOP's need to develop processes and procedures to provide remote isolation. This will prevent jobs being unnecessarily aborted and defects reported incorrectly to SSEN. | Customers, Suppliers and DNO's. Currently unnecessary costs are borne by the DNO. | Bilatteral |  | AMO & MOCOPA, report back at the May meeting and close or move forward
G3 | DNO | SP Energy Networks | John Gray | Suppliers responsibilities | MOCOPA/ENA | It is difficult to contact small suppliers in times of an unsafe incident | Make all Suppliers aware of their obligations to investigate unsafe incidents and consent to provide dedicated contact point available 24/7. | Everybody | DCUSA IWG |  | Request a list of suppliers working hours and out of hours contact from EUK, take to DCUSA afterwards if necessary
G1 | DNO | Northern Powergrid | Martin Murphy | SLA / Misreports | 3 | Misuse of DNO emergency responders to Category A calls that here the MOp has made safe, fitted the meter and left site. | Review and amend the rules around reporting of such incidents | DNO's and Meter Operators | Workshop
G1 | DNO | Northern Powergrid | Martin Murphy | SLA / Misreports | 1 | Over reporting of category A07 incidents | Agree a national approach to what constitutes a category A07 report to ensure consistency across all Suppliers and Mops | All parties and our Customers | Workshop
G1 | DNO | Northern Powergrid | Martin Murphy | SLA / Misreports | 1 | Accuracy of reported incidents | Submission of good quality photographs to help DNO's triage report | All parties and our Customers | Workshop
G2 | Supplier | Npower | DW | Customer Service | MOCOPA CP113M & 0089M | Shared Supply / fuses | Feedback from AMO | Customers and Smart programme | IWG for now |  | Close
G1 | DNO | ENWL | Jane Eccleston | SLA / Misreports | 1 | Disproportionately high level of A07 Reports compared other A codes. Is this correct or sympton of mis-reporting. | DNO needs to monitor and provide regular feedback to suppliers.2. Suppliers need to ensure MOP's are fully trained and making use of the MOCOPA guidance and other materials available. | Suppliers/MOPs/DNO/ Customer | Workshop | Misreporting is not currently an issue for us. | Close
G1 | DNO | SSEN | D C Brogden | SLA / Misreports | 1 | Volumes of category A07 reports by MOp's are significantly higher than they should be. Some MOp's are potentially abusing the reporting system by reporting significantly higher volumes of category A07 issues than other industry parties. In many instances when SSEN staff attend site we discover no defect present or a category B issues or Category C asset information issues only. The suppliers reporting very high volumes of A07's provide significantly lower volumes of category B and C reports. When comparing figures between suppliers it is clear that some parties are over reporting A codes to the detriment of other industry parties and in potentially in contravention of the DCUSA. | Suppliers/ MOp's need to ensure that they apply the rules regarding reporting of defects in an accurate/ consistent way. The new MOCOPA guidance is an opportunity to change the behaviour of MOp's who currently over report. Better training to be provided - SSEN still get significant volumes of missing earth covers, single insulated conductors and bare neutral earth conductors incorrectly reported as A07 defects. Using mirrors to look inside DNO equipment should cease. Inspection of cut outs should be a visual unaided inspection. | Customers, Suppliers and DNO's. Currently unnecessary costs are borne by the DNO. | Workshop
G1 | Supplier | Npower | D Wright | Standardisation of Operation or cut-outs | 4 | Ensuring a Band/restricted types of cut-out are brought to the group to be discussed, and an agreed methodology of whether they can be operated or not | Take to MOCoPA | MOp | Workshop
G2 | DNO | UKPN | Paul Morris | SLA / Misreports | 1 | Incorrect categorisation of jobs | many jobs are reported as Cat A or Cat B when they should be Cat C or not reported at all | Customer / DNO | Workshop
G2 | DNO | UKPN | Paul Morris | Customer Service | Staying on site for CAT A - first time resolution | Monitor Customer Service and Cost | Customer / Meter Operator / DNO | DCUSA IWG

## Pivots
Grade | (All)
Row Labels | Count of Grade | Row Labels | Count of Grade | Row Labels | Count of Forum
Customer Service | 6 | (blank) |  | Bilatteral | 2
DCUSA and MOCoPA | 1 | G1 | 14 | DCUSA IWG | 5
MOCOPA audits | 1 | G2 | 13 | MOCoPA | 15
SLA / Misreports | 19 | G3 | 4 | Workshop | 9
Standardisation of Operation or cut-outs | 1 | Grand Total | 31 | (blank)
Suppliers responsibilities | 2 |  |  | Grand Total | 31
Voltage Checking A19 | 1
(blank)
Grand Total | 31