## CPs
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Current Status | Status Changed in the last month | Date Issued to Ofgem | Original Expected Decision Date | Latest Expected Decision Date
STATUS - INITIAL ASSESSMENT
No
STATUS - DEFINITION
DCP 325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20. | The intent of this Change Proposal is to combine, review and if appropriate, amend the requirements of Section 35A, Section 35B, Schedule 15 and Schedule 20 to improve transparency and efficiency in the data published by DNOs | General | 2 | Richard Colwill / Melissa Kendal | N/A | 2018-11-07 | 11 | No | Next scheduled release following approval | The DCP 325 Working Group is looking to issue a consultation to industry shortly. | DEFINITION | N/A
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | The intent of this modification is to define “Mixed Demand” Sites and apply a proportionate Residual charge where a Site meets the mixed demand definition. | General | 1 | John Lawton / Andy Green | Andrew Malley | 2021-04-14 | 17 | No | TBC | The Working Group met on 02 October to review the need for a BSC change. It was agreed that a BSC change was required and that DCP 388 couldn’t be progressed until the BSC modification had been defined so DCP 388 has been paused until the Proposer raises the required BSC modification. | DEFINITION | N/A
DCP 412 | Discounts from TCR charges for ‘peaky’ final demand customers | This Change Proposal aims to create a discount against the residual charge for ‘peaky’ customers, removing the disproportionate impact of allocating residual charges on the basis of the Agreed Supply Capacity. | CDCM / EDCM | 1 | Craig Booth / Richard Colwill | Andrew Malley | 2022-10-11 | 32 | No | TBC | The DCP 412 Working Group is finalising the consultation and aims to issue industry shortly. | DEFINITION | N/A
DCP 415 | Replacement of D0242/D0315 for MHHS | To create a new DCUSA owned DIP data message for supercustomer billing statements using MHHS data. | Billing | 2 | Hannah Proffitt / Craig Booth | N/A | 10/22/2022 | 3 | No | TBC (dependent on date required for DIP testing) | The Change Report was submitted to the Panel for review in the February 2023 Panel meeting. The Panel agreed that it would not progress to Party voting and that it should be sent back to the Working Group but that the Working Group won’t need to meet until the MHHS Programme have been able to carry out an Impact Assessment for the solution they developed. It was noted that even then, no further work may be required but that it was too early to know that for sure. | DEFINITION | N/A
DCP 416 | Electronic Invoicing Post MHHS | To create a new DCUSA owned DIP data message for electronic Distributor billing post MHHS. | Billing | 2 | Melissa Kendal / Andy Green | N/A | 2022-11-14 | 5 | No | TBC (dependent on date required for DIP testing) | The Working Group have reviewed the consultation responses and met on 23 June 2023 to finalise the conclusions to the second consultation. A decision on whether or not a Change Report is to be produced is to be made by the Panel but the Proposer has initated a MHHS Change Request for the CP to be impact assessed and so it is expected that DCP 416 will be put on hold, pending outcome of the MHHS Change Request. | DEFINITION | N/A
DCP 419 | Pre-Notifications of Planned Supply De-Energisations | This change seeks to ensure that all DCUSA Parties, that de-energise metering equipment as part of any planned work, provide the Distributor with advance notification of the supply interruption. | General | 1 | Alysson Pena / Richard Colwill | TBC | 2023-03-06 | 10 | No | Next scheduled release following approval | The next DCP 419 Working Group is to be held on 11 July 2024 where the Working Group will review draft Change Report. | DEFINITION | N/A
DCP 420 | Include Car Charging Stations In The Definition For Non Final Demand | This change proposal aims to expand the definition of Non Final Demand to include Non Domestic sites which are solely for the use of charging vehicles where electricity is sold with a commercial transaction to a private user. These are to include e.g. Council run services, electric charging stations at car parks and service stations or petrol forecourts but are not to include private fleet charging stations. This is a temporary fix to be put in place until the charging stations included are commercially viable. | General | 1 | Craig Booth / Richard Colwill | TBC | 2023-03-29 | 9 | No | TBC | The Working Group is currently awaiting Panel approval to progress with legal advice. | DEFINITION | N/A
DCP 421 | Update the Tables in schedule 15 of DCUSA | To amend the current tables within Schedule 15 of DCUSA to correctly represent ED2 revenue. | General | 2 | Craig Booth / Andy Green | N/A | 2023-04-12 | 9 | No | Next scheduled release following approval | DCP 421 will be issued for further consultation shortly. | DEFINITION | N/A
DCP 423 | LDNO Discounts for negative scaling | The purpose of this change proposal is to set a floor on the LDNO discount applied to negative tariff components, after scaling, for demand tariffs. The intent of this change proposal is to seek to remedy what the proposer believes is an unintended outcome of the implementation of Ofgem’s Targeted Charging Review where LDNO tariffs can be higher than the equivalent all-the-way tariff i.e. the LDNO margin is negative for that component. | CDCM | 1 | Melissa Kendal / Andy Green | TBC | 2023-05-09 | 5 | No | 2025-04-01 | DCP 423 is currently out for consultation and the Working Group will meet again shortly to review responses and determine next steps. | DEFINITION | N/A
DCP 424 | Use of System charging for complex sites | This change proposal enables the correct DUoS to be paid by meters that are class F or G within a Class 5 or Class 6 Complex Site as described in BSC Modification P441 (where netting of Import and Export takes place for BSC Settlement purposes) in a practical manner. Under p441 where generation and demand are netted before settlement, the gross values must be added to the D0036 or D0275 to ensure the correct DUoS is charged. However, for class F and G the MPAN counts are included on the D0030 data flows but the volumes are zero. In order for the volumes to be correctly charged DUoS it is proposed that these volumes are included in the D0036 or D0275 using a pseudo MPAN for the gross value. | CDCM | 1 | Andy Green / Craig Booth | TBC | 2023-05-10 | 6 | No | Aligned to BSC Mod P441 Implementation Date | DCP 424 has been delayed due a request by Ofgem for further impact analysis on the proposed BSC solution (P441 - Creation of Complex Site Classes). The DCP 424 consultation is now estimated to be released in Q3 2024. | DEFINITION | N/A
DCP 437 | To Shorten the DUoS Pricing Notice Periods | This change proposal aims to shorten the DUoS Pricing Notice Periods so there is longer period between the publication of the PCFM where OFGEM have the option to make changes to our allowed revenue at short notice and the setting of the prices | CDCM | 1 | Hannah Proffitt / Craig Booth | TBC | 2024-02-13 | 3 | 2 | 2024-11-07 | The DCP 437 Working Group met on 9 July 2024, where they reviewed consultation responses. They aim to issue the Change Report to the August Panel. | DEFINITION | N/A
DCP 439 | Backdating Tariff Changes | This change proposal seeks to add a sensible backstop to backdating. | CDCM | 1 | Hannah Proffitt / Richard Colwill | TBC | 2024-03-14 | 4 | No |  | The DCP 437 Working Group is to meet on 12 July 2024, where they will review consultation responses and determine next steps. | DEFINITION | N/A
DCP 440 | Consuming “de-energised” sites | To ensure all consuming “de-energised” sites are charged DUoS. | CDCM | 1 | Hannah Proffitt / Richard Colwill | TBC | 2024-03-14 | 2 | No |  | The DCP 440 Working Group is to meet on 10 July 2024, where they will review consultation responses and determine next steps. | DEFINITION | CONSULTATION
STATUS - CHANGE REPORT
N/A
STATUS - VOTING
DCP 438 | Rate of Return Change Proposal | This change proposal aims to update the rate of return as the previous legal text is out of date | CDCM | 1 | Hannah Proffitt / Craig Booth | TBC | 2024-02-27 | 2 | No | 2025-04-01 | The Working Group met in April and agreed to issue a consultation for DCP 438. The consultation was issued on 07 May, with responses due by 29 May 2024. The second Working Group meeting was held on 04 June 2024 to review responses and the draft Change Report. The Change Report was issued to the Panel during the June Panel meeting, where it was approved to be issued for Party voting. | VOTING | VOTING
DCP 441 | Proposal to increase the number of allowed Change Report alternative variations from two to three | This Change Proposal seeks to change the number of alternative variations that can be added by the Panel to a Change Report from two to three. | General | 1 | Alysson Pena | N/A | 2024-01-05 | 2 | No | 2024-06-27 | DCP 441 was submitted to the Panel for Initial Assessment during their May meeting. The Panel approved for DCP 441 to progress to the Change Report Phase. The Change Report was issued to the Panel during the June Panel meeting, where it was approved to be issued for Party voting. | VOTING | VOTING
STATUS - AWAITING AUTHORITY CONSENT
DCP 425 | Cost Apportionment Factor “cap” Methodology | The intent of this Change Proposal (“CP”) is to provide further clarification as to how costs of Reinforcement are apportioned between the Company and the Customer (a Generation Connection) when the High-Cost Project Threshold is triggered. | General | 1 | Richard Colwill/ Craig Booth | TBC | 2023-07-13 | 5 | No | 2023-12-19 | The Change Report was issued for voting following the March Panel meeting for a period of three weeks. The outcome of the Party voting was a recommendation that Ofgem Accept DCP 425 and the Change Declaration was issued to Authority for approval. | AWAITING AUTHORITY CONSENT | N/A
DCP 435 | Party Novation Process | To add a process within DCUSA to enable a Party to transfer its rights and obligations to another Party via a novation agreement. | General | 1 | Craig Booth | N/A | 2024-02-09 | 0 | No | Next release after approval. | The Change Report was issued for voting following the March Panel meeting for a period of three weeks. The outcome of the Party voting was a recommendation that Ofgem Accept DCP 435 and the Change Declaration was issued to Authority for approval. | AWAITING AUTHORITY CONSENT | N/A
DCP 417 | Ability for the DCUSA Secretariat to Raise Change Proposals | This change seeks to grant the ability to the Secretariat to raise Change Proposals where it identifies a change that would better facilitate the DCUSA Objectives and to introduce an obligation for the Secretariat to raise Change Proposals in certain circumstances, such as at the direction of the Authority. | General | 1 | Melissa Kendal / Richard Colwill | Nadir Hafeez | 2022-12-14 | 12 | No | Next scheduled release following approval | The Working Group met on 23 April, with a representative from Gowling WLG in attendance, in order to finalise the legal text. The legal text was agreed with the legal representative from Gowling WLG. The Change Report presented to the Panel during their May 2024 meeting, where it was approved and was subsequently issued for voting following the May Panel meeting for a period of 15 Working Days. The outcome of the Party voting was a recommendation that Ofgem Accept DCP 417 and the Change Declaration was issued to Authority for approval on 11 June 2024. | AWAITING AUTHORITY CONSENT | N/A
DCP 433 | Limitation for backdating of rebates/charges under Schedule 32 | The intent of this Change Proposal is to amend Schedule 32 to ensure that processes which may result in the backdating of rebates/charges are reflective of the limitations within the current industry arrangements. | General | 1 | Craig Booth | TBC | 2024-01-05 | 5 | No | 2024-06-27 | The Change Report was presented to the Panel during their May 2024 meeting, where it was approved and was subsequently issued for voting following the May Panel meeting for a period of 15 Working Days. The outcome of the Party voting was a recommendation that Ofgem Accept DCP 433 and the Change Declaration was issued to Authority for approval on 10 June 2024. | AWAITING AUTHORITY CONSENT | N/A
STATUS - AWAITING IMPLEMENTATION
2025-04-01
DCP 428 | Zero REP-002/A Data | To specify how parties should deal with zero or blank data in the supercustomer/aggregated billing messages when sending daily statements or raising invoices. | General | 2 | Richard Colwill/ Alysson Peña | TBC | 2023-07-25 | 4 | No | 2025-04-01 | The DCP 428 Working Group finalised their review of the legal text to confirm it was fit for purpose and the Change Report was approved by the Panel ex-committee and subsequently issued for voting on 10 April 2024. The outcome of the Party voting was to Accept DCP 428 and therefore the change will be implemented. | AWAITING IMPLEMENTATION | N/A
STATUS - SENT BACK
N/A | N/A | [7 empty] | No |  |  |  | N/A
STATUS - IMPLEMENTED
DCP 436 | Date change for the provision of Rota Load Block Alpha Identifiers | The proposal is to change the dates related to the provision of Rota Load Block Alpha Identifiers to later dates. Later dates would ensure that the most up to date Rota Load Block Alpha Identifiers are provided to Customers via Suppliers during the winter when the use of Rota Load Disconnections are most likely to be needed. Without changing the dates, (I)DNOs would need to issue Rota Load Block Alpha Identifiers to Suppliers twice per year to achieve this accuracy during winter, which is disruptive to (I)DNOs and Suppliers. | General | 2 | Craig Booth | TBC | 2024-02-12 | 4 | No | 2024-06-27 | The Working Group submitted their Change Report to the Panel in May 2024, during which, the Panel approved for the DCP 436 Change Report to be issued to Parties for voting for a period of 10 Working Days. A Change Declaration was issued on 31 May 2024, confirming the outcome of the Party voting, which was to accept botht the proposed variation as well as the implementation date and therefore, DCP 436 will be implemented on 27 June 2024. | IMPLEMENTED | IMPLEMENTED
DCP 434 | Credit Cover RAV in ED-2 | The RAV calculation used in Credit Cover needs to be updated to reflect ED-2 | General | 2 | Andy Green | N/A | 2024-02-09 | 0 | No | 2024-06-27 | The Change Report was issued for voting following the March Panel meeting for a period of three weeks. The outcome of the Party voting was to Accept DCP 434 and therefore the change will be implemented. | IMPLEMENTED | IMPLEMENTED
STATUS - REJECTED
N/A | N/A | [7 empty] | No |  |  |  | N/A
STATUS - WITHDRAWN
N/A | N/A | [7 empty] | No |  |  |  | N/A
Change Register - July 2024

## Status Changes
[14 empty] | AWAITING IMPLEMENTATION | 1
[14 empty] | IMPLEMENTED | 2
[14 empty] | REJECTED | 0
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status | Status Changed in the last month | DEFINITION | 13
DCP 440 | Consuming “de-energised” sites | To ensure all consuming “de-energised” sites are charged DUoS. | CDCM | 1 | Hannah Proffitt / Richard Colwill | TBC | 2024-03-14 | 2 | No | 0 | The DCP 440 Working Group is to meet on 10 July 2024, where they will review consultation responses and determine next steps. | DEFINITION | CONSULTATION | CONSULTATION | 0
DCP 438 | Rate of Return Change Proposal | This change proposal aims to update the rate of return as the previous legal text is out of date | CDCM | 1 | Hannah Proffitt / Craig Booth | TBC | 2024-02-27 | 2 | No | 2025-04-01 | The Working Group met in April and agreed to issue a consultation for DCP 438. The consultation was issued on 07 May, with responses due by 29 May 2024. The second Working Group meeting was held on 04 June 2024 to review responses and the draft Change Report. The Change Report was issued to the Panel during the June Panel meeting, where it was approved to be issued for Party voting. | VOTING | VOTING | AWAITING AUTHORITY CONSENT | 4
DCP 441 | Proposal to increase the number of allowed Change Report alternative variations from two to three | This Change Proposal seeks to change the number of alternative variations that can be added by the Panel to a Change Report from two to three. | General | 1 | Alysson Pena | N/A | 2024-01-05 | 2 | No | 2024-06-27 | DCP 441 was submitted to the Panel for Initial Assessment during their May meeting. The Panel approved for DCP 441 to progress to the Change Report Phase. The Change Report was issued to the Panel during the June Panel meeting, where it was approved to be issued for Party voting. | VOTING | VOTING | AWAITING IMPLEMENTATION | 1
DCP 436 | Date change for the provision of Rota Load Block Alpha Identifiers | The proposal is to change the dates related to the provision of Rota Load Block Alpha Identifiers to later dates. Later dates would ensure that the most up to date Rota Load Block Alpha Identifiers are provided to Customers via Suppliers during the winter when the use of Rota Load Disconnections are most likely to be needed. Without changing the dates, (I)DNOs would need to issue Rota Load Block Alpha Identifiers to Suppliers twice per year to achieve this accuracy during winter, which is disruptive to (I)DNOs and Suppliers. | General | 2 | Craig Booth | TBC | 2024-02-12 | 4 | No | 2024-06-27 | The Working Group submitted their Change Report to the Panel in May 2024, during which, the Panel approved for the DCP 436 Change Report to be issued to Parties for voting for a period of 10 Working Days. A Change Declaration was issued on 31 May 2024, confirming the outcome of the Party voting, which was to accept botht the proposed variation as well as the implementation date and therefore, DCP 436 will be implemented on 27 June 2024. | IMPLEMENTED | IMPLEMENTED | VOTING | 2
DCP 434 | Credit Cover RAV in ED-2 | The RAV calculation used in Credit Cover needs to be updated to reflect ED-2 | General | 2 | Andy Green | N/A | 2024-02-09 | 0 | No | 2024-06-27 | The Change Report was issued for voting following the March Panel meeting for a period of three weeks. The outcome of the Party voting was to Accept DCP 434 and therefore the change will be implemented. | IMPLEMENTED | IMPLEMENTED | CHANGE REPORT | 0
23
Status Change - July 2024

## Timetables
DCP | Title | Part 1/ Part 2 Matter | Standard/ Urgent | Proposer | Party | Technical Secretariat | Chair | Timetable Change | [7 empty] | Notes
[9 empty] | Jun | Jul | Aug | Sep | Oct | Nov | Dec
441 | Proposal to increase the number of allowed Change Report alternative variations from two to three | Part 1 | Standard | Simon Vicary | EDF | Alysson Peña |  |  | CR | CD
440 | Consuming “de-energised” sites | Part 1 | Standard | Peter Waymont | UKPN | Hannah Proffitt | Andy Green | Y | CON | Def | Def | CR | CD | CD
439 | Backdating Tariff Changes | Part 1 | Standard | Peter Waymont | UKPN | Hannah Proffitt | Andy Green |  | CON | Def | Def | CR | CD
438 | Rate of Return Change Proposal | Part 1 | Standard | Babatunde Olukotun | NGED | Craig Booth | Craig Booth |  | CR | CD
437 | To Shorten the DUoS Pricing Notice Periods | Part 1 | Standard | Dave Wornell | NGED | Andy Green | Richard Colwill | Y | CON | Def | CR | CD
424 | Use of System charging for complex sites | Part 1 | Standard | Mary Gillie | NPg | Craig Booth | Andy Green |  |  | O/H | [5 empty] | Dependent on BSC P411
423 | LDNO Discounts for negative scaling | Part 1 | Standard | Tom Cadge | ENC | Melissa Kendall | Andy Green |  | CR | CD | WO
New timetable | [8 empty] | Def | Def | CR | CD | WO
421 | Update the Tables in schedule 15 of DCUSA | Part 1 | Standard | Dave Wornell | NGED | Craig Booth | Andy Green |  | CR | CD | WO
New timetable | [8 empty] | Def | CON 2 | CR | CD | WO
420 | Include Car Charging Stations In The Definition For Non Final Demand | Part 1 | Standard | Dave Wornell | NGED | Craig Booth | Richard Colwill | Y | Def | CON 2 | Def | CR | CD | WO
New timetable | [8 empty] | Def | Def | CON 2 | Def | CR | CD | WO
419 | Pre-notification of Planned Supply De-energisations | Part 1 | Standard | Nikhel Jethwa | SSEN | Alysson Peña | Richard Colwill |  | Def | CR | CD | WO
New timetable | [8 empty] | Def | Def | CR | CD | WO
416 | Electronic Invoicing Post MHHS | Part 2 | Standard | Peter Waymont | UKPN | Craig Booth | Andy Green |  |  | O/H
415 | Replacement of D0242/D0315 for MHHS | Part 2 | Standard | Peter Waymont | UKPN | Melissa Kendall | Craig Booth |  |  | O/H
412 | Discounts from TCR charges for ‘peaky’ final demand customers | Part 1 | Standard | Lee Stone | E.ON | Craig Booth | Richard Colwill |  | CON 2 | Def | CR | CD | WO
New timetable | [8 empty] | Def | CON 2 | Def | CR | CD | WO
388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | Part 1 | Standard | Lee Stone | E.on | Andy Green | John Lawton |  |  | O/H
325 | Reviewing the requirements of Sections 35A (‘Provision of Cost Information’), 35B (‘Production of the Annual Review Pack’), Schedule 15 (‘Cost Information Table’) and Schedule 20 (‘Production of the Annual Review Pack’) | Part 1 | Standard | Kara Burke | NPg | Craig Booth | Andy Green |  | Def | CON 2 | Def | CR | CD
Definition | Def
RFI | RFI
Consultation | CON/ CON 2
Change Report | CR
Voting/ Change Declaration | CD
With Ofgem | WO
Implementation | Imp
Decision | Dec
Withdrwan | Wd

## Legal Text Overlap Tracker
YES
|  | MHHS | DCP 424 | DCP 325 | DCP 421 | DCP 423 | DCP 388 | DCP 412 | DCP 420
|  | Unknown | 2024-04-01 | Next Scheduled | Next Scheduled | 2025-04-01 | TBC | TBC | TBC |  | NOTES TO ASSIST
Schedules | Paragraph Number |  | Definition | Definition | Definition | Definition | Definition | Definition | Definition | Number of CPs Impacting Paragraph
Schedule 15 | Table 1 |  |  | YES | YES |  |  |  |  | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 2 |  |  | YES | YES |  |  |  |  | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 3 |  |  | YES | YES |  |  |  |  | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
0
Schedule 16 | Introduction | [8 empty] | 0
Schedule 16 | 1 | [8 empty] | 0
Schedule 16 | 2 | [8 empty] | 0
Schedule 16 | 3 | [8 empty] | 0 | Model reference number and date
Schedule 16 | 4 | [8 empty] | 0
Schedule 16 | 5 | [8 empty] | 0
Schedule 16 | 6 | [8 empty] | 0
Schedule 16 | 7 | [8 empty] | 0
Schedule 16 | 7A | [8 empty] | 0
Schedule 16 | 8 | [8 empty] | 0
Schedule 16 | 9 | [8 empty] | 0
Schedule 16 | 10 | [8 empty] | 0
Schedule 16 | 10A | [8 empty] | 0
Schedule 16 | 11 | [8 empty] | 0
Schedule 16 | 12 | [8 empty] | 0
Schedule 16 | 13 | [8 empty] | 0
Schedule 16 | 14 | [8 empty] | 0
Schedule 16 | 15 | [8 empty] | 0
Schedule 16 | 16 | [8 empty] | 0
Schedule 16 | 17 | [8 empty] | 0
Schedule 16 | 18 | [8 empty] | 0
Schedule 16 | 19 | [8 empty] | 0
Schedule 16 | 20 | [8 empty] | 0
Schedule 16 | 21 | [8 empty] | 0
Schedule 16 | 22 | [8 empty] | 0
Schedule 16 | 23 | [8 empty] | 0
Schedule 16 | 24 | [8 empty] | 0
Schedule 16 | 25 | [8 empty] | 0
Schedule 16 | 26 | [8 empty] | 0
Schedule 16 | 27 | [8 empty] | 0
Schedule 16 | 28 | [8 empty] | 0
Schedule 16 | 29 | [8 empty] | 0
Schedule 16 | 30 | [8 empty] | 0
Schedule 16 | 31 | [8 empty] | 0
Schedule 16 | 32 | [8 empty] | 0
Schedule 16 | 33 | [8 empty] | 0
Schedule 16 | 34 | [8 empty] | 0
Schedule 16 | 35 | [8 empty] | 0
Schedule 16 | 36 | [8 empty] | 0
Schedule 16 | 37 | [8 empty] | 0
Schedule 16 | 38 | [8 empty] | 0
Schedule 16 | 39 | [8 empty] | 0
Schedule 16 | 40 | [8 empty] | 0
Schedule 16 | 41 | [8 empty] | 0
Schedule 16 | 41A | [8 empty] | 0
Schedule 16 | 41B | [8 empty] | 0
Schedule 16 | 42 | [8 empty] | 0
Schedule 16 | 42A | YES | [7 empty] | 1
Schedule 16 | 43 | [8 empty] | 0
Schedule 16 | 44 | YES | [7 empty] | 1
Schedule 16 | 45 | [8 empty] | 0
Schedule 16 | 46 | [8 empty] | 0
Schedule 16 | 47 | [8 empty] | 0
Schedule 16 | 48 | [8 empty] | 0
Schedule 16 | 49 | [8 empty] | 0
Schedule 16 | 50 | [8 empty] | 0
Schedule 16 | 51 | [8 empty] | 0
Schedule 16 | 52 | [8 empty] | 0
Schedule 16 | 52A | [8 empty] | 0
Schedule 16 | 53 | [8 empty] | 0
Schedule 16 | 54 | [8 empty] | 0
Schedule 16 | 55 | [8 empty] | 0
Schedule 16 | 56 | [8 empty] | 0
Schedule 16 | 57 | [8 empty] | 0
Schedule 16 | 58 | [8 empty] | 0
Schedule 16 | 59 | [8 empty] | 0
Schedule 16 | 60 | [8 empty] | 0
Schedule 16 | 61 | [8 empty] | 0
Schedule 16 | 62 | [8 empty] | 0
Schedule 16 | 63 | [8 empty] | 0
Schedule 16 | 64 | [8 empty] | 0
Schedule 16 | 65 | [8 empty] | 0
Schedule 16 | 66 | [8 empty] | 0
Schedule 16 | 67 | [8 empty] | 0
Schedule 16 | 68 | [8 empty] | 0
Schedule 16 | 69 | [8 empty] | 0
Schedule 16 | 70 | YES | [7 empty] | 1
Schedule 16 | 71 | [8 empty] | 0
Schedule 16 | 72 | [8 empty] | 0
Schedule 16 | 72A | [8 empty] | 0
Schedule 16 | 73 | [8 empty] | 0
Schedule 16 | 74 | [8 empty] | 0
Schedule 16 | 75 | [8 empty] | 0
Schedule 16 | 76 | [8 empty] | 0
Schedule 16 | 77 | [8 empty] | 0
Schedule 16 | 78 | [8 empty] | 0
Schedule 16 | 79 | [8 empty] | 0
Schedule 16 | 80 | YES | [7 empty] | 1
Schedule 16 | 81 | [8 empty] | 0
Schedule 16 | 82 | [8 empty] | 0
Schedule 16 | 83 | [8 empty] | 0
Schedule 16 | 84 | [8 empty] | 0
Schedule 16 | 85 | [8 empty] | 0
Schedule 16 | 86 | [8 empty] | 0
Schedule 16 | 87 | [8 empty] | 0
Schedule 16 | 88 | [8 empty] | 0
Schedule 16 | 89 | [8 empty] | 0
Schedule 16 | 90 | [8 empty] | 0
Schedule 16 | 91 | [8 empty] | 0
Schedule 16 | 92 | [8 empty] | 0
Schedule 16 | 92A | [8 empty] | 0
Schedule 16 | 92B | [8 empty] | 0
Schedule 16 | 92C | [8 empty] | 0
Schedule 16 | 93 | [8 empty] | 0
Schedule 16 | 94 | [8 empty] | 0
Schedule 16 | 95 | [8 empty] | 0
Schedule 16 | 96 | [8 empty] | 0
Schedule 16 | 97 | [8 empty] | 0
Schedule 16 | 98 |  |  |  |  | YES |  |  |  | 1
Schedule 16 | 99 | [8 empty] | 0
Schedule 16 | 100 | [8 empty] | 0
Schedule 16 | 101 | [8 empty] | 0
Schedule 16 | 102 | [8 empty] | 0
Schedule 16 | 102A | [8 empty] | 0
Schedule 16 | 102B | [8 empty] | 0
Schedule 16 | 103 | [8 empty] | 0
Schedule 16 | 104 | [8 empty] | 0
Schedule 16 | 105 | [8 empty] | 0
Schedule 16 | 106 | [8 empty] | 0
Schedule 16 | 107 | [8 empty] | 0
Schedule 16 | 108 | [8 empty] | 0
Schedule 16 | 108A | [8 empty] | 0
Schedule 16 | 109 | [8 empty] | 0
Schedule 16 | 110 | [8 empty] | 0
Schedule 16 | 111 | [8 empty] | 0
Schedule 16 | 112 | [8 empty] | 0
Schedule 16 | 112A | [8 empty] | 0
Schedule 16 | 113 | [8 empty] | 0
Schedule 16 | 113A | [8 empty] | 0
Schedule 16 | 113B | [8 empty] | 0
Schedule 16 | 113C | [8 empty] | 0
Schedule 16 | 113D | [8 empty] | 0
Schedule 16 | 113E | [8 empty] | 0
Schedule 16 | 114 | [8 empty] | 0
Schedule 16 | 115 | [8 empty] | 0
Schedule 16 | 116 | [8 empty] | 0
Schedule 16 | 117 | [8 empty] | 0
Schedule 16 | 118 | [8 empty] | 0
Schedule 16 | 119 | [8 empty] | 0
Schedule 16 | 120 | [8 empty] | 0
Schedule 16 | 121 | [8 empty] | 0
Schedule 16 | 122 | [8 empty] | 0
Schedule 16 | 123 | [8 empty] | 0
Schedule 16 | 124 | [8 empty] | 0
Schedule 16 | 125 | [8 empty] | 0
Schedule 16 | 126 | [8 empty] | 0
Schedule 16 | 127 | [8 empty] | 0
Schedule 16 | 127A | [8 empty] | 0
Schedule 16 | 128 | YES | YES | [6 empty] | 2
Schedule 16 | 129 | YES | [7 empty] | 1
Schedule 16 | 130 | YES | [7 empty] | 1
Schedule 16 | 131 | [8 empty] | 0
Schedule 16 | 132 | YES | [7 empty] | 1
Schedule 16 | 132A | [8 empty] | 0
Schedule 16 | 132B | [8 empty] | 0
Schedule 16 | 132C | YES | [7 empty] | 1
Schedule 16 | 132D | [8 empty] | 0
Schedule 16 | 133 | YES | [7 empty] | 1
Schedule 16 | 134 | [8 empty] | 0
Schedule 16 | 135 | [8 empty] | 0
Schedule 16 | 135A | YES | [7 empty] | 1 | DCP 414 adds two new rows to table for tariffs named 'Domestic Aggregated or CT' and 'Non-Domestic Aggregated or CT' whereas, for MHHS it is proposed to remove the last column containing applicable MC
Schedule 16 | 135B | [8 empty] | 0
Schedule 16 | 136 | [8 empty] | 0
Schedule 16 | 137 | [8 empty] | 0
Schedule 16 | 138 | [8 empty] | 0
Schedule 16 | 139 | [8 empty] | 0
Schedule 16 | 140 | [8 empty] | 0
Schedule 16 | 140A | YES | [7 empty] | 1
Schedule 16 | 140B | YES | [7 empty] | 1
Schedule 16 | 140C | YES | [7 empty] | 1
Schedule 16 | 140D | [8 empty] | 0
Schedule 16 | 140E | [8 empty] | 0
Schedule 16 | 141 | [8 empty] | 0
Schedule 16 | 142 | YES | [7 empty] | 1
Schedule 16 | 143 | YES | [7 empty] | 1
Schedule 16 | 144 | YES | [7 empty] | 1
Schedule 16 | 145 | [8 empty] | 0
Schedule 16 | 146 | [8 empty] | 0
Schedule 16 | 147 | [8 empty] | 0
Schedule 16 | 148 | [8 empty] | 0
Schedule 16 | 149 | [8 empty] | 0
Schedule 16 | 150 | [8 empty] | 0
Schedule 16 | 151 | [8 empty] | 0
Schedule 16 | 152 | [8 empty] | 0
Schedule 16 | 153 | [8 empty] | 0
Schedule 16 | 154 | [8 empty] | 0
Schedule 16 | 155 | [8 empty] | 0
Schedule 16 | 156 | [8 empty] | 0
Schedule 16 | 157 | [8 empty] | 0
Schedule 16 | 158 | [8 empty] | 0
Schedule 16 | 159 | [8 empty] | 0
Schedule 16 | 160 | [8 empty] | 0
Schedule 16 | 161 | [8 empty] | 0
Schedule 16 | 162 | [8 empty] | 0
Schedule 16 | 163 | [8 empty] | 0
Schedule 16 | 164 | [8 empty] | 0
Schedule 16 | 165 | [8 empty] | 0
Schedule 16 | 166 | [8 empty] | 0
Schedule 16 | 167 | [8 empty] | 0
Schedule 16 | 168 | [8 empty] | 0
Schedule 16 | 169 | [8 empty] | 0
Schedule 16 | 170 | [8 empty] | 0
Schedule 16 | 171 | [8 empty] | 0
Schedule 16 | 172 | [8 empty] | 0
Schedule 16 | 173 | [8 empty] | 0
Schedule 16 | 174 | [8 empty] | 0
Schedule 16 | 175 | [8 empty] | 0
Schedule 16 | 176 | [8 empty] | 0
Schedule 16 | 177 | [8 empty] | 0
Schedule 16 | 178 | [8 empty] | 0
Schedule 16 | 179 | [8 empty] | 0
Schedule 16 | 180 | [8 empty] | 0
Schedule 16 | 181 | [8 empty] | 0
Schedule 16 | 182 | [8 empty] | 0
Schedule 16 | 183 | [8 empty] | 0
Schedule 16 | 184 | [8 empty] | 0
Schedule 16 | Glossary | YES | [7 empty] | 1
0
Schedule 17 | Introduction | [8 empty] | 0
Schedule 17 | 1 | [8 empty] | 0
Schedule 17 | 1.1 | [8 empty] | 0
Schedule 17 | 1.2 | [8 empty] | 0
Schedule 17 | 1.3 | [8 empty] | 0 | Model reference number and date
Schedule 17 | 1.3A | [8 empty] | 0
Schedule 17 | 1.4 | [8 empty] | 0
Schedule 17 | 1.5 | [8 empty] | 0
Schedule 17 | 1.6 | [8 empty] | 0
Schedule 17 | 1.7 | [8 empty] | 0
Schedule 17 | 1.8 | [8 empty] | 0
Schedule 17 | 1.9 | [8 empty] | 0
Schedule 17 | 2 | [8 empty] | 0
Schedule 17 | 2.1 | [8 empty] | 0
Schedule 17 | 2.2 | [8 empty] | 0
Schedule 17 | 2.3 | [8 empty] | 0
Schedule 17 | 2.4 | [8 empty] | 0
Schedule 17 | 2.5 | [8 empty] | 0
Schedule 17 | 2.6 | [8 empty] | 0
Schedule 17 | 2.7 | [8 empty] | 0
Schedule 17 | 2.8 | [8 empty] | 0
Schedule 17 | 2.9 | [8 empty] | 0
Schedule 17 | 2.1 | [8 empty] | 0
Schedule 17 | 2.11 | [8 empty] | 0
Schedule 17 | 2.12 | [8 empty] | 0
Schedule 17 | 2.13 | [8 empty] | 0
Schedule 17 | 2.14 | [8 empty] | 0
Schedule 17 | 2.15 | [8 empty] | 0
Schedule 17 | 2.16 | [8 empty] | 0
Schedule 17 | 2.17 | [8 empty] | 0
Schedule 17 | 2.18 | [8 empty] | 0
Schedule 17 | 2.19 | [8 empty] | 0
Schedule 17 | 3 | [8 empty] | 0
Schedule 17 | 3.1 | [8 empty] | 0
Schedule 17 | 3.2 | [8 empty] | 0
Schedule 17 | 3.3 | [8 empty] | 0
Schedule 17 | 3.4 | [8 empty] | 0
Schedule 17 | 3.5 | [8 empty] | 0
Schedule 17 | 3.6 | [8 empty] | 0
Schedule 17 | 3.7 | [8 empty] | 0
Schedule 17 | 4 | [8 empty] | 0
Schedule 17 | 4.1 | [8 empty] | 0
Schedule 17 | 5 | [8 empty] | 0
Schedule 17 | 5.1 | [8 empty] | 0
Schedule 17 | 6 | [8 empty] | 0
Schedule 17 | 6.1 | [8 empty] | 0
Schedule 17 | 6.2 | [8 empty] | 0
Schedule 17 | 6.3 | [8 empty] | 0
Schedule 17 | 7 | [8 empty] | 0
Schedule 17 | 7.1 | [8 empty] | 0
Schedule 17 | 8 | [8 empty] | 0
Schedule 17 | 8.1 | [8 empty] | 0
Schedule 17 | 8.2 | [8 empty] | 0
Schedule 17 | 8.3 | [8 empty] | 0
Schedule 17 | 8.4 | [8 empty] | 0
Schedule 17 | 9 | [8 empty] | 0
Schedule 17 | 9.1 | [8 empty] | 0
Schedule 17 | 9.2 | [8 empty] | 0
Schedule 17 | 9.3 | [8 empty] | 0
Schedule 17 | 10 | [8 empty] | 0
Schedule 17 | 10.1 | [8 empty] | 0
Schedule 17 | 10.2 | [8 empty] | 0
Schedule 17 | 10.3 | [8 empty] | 0
Schedule 17 | 10.4 | [8 empty] | 0
Schedule 17 | 11 | [8 empty] | 0
Schedule 17 | 11.1 | [8 empty] | 0
Schedule 17 | 12 | [8 empty] | 0
Schedule 17 | 12.1 | [8 empty] | 0
Schedule 17 | 12.2 | [8 empty] | 0
Schedule 17 | 12.3 | [8 empty] | 0
Schedule 17 | 13 | [8 empty] | 0
Schedule 17 | 13.1 | [8 empty] | 0
Schedule 17 | 13.2 | [8 empty] | 0
Schedule 17 | 13.3 | [8 empty] | 0
Schedule 17 | 13.4 | [8 empty] | 0
Schedule 17 | 14 | [8 empty] | 0
Schedule 17 | 14.1 | [8 empty] | 0
Schedule 17 | 14.2 | [8 empty] | 0
Schedule 17 | 14.3 | [8 empty] | 0
Schedule 17 | 14.4 | [8 empty] | 0
Schedule 17 | 14.5 | [8 empty] | 0
Schedule 17 | 15 | [8 empty] | 0
Schedule 17 | 15.1 | [8 empty] | 0
Schedule 17 | 15.2 | [8 empty] | 0
Schedule 17 | 15.3 | [8 empty] | 0
Schedule 17 | 15.4 | [8 empty] | 0
Schedule 17 | 15.5 | [8 empty] | 0
Schedule 17 | 15.6 | [8 empty] | 0
Schedule 17 | 15.7 | [8 empty] | 0
Schedule 17 | 15.8 | [8 empty] | 0
Schedule 17 | 15.9 | [8 empty] | 0
Schedule 17 | 15.1 | [8 empty] | 0
Schedule 17 | 15.11 | [8 empty] | 0
Schedule 17 | 15.12 | [8 empty] | 0
Schedule 17 | 15.15 | [8 empty] | 0
Schedule 17 | 16 | [8 empty] | 0
Schedule 17 | 16.1 | [8 empty] | 0
Schedule 17 | 16.2 | [8 empty] | 0
Schedule 17 | 16.3 | [8 empty] | 0
Schedule 17 | 16.4 | [8 empty] | 0
Schedule 17 | 16.5 | [8 empty] | 0
Schedule 17 | 16.6 | [8 empty] | 0
Schedule 17 | 16.7 | [8 empty] | 0
Schedule 17 | 16.8 | [8 empty] | 0
Schedule 17 | 16.9 | [8 empty] | 0
Schedule 17 | 16.1 | [8 empty] | 0
Schedule 17 | 17 | [8 empty] | 0
Schedule 17 | 17.1 | [8 empty] | 0
Schedule 17 | 17.2 | [8 empty] | 0
Schedule 17 | 17.3 | [8 empty] | 0
Schedule 17 | 18 | [8 empty] | 0
Schedule 17 | 18.1 | [8 empty] | 0
Schedule 17 | 18.2 | [8 empty] | 0
Schedule 17 | 18.3 | [8 empty] | 0
Schedule 17 | 18.4 | [8 empty] | 0
Schedule 17 | 18.5 | [8 empty] | 0
Schedule 17 | 18.6 | [8 empty] | 0
Schedule 17 | 18.7 | [8 empty] | 0
Schedule 17 | 18.8 | [8 empty] | 0
Schedule 17 | 18.9 | [8 empty] | 0
Schedule 17 | 18.1 | [8 empty] | 0
Schedule 17 | 18.11 | [8 empty] | 0
Schedule 17 | 18.12 | [8 empty] | 0
Schedule 17 | 18.13 | [8 empty] | 0
Schedule 17 | 18.14 | [8 empty] | 0
Schedule 17 | 18.15 | [8 empty] | 0
Schedule 17 | 18.16 | [8 empty] | 0
Schedule 17 | 18.17 | [8 empty] | 0
Schedule 17 | 18.18 | [8 empty] | 0
Schedule 17 | 18.19 | [8 empty] | 0
Schedule 17 | 18.2 | [8 empty] | 0
Schedule 17 | 18.21 | [8 empty] | 0
Schedule 17 | 19 | [8 empty] | 0
Schedule 17 | 19.1 | [8 empty] | 0
Schedule 17 | 19.2 | [8 empty] | 0
Schedule 17 | 19.3 | [8 empty] | 0
Schedule 17 | 19.4 | [8 empty] | 0
Schedule 17 | 19.5 | [8 empty] | 0
Schedule 17 | 19.6 | [8 empty] | 0
Schedule 17 | 19.7 | [8 empty] | 0
Schedule 17 | 19.8 | [8 empty] | 0
Schedule 17 | 19.9 | [8 empty] | 0
Schedule 17 | 19.1 | [8 empty] | 0
Schedule 17 | 19.11 | [8 empty] | 0
Schedule 17 | 20 | [8 empty] | 0
Schedule 17 | 20.1 | [8 empty] | 0
Schedule 17 | 20.2 | [8 empty] | 0
Schedule 17 | 20.3 | [8 empty] | 0
Schedule 17 | 20.4 | [8 empty] | 0
Schedule 17 | 20.5 | [8 empty] | 0
Schedule 17 | 20.6 | [8 empty] | 0
Schedule 17 | 20.7 | [8 empty] | 0
Schedule 17 | 20.8 | [8 empty] | 0
Schedule 17 | 20.9 | [8 empty] | 0
Schedule 17 | 21 | [8 empty] | 0
Schedule 17 | 21.1 | [8 empty] | 0
Schedule 17 | 21.2 | [8 empty] | 0
Schedule 17 | 22 | [8 empty] | 0
Schedule 17 | 22.1 | [8 empty] | 0
Schedule 17 | 22.2 | [8 empty] | 0
Schedule 17 | 22.3 | [8 empty] | 0
Schedule 17 | 22.4 | [8 empty] | 0
Schedule 17 | 23 | [8 empty] | 0
Schedule 17 | 23.1 | [8 empty] | 0
Schedule 17 | 23.2 | [8 empty] | 0
Schedule 17 | 23.3 | [8 empty] | 0
Schedule 17 | 23.4 | [8 empty] | 0
Schedule 17 | 23.5 | [8 empty] | 0
Schedule 17 | 24 | [8 empty] | 0
Schedule 17 | 24.1 | [8 empty] | 0
Schedule 17 | 24.2 | [8 empty] | 0
Schedule 17 | 24.3 | [8 empty] | 0
Schedule 17 | 24.4 | [8 empty] | 0
Schedule 17 | 24.5 | [8 empty] | 0
Schedule 17 | 24.6 | [8 empty] | 0
Schedule 17 | 24.7 | [8 empty] | 0
Schedule 17 | 24.8 | [8 empty] | 0
Schedule 17 | 24.9 | [8 empty] | 0
Schedule 17 | 25 | [8 empty] | 0
Schedule 17 | 25.1 | [8 empty] | 0
Schedule 17 | 25.2 | [8 empty] | 0
Schedule 17 | 25.3 | [8 empty] | 0
Schedule 17 | 25.4 | [8 empty] | 0
Schedule 17 | 25.5 | [8 empty] | 0
Schedule 17 | 25.6 | [8 empty] | 0
Schedule 17 | 25.7 | [8 empty] | 0
Schedule 17 | 25.8 | [8 empty] | 0
Schedule 17 | 25.9 | [8 empty] | 0
Schedule 17 | 25.1 | [8 empty] | 0
Schedule 17 | 25.11 | [8 empty] | 0
Schedule 17 | 25.12 | [8 empty] | 0
Schedule 17 | 25.13 | [8 empty] | 0
Schedule 17 | 25.14 | [8 empty] | 0
Schedule 17 | 25.15 | [8 empty] | 0
Schedule 17 | 25.16 | [8 empty] | 0
Schedule 17 | 25.17 | [8 empty] | 0
Schedule 17 | 25.18 | [8 empty] | 0
Schedule 17 | 25.19 | [8 empty] | 0
Schedule 17 | 26 | [8 empty] | 0
Schedule 17 | 26.1 | [8 empty] | 0
Schedule 17 | 26.2 | [8 empty] | 0
Schedule 17 | 26.3 | [8 empty] | 0
Schedule 17 | 26.4 | [8 empty] | 0
Schedule 17 | 26.5 | [8 empty] | 0
Schedule 17 | 26.6 | [8 empty] | 0
Schedule 17 | 26.7 | [8 empty] | 0
Schedule 17 | 26.8 | [8 empty] | 0
Schedule 17 | 26.9 | [8 empty] | 0
Schedule 17 | 26.1 | [8 empty] | 0
Schedule 17 | 26.11 | [8 empty] | 0
Schedule 17 | 27 | [8 empty] | 0
Schedule 17 | 27.1 | [8 empty] | 0
Schedule 17 | 27.2 | [8 empty] | 0
Schedule 17 | 27.3 | [8 empty] | 0
Schedule 17 | 27.4 | [8 empty] | 0
Schedule 17 | 28 | [8 empty] | 0
Schedule 17 | 28.1 | [8 empty] | 0
Schedule 17 | 28.2 | [8 empty] | 0
Schedule 17 | 29 | [8 empty] | 0
Schedule 17 | 29.1 | [8 empty] | 0
Schedule 17 | 29.2 | [8 empty] | 0
Schedule 17 | 29.3 | [8 empty] | 0
Schedule 17 | 29.4 | [8 empty] | 0
Schedule 17 | 30 | [8 empty] | 0
Schedule 17 | 30.1 | [8 empty] | 0
Schedule 17 | 30.2 | [8 empty] | 0
Schedule 17 | 30.3 | [8 empty] | 0
Schedule 17 | 30.4 | [8 empty] | 0
Schedule 17 | 30.5 | [8 empty] | 0
Schedule 17 | 30.6 | [8 empty] | 0
Schedule 17 | 30.7 | [8 empty] | 0
Schedule 17 | 30.8 | [8 empty] | 0
Schedule 17 | 30.9 | [8 empty] | 0
Schedule 17 | 30.1 | [8 empty] | 0
Schedule 17 | 30.11 | [8 empty] | 0
Schedule 17: Annex 1 | 1 | [8 empty] | 0
Schedule 17: Annex 1 | 2 | [8 empty] | 0
Schedule 17: Annex 1 | 2.1 | [8 empty] | 0
Schedule 17: Annex 1 | 2.2 | [8 empty] | 0
Schedule 17: Annex 1 | 2.3 | [8 empty] | 0
Schedule 17: Annex 1 | 2.4 | [8 empty] | 0
Schedule 17: Annex 1 | 2.5 | [8 empty] | 0
Schedule 17: Annex 1 | 3 | [8 empty] | 0
Schedule 17: Annex 1 | Definitions | [8 empty] | 0
Schedule 17: Annex 1 | 4 | [8 empty] | 0
Schedule 17: Annex 1 | 4.1 | [8 empty] | 0
Schedule 17: Annex 1 | 4.2 | [8 empty] | 0
Schedule 17: Annex 1 | 4.3 | [8 empty] | 0
Schedule 17: Annex 1 | 4.4 | [8 empty] | 0
Schedule 17: Annex 1 | 4.5 | [8 empty] | 0
Schedule 17: Annex 1 | 4.6 | [8 empty] | 0
Schedule 17: Annex 1 | 4.7 | [8 empty] | 0
Schedule 17: Annex 1 | 4.8 | [8 empty] | 0
Schedule 17: Annex 1 | 4.9 | [8 empty] | 0
Schedule 17: Annex 1 | 4.1 | [8 empty] | 0
Schedule 17: Annex 1 | 5 | [8 empty] | 0
Schedule 17: Annex 1 | 5.1 | [8 empty] | 0
Schedule 17: Annex 1 | 5.2 | [8 empty] | 0
Schedule 17: Annex 1 | 5.3 | [8 empty] | 0
Schedule 17: Annex 1 | 5.4 | [8 empty] | 0
Schedule 17: Annex 1 | 5.5 | [8 empty] | 0
Schedule 17: Annex 1 | 5.6 | [8 empty] | 0
Schedule 17: Annex 1 | 5.7 | [8 empty] | 0
Schedule 17: Annex 1 | 5.8 | [8 empty] | 0
Schedule 17: Annex 1 | 5.9 | [8 empty] | 0
Schedule 17: Annex 1 | 5.1 | [8 empty] | 0
Schedule 17: Annex 1 | 5.11 | [8 empty] | 0
Schedule 17: Annex 1 | 5.12 | [8 empty] | 0
Schedule 17: Annex 1 | 5.13 | [8 empty] | 0
Schedule 17: Annex 1 | 5.14 | [8 empty] | 0
Schedule 17: Annex 1 | 5.15 | [8 empty] | 0
Schedule 17: Annex 1 | 5.16 | [8 empty] | 0
Schedule 17: Annex 1 | 5.17 | [8 empty] | 0
Schedule 17: Annex 1 | 5.18 | [8 empty] | 0
Schedule 17: Annex 1 | 5.19 | [8 empty] | 0
Schedule 17: Annex 1 | 5.2 | [8 empty] | 0
Schedule 17: Annex 1 | 5.21 | [8 empty] | 0
Schedule 17: Annex 1 | 5.22 | [8 empty] | 0
Schedule 17: Annex 1 | 5.23 | [8 empty] | 0
Schedule 17: Annex 1 | 5.24 | [8 empty] | 0
Schedule 17: Annex 1 | 5.25 | [8 empty] | 0
Schedule 17: Annex 1 | 5.26 | [8 empty] | 0
Schedule 17: Annex 1 | 5.27 | [8 empty] | 0
Schedule 17: Annex 1 | 5.28 | [8 empty] | 0
Schedule 17: Annex 1 | 5.29 | [8 empty] | 0
Schedule 17: Annex 1 | 5.3 | [8 empty] | 0
Schedule 17: Annex 1 | 5.31 | [8 empty] | 0
Schedule 17: Annex 1 | 5.32 | [8 empty] | 0
Schedule 17: Annex 1 | 5.33 | [8 empty] | 0
Schedule 17: Annex 1 | 5.34 | [8 empty] | 0
Schedule 17: Annex 1 | 5.35 | [8 empty] | 0
Schedule 17: Annex 1 | 5.36 | [8 empty] | 0
Schedule 17: Annex 1 | 5.37 | [8 empty] | 0
Schedule 17: Annex 1 | 5.38 | [8 empty] | 0
Schedule 17: Annex 1 | 5.39 | [8 empty] | 0
Schedule 17: Annex 1 | 5.4 | [8 empty] | 0
Schedule 17: Annex 1 | 5.41 | [8 empty] | 0
Schedule 17: Annex 1 | 5.42 | [8 empty] | 0
Schedule 17: Annex 1 | 5.43 | [8 empty] | 0
Schedule 17: Annex 1 | 5.44 | [8 empty] | 0
Schedule 17: Annex 1 | 5.45 | [8 empty] | 0
Schedule 17: Annex 1 | 6 | [8 empty] | 0
Schedule 17: Annex 1 | 6.1 | [8 empty] | 0
Schedule 17: Annex 1 | 6.2 | [8 empty] | 0
Schedule 17: Annex 1 | 6.3 | [8 empty] | 0
Schedule 17: Annex 1 | 6.4 | [8 empty] | 0
Schedule 17: Annex 1 | 6.5 | [8 empty] | 0
Schedule 17: Annex 1 | 6.6 | [8 empty] | 0
Schedule 17: Annex 1 | 6.7 | [8 empty] | 0
Schedule 17: Annex 1 | 6.8 | [8 empty] | 0
Schedule 17: Annex 1 | 7 | [8 empty] | 0
Schedule 17: Annex 1 | 7.1 | [8 empty] | 0
Schedule 17: Annex 1 | 7.2 | [8 empty] | 0
Schedule 17: Annex 1 | 7.3 | [8 empty] | 0
Schedule 17: Annex 1 | 7.4 | [8 empty] | 0
Schedule 17: Annex 1 | 7.5 | [8 empty] | 0
Schedule 17: Annex 1 | 7.6 | [8 empty] | 0
Schedule 17: Annex 1 | 7.7 | [8 empty] | 0
Schedule 17: Annex 1 | 7.8 | [8 empty] | 0
Schedule 17: Annex 1 | 8 | [8 empty] | 0
Schedule 17: Annex 1 | 8.1 | [8 empty] | 0
Schedule 17: Annex 1 | 8.2 | [8 empty] | 0
Schedule 17: Annex 1 | 8.3 | [8 empty] | 0
Schedule 17: Annex 1 | 8.4 | [8 empty] | 0
Schedule 17: Annex 1 | 9 | [8 empty] | 0
Schedule 17: Annex 1 | 9.1 | [8 empty] | 0
Schedule 17: Annex 1 | 9.2 | [8 empty] | 0
Schedule 17: Annex 1 | 9.3 | [8 empty] | 0
Schedule 17: Annex 1 | 9.4 | [8 empty] | 0
Schedule 17: Annex 1 | 9.5 | [8 empty] | 0
Schedule 17: Annex 1 | 9.6 | [8 empty] | 0
Schedule 17: Annex 1 | 9.7 | [8 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [8 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [8 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [8 empty] | 0
Schedule 17: Annex 1 | Attachment 3 | [8 empty] | 0
Schedule 17: Annex 2 | Annex 2 | [8 empty] | 0
0
Schedule 18 | Introduction | [8 empty] | 0
Schedule 18 | 1 | [8 empty] | 0
Schedule 18 | 1.1 | [8 empty] | 0
Schedule 18 | 1.2 | [8 empty] | 0
Schedule 18 | 1.3 | [8 empty] | 0 | Model reference number and date
Schedule 18 | 1.3A | [8 empty] | 0
Schedule 18 | 1.4 | [8 empty] | 0
Schedule 18 | 1.5 | [8 empty] | 0
Schedule 18 | 1.6 | [8 empty] | 0
Schedule 18 | 1.7 | [8 empty] | 0
Schedule 18 | 1.8 | [8 empty] | 0
Schedule 18 | 1.9 | [8 empty] | 0
Schedule 18 | 2 | [8 empty] | 0
Schedule 18 | 2.1 | [8 empty] | 0
Schedule 18 | 2.2 | [8 empty] | 0
Schedule 18 | 2.3 | [8 empty] | 0
Schedule 18 | 2.4 | [8 empty] | 0
Schedule 18 | 2.5 | [8 empty] | 0
Schedule 18 | 2.6 | [8 empty] | 0
Schedule 18 | 2.7 | [8 empty] | 0
Schedule 18 | 2.8 | [8 empty] | 0
Schedule 18 | 2.9 | [8 empty] | 0
Schedule 18 | 2.1 | [8 empty] | 0
Schedule 18 | 2.11 | [8 empty] | 0
Schedule 18 | 2.12 | [8 empty] | 0
Schedule 18 | 2.13 | [8 empty] | 0
Schedule 18 | 2.14 | [8 empty] | 0
Schedule 18 | 2.15 | [8 empty] | 0
Schedule 18 | 2.16 | [8 empty] | 0
Schedule 18 | 2.17 | [8 empty] | 0
Schedule 18 | 2.18 | [8 empty] | 0
Schedule 18 | 2.19 | [8 empty] | 0
Schedule 18 | 2.2 | [8 empty] | 0
Schedule 18 | 2.21 | [8 empty] | 0
Schedule 18 | 2.22 | [8 empty] | 0
Schedule 18 | 2.23 | [8 empty] | 0
Schedule 18 | 2.24 | [8 empty] | 0
Schedule 18 | 2.25 | [8 empty] | 0
Schedule 18 | 2.26 | [8 empty] | 0
Schedule 18 | 2.27 | [8 empty] | 0
Schedule 18 | 2.28 | [8 empty] | 0
Schedule 18 | 2.29 | [8 empty] | 0
Schedule 18 | 2.3 | [8 empty] | 0
Schedule 18 | 3 | [8 empty] | 0
Schedule 18 | 3.1 | [8 empty] | 0
Schedule 18 | 3.2 | [8 empty] | 0
Schedule 18 | 3.3 | [8 empty] | 0
Schedule 18 | 3.4 | [8 empty] | 0
Schedule 18 | 3.5 | [8 empty] | 0
Schedule 18 | 3.6 | [8 empty] | 0
Schedule 18 | 3.7 | [8 empty] | 0
Schedule 18 | 4 | [8 empty] | 0
Schedule 18 | 4.1 | [8 empty] | 0
Schedule 18 | 5 | [8 empty] | 0
Schedule 18 | 5.1 | [8 empty] | 0
Schedule 18 | 6 | [8 empty] | 0
Schedule 18 | 6.1 | [8 empty] | 0
Schedule 18 | 6.2 | [8 empty] | 0
Schedule 18 | 6.3 | [8 empty] | 0
Schedule 18 | 6.4 | [8 empty] | 0
Schedule 18 | 6.5 | [8 empty] | 0
Schedule 18 | 7 | [8 empty] | 0
Schedule 18 | 7.1 | [8 empty] | 0
Schedule 18 | 8 | [8 empty] | 0
Schedule 18 | 8.1 | [8 empty] | 0
Schedule 18 | 8.2 | [8 empty] | 0
Schedule 18 | 8.3 | [8 empty] | 0
Schedule 18 | 8.4 | [8 empty] | 0
Schedule 18 | 9 | [8 empty] | 0
Schedule 18 | 9.1 | [8 empty] | 0
Schedule 18 | 9.2 | [8 empty] | 0
Schedule 18 | 10 | [8 empty] | 0
Schedule 18 | 10.1 | [8 empty] | 0
Schedule 18 | 10.2 | [8 empty] | 0
Schedule 18 | 10.3 | [8 empty] | 0
Schedule 18 | 10.4 | [8 empty] | 0
Schedule 18 | 10.5 | [8 empty] | 0
Schedule 18 | 11 | [8 empty] | 0
Schedule 18 | 11.1 | [8 empty] | 0
Schedule 18 | 12 | [8 empty] | 0
Schedule 18 | 12.1 | [8 empty] | 0
Schedule 18 | 12.2 | [8 empty] | 0
Schedule 18 | 12.3 | [8 empty] | 0
Schedule 18 | 12.4 | [8 empty] | 0
Schedule 18 | 12.5 | [8 empty] | 0
Schedule 18 | 12.6 | [8 empty] | 0
Schedule 18 | 13 | [8 empty] | 0
Schedule 18 | 13.1 | [8 empty] | 0
Schedule 18 | 13.2 | [8 empty] | 0
Schedule 18 | 13.3 | [8 empty] | 0
Schedule 18 | 13.4 | [8 empty] | 0
Schedule 18 | 14 | [8 empty] | 0
Schedule 18 | 14.1 | [8 empty] | 0
Schedule 18 | 14.2 | [8 empty] | 0
Schedule 18 | 14.3 | [8 empty] | 0
Schedule 18 | 14.4 | [8 empty] | 0
Schedule 18 | 14.5 | [8 empty] | 0
Schedule 18 | 15 | [8 empty] | 0
Schedule 18 | 15.1 | [8 empty] | 0
Schedule 18 | 15.2 | [8 empty] | 0
Schedule 18 | 15.3 | [8 empty] | 0
Schedule 18 | 15.4 | [8 empty] | 0
Schedule 18 | 15.5 | [8 empty] | 0
Schedule 18 | 15.6 | [8 empty] | 0
Schedule 18 | 15.7 | [8 empty] | 0
Schedule 18 | 15.8 | [8 empty] | 0
Schedule 18 | 15.9 | [8 empty] | 0
Schedule 18 | 15.1 | [8 empty] | 0
Schedule 18 | 15.11 | [8 empty] | 0
Schedule 18 | 15.12 | [8 empty] | 0
Schedule 18 | 15.15 | [8 empty] | 0
Schedule 18 | 16 | [8 empty] | 0
Schedule 18 | 16.1 | [8 empty] | 0
Schedule 18 | 16.2 | [8 empty] | 0
Schedule 18 | 16.3 | [8 empty] | 0
Schedule 18 | 16.4 | [8 empty] | 0
Schedule 18 | 16.5 | [8 empty] | 0
Schedule 18 | 16.6 | [8 empty] | 0
Schedule 18 | 16.7 | [8 empty] | 0
Schedule 18 | 16.8 | [8 empty] | 0
Schedule 18 | 16.9 | [8 empty] | 0
Schedule 18 | 16.1 | [8 empty] | 0
Schedule 18 | 17 | [8 empty] | 0
Schedule 18 | 17.1 | [8 empty] | 0
Schedule 18 | 17.2 | [8 empty] | 0
Schedule 18 | 17.3 | [8 empty] | 0
Schedule 18 | 18 | [8 empty] | 0
Schedule 18 | 18.1 | [8 empty] | 0
Schedule 18 | 18.2 | [8 empty] | 0
Schedule 18 | 18.3 | [8 empty] | 0
Schedule 18 | 18.4 | [8 empty] | 0
Schedule 18 | 18.5 | [8 empty] | 0
Schedule 18 | 18.6 | [8 empty] | 0
Schedule 18 | 18.7 | [8 empty] | 0
Schedule 18 | 18.8 | [8 empty] | 0
Schedule 18 | 18.9 | [8 empty] | 0
Schedule 18 | 18.1 | [8 empty] | 0
Schedule 18 | 18.11 | [8 empty] | 0
Schedule 18 | 18.12 | [8 empty] | 0
Schedule 18 | 18.13 | [8 empty] | 0
Schedule 18 | 18.14 | [8 empty] | 0
Schedule 18 | 18.15 | [8 empty] | 0
Schedule 18 | 18.16 | [8 empty] | 0
Schedule 18 | 18.17 | [8 empty] | 0
Schedule 18 | 18.18 | [8 empty] | 0
Schedule 18 | 18.19 | [8 empty] | 0
Schedule 18 | 18.2 | [8 empty] | 0
Schedule 18 | 18.21 | [8 empty] | 0
Schedule 18 | 19 | [8 empty] | 0
Schedule 18 | 19.1 | [8 empty] | 0
Schedule 18 | 19.2 | [8 empty] | 0
Schedule 18 | 19.3 | [8 empty] | 0
Schedule 18 | 19.4 | [8 empty] | 0
Schedule 18 | 19.5 | [8 empty] | 0
Schedule 18 | 19.6 | [8 empty] | 0
Schedule 18 | 19.7 | [8 empty] | 0
Schedule 18 | 19.8 | [8 empty] | 0
Schedule 18 | 19.9 | [8 empty] | 0
Schedule 18 | 19.1 | [8 empty] | 0
Schedule 18 | 19.11 | [8 empty] | 0
Schedule 18 | 20 | [8 empty] | 0
Schedule 18 | 20.1 | [8 empty] | 0
Schedule 18 | 20.2 | [8 empty] | 0
Schedule 18 | 20.3 | [8 empty] | 0
Schedule 18 | 20.4 | [8 empty] | 0
Schedule 18 | 20.5 | [8 empty] | 0
Schedule 18 | 20.6 | [8 empty] | 0
Schedule 18 | 20.7 | [8 empty] | 0
Schedule 18 | 20.8 | [8 empty] | 0
Schedule 18 | 20.9 | [8 empty] | 0
Schedule 18 | 21 | [8 empty] | 0
Schedule 18 | 21.1 | [8 empty] | 0
Schedule 18 | 21.2 | [8 empty] | 0
Schedule 18 | 22 | [8 empty] | 0
Schedule 18 | 22.1 | [8 empty] | 0
Schedule 18 | 22.2 | [8 empty] | 0
Schedule 18 | 22.3 | [8 empty] | 0
Schedule 18 | 22.4 | [8 empty] | 0
Schedule 18 | 23 | [8 empty] | 0
Schedule 18 | 23.1 | [8 empty] | 0
Schedule 18 | 23.2 | [8 empty] | 0
Schedule 18 | 23.3 | [8 empty] | 0
Schedule 18 | 23.4 | [8 empty] | 0
Schedule 18 | 23.5 | [8 empty] | 0
Schedule 18 | 24 | [8 empty] | 0
Schedule 18 | 24.1 | [8 empty] | 0
Schedule 18 | 24.2 | [8 empty] | 0
Schedule 18 | 24.3 | [8 empty] | 0
Schedule 18 | 24.4 | [8 empty] | 0
Schedule 18 | 24.5 | [8 empty] | 0
Schedule 18 | 24.6 | [8 empty] | 0
Schedule 18 | 24.7 | [8 empty] | 0
Schedule 18 | 24.8 | [8 empty] | 0
Schedule 18 | 24.9 | [8 empty] | 0
Schedule 18 | 25 | [8 empty] | 0
Schedule 18 | 25.1 | [8 empty] | 0
Schedule 18 | 25.2 | [8 empty] | 0
Schedule 18 | 25.3 | [8 empty] | 0
Schedule 18 | 25.4 | [8 empty] | 0
Schedule 18 | 25.5 | [8 empty] | 0
Schedule 18 | 25.6 | [8 empty] | 0
Schedule 18 | 25.7 | [8 empty] | 0
Schedule 18 | 25.8 | [8 empty] | 0
Schedule 18 | 25.9 | [8 empty] | 0
Schedule 18 | 25.1 | [8 empty] | 0
Schedule 18 | 25.11 | [8 empty] | 0
Schedule 18 | 25.12 | [8 empty] | 0
Schedule 18 | 25.13 | [8 empty] | 0
Schedule 18 | 25.14 | [8 empty] | 0
Schedule 18 | 25.15 | [8 empty] | 0
Schedule 18 | 25.16 | [8 empty] | 0
Schedule 18 | 25.17 | [8 empty] | 0
Schedule 18 | 25.18 | [8 empty] | 0
Schedule 18 | 25.19 | [8 empty] | 0
Schedule 18 | 26 | [8 empty] | 0
Schedule 18 | 26.1 | [8 empty] | 0
Schedule 18 | 26.2 | [8 empty] | 0
Schedule 18 | 26.3 | [8 empty] | 0
Schedule 18 | 26.4 | [8 empty] | 0
Schedule 18 | 26.5 | [8 empty] | 0
Schedule 18 | 26.6 | [8 empty] | 0
Schedule 18 | 26.7 | [8 empty] | 0
Schedule 18 | 26.8 | [8 empty] | 0
Schedule 18 | 26.9 | [8 empty] | 0
Schedule 18 | 26.1 | [8 empty] | 0
Schedule 18 | 26.11 | [8 empty] | 0
Schedule 18 | 27 | [8 empty] | 0
Schedule 18 | 27.1 | [8 empty] | 0
Schedule 18 | 27.2 | [8 empty] | 0
Schedule 18 | 27.3 | [8 empty] | 0
Schedule 18 | 27.4 | [8 empty] | 0
Schedule 18 | 28 | [8 empty] | 0
Schedule 18 | 28.1 | [8 empty] | 0
Schedule 18 | 28.2 | [8 empty] | 0
Schedule 18 | 29 | [8 empty] | 0
Schedule 18 | 29.1 | [8 empty] | 0
Schedule 18 | 29.2 | [8 empty] | 0
Schedule 18 | 29.3 | [8 empty] | 0
Schedule 18 | 29.4 | [8 empty] | 0
Schedule 18 | 30 | [8 empty] | 0
Schedule 18 | 30.1 | [8 empty] | 0
Schedule 18 | 30.2 | [8 empty] | 0
Schedule 18 | 30.3 | [8 empty] | 0
Schedule 18 | 30.4 | [8 empty] | 0
Schedule 18 | 30.5 | [8 empty] | 0
Schedule 18 | 30.6 | [8 empty] | 0
Schedule 18 | 30.7 | [8 empty] | 0
Schedule 18 | 30.8 | [8 empty] | 0
Schedule 18 | 30.9 | [8 empty] | 0
Schedule 18 | 30.1 | [8 empty] | 0
Schedule 18 | 30.11 | [8 empty] | 0
Schedule 18: Annex 1 | 1 | [8 empty] | 0
Schedule 18: Annex 1 | 1.1 | [8 empty] | 0
Schedule 18: Annex 1 | 2 | [8 empty] | 0
Schedule 18: Annex 1 | 2.1 | [8 empty] | 0
Schedule 18: Annex 1 | 2.2 | [8 empty] | 0
Schedule 18: Annex 1 | 2.3 | [8 empty] | 0
Schedule 18: Annex 1 | 2.4 | [8 empty] | 0
Schedule 18: Annex 1 | 2.5 | [8 empty] | 0
Schedule 18: Annex 1 | 3 | [8 empty] | 0
Schedule 18: Annex 1 | Definitions | [8 empty] | 0
Schedule 18: Annex 1 | 4 | [8 empty] | 0
Schedule 18: Annex 1 | 4.1 | [8 empty] | 0
Schedule 18: Annex 1 | 4.2 | [8 empty] | 0
Schedule 18: Annex 1 | 4.3 | [8 empty] | 0
Schedule 18: Annex 1 | 4.4 | [8 empty] | 0
Schedule 18: Annex 1 | 4.5 | [8 empty] | 0
Schedule 18: Annex 1 | 4.6 | [8 empty] | 0
Schedule 18: Annex 1 | 4.7 | [8 empty] | 0
Schedule 18: Annex 1 | 4.8 | [8 empty] | 0
Schedule 18: Annex 1 | 4.9 | [8 empty] | 0
Schedule 18: Annex 1 | 5 | [8 empty] | 0
Schedule 18: Annex 1 | 5.1 | [8 empty] | 0
Schedule 18: Annex 1 | 5.2 | [8 empty] | 0
Schedule 18: Annex 1 | 5.3 | [8 empty] | 0
Schedule 18: Annex 1 | 5.4 | [8 empty] | 0
Schedule 18: Annex 1 | 5.5 | [8 empty] | 0
Schedule 18: Annex 1 | 5.6 | [8 empty] | 0
Schedule 18: Annex 1 | 5.7 | [8 empty] | 0
Schedule 18: Annex 1 | 5.8 | [8 empty] | 0
Schedule 18: Annex 1 | 5.9 | [8 empty] | 0
Schedule 18: Annex 1 | 5.1 | [8 empty] | 0
Schedule 18: Annex 1 | 5.11 | [8 empty] | 0
Schedule 18: Annex 1 | 5.12 | [8 empty] | 0
Schedule 18: Annex 1 | 5.13 | [8 empty] | 0
Schedule 18: Annex 1 | 5.14 | [8 empty] | 0
Schedule 18: Annex 1 | 5.15 | [8 empty] | 0
Schedule 18: Annex 1 | 5.16 | [8 empty] | 0
Schedule 18: Annex 1 | 5.17 | [8 empty] | 0
Schedule 18: Annex 1 | 5.18 | [8 empty] | 0
Schedule 18: Annex 1 | 5.19 | [8 empty] | 0
Schedule 18: Annex 1 | 5.2 | [8 empty] | 0
Schedule 18: Annex 1 | 5.21 | [8 empty] | 0
Schedule 18: Annex 1 | 5.22 | [8 empty] | 0
Schedule 18: Annex 1 | 5.23 | [8 empty] | 0
Schedule 18: Annex 1 | 5.24 | [8 empty] | 0
Schedule 18: Annex 1 | 5.25 | [8 empty] | 0
Schedule 18: Annex 1 | 5.26 | [8 empty] | 0
Schedule 18: Annex 1 | 5.27 | [8 empty] | 0
Schedule 18: Annex 1 | 5.28 | [8 empty] | 0
Schedule 18: Annex 1 | 5.29 | [8 empty] | 0
Schedule 18: Annex 1 | 5.3 | [8 empty] | 0
Schedule 18: Annex 1 | 5.31 | [8 empty] | 0
Schedule 18: Annex 1 | 5.32 | [8 empty] | 0
Schedule 18: Annex 1 | 5.33 | [8 empty] | 0
Schedule 18: Annex 1 | 5.34 | [8 empty] | 0
Schedule 18: Annex 1 | 5.35 | [8 empty] | 0
Schedule 18: Annex 1 | 5.36 | [8 empty] | 0
Schedule 18: Annex 1 | 5.37 | [8 empty] | 0
Schedule 18: Annex 1 | 5.38 | [8 empty] | 0
Schedule 18: Annex 1 | 5.39 | [8 empty] | 0
Schedule 18: Annex 1 | 5.4 | [8 empty] | 0
Schedule 18: Annex 1 | 5.41 | [8 empty] | 0
Schedule 18: Annex 1 | 5.42 | [8 empty] | 0
Schedule 18: Annex 1 | 6 | [8 empty] | 0
Schedule 18: Annex 1 | 6.1 | [8 empty] | 0
Schedule 18: Annex 1 | 6.2 | [8 empty] | 0
Schedule 18: Annex 1 | 6.3 | [8 empty] | 0
Schedule 18: Annex 1 | 6.4 | [8 empty] | 0
Schedule 18: Annex 1 | 6.5 | [8 empty] | 0
Schedule 18: Annex 1 | 6.6 | [8 empty] | 0
Schedule 18: Annex 1 | 6.7 | [8 empty] | 0
Schedule 18: Annex 1 | 6.8 | [8 empty] | 0
Schedule 18: Annex 1 | 6.9 | [8 empty] | 0
Schedule 18: Annex 1 | 6.1 | [8 empty] | 0
Schedule 18: Annex 1 | 6.11 | [8 empty] | 0
Schedule 18: Annex 1 | 6.12 | [8 empty] | 0
Schedule 18: Annex 1 | 6.13 | [8 empty] | 0
Schedule 18: Annex 1 | 6.14 | [8 empty] | 0
Schedule 18: Annex 1 | 6.15 | [8 empty] | 0
Schedule 18: Annex 1 | 6.16 | [8 empty] | 0
Schedule 18: Annex 1 | 6.17 | [8 empty] | 0
Schedule 18: Annex 1 | 6.18 | [8 empty] | 0
Schedule 18: Annex 1 | 6.19 | [8 empty] | 0
Schedule 18: Annex 1 | 6.2 | [8 empty] | 0
Schedule 18: Annex 1 | 6.21 | [8 empty] | 0
Schedule 18: Annex 1 | 6.22 | [8 empty] | 0
Schedule 18: Annex 1 | 6.23 | [8 empty] | 0
Schedule 18: Annex 1 | 6.24 | [8 empty] | 0
Schedule 18: Annex 1 | 6.25 | [8 empty] | 0
Schedule 18: Annex 1 | 6.26 | [8 empty] | 0
Schedule 18: Annex 1 | 6.27 | [8 empty] | 0
Schedule 18: Annex 1 | 6.28 | [8 empty] | 0
Schedule 18: Annex 1 | 6.29 | [8 empty] | 0
Schedule 18: Annex 1 | 6.3 | [8 empty] | 0
Schedule 18: Annex 1 | 6.31 | [8 empty] | 0
Schedule 18: Annex 1 | 6.32 | [8 empty] | 0
Schedule 18: Annex 1 | 6.33 | [8 empty] | 0
Schedule 18: Annex 1 | 6.34 | [8 empty] | 0
Schedule 18: Annex 1 | 7 | [8 empty] | 0
Schedule 18: Annex 1 | 7.1 | [8 empty] | 0
Schedule 18: Annex 1 | 7.2 | [8 empty] | 0
Schedule 18: Annex 1 | 7.3 | [8 empty] | 0
Schedule 18: Annex 1 | 7.4 | [8 empty] | 0
Schedule 18: Annex 1 | 7.5 | [8 empty] | 0
Schedule 18: Annex 1 | 8 | [8 empty] | 0
Schedule 18: Annex 1 | 8.1 | [8 empty] | 0
Schedule 18: Annex 1 | 8.2 | [8 empty] | 0
Schedule 18: Annex 1 | 8.3 | [8 empty] | 0
Schedule 18: Annex 1 | 8.4 | [8 empty] | 0
Schedule 18: Annex 1 | 8.5 | [8 empty] | 0
Schedule 18: Annex 1 | 8.6 | [8 empty] | 0
Schedule 18: Annex 1 | 8.7 | [8 empty] | 0
Schedule 18: Annex 1 | 8.8 | [8 empty] | 0
Schedule 18: Annex 1 | 8.9 | [8 empty] | 0
Schedule 18: Annex 1 | 8.1 | [8 empty] | 0
Schedule 18: Annex 1 | 8.11 | [8 empty] | 0
Schedule 18: Annex 1 | 8.12 | [8 empty] | 0
Schedule 18: Annex 1 | 8.13 | [8 empty] | 0
Schedule 18: Annex 1 | 8.14 | [8 empty] | 0
Schedule 18: Annex 1 | 8.15 | [8 empty] | 0
Schedule 18: Annex 1 | 8.16 | [8 empty] | 0
Schedule 18: Annex 1 | 8.17 | [8 empty] | 0
Schedule 18: Annex 1 | 8.18 | [8 empty] | 0
Schedule 18: Annex 1 | 8.19 | [8 empty] | 0
Schedule 18: Annex 1 | 8.2 | [8 empty] | 0
Schedule 18: Annex 1 | 8.21 | [8 empty] | 0
Schedule 18: Annex 1 | Attachment 1 | [8 empty] | 0
Schedule 18: Annex 1 | Attachment 2 | [8 empty] | 0
Schedule 18: Annex 1 | Attachment 3 | [8 empty] | 0
Schedule 18: Annex 2 | Annex 2 | [8 empty] | 0
0
Schedule 20 | Introduction |  |  | YES | [5 empty] | 1
Schedule 20 | 1.1 |  |  | YES | [5 empty] | 1
Schedule 20 | 2.1 |  |  | YES | [5 empty] | 1
Schedule 20 | 3.1 |  |  | YES | [5 empty] | 1
Schedule 20 | 3.2 |  |  | YES | [5 empty] | 1
0
Schedule 29 | Introduction | [8 empty] | 0
Schedule 29 | 1 | [8 empty] | 0
Schedule 29 | 1A | [8 empty] | 0
Schedule 29 | 2 | [8 empty] | 0
Schedule 29 | 3 | [8 empty] | 0
Schedule 29 | 4 | [8 empty] | 0
Schedule 29 | 5 | [8 empty] | 0
Schedule 29 | 6 | [8 empty] | 0
Schedule 29 | 7 | [8 empty] | 0
Schedule 29 | 8 | [8 empty] | 0
Schedule 29 | 9 | [8 empty] | 0
Schedule 29 | 10 | [8 empty] | 0
Schedule 29 | 11 | [8 empty] | 0
Schedule 29 | 11A | [8 empty] | 0
Schedule 29 | 12 | [8 empty] | 0
Schedule 29 | 13 | [8 empty] | 0
Schedule 29 | 14 | [8 empty] | 0
Schedule 29 | 15 | [8 empty] | 0
Schedule 29 | 16 | [8 empty] | 0
Schedule 29 | 17 | [8 empty] | 0
Schedule 29 | 18 | [8 empty] | 0
Schedule 29 | 19 | [8 empty] | 0
Schedule 29 | 20 | [8 empty] | 0
Schedule 29 | 21 | [8 empty] | 0
Schedule 29 | 22 | [8 empty] | 0
Schedule 29 | 23 | [8 empty] | 0
Schedule 29 | 24 | [8 empty] | 0
Schedule 29 | 25 | [8 empty] | 0
Schedule 29 | 26 | [8 empty] | 0
Schedule 29 | 27 | [8 empty] | 0
Schedule 29 | 28 | [8 empty] | 0
Schedule 29 | 29 | [8 empty] | 0
Schedule 29 | 30 | [8 empty] | 0
Schedule 29 | 31 | [8 empty] | 0
Schedule 29 | 32 | [8 empty] | 0
Schedule 29 | 33 | [8 empty] | 0
Schedule 29 | 34 | [8 empty] | 0
Schedule 29 | 35 | [8 empty] | 0
Schedule 29 | 36 | [8 empty] | 0
Schedule 29 | 37 | [8 empty] | 0
Schedule 29 | 38 | [8 empty] | 0
Schedule 29 | 39 | [8 empty] | 0
Schedule 29 | 40 | [8 empty] | 0
Schedule 29 | 41 | [8 empty] | 0
Schedule 29 | 42 | [8 empty] | 0
Schedule 29 | 43 | [8 empty] | 0
Schedule 29 | 44 | [8 empty] | 0
Schedule 29 | 45 | [8 empty] | 0
Schedule 29 | 46 | [8 empty] | 0
Schedule 29 | 46A | [8 empty] | 0
Schedule 29 | 47 | [8 empty] | 0
0
Schedule 32 | 1 | [8 empty] | 0
Schedule 32 | 1.1 | [8 empty] | 0
Schedule 32 | 1.2 | [8 empty] | 0
Schedule 32 | 1.2A | [8 empty] | 0
Schedule 32 | 1.3 | [8 empty] | 0
Schedule 32 | 1.4 | [8 empty] | 0
Schedule 32 | 1.5 | [8 empty] | 0
Schedule 32 | 1.6 | [8 empty] | 0
Schedule 32 | 1.7 | [8 empty] | 0
Schedule 32 | 1.8 | [5 empty] | YES |  |  | 1
Schedule 32 | 1.9 | [8 empty] | 0
Schedule 32 | 1.10 | [5 empty] | YES |  |  | 1
Schedule 32 | 2 | [8 empty] | 0
Schedule 32 | 2.1 | [8 empty] | 0
Schedule 32 | 2.2 | [8 empty] | 0
Schedule 32 | 2.3 | [8 empty] | 0
Schedule 32 | 2.4 | [8 empty] | 0
Schedule 32 | 2.5 | [8 empty] | 0
Schedule 32 | 3 | [8 empty] | 0
Schedule 32 | 3.1 | [5 empty] | YES |  |  | 1
Schedule 32 | 3.2 | [8 empty] | 0
Schedule 32 | 3.3 | [8 empty] | 0
Schedule 32 | 3.4 | [8 empty] | 0
Schedule 32 | 3.5 | [8 empty] | 0
Schedule 32 | 3.6 | [8 empty] | 0
Schedule 32 | 4 | [8 empty] | 0
Schedule 32 | 4.1 | [5 empty] | YES |  |  | 1
Schedule 32 | 4.2 | [5 empty] | YES |  |  | 1
Schedule 32 | 4.2A | [5 empty] | YES |  |  | 1
Schedule 32 | 4.3 | [8 empty] | 0
Schedule 32 | 4.4 | [8 empty] | 0
Schedule 32 | 4.5 | [5 empty] | YES |  |  | 1
Schedule 32 | 4.6 | [8 empty] | 0
Schedule 32 | 5 | [8 empty] | 0
Schedule 32 | 5.1 | [8 empty] | 0
Schedule 32 | 5.2 | [8 empty] | 0
Schedule 32 | 5.3 | [8 empty] | 0
Schedule 32 | 5A. | [5 empty] | YES |  |  | 1
Schedule 32 | 5A.1 | [8 empty] | 0
Schedule 32 | 5A.1A | [8 empty] | 0
Schedule 32 | 5A.2 | [8 empty] | 0
Schedule 32 | 6 | [8 empty] | 0
Schedule 32 | 6.1 | [6 empty] | YES |  | 1
Schedule 32 | 6.2 | [6 empty] | YES |  | 1
Schedule 32 | 6.3 | [5 empty] | YES |  |  | 1
Schedule 32 | 6.4 | [8 empty] | 0
Schedule 32 | 6.4A | [8 empty] | 0
Schedule 32 | 6.5 | [5 empty] | YES |  |  | 1
Schedule 32 | 6.6 | [8 empty] | 0
Schedule 32 | 6.7 | [8 empty] | 0
Schedule 32 | 6.8 | [8 empty] | 0
Schedule 32 | 6.9 | [8 empty] | 0
Schedule 32 | 6.10 | [8 empty] | 0
Schedule 32 | 6.11 | [8 empty] | 0
Schedule 32 | 7 | [8 empty] | 0
Schedule 32 | 7.1 | [8 empty] | 0
Schedule 32 | 7.2 | [8 empty] | 0
Schedule 32 | 7.3 | [8 empty] | 0
Schedule 32 | 7.4 | [8 empty] | 0
Schedule 32 | 7.5 | [8 empty] | 0
Schedule 32 | 7.6 | [8 empty] | 0
Schedule 32 | 7.7 | [8 empty] | 0
Schedule 32 | 7.8 | [8 empty] | 0
Schedule 32 | 7.9 | [8 empty] | 0
Schedule 32 | 7.1 | [8 empty] | 0
Schedule 32 | 7.11 | [8 empty] | 0
Schedule 32 | 7.12 | [8 empty] | 0
Schedule 32 | 7.13 | [8 empty] | 0
Schedule 32 | 7.14 | [8 empty] | 0
Schedule 32 | 7.15 | [8 empty] | 0
Schedule 32 | 7.16 | [8 empty] | 0
Schedule 32 | 7.17 | [8 empty] | 0
Schedule 32 | 8 | [8 empty] | 0
Schedule 32 | 8.1 | [8 empty] | 0
Schedule 31 | 8.2 | [8 empty] | 0
Schedule 32 | Definitions | [5 empty] | YES | YES |  | 2
Charging Methodology CPs Legal Text Overlap Tracker