## CPs
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Current Status | Status Changed in the last month | Date Issued to Ofgem | Original Expected Decision Date | Latest Expected Decision Date
STATUS - INITIAL ASSESSMENT
No
STATUS - DEFINITION
DCP 325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20. | The intent of this Change Proposal is to combine, review and if appropriate, amend the requirements of Section 35A, Section 35B, Schedule 15 and Schedule 20 to improve transparency and efficiency in the data published by DNOs | General | 2 | Richard Colwill / Melissa Kendal | N/A | 2018-11-07 | 11 | No | Next scheduled release following approval | The next DCP 325 Working Group scheduled for 16 September 2024, where the intent is for the Working Group to review a draft consultation document. | DEFINITION | N/A
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | The intent of this modification is to define “Mixed Demand” Sites and apply a proportionate Residual charge where a Site meets the mixed demand definition. | General | 1 | John Lawton / Andy Green | Andrew Malley | 2021-04-14 | 17 | No | TBC | The Working Group met on 02 October to review the need for a BSC change. It was agreed that a BSC change was required and that DCP 388 couldn’t be progressed until the BSC modification had been defined so DCP 388 has been paused until the Proposer raises the required BSC modification. | DEFINITION | N/A
DCP 412 | Discounts from TCR charges for ‘peaky’ final demand customers | This Change Proposal aims to create a discount against the residual charge for ‘peaky’ customers, removing the disproportionate impact of allocating residual charges on the basis of the Agreed Supply Capacity. | CDCM / EDCM | 1 | Craig Booth / Richard Colwill | Andrew Malley | 2022-10-11 | 35 | No | TBC | The DCP 412 Working Group is due to meet on 02 October, where they will review a draft of the Change Report which is expected to be issued to the Panel in October. | DEFINITION | N/A
DCP 415 | Replacement of D0242/D0315 for MHHS | To create a new DCUSA owned DIP data message for supercustomer billing statements using MHHS data. | Billing | 2 | Hannah Proffitt / Craig Booth | N/A | 10/22/2022 | 3 | No | TBC (dependent on date required for DIP testing) | The Change Report was submitted to the Panel for review in the February 2023 Panel meeting. The Panel agreed that it would not progress to Party voting and that it should be sent back to the Working Group but that the Working Group won’t need to meet until the MHHS Programme have been able to carry out an Impact Assessment for the solution they developed. It was noted that even then, no further work may be required but that it was too early to know that for sure. | DEFINITION | N/A
DCP 416 | Electronic Invoicing Post MHHS | To create a new DCUSA owned DIP data message for electronic Distributor billing post MHHS. | Billing | 2 | Melissa Kendal / Andy Green | N/A | 2022-11-14 | 5 | No | TBC (dependent on date required for DIP testing) | The Working Group have reviewed the consultation responses and met on 23 June 2023 to finalise the conclusions to the second consultation. A decision on whether or not a Change Report is to be produced is to be made by the Panel but the Proposer has initated a MHHS Change Request for the CP to be impact assessed and so it is expected that DCP 416 will be put on hold, pending outcome of the MHHS Change Request. | DEFINITION | N/A
DCP 419 | Pre-Notifications of Planned Supply De-Energisations | This change seeks to ensure that all DCUSA Parties, that de-energise metering equipment as part of any planned work, provide the Distributor with advance notification of the supply interruption. | General | 1 | Alysson Pena / Richard Colwill | TBC | 2023-03-06 | 12 | No | Next scheduled release following approval | The DCP 419 Working Group last met on 14 August 2024 where they considered potential REC impacts and are next due to meet on 25 September 2024 where the intent is for the Working Group to review potential solutions. | DEFINITION | N/A
DCP 420 | Include Car Charging Stations In The Definition For Non Final Demand | This change proposal aims to expand the definition of Non Final Demand to include Non Domestic sites which are solely for the use of charging vehicles where electricity is sold with a commercial transaction to a private user. These are to include e.g. Council run services, electric charging stations at car parks and service stations or petrol forecourts but are not to include private fleet charging stations. This is a temporary fix to be put in place until the charging stations included are commercially viable. | General | 1 | Craig Booth / Richard Colwill | TBC | 2023-03-29 | 10 | No | TBC | The DCP 420 Working Group is due to meet on 17 September 2024 with the intent being to review and finalise the consultation document. | DEFINITION | N/A
DCP 423 | LDNO Discounts for negative scaling | The purpose of this change proposal is to set a floor on the LDNO discount applied to negative tariff components, after scaling, for demand tariffs. The intent of this change proposal is to seek to remedy what the proposer believes is an unintended outcome of the implementation of Ofgem’s Targeted Charging Review where LDNO tariffs can be higher than the equivalent all-the-way tariff i.e. the LDNO margin is negative for that component. | CDCM | 1 | Melissa Kendal / Andy Green | TBC | 2023-05-09 | 4 | No | 2025-04-01 | The DCP 423 Working Group will meet again on 25 September 2024 where they will review the previous modeling work following feedback from the consultation which identified a potential flaw. | DEFINITION | N/A
DCP 424 | Use of System charging for complex sites | This change proposal enables the correct DUoS to be paid by meters that are class F or G within a Class 5 or Class 6 Complex Site as described in BSC Modification P441 (where netting of Import and Export takes place for BSC Settlement purposes) in a practical manner. Under p441 where generation and demand are netted before settlement, the gross values must be added to the D0036 or D0275 to ensure the correct DUoS is charged. However, for class F and G the MPAN counts are included on the D0030 data flows but the volumes are zero. In order for the volumes to be correctly charged DUoS it is proposed that these volumes are included in the D0036 or D0275 using a pseudo MPAN for the gross value. | CDCM | 1 | Andy Green / Craig Booth | TBC | 2023-05-10 | 6 | No | Aligned to BSC Mod P441 Implementation Date | DCP 424 has been delayed due a request by Ofgem for further impact analysis on the proposed BSC solution (P441 - Creation of Complex Site Classes). The DCP 424 consultation is now estimated to be released in Q3 2024. | DEFINITION | N/A
DCP 442 | Aligning enduring flexible connections | The intent of this Change Proposal is to align (and clarify) the two approaches that currently may result in a flexible connection being provided on an enduring basis. A flexible connection on an enduring basis is an arrangement that allows a Customer’s import/export of electricity via a connection to be restricted by a DNO/IDNO Party in perpetuity. This CP proposes that such a connection shall be a Flexible Connection rather than a Curtailable Connection. | General | 1 | Melissa Kendall / Craig Booth | TBC | 2024-07-01 | 1 | No | 2025-04-01 | The DCP 442 Working Group have met once and are currently reviewing potential solutions. They are next due to meet on 12 September 2024, where they will discuss the solution options and consider next steps. | DEFINITION | N/A
DCP 443 | Excess Capacity | The purpose of this Change Proposal is to drive the correct customer behaviour regarding exceeding capacity. | CDCM / EDCM | 1 | Melissa Kendal / Andy Green | TBC | 2024-07-09 | 3 | No | 2026-04-01 | The DCP 443 Working Group have met three times and have developed a consultation document which is scheduled to be issued on 13 September for a period of 3 weeks. The Working Group is scheduled to meet again on 14 October 2024 to review the consultation responses. | DEFINITION | N/A
STATUS - CHANGE REPORT
DCP 437 | To Shorten the DUoS Pricing Notice Periods | This change proposal aims to shorten the DUoS Pricing Notice Periods so there is longer period between the publication of the PCFM where OFGEM have the option to make changes to our allowed revenue at short notice and the setting of the prices | CDCM | 1 | Hannah Proffitt / Richard Colwill | TBC | 2024-02-13 | 4 | No | 1 Working Day following approval | The DCP 437 Working Group met on 03 September 2024, where they reviewed the draft Change Report and proposed legal drafting. The DCP 437 Change Report is being issued to the September Panel meeting. | CHANGE REPORT | CHANGE REPORT
DCP 440 | Consuming “de-energised” sites | To ensure all consuming “de-energised” sites are charged DUoS. | CDCM | 1 | Hannah Proffitt / Richard Colwill | TBC | 2024-03-14 | 5 | No | 2026-04-01 | The DCP 440 Working Group last met on 29 July, where they reviewed the consultation responses and legal drafting. Further data had been requested from Elexon and this has now been received and therefore the Working Group are intending on issuing the Change Report to the September Panel meeting. | CHANGE REPORT | CHANGE REPORT
STATUS - VOTING
DCP 421 | Update the Tables in schedule 15 of DCUSA | To amend the current tables within Schedule 15 of DCUSA to correctly represent ED2 revenue. | General | 2 | Hannah Proffitt / Andy Green | N/A | 2023-04-12 | 10 | No | Next scheduled release following approval | The DCP 421 Change Report was issued to the August Panel meeeting for approval to progress to voting. During their meeting, the Panel requested for some amendments to be made and agreed to consider the the Change Report ex-committee. Approval was subsequently obtained via email and the Change Report was issued for voting for a period of 15 Working Days. | VOTING | VOTING
DCP 439 | Backdating Tariff Changes | This change proposal seeks to add a sensible backstop to backdating. | CDCM | 1 | Hannah Proffitt / Andy Green | TBC | 2024-03-14 | 4 | No | 2025-04-01 | The DCP 439 Change Report was issued to the August Panel meeeting for approval to progress to voting. During their meeting, the Panel requested for some amendments to be made and agreed to consider the the Change Report ex-committee. Approval was subsequently obtained via email and the Change Report was issued for voting for a period of 15 Working Days. | VOTING | VOTING
STATUS - AWAITING AUTHORITY CONSENT
DCP 425 | Cost Apportionment Factor “cap” Methodology | The intent of this Change Proposal (“CP”) is to provide further clarification as to how costs of Reinforcement are apportioned between the Company and the Customer (a Generation Connection) when the High-Cost Project Threshold is triggered. | General | 1 | Richard Colwill/ Craig Booth | TBC | 2023-07-13 | 5 | No | 2023-12-19 | The Change Report was issued for voting following the March Panel meeting for a period of three weeks. The outcome of the Party voting was a recommendation that Ofgem Accept DCP 425 and the Change Declaration was issued to Authority for approval. | AWAITING AUTHORITY CONSENT | N/A
DCP 417 | Ability for the DCUSA Secretariat to Raise Change Proposals | This change seeks to grant the ability to the Secretariat to raise Change Proposals where it identifies a change that would better facilitate the DCUSA Objectives and to introduce an obligation for the Secretariat to raise Change Proposals in certain circumstances, such as at the direction of the Authority. | General | 1 | Melissa Kendal / Richard Colwill | Nadir Hafeez | 2022-12-14 | 12 | No | Next scheduled release following approval | The Working Group met on 23 April, with a representative from Gowling WLG in attendance, in order to finalise the legal text. The legal text was agreed with the legal representative from Gowling WLG. The Change Report presented to the Panel during their May 2024 meeting, where it was approved and was subsequently issued for voting following the May Panel meeting for a period of 15 Working Days. The outcome of the Party voting was a recommendation that Ofgem Accept DCP 417 and the Change Declaration was issued to Authority for approval on 11 June 2024. | AWAITING AUTHORITY CONSENT | N/A
DCP 433 | Limitation for backdating of rebates/charges under Schedule 32 | The intent of this Change Proposal is to amend Schedule 32 to ensure that processes which may result in the backdating of rebates/charges are reflective of the limitations within the current industry arrangements. | General | 1 | Craig Booth | TBC | 2024-01-05 | 5 | No | 2024-06-27 | The Change Report was presented to the Panel during their May 2024 meeting, where it was approved and was subsequently issued for voting following the May Panel meeting for a period of 15 Working Days. The outcome of the Party voting was a recommendation that Ofgem Accept DCP 433 and the Change Declaration was issued to Authority for approval on 10 June 2024. | AWAITING AUTHORITY CONSENT | N/A
DCP 438 | Rate of Return Change Proposal | This change proposal aims to update the rate of return as the previous legal text is out of date | CDCM | 1 | Hannah Proffitt / Craig Booth | TBC | 2024-02-27 | 2 | No | 2025-04-01 | The Working Group met in April and agreed to issue a consultation for DCP 438. The consultation was issued on 07 May, with responses due by 29 May 2024. The second Working Group meeting was held on 04 June 2024 to review responses and the draft Change Report. The Change Report was issued to the Panel during the June Panel meeting, where it was approved to be issued for Party voting. | AWAITING AUTHORITY CONSENT | N/A
DCP 441 | Proposal to increase the number of allowed Change Report alternative variations from two to three | This Change Proposal seeks to change the number of alternative variations that can be added by the Panel to a Change Report from two to three. | General | 1 | Alysson Pena | N/A | 2024-01-05 | 2 | No | 2024-06-27 | DCP 441 was submitted to the Panel for Initial Assessment during their May meeting. The Panel approved for DCP 441 to progress to the Change Report Phase. The Change Report was issued to the Panel during the June Panel meeting, where it was approved to be issued for Party voting. | AWAITING AUTHORITY CONSENT | N/A
STATUS - AWAITING IMPLEMENTATION
2024-11-07
DCP 435 | Party Novation Process | To add a process within DCUSA to enable a Party to transfer its rights and obligations to another Party via a novation agreement. | General | 1 | Craig Booth | N/A | 2024-02-09 | 0 | No | Next release after approval. | The Change Report was issued for voting following the March Panel meeting for a period of three weeks. The outcome of the Party voting was a recommendation that Ofgem Accept DCP 435 and the Change Declaration was issued to Authority for approval. | AWAITING IMPLEMENTATION | N/A
2025-04-01
DCP 428 | Zero REP-002/A Data | To specify how parties should deal with zero or blank data in the supercustomer/aggregated billing messages when sending daily statements or raising invoices. | General | 2 | Richard Colwill/ Alysson Peña | TBC | 2023-07-25 | 4 | No | 2025-04-01 | The DCP 428 Working Group finalised their review of the legal text to confirm it was fit for purpose and the Change Report was approved by the Panel ex-committee and subsequently issued for voting on 10 April 2024. The outcome of the Party voting was to Accept DCP 428 and therefore the change will be implemented. | AWAITING IMPLEMENTATION | N/A
STATUS - SENT BACK
N/A | N/A | [7 empty] | No |  |  |  | N/A
STATUS - IMPLEMENTED
N/A
STATUS - REJECTED
N/A | N/A | [7 empty] | No |  |  |  | N/A
STATUS - WITHDRAWN
N/A | N/A | [7 empty] | No |  |  |  | N/A
Change Register - September 2024

## Status Changes
[14 empty] | AWAITING IMPLEMENTATION | 2
[14 empty] | IMPLEMENTED | 0
[14 empty] | REJECTED | 0
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status | Status Changed in the last month | DEFINITION | 11
DCP 437 | To Shorten the DUoS Pricing Notice Periods | This change proposal aims to shorten the DUoS Pricing Notice Periods so there is longer period between the publication of the PCFM where OFGEM have the option to make changes to our allowed revenue at short notice and the setting of the prices | CDCM | 1 | Hannah Proffitt / Richard Colwill | TBC | 2024-02-13 | 4 | No | 1 Working Day following approval | The DCP 437 Working Group met on 03 September 2024, where they reviewed the draft Change Report and proposed legal drafting. The DCP 437 Change Report is being issued to the September Panel meeting. | CHANGE REPORT | CHANGE REPORT | CONSULTATION | 0
DCP 440 | Consuming “de-energised” sites | To ensure all consuming “de-energised” sites are charged DUoS. | CDCM | 1 | Hannah Proffitt / Richard Colwill | TBC | 2024-03-14 | 5 | No | 2026-04-01 | The DCP 440 Working Group last met on 29 July, where they reviewed the consultation responses and legal drafting. Further data had been requested from Elexon and this has now been received and therefore the Working Group are intending on issuing the Change Report to the September Panel meeting. | CHANGE REPORT | CHANGE REPORT | AWAITING AUTHORITY CONSENT | 5
DCP 421 | Update the Tables in schedule 15 of DCUSA | To amend the current tables within Schedule 15 of DCUSA to correctly represent ED2 revenue. | General | 2 | Hannah Proffitt / Andy Green | N/A | 2023-04-12 | 10 | No | Next scheduled release following approval | The DCP 421 Change Report was issued to the August Panel meeeting for approval to progress to voting. During their meeting, the Panel requested for some amendments to be made and agreed to consider the the Change Report ex-committee. Approval was subsequently obtained via email and the Change Report was issued for voting for a period of 15 Working Days. | VOTING | VOTING | AWAITING IMPLEMENTATION | 2
DCP 439 | Backdating Tariff Changes | This change proposal seeks to add a sensible backstop to backdating. | CDCM | 1 | Hannah Proffitt / Andy Green | TBC | 2024-03-14 | 4 | No | 2025-04-01 | The DCP 439 Change Report was issued to the August Panel meeeting for approval to progress to voting. During their meeting, the Panel requested for some amendments to be made and agreed to consider the the Change Report ex-committee. Approval was subsequently obtained via email and the Change Report was issued for voting for a period of 15 Working Days. | VOTING | VOTING | VOTING | 2
[14 empty] | CHANGE REPORT | 2
24
Status Change - September 2024

## Timetables
DCP | Title | Part 1/ Part 2 Matter | Standard/ Urgent | Proposer | Party | Technical Secretariat | Chair | Timetable Change | [6 empty] | Notes
[9 empty] | Sep | Oct | Nov | Dec | Jan | Feb
443 | Excess Capacity | Part 1 | Standard | Peter Waymont | UKPN | Melissa Kendall | Andy Green | N | CON | DEF | DEF | DEF | CR
442 | Aligning enduring flexible connections | Part 1 | Standard | Lee Wells | NPg | Melissa Kendall | Craig Booth | N | DEF | CON | DEF | CR
440 | Consuming “de-energised” sites | Part 1 | Standard | Peter Waymont | UKPN | Hannah Proffitt | Andy Green | N | CR
437 | To Shorten the DUoS Pricing Notice Periods | Part 1 | Standard | Dave Wornell | NGED | Hannah Proffitt | Richard Colwill | N | CR
424 | Use of System charging for complex sites | Part 1 | Standard | Mary Gillie | NPg | Craig Booth | Andy Green | N | O/H
423 | LDNO Discounts for negative scaling | Part 1 | Standard | Tom Cadge | ENC | Melissa Kendall | Andy Green | Y | CR
New timetable | [8 empty] | DEF | DEF | CR |  |  |  | Currently reviewing modelling and aim to issue Change Report in November.
420 | Include Car Charging Stations In The Definition For Non Final Demand | Part 1 | Standard | Dave Wornell | NGED | Craig Booth | Richard Colwill | Y | DEF | CR
New timetable | [8 empty] | CON 2 | DEF | CR |  |  |  | Consultation originally planned for August
419 | Pre-notification of Planned Supply De-energisations | Part 1 | Standard | Nikhel Jethwa | SSEN | Alysson Peña | Richard Colwill | Y | DEF | CR
New timetable | [8 empty] | DEF | DEF | DEF | CR |  |  | Exploring potential solution with DCC and need to understand REC impacts.
416 | Electronic Invoicing Post MHHS | Part 2 | Standard | Peter Waymont | UKPN | Craig Booth | Andy Green | N | O/H
415 | Replacement of D0242/D0315 for MHHS | Part 2 | Standard | Peter Waymont | UKPN | Melissa Kendall | Craig Booth | N | O/H
412 | Discounts from TCR charges for ‘peaky’ final demand customers | Part 1 | Standard | Lee Stone | E.ON | Craig Booth | Richard Colwill | Y | CR
New timetable | [8 empty] | DEF | CR |  |  |  |  | Reviewing of consultation responses required more time than orginally planned for given the number and content of the responses received.
388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | Part 1 | Standard | Lee Stone | E.on | Andy Green | John Lawton | N | O/H
325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20 | Part 1 | Standard | Kara Burke | NPg | Craig Booth | Andy Green | N | CON 2 | DEF | CR
| DEFINITION | DEF
| RFI | RFI
| CONSULTATION | CON/ CON 2
| CHANGE REPORT | CR
| ON HOLD | O/H

## Legal Text Overlap Tracker
YES
|  | MHHS | DCP 424 | DCP 325 | DCP 421 | DCP 423 | DCP 388 | DCP 412 | DCP 420 | DCP 433 | DCP 438 | DCP 439 | DCP 440 | DCP 443
|  | Unknown | 2024-11-21 | Next Scheduled | Next Scheduled | 2025-04-01 | TBC | TBC | 2025-04-01 | 2024-11-07 | 2024-11-07 | 2025-04-01 | 2026-04-01 | TBC |  | NOTES TO ASSIST
Schedules | Paragraph Number |  | Definition | Definition | Definition | Definition | Definition | Definition | Definition | Awaiting Consent | Awaiting Consent | Change Report | Change Report | Definition | Number of CPs Impacting Paragraph
Schedule 15 | Table 1 |  |  | YES | YES | [9 empty] | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 2 |  |  | YES | YES | [9 empty] | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 3 |  |  | YES | YES | [9 empty] | 2 | The WGs for DCP 325 and DCP 421 are aware of the interactions
0
Schedule 16 | Introduction | [13 empty] | 0
Schedule 16 | 1 | [13 empty] | 0
Schedule 16 | 2 | [13 empty] | 0
Schedule 16 | 3 | [13 empty] | 0 | Model reference number and date
Schedule 16 | 4 | [13 empty] | 0
Schedule 16 | 5 | [13 empty] | 0
Schedule 16 | 6 | [13 empty] | 0
Schedule 16 | 7 | [13 empty] | 0
Schedule 16 | 7A | [13 empty] | 0
Schedule 16 | 8 | [13 empty] | 0
Schedule 16 | 9 | [13 empty] | 0
Schedule 16 | 10 | [13 empty] | 0
Schedule 16 | 10A | [13 empty] | 0
Schedule 16 | 11 | [13 empty] | 0
Schedule 16 | 12 | [13 empty] | 0
Schedule 16 | 13 | [13 empty] | 0
Schedule 16 | 14 | [13 empty] | 0
Schedule 16 | 15 | [13 empty] | 0
Schedule 16 | 16 | [13 empty] | 0
Schedule 16 | 17 | [13 empty] | 0
Schedule 16 | 18 | [13 empty] | 0
Schedule 16 | 19 | [13 empty] | 0
Schedule 16 | 20 | [13 empty] | 0
Schedule 16 | 21 | [13 empty] | 0
Schedule 16 | 22 | [13 empty] | 0
Schedule 16 | 23 | [13 empty] | 0
Schedule 16 | 24 | [13 empty] | 0
Schedule 16 | 25 | [13 empty] | 0
Schedule 16 | 26 | [13 empty] | 0
Schedule 16 | 27 | [13 empty] | 0
Schedule 16 | 28 | [13 empty] | 0
Schedule 16 | 29 | [13 empty] | 0
Schedule 16 | 30 | [13 empty] | 0
Schedule 16 | 31 | [13 empty] | 0
Schedule 16 | 32 | [13 empty] | 0
Schedule 16 | 33 | [13 empty] | 0
Schedule 16 | 34 | [13 empty] | 0
Schedule 16 | 35 | [13 empty] | 0
Schedule 16 | 36 | [13 empty] | 0
Schedule 16 | 37 | [13 empty] | 0
Schedule 16 | 38 | [13 empty] | 0
Schedule 16 | 39 | [13 empty] | 0
Schedule 16 | 40 | [13 empty] | 0
Schedule 16 | 41 | [13 empty] | 0
Schedule 16 | 41A | [13 empty] | 0
Schedule 16 | 41B | [13 empty] | 0
Schedule 16 | 42 | [13 empty] | 0
Schedule 16 | 42A | YES | [12 empty] | 1
Schedule 16 | 43 | [13 empty] | 0
Schedule 16 | 44 | YES | [12 empty] | 1
Schedule 16 | 45 | [13 empty] | 0
Schedule 16 | 46 | [13 empty] | 0
Schedule 16 | 47 | [13 empty] | 0
Schedule 16 | 48 | [13 empty] | 0
Schedule 16 | 49 | [13 empty] | 0
Schedule 16 | 50 | [13 empty] | 0
Schedule 16 | 51 | [13 empty] | 0
Schedule 16 | 52 | [13 empty] | 0
Schedule 16 | 52A | [13 empty] | 0
Schedule 16 | 53 | [13 empty] | 0
Schedule 16 | 54 | [13 empty] | 0
Schedule 16 | 55 | [13 empty] | 0
Schedule 16 | 56 | [13 empty] | 0
Schedule 16 | 57 | [13 empty] | 0
Schedule 16 | 58 | [13 empty] | 0
Schedule 16 | 59 | [13 empty] | 0
Schedule 16 | 60 | [13 empty] | 0
Schedule 16 | 61 | [13 empty] | 0
Schedule 16 | 62 | [13 empty] | 0
Schedule 16 | 63 | [13 empty] | 0
Schedule 16 | 64 | [13 empty] | 0
Schedule 16 | 65 | [13 empty] | 0
Schedule 16 | 66 | [13 empty] | 0
Schedule 16 | 67 | [13 empty] | 0
Schedule 16 | 68 | [13 empty] | 0
Schedule 16 | 69 | [13 empty] | 0
Schedule 16 | 70 | YES | [12 empty] | 1
Schedule 16 | 71 | [13 empty] | 0
Schedule 16 | 72 | [13 empty] | 0
Schedule 16 | 72A | [13 empty] | 0
Schedule 16 | 73 | [13 empty] | 0
Schedule 16 | 74 | [13 empty] | 0
Schedule 16 | 75 | [13 empty] | 0
Schedule 16 | 76 | [13 empty] | 0
Schedule 16 | 77 | [13 empty] | 0
Schedule 16 | 78 | [13 empty] | 0
Schedule 16 | 79 | [13 empty] | 0
Schedule 16 | 80 | YES | [12 empty] | 1
Schedule 16 | 81 | [13 empty] | 0
Schedule 16 | 82 | [13 empty] | 0
Schedule 16 | 83 | [13 empty] | 0
Schedule 16 | 84 | [13 empty] | 0
Schedule 16 | 85 | [13 empty] | 0
Schedule 16 | 86 | [13 empty] | 0
Schedule 16 | 87 | [13 empty] | 0
Schedule 16 | 88 | [13 empty] | 0
Schedule 16 | 89 | [13 empty] | 0
Schedule 16 | 90 | [13 empty] | 0
Schedule 16 | 91 | [13 empty] | 0
Schedule 16 | 92 | [13 empty] | 0
Schedule 16 | 92A | [13 empty] | 0
Schedule 16 | 92B | [13 empty] | 0
Schedule 16 | 92C | [13 empty] | 0
Schedule 16 | 93 | [13 empty] | 0
Schedule 16 | 94 | [13 empty] | 0
Schedule 16 | 95 | [13 empty] | 0
Schedule 16 | 96 | [13 empty] | 0
Schedule 16 | 97 | [13 empty] | 0
Schedule 16 | 98 |  |  |  |  | YES | [8 empty] | 1
Schedule 16 | 99 | [13 empty] | 0
Schedule 16 | 100 | [13 empty] | 0
Schedule 16 | 101 | [13 empty] | 0
Schedule 16 | 102 | [13 empty] | 0
Schedule 16 | 102A | [13 empty] | 0
Schedule 16 | 102B | [13 empty] | 0
Schedule 16 | 103 | [13 empty] | 0
Schedule 16 | 104 | [13 empty] | 0
Schedule 16 | 105 | [13 empty] | 0
Schedule 16 | 106 | [13 empty] | 0
Schedule 16 | 107 | [13 empty] | 0
Schedule 16 | 108 | [13 empty] | 0
Schedule 16 | 108A | [13 empty] | 0
Schedule 16 | 109 | [13 empty] | 0
Schedule 16 | 110 | [13 empty] | 0
Schedule 16 | 111 | [13 empty] | 0
Schedule 16 | 112 | [13 empty] | 0
Schedule 16 | 112A | [13 empty] | 0
Schedule 16 | 113 | [13 empty] | 0
Schedule 16 | 113A | [13 empty] | 0
Schedule 16 | 113B | [13 empty] | 0
Schedule 16 | 113C | [13 empty] | 0
Schedule 16 | 113D | [13 empty] | 0
Schedule 16 | 113E | [13 empty] | 0
Schedule 16 | 114 | [13 empty] | 0
Schedule 16 | 115 | [13 empty] | 0
Schedule 16 | 116 | [13 empty] | 0
Schedule 16 | 117 | [13 empty] | 0
Schedule 16 | 118 | [13 empty] | 0
Schedule 16 | 119 | [13 empty] | 0
Schedule 16 | 120 | [13 empty] | 0
Schedule 16 | 121 | [13 empty] | 0
Schedule 16 | 122 | [13 empty] | 0
Schedule 16 | 123 | [13 empty] | 0
Schedule 16 | 124 | [13 empty] | 0
Schedule 16 | 125 | [13 empty] | 0
Schedule 16 | 126 | [13 empty] | 0
Schedule 16 | 127 | [13 empty] | 0
Schedule 16 | 127A | [13 empty] | 0
Schedule 16 | 128 | YES | YES | [11 empty] | 2
Schedule 16 | 129 | YES | [12 empty] | 1
Schedule 16 | 130 | YES | [12 empty] | 1
Schedule 16 | 131 | [13 empty] | 0
Schedule 16 | 132 | YES | [12 empty] | 1
Schedule 16 | 132A | [13 empty] | 0
Schedule 16 | 132B | [13 empty] | 0
Schedule 16 | 132C | YES | [12 empty] | 1
Schedule 16 | 132D | [13 empty] | 0
Schedule 16 | 133 | YES | [12 empty] | 1
Schedule 16 | 134 | [13 empty] | 0
Schedule 16 | 135 | [13 empty] | 0
Schedule 16 | 135A | YES | [12 empty] | 1 | MHHS CP seeks to remove the last column containing applicable Measurement Class
Schedule 16 | 135B | [13 empty] | 0
Schedule 16 | 136 | [13 empty] | 0
Schedule 16 | 137 | [13 empty] | 0
Schedule 16 | 138 | [13 empty] | 0
Schedule 16 | 139 | [13 empty] | 0
Schedule 16 | 140 | [11 empty] | YES |  | 1
Schedule 16 | 140A | YES | [12 empty] | 1
Schedule 16 | 140B | YES | [12 empty] | 1
Schedule 16 | 140C | YES | [12 empty] | 1
Schedule 16 | 140D | [13 empty] | 0
Schedule 16 | 140E | [13 empty] | 0
Schedule 16 | 141 | [13 empty] | 0
Schedule 16 | 142 | YES | [12 empty] | 1
Schedule 16 | 143 | YES | [12 empty] | 1
Schedule 16 | 144 | YES | [12 empty] | 1
Schedule 16 | 145 | [13 empty] | 0
Schedule 16 | 146 | [13 empty] | 0
Schedule 16 | 147 | [13 empty] | 0
Schedule 16 | 148 | [13 empty] | 0
Schedule 16 | 149 | [13 empty] | 0
Schedule 16 | 150 | [13 empty] | 0
Schedule 16 | 151 | [13 empty] | 0
Schedule 16 | 152 | [13 empty] | 0
Schedule 16 | 153 | [12 empty] | YES | 1
Schedule 16 | 154 | [13 empty] | 0
Schedule 16 | 155 | [13 empty] | 0
Schedule 16 | 156 | [13 empty] | 0
Schedule 16 | 157 | [9 empty] | YES |  |  |  | 1
Schedule 16 | 158 | [13 empty] | 0
Schedule 16 | 159 | [13 empty] | 0
Schedule 16 | 160 | [13 empty] | 0
Schedule 16 | 161 | [13 empty] | 0
Schedule 16 | 162 | [13 empty] | 0
Schedule 16 | 163 | [13 empty] | 0
Schedule 16 | 164 | [13 empty] | 0
Schedule 16 | 165 | [13 empty] | 0
Schedule 16 | 166 | [13 empty] | 0
Schedule 16 | 167 | [13 empty] | 0
Schedule 16 | 168 | [13 empty] | 0
Schedule 16 | 169 | [13 empty] | 0
Schedule 16 | 170 | [13 empty] | 0
Schedule 16 | 171 | [13 empty] | 0
Schedule 16 | 172 | [13 empty] | 0
Schedule 16 | 173 | [13 empty] | 0
Schedule 16 | 173A | [10 empty] | YES |  |  | 1 | DCP 439 Introduces new Paragraph 173A
Schedule 16 | 174 | [13 empty] | 0
Schedule 16 | 175 | [13 empty] | 0
Schedule 16 | 176 | [13 empty] | 0
Schedule 16 | 177 | [13 empty] | 0
Schedule 16 | 178 | [13 empty] | 0
Schedule 16 | 179 | [13 empty] | 0
Schedule 16 | 180 | [13 empty] | 0
Schedule 16 | 181 | [13 empty] | 0
Schedule 16 | 182 | [13 empty] | 0
Schedule 16 | 183 | [13 empty] | 0
Schedule 16 | 184 | [13 empty] | 0
Schedule 16 | Glossary | YES | [12 empty] | 1
0
Schedule 17 | Introduction | [13 empty] | 0
Schedule 17 | 1 | [13 empty] | 0
Schedule 17 | 1.1 | [13 empty] | 0
Schedule 17 | 1.2 | [13 empty] | 0
Schedule 17 | 1.3 | [13 empty] | 0 | Model reference number and date
Schedule 17 | 1.3A | [13 empty] | 0
Schedule 17 | 1.4 | [13 empty] | 0
Schedule 17 | 1.5 | [13 empty] | 0
Schedule 17 | 1.6 | [13 empty] | 0
Schedule 17 | 1.7 | [13 empty] | 0
Schedule 17 | 1.8 | [13 empty] | 0
Schedule 17 | 1.9 | [13 empty] | 0
Schedule 17 | 2 | [13 empty] | 0
Schedule 17 | 2.1 | [13 empty] | 0
Schedule 17 | 2.2 | [13 empty] | 0
Schedule 17 | 2.3 | [13 empty] | 0
Schedule 17 | 2.4 | [13 empty] | 0
Schedule 17 | 2.5 | [13 empty] | 0
Schedule 17 | 2.6 | [13 empty] | 0
Schedule 17 | 2.7 | [13 empty] | 0
Schedule 17 | 2.8 | [13 empty] | 0
Schedule 17 | 2.9 | [13 empty] | 0
Schedule 17 | 2.1 | [13 empty] | 0
Schedule 17 | 2.11 | [13 empty] | 0
Schedule 17 | 2.12 | [13 empty] | 0
Schedule 17 | 2.13 | [13 empty] | 0
Schedule 17 | 2.14 | [13 empty] | 0
Schedule 17 | 2.15 | [13 empty] | 0
Schedule 17 | 2.16 | [9 empty] | YES |  |  |  | 1
Schedule 17 | 2.17 | [13 empty] | 0
Schedule 17 | 2.18 | [13 empty] | 0
Schedule 17 | 2.19 | [13 empty] | 0
Schedule 17 | 3 | [13 empty] | 0
Schedule 17 | 3.1 | [13 empty] | 0
Schedule 17 | 3.2 | [13 empty] | 0
Schedule 17 | 3.3 | [13 empty] | 0
Schedule 17 | 3.4 | [13 empty] | 0
Schedule 17 | 3.5 | [13 empty] | 0
Schedule 17 | 3.6 | [13 empty] | 0
Schedule 17 | 3.7 | [13 empty] | 0
Schedule 17 | 4 | [13 empty] | 0
Schedule 17 | 4.1 | [13 empty] | 0
Schedule 17 | 5 | [13 empty] | 0
Schedule 17 | 5.1 | [13 empty] | 0
Schedule 17 | 6 | [13 empty] | 0
Schedule 17 | 6.1 | [13 empty] | 0
Schedule 17 | 6.2 | [13 empty] | 0
Schedule 17 | 6.3 | [13 empty] | 0
Schedule 17 | 7 | [13 empty] | 0
Schedule 17 | 7.1 | [13 empty] | 0
Schedule 17 | 8 | [13 empty] | 0
Schedule 17 | 8.1 | [13 empty] | 0
Schedule 17 | 8.2 | [13 empty] | 0
Schedule 17 | 8.3 | [13 empty] | 0
Schedule 17 | 8.4 | [13 empty] | 0
Schedule 17 | 9 | [13 empty] | 0
Schedule 17 | 9.1 | [13 empty] | 0
Schedule 17 | 9.2 | [13 empty] | 0
Schedule 17 | 9.3 | [13 empty] | 0
Schedule 17 | 10 | [13 empty] | 0
Schedule 17 | 10.1 | [13 empty] | 0
Schedule 17 | 10.2 | [13 empty] | 0
Schedule 17 | 10.3 | [13 empty] | 0
Schedule 17 | 10.4 | [13 empty] | 0
Schedule 17 | 11 | [13 empty] | 0
Schedule 17 | 11.1 | [13 empty] | 0
Schedule 17 | 12 | [13 empty] | 0
Schedule 17 | 12.1 | [13 empty] | 0
Schedule 17 | 12.2 | [13 empty] | 0
Schedule 17 | 12.3 | [13 empty] | 0
Schedule 17 | 13 | [13 empty] | 0
Schedule 17 | 13.1 | [13 empty] | 0
Schedule 17 | 13.2 | [13 empty] | 0
Schedule 17 | 13.3 | [13 empty] | 0
Schedule 17 | 13.4 | [13 empty] | 0
Schedule 17 | 14 | [13 empty] | 0
Schedule 17 | 14.1 | [13 empty] | 0
Schedule 17 | 14.2 | [13 empty] | 0
Schedule 17 | 14.3 | [13 empty] | 0
Schedule 17 | 14.4 | [13 empty] | 0
Schedule 17 | 14.5 | [13 empty] | 0
Schedule 17 | 15 | [13 empty] | 0
Schedule 17 | 15.1 | [13 empty] | 0
Schedule 17 | 15.2 | [13 empty] | 0
Schedule 17 | 15.3 | [13 empty] | 0
Schedule 17 | 15.4 | [13 empty] | 0
Schedule 17 | 15.5 | [13 empty] | 0
Schedule 17 | 15.6 | [13 empty] | 0
Schedule 17 | 15.7 | [13 empty] | 0
Schedule 17 | 15.8 | [13 empty] | 0
Schedule 17 | 15.9 | [13 empty] | 0
Schedule 17 | 15.1 | [13 empty] | 0
Schedule 17 | 15.11 | [13 empty] | 0
Schedule 17 | 15.12 | [13 empty] | 0
Schedule 17 | 15.15 | [13 empty] | 0
Schedule 17 | 16 | [13 empty] | 0
Schedule 17 | 16.1 | [13 empty] | 0
Schedule 17 | 16.2 | [13 empty] | 0
Schedule 17 | 16.3 | [13 empty] | 0
Schedule 17 | 16.4 | [13 empty] | 0
Schedule 17 | 16.5 | [13 empty] | 0
Schedule 17 | 16.6 | [13 empty] | 0
Schedule 17 | 16.7 | [13 empty] | 0
Schedule 17 | 16.8 | [13 empty] | 0
Schedule 17 | 16.9 | [13 empty] | 0
Schedule 17 | 16.1 | [13 empty] | 0
Schedule 17 | 17 | [13 empty] | 0
Schedule 17 | 17.1 | [13 empty] | 0
Schedule 17 | 17.2 | [13 empty] | 0
Schedule 17 | 17.3 | [13 empty] | 0
Schedule 17 | 18 | [13 empty] | 0
Schedule 17 | 18.1 | [13 empty] | 0
Schedule 17 | 18.2 | [13 empty] | 0
Schedule 17 | 18.3 | [13 empty] | 0
Schedule 17 | 18.4 | [13 empty] | 0
Schedule 17 | 18.5 | [13 empty] | 0
Schedule 17 | 18.6 | [13 empty] | 0
Schedule 17 | 18.7 | [13 empty] | 0
Schedule 17 | 18.8 | [13 empty] | 0
Schedule 17 | 18.9 | [13 empty] | 0
Schedule 17 | 18.1 | [13 empty] | 0
Schedule 17 | 18.11 | [13 empty] | 0
Schedule 17 | 18.12 | [13 empty] | 0
Schedule 17 | 18.13 | [13 empty] | 0
Schedule 17 | 18.14 | [13 empty] | 0
Schedule 17 | 18.15 | [13 empty] | 0
Schedule 17 | 18.16 | [13 empty] | 0
Schedule 17 | 18.17 | [13 empty] | 0
Schedule 17 | 18.18 | [13 empty] | 0
Schedule 17 | 18.19 | [13 empty] | 0
Schedule 17 | 18.2 | [13 empty] | 0
Schedule 17 | 18.21 | [13 empty] | 0
Schedule 17 | 19 | [13 empty] | 0
Schedule 17 | 19.1 | [13 empty] | 0
Schedule 17 | 19.2 | [13 empty] | 0
Schedule 17 | 19.3 | [13 empty] | 0
Schedule 17 | 19.4 | [13 empty] | 0
Schedule 17 | 19.5 | [13 empty] | 0
Schedule 17 | 19.6 | [13 empty] | 0
Schedule 17 | 19.7 | [13 empty] | 0
Schedule 17 | 19.8 | [13 empty] | 0
Schedule 17 | 19.9 | [13 empty] | 0
Schedule 17 | 19.1 | [13 empty] | 0
Schedule 17 | 19.11 | [13 empty] | 0
Schedule 17 | 20 | [13 empty] | 0
Schedule 17 | 20.1 | [13 empty] | 0
Schedule 17 | 20.2 | [13 empty] | 0
Schedule 17 | 20.3 | [13 empty] | 0
Schedule 17 | 20.4 | [13 empty] | 0
Schedule 17 | 20.5 | [13 empty] | 0
Schedule 17 | 20.6 | [12 empty] | YES | 1
Schedule 17 | 20.7 | [12 empty] | YES | 1
Schedule 17 | 20.8 | [13 empty] | 0
Schedule 17 | 20.9 | [12 empty] | YES | 1
Schedule 17 | 21 | [13 empty] | 0
Schedule 17 | 21.1 | [13 empty] | 0
Schedule 17 | 21.2 | [13 empty] | 0
Schedule 17 | 22 | [13 empty] | 0
Schedule 17 | 22.1 | [13 empty] | 0
Schedule 17 | 22.2 | [13 empty] | 0
Schedule 17 | 22.3 | [13 empty] | 0
Schedule 17 | 22.4 | [13 empty] | 0
Schedule 17 | 23 | [13 empty] | 0
Schedule 17 | 23.1 | [13 empty] | 0
Schedule 17 | 23.2 | [13 empty] | 0
Schedule 17 | 23.3 | [13 empty] | 0
Schedule 17 | 23.4 | [13 empty] | 0
Schedule 17 | 23.5 | [13 empty] | 0
Schedule 17 | 24 | [13 empty] | 0
Schedule 17 | 24.1 | [13 empty] | 0
Schedule 17 | 24.2 | [13 empty] | 0
Schedule 17 | 24.3 | [13 empty] | 0
Schedule 17 | 24.4 | [13 empty] | 0
Schedule 17 | 24.5 | [13 empty] | 0
Schedule 17 | 24.6 | [13 empty] | 0
Schedule 17 | 24.7 | [13 empty] | 0
Schedule 17 | 24.8 | [13 empty] | 0
Schedule 17 | 24.9 | [13 empty] | 0
Schedule 17 | 25 | [13 empty] | 0
Schedule 17 | 25.1 | [13 empty] | 0
Schedule 17 | 25.2 | [13 empty] | 0
Schedule 17 | 25.3 | [13 empty] | 0
Schedule 17 | 25.4 | [13 empty] | 0
Schedule 17 | 25.5 | [13 empty] | 0
Schedule 17 | 25.6 | [13 empty] | 0
Schedule 17 | 25.7 | [13 empty] | 0
Schedule 17 | 25.8 | [13 empty] | 0
Schedule 17 | 25.9 | [13 empty] | 0
Schedule 17 | 25.1 | [13 empty] | 0
Schedule 17 | 25.11 | [13 empty] | 0
Schedule 17 | 25.12 | [13 empty] | 0
Schedule 17 | 25.13 | [13 empty] | 0
Schedule 17 | 25.14 | [13 empty] | 0
Schedule 17 | 25.15 | [13 empty] | 0
Schedule 17 | 25.16 | [13 empty] | 0
Schedule 17 | 25.17 | [13 empty] | 0
Schedule 17 | 25.18 | [13 empty] | 0
Schedule 17 | 25.19 | [13 empty] | 0
Schedule 17 | 26 | [13 empty] | 0
Schedule 17 | 26.1 | [13 empty] | 0
Schedule 17 | 26.2 | [13 empty] | 0
Schedule 17 | 26.3 | [13 empty] | 0
Schedule 17 | 26.4 | [13 empty] | 0
Schedule 17 | 26.5 | [13 empty] | 0
Schedule 17 | 26.6 | [13 empty] | 0
Schedule 17 | 26.7 | [13 empty] | 0
Schedule 17 | 26.8 | [13 empty] | 0
Schedule 17 | 26.9 | [13 empty] | 0
Schedule 17 | 26.1 | [13 empty] | 0
Schedule 17 | 26.11 | [13 empty] | 0
Schedule 17 | 27 | [13 empty] | 0
Schedule 17 | 27.1 | [13 empty] | 0
Schedule 17 | 27.2 | [13 empty] | 0
Schedule 17 | 27.3 | [13 empty] | 0
Schedule 17 | 27.4 | [13 empty] | 0
Schedule 17 | 28 | [13 empty] | 0
Schedule 17 | 28.1 | [13 empty] | 0
Schedule 17 | 28.2 | [13 empty] | 0
Schedule 17 | 29 | [13 empty] | 0
Schedule 17 | 29.1 | [13 empty] | 0
Schedule 17 | 29.2 | [13 empty] | 0
Schedule 17 | 29.3 | [13 empty] | 0
Schedule 17 | 29.4 | [13 empty] | 0
Schedule 17 | 30 | [13 empty] | 0
Schedule 17 | 30.1 | [13 empty] | 0
Schedule 17 | 30.2 | [13 empty] | 0
Schedule 17 | 30.3 | [13 empty] | 0
Schedule 17 | 30.4 | [13 empty] | 0
Schedule 17 | 30.5 | [13 empty] | 0
Schedule 17 | 30.6 | [13 empty] | 0
Schedule 17 | 30.7 | [13 empty] | 0
Schedule 17 | 30.8 | [13 empty] | 0
Schedule 17 | 30.9 | [13 empty] | 0
Schedule 17 | 30.1 | [13 empty] | 0
Schedule 17 | 30.11 | [13 empty] | 0
Schedule 17 | 31 | [10 empty] | YES |  |  | 1 | DCP 439 Introduces new Paragraph 31
Schedule 17 | 31.1 | [10 empty] | YES |  |  | 1 | DCP 439 Introduces new Paragraph 31.1
Schedule 17: Annex 1 | 1 | [13 empty] | 0
Schedule 17: Annex 1 | 2 | [13 empty] | 0
Schedule 17: Annex 1 | 2.1 | [13 empty] | 0
Schedule 17: Annex 1 | 2.2 | [13 empty] | 0
Schedule 17: Annex 1 | 2.3 | [13 empty] | 0
Schedule 17: Annex 1 | 2.4 | [13 empty] | 0
Schedule 17: Annex 1 | 2.5 | [13 empty] | 0
Schedule 17: Annex 1 | 3 | [13 empty] | 0
Schedule 17: Annex 1 | Definitions | [13 empty] | 0
Schedule 17: Annex 1 | 4 | [13 empty] | 0
Schedule 17: Annex 1 | 4.1 | [13 empty] | 0
Schedule 17: Annex 1 | 4.2 | [13 empty] | 0
Schedule 17: Annex 1 | 4.3 | [13 empty] | 0
Schedule 17: Annex 1 | 4.4 | [13 empty] | 0
Schedule 17: Annex 1 | 4.5 | [13 empty] | 0
Schedule 17: Annex 1 | 4.6 | [13 empty] | 0
Schedule 17: Annex 1 | 4.7 | [13 empty] | 0
Schedule 17: Annex 1 | 4.8 | [13 empty] | 0
Schedule 17: Annex 1 | 4.9 | [13 empty] | 0
Schedule 17: Annex 1 | 4.1 | [13 empty] | 0
Schedule 17: Annex 1 | 5 | [13 empty] | 0
Schedule 17: Annex 1 | 5.1 | [13 empty] | 0
Schedule 17: Annex 1 | 5.2 | [13 empty] | 0
Schedule 17: Annex 1 | 5.3 | [13 empty] | 0
Schedule 17: Annex 1 | 5.4 | [13 empty] | 0
Schedule 17: Annex 1 | 5.5 | [13 empty] | 0
Schedule 17: Annex 1 | 5.6 | [13 empty] | 0
Schedule 17: Annex 1 | 5.7 | [13 empty] | 0
Schedule 17: Annex 1 | 5.8 | [13 empty] | 0
Schedule 17: Annex 1 | 5.9 | [13 empty] | 0
Schedule 17: Annex 1 | 5.1 | [13 empty] | 0
Schedule 17: Annex 1 | 5.11 | [13 empty] | 0
Schedule 17: Annex 1 | 5.12 | [13 empty] | 0
Schedule 17: Annex 1 | 5.13 | [13 empty] | 0
Schedule 17: Annex 1 | 5.14 | [13 empty] | 0
Schedule 17: Annex 1 | 5.15 | [13 empty] | 0
Schedule 17: Annex 1 | 5.16 | [13 empty] | 0
Schedule 17: Annex 1 | 5.17 | [13 empty] | 0
Schedule 17: Annex 1 | 5.18 | [13 empty] | 0
Schedule 17: Annex 1 | 5.19 | [13 empty] | 0
Schedule 17: Annex 1 | 5.2 | [13 empty] | 0
Schedule 17: Annex 1 | 5.21 | [13 empty] | 0
Schedule 17: Annex 1 | 5.22 | [13 empty] | 0
Schedule 17: Annex 1 | 5.23 | [13 empty] | 0
Schedule 17: Annex 1 | 5.24 | [13 empty] | 0
Schedule 17: Annex 1 | 5.25 | [13 empty] | 0
Schedule 17: Annex 1 | 5.26 | [13 empty] | 0
Schedule 17: Annex 1 | 5.27 | [13 empty] | 0
Schedule 17: Annex 1 | 5.28 | [13 empty] | 0
Schedule 17: Annex 1 | 5.29 | [13 empty] | 0
Schedule 17: Annex 1 | 5.3 | [13 empty] | 0
Schedule 17: Annex 1 | 5.31 | [13 empty] | 0
Schedule 17: Annex 1 | 5.32 | [13 empty] | 0
Schedule 17: Annex 1 | 5.33 | [13 empty] | 0
Schedule 17: Annex 1 | 5.34 | [13 empty] | 0
Schedule 17: Annex 1 | 5.35 | [13 empty] | 0
Schedule 17: Annex 1 | 5.36 | [13 empty] | 0
Schedule 17: Annex 1 | 5.37 | [13 empty] | 0
Schedule 17: Annex 1 | 5.38 | [13 empty] | 0
Schedule 17: Annex 1 | 5.39 | [13 empty] | 0
Schedule 17: Annex 1 | 5.4 | [13 empty] | 0
Schedule 17: Annex 1 | 5.41 | [13 empty] | 0
Schedule 17: Annex 1 | 5.42 | [13 empty] | 0
Schedule 17: Annex 1 | 5.43 | [13 empty] | 0
Schedule 17: Annex 1 | 5.44 | [13 empty] | 0
Schedule 17: Annex 1 | 5.45 | [13 empty] | 0
Schedule 17: Annex 1 | 6 | [13 empty] | 0
Schedule 17: Annex 1 | 6.1 | [13 empty] | 0
Schedule 17: Annex 1 | 6.2 | [13 empty] | 0
Schedule 17: Annex 1 | 6.3 | [13 empty] | 0
Schedule 17: Annex 1 | 6.4 | [13 empty] | 0
Schedule 17: Annex 1 | 6.5 | [13 empty] | 0
Schedule 17: Annex 1 | 6.6 | [13 empty] | 0
Schedule 17: Annex 1 | 6.7 | [13 empty] | 0
Schedule 17: Annex 1 | 6.8 | [13 empty] | 0
Schedule 17: Annex 1 | 7 | [13 empty] | 0
Schedule 17: Annex 1 | 7.1 | [13 empty] | 0
Schedule 17: Annex 1 | 7.2 | [13 empty] | 0
Schedule 17: Annex 1 | 7.3 | [13 empty] | 0
Schedule 17: Annex 1 | 7.4 | [13 empty] | 0
Schedule 17: Annex 1 | 7.5 | [13 empty] | 0
Schedule 17: Annex 1 | 7.6 | [13 empty] | 0
Schedule 17: Annex 1 | 7.7 | [13 empty] | 0
Schedule 17: Annex 1 | 7.8 | [13 empty] | 0
Schedule 17: Annex 1 | 8 | [13 empty] | 0
Schedule 17: Annex 1 | 8.1 | [13 empty] | 0
Schedule 17: Annex 1 | 8.2 | [13 empty] | 0
Schedule 17: Annex 1 | 8.3 | [13 empty] | 0
Schedule 17: Annex 1 | 8.4 | [13 empty] | 0
Schedule 17: Annex 1 | 9 | [13 empty] | 0
Schedule 17: Annex 1 | 9.1 | [13 empty] | 0
Schedule 17: Annex 1 | 9.2 | [9 empty] | YES |  |  |  | 1
Schedule 17: Annex 1 | 9.3 | [13 empty] | 0
Schedule 17: Annex 1 | 9.4 | [13 empty] | 0
Schedule 17: Annex 1 | 9.5 | [13 empty] | 0
Schedule 17: Annex 1 | 9.6 | [13 empty] | 0
Schedule 17: Annex 1 | 9.7 | [13 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [13 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [13 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [13 empty] | 0
Schedule 17: Annex 1 | Attachment 3 | [13 empty] | 0
Schedule 17: Annex 2 | Annex 2 | [9 empty] | YES |  |  |  | 1
0
Schedule 18 | Introduction | [13 empty] | 0
Schedule 18 | 1 | [13 empty] | 0
Schedule 18 | 1.1 | [13 empty] | 0
Schedule 18 | 1.2 | [13 empty] | 0
Schedule 18 | 1.3 | [13 empty] | 0 | Model reference number and date
Schedule 18 | 1.3A | [13 empty] | 0
Schedule 18 | 1.4 | [13 empty] | 0
Schedule 18 | 1.5 | [13 empty] | 0
Schedule 18 | 1.6 | [13 empty] | 0
Schedule 18 | 1.7 | [13 empty] | 0
Schedule 18 | 1.8 | [13 empty] | 0
Schedule 18 | 1.9 | [13 empty] | 0
Schedule 18 | 2 | [13 empty] | 0
Schedule 18 | 2.1 | [13 empty] | 0
Schedule 18 | 2.2 | [13 empty] | 0
Schedule 18 | 2.3 | [13 empty] | 0
Schedule 18 | 2.4 | [13 empty] | 0
Schedule 18 | 2.5 | [13 empty] | 0
Schedule 18 | 2.6 | [13 empty] | 0
Schedule 18 | 2.7 | [13 empty] | 0
Schedule 18 | 2.8 | [13 empty] | 0
Schedule 18 | 2.9 | [9 empty] | YES |  |  |  | 1
Schedule 18 | 2.1 | [13 empty] | 0
Schedule 18 | 2.11 | [13 empty] | 0
Schedule 18 | 2.12 | [13 empty] | 0
Schedule 18 | 2.13 | [13 empty] | 0
Schedule 18 | 2.14 | [13 empty] | 0
Schedule 18 | 2.15 | [13 empty] | 0
Schedule 18 | 2.16 | [13 empty] | 0
Schedule 18 | 2.17 | [13 empty] | 0
Schedule 18 | 2.18 | [13 empty] | 0
Schedule 18 | 2.19 | [13 empty] | 0
Schedule 18 | 2.2 | [13 empty] | 0
Schedule 18 | 2.21 | [13 empty] | 0
Schedule 18 | 2.22 | [13 empty] | 0
Schedule 18 | 2.23 | [13 empty] | 0
Schedule 18 | 2.24 | [13 empty] | 0
Schedule 18 | 2.25 | [13 empty] | 0
Schedule 18 | 2.26 | [13 empty] | 0
Schedule 18 | 2.27 | [13 empty] | 0
Schedule 18 | 2.28 | [13 empty] | 0
Schedule 18 | 2.29 | [13 empty] | 0
Schedule 18 | 2.3 | [13 empty] | 0
Schedule 18 | 3 | [13 empty] | 0
Schedule 18 | 3.1 | [13 empty] | 0
Schedule 18 | 3.2 | [13 empty] | 0
Schedule 18 | 3.3 | [13 empty] | 0
Schedule 18 | 3.4 | [13 empty] | 0
Schedule 18 | 3.5 | [13 empty] | 0
Schedule 18 | 3.6 | [13 empty] | 0
Schedule 18 | 3.7 | [13 empty] | 0
Schedule 18 | 4 | [13 empty] | 0
Schedule 18 | 4.1 | [13 empty] | 0
Schedule 18 | 5 | [13 empty] | 0
Schedule 18 | 5.1 | [13 empty] | 0
Schedule 18 | 6 | [13 empty] | 0
Schedule 18 | 6.1 | [13 empty] | 0
Schedule 18 | 6.2 | [13 empty] | 0
Schedule 18 | 6.3 | [13 empty] | 0
Schedule 18 | 6.4 | [13 empty] | 0
Schedule 18 | 6.5 | [13 empty] | 0
Schedule 18 | 7 | [13 empty] | 0
Schedule 18 | 7.1 | [13 empty] | 0
Schedule 18 | 8 | [13 empty] | 0
Schedule 18 | 8.1 | [13 empty] | 0
Schedule 18 | 8.2 | [13 empty] | 0
Schedule 18 | 8.3 | [13 empty] | 0
Schedule 18 | 8.4 | [13 empty] | 0
Schedule 18 | 9 | [13 empty] | 0
Schedule 18 | 9.1 | [13 empty] | 0
Schedule 18 | 9.2 | [13 empty] | 0
Schedule 18 | 10 | [13 empty] | 0
Schedule 18 | 10.1 | [13 empty] | 0
Schedule 18 | 10.2 | [13 empty] | 0
Schedule 18 | 10.3 | [13 empty] | 0
Schedule 18 | 10.4 | [13 empty] | 0
Schedule 18 | 10.5 | [13 empty] | 0
Schedule 18 | 11 | [13 empty] | 0
Schedule 18 | 11.1 | [13 empty] | 0
Schedule 18 | 12 | [13 empty] | 0
Schedule 18 | 12.1 | [13 empty] | 0
Schedule 18 | 12.2 | [13 empty] | 0
Schedule 18 | 12.3 | [13 empty] | 0
Schedule 18 | 12.4 | [13 empty] | 0
Schedule 18 | 12.5 | [13 empty] | 0
Schedule 18 | 12.6 | [13 empty] | 0
Schedule 18 | 13 | [13 empty] | 0
Schedule 18 | 13.1 | [13 empty] | 0
Schedule 18 | 13.2 | [13 empty] | 0
Schedule 18 | 13.3 | [13 empty] | 0
Schedule 18 | 13.4 | [13 empty] | 0
Schedule 18 | 14 | [13 empty] | 0
Schedule 18 | 14.1 | [13 empty] | 0
Schedule 18 | 14.2 | [13 empty] | 0
Schedule 18 | 14.3 | [13 empty] | 0
Schedule 18 | 14.4 | [13 empty] | 0
Schedule 18 | 14.5 | [13 empty] | 0
Schedule 18 | 15 | [13 empty] | 0
Schedule 18 | 15.1 | [13 empty] | 0
Schedule 18 | 15.2 | [13 empty] | 0
Schedule 18 | 15.3 | [13 empty] | 0
Schedule 18 | 15.4 | [13 empty] | 0
Schedule 18 | 15.5 | [13 empty] | 0
Schedule 18 | 15.6 | [13 empty] | 0
Schedule 18 | 15.7 | [13 empty] | 0
Schedule 18 | 15.8 | [13 empty] | 0
Schedule 18 | 15.9 | [13 empty] | 0
Schedule 18 | 15.1 | [13 empty] | 0
Schedule 18 | 15.11 | [13 empty] | 0
Schedule 18 | 15.12 | [13 empty] | 0
Schedule 18 | 15.15 | [13 empty] | 0
Schedule 18 | 16 | [13 empty] | 0
Schedule 18 | 16.1 | [13 empty] | 0
Schedule 18 | 16.2 | [13 empty] | 0
Schedule 18 | 16.3 | [13 empty] | 0
Schedule 18 | 16.4 | [13 empty] | 0
Schedule 18 | 16.5 | [13 empty] | 0
Schedule 18 | 16.6 | [13 empty] | 0
Schedule 18 | 16.7 | [13 empty] | 0
Schedule 18 | 16.8 | [13 empty] | 0
Schedule 18 | 16.9 | [13 empty] | 0
Schedule 18 | 16.1 | [13 empty] | 0
Schedule 18 | 17 | [13 empty] | 0
Schedule 18 | 17.1 | [13 empty] | 0
Schedule 18 | 17.2 | [13 empty] | 0
Schedule 18 | 17.3 | [13 empty] | 0
Schedule 18 | 18 | [13 empty] | 0
Schedule 18 | 18.1 | [13 empty] | 0
Schedule 18 | 18.2 | [13 empty] | 0
Schedule 18 | 18.3 | [13 empty] | 0
Schedule 18 | 18.4 | [13 empty] | 0
Schedule 18 | 18.5 | [13 empty] | 0
Schedule 18 | 18.6 | [13 empty] | 0
Schedule 18 | 18.7 | [13 empty] | 0
Schedule 18 | 18.8 | [13 empty] | 0
Schedule 18 | 18.9 | [13 empty] | 0
Schedule 18 | 18.1 | [13 empty] | 0
Schedule 18 | 18.11 | [13 empty] | 0
Schedule 18 | 18.12 | [13 empty] | 0
Schedule 18 | 18.13 | [13 empty] | 0
Schedule 18 | 18.14 | [13 empty] | 0
Schedule 18 | 18.15 | [13 empty] | 0
Schedule 18 | 18.16 | [13 empty] | 0
Schedule 18 | 18.17 | [13 empty] | 0
Schedule 18 | 18.18 | [13 empty] | 0
Schedule 18 | 18.19 | [13 empty] | 0
Schedule 18 | 18.2 | [13 empty] | 0
Schedule 18 | 18.21 | [13 empty] | 0
Schedule 18 | 19 | [13 empty] | 0
Schedule 18 | 19.1 | [13 empty] | 0
Schedule 18 | 19.2 | [13 empty] | 0
Schedule 18 | 19.3 | [13 empty] | 0
Schedule 18 | 19.4 | [13 empty] | 0
Schedule 18 | 19.5 | [13 empty] | 0
Schedule 18 | 19.6 | [13 empty] | 0
Schedule 18 | 19.7 | [13 empty] | 0
Schedule 18 | 19.8 | [13 empty] | 0
Schedule 18 | 19.9 | [13 empty] | 0
Schedule 18 | 19.1 | [13 empty] | 0
Schedule 18 | 19.11 | [13 empty] | 0
Schedule 18 | 20 | [13 empty] | 0
Schedule 18 | 20.1 | [13 empty] | 0
Schedule 18 | 20.2 | [13 empty] | 0
Schedule 18 | 20.3 | [13 empty] | 0
Schedule 18 | 20.4 | [13 empty] | 0
Schedule 18 | 20.5 | [13 empty] | 0
Schedule 18 | 20.6 | [12 empty] | YES | 1
Schedule 18 | 20.7 | [12 empty] | YES | 1
Schedule 18 | 20.8 | [13 empty] | 0
Schedule 18 | 20.9 | [12 empty] | YES | 1
Schedule 18 | 21 | [13 empty] | 0
Schedule 18 | 21.1 | [13 empty] | 0
Schedule 18 | 21.2 | [13 empty] | 0
Schedule 18 | 22 | [13 empty] | 0
Schedule 18 | 22.1 | [13 empty] | 0
Schedule 18 | 22.2 | [13 empty] | 0
Schedule 18 | 22.3 | [13 empty] | 0
Schedule 18 | 22.4 | [13 empty] | 0
Schedule 18 | 23 | [13 empty] | 0
Schedule 18 | 23.1 | [13 empty] | 0
Schedule 18 | 23.2 | [13 empty] | 0
Schedule 18 | 23.3 | [13 empty] | 0
Schedule 18 | 23.4 | [13 empty] | 0
Schedule 18 | 23.5 | [13 empty] | 0
Schedule 18 | 24 | [13 empty] | 0
Schedule 18 | 24.1 | [13 empty] | 0
Schedule 18 | 24.2 | [13 empty] | 0
Schedule 18 | 24.3 | [13 empty] | 0
Schedule 18 | 24.4 | [13 empty] | 0
Schedule 18 | 24.5 | [13 empty] | 0
Schedule 18 | 24.6 | [13 empty] | 0
Schedule 18 | 24.7 | [13 empty] | 0
Schedule 18 | 24.8 | [13 empty] | 0
Schedule 18 | 24.9 | [13 empty] | 0
Schedule 18 | 25 | [13 empty] | 0
Schedule 18 | 25.1 | [13 empty] | 0
Schedule 18 | 25.2 | [13 empty] | 0
Schedule 18 | 25.3 | [13 empty] | 0
Schedule 18 | 25.4 | [13 empty] | 0
Schedule 18 | 25.5 | [13 empty] | 0
Schedule 18 | 25.6 | [13 empty] | 0
Schedule 18 | 25.7 | [13 empty] | 0
Schedule 18 | 25.8 | [13 empty] | 0
Schedule 18 | 25.9 | [13 empty] | 0
Schedule 18 | 25.1 | [13 empty] | 0
Schedule 18 | 25.11 | [13 empty] | 0
Schedule 18 | 25.12 | [13 empty] | 0
Schedule 18 | 25.13 | [13 empty] | 0
Schedule 18 | 25.14 | [13 empty] | 0
Schedule 18 | 25.15 | [13 empty] | 0
Schedule 18 | 25.16 | [13 empty] | 0
Schedule 18 | 25.17 | [13 empty] | 0
Schedule 18 | 25.18 | [13 empty] | 0
Schedule 18 | 25.19 | [13 empty] | 0
Schedule 18 | 26 | [13 empty] | 0
Schedule 18 | 26.1 | [13 empty] | 0
Schedule 18 | 26.2 | [13 empty] | 0
Schedule 18 | 26.3 | [13 empty] | 0
Schedule 18 | 26.4 | [13 empty] | 0
Schedule 18 | 26.5 | [13 empty] | 0
Schedule 18 | 26.6 | [13 empty] | 0
Schedule 18 | 26.7 | [13 empty] | 0
Schedule 18 | 26.8 | [13 empty] | 0
Schedule 18 | 26.9 | [13 empty] | 0
Schedule 18 | 26.1 | [13 empty] | 0
Schedule 18 | 26.11 | [13 empty] | 0
Schedule 18 | 27 | [13 empty] | 0
Schedule 18 | 27.1 | [13 empty] | 0
Schedule 18 | 27.2 | [13 empty] | 0
Schedule 18 | 27.3 | [13 empty] | 0
Schedule 18 | 27.4 | [13 empty] | 0
Schedule 18 | 28 | [13 empty] | 0
Schedule 18 | 28.1 | [13 empty] | 0
Schedule 18 | 28.2 | [13 empty] | 0
Schedule 18 | 29 | [13 empty] | 0
Schedule 18 | 29.1 | [13 empty] | 0
Schedule 18 | 29.2 | [13 empty] | 0
Schedule 18 | 29.3 | [13 empty] | 0
Schedule 18 | 29.4 | [13 empty] | 0
Schedule 18 | 30 | [13 empty] | 0
Schedule 18 | 30.1 | [13 empty] | 0
Schedule 18 | 30.2 | [13 empty] | 0
Schedule 18 | 30.3 | [13 empty] | 0
Schedule 18 | 30.4 | [13 empty] | 0
Schedule 18 | 30.5 | [13 empty] | 0
Schedule 18 | 30.6 | [13 empty] | 0
Schedule 18 | 30.7 | [13 empty] | 0
Schedule 18 | 30.8 | [13 empty] | 0
Schedule 18 | 30.9 | [13 empty] | 0
Schedule 18 | 30.1 | [13 empty] | 0
Schedule 18 | 30.11 | [13 empty] | 0
Schedule 18 | 31 | [13 empty] | 0 | DCP 439 Introduces new Paragraph 31
Schedule 18 | 31.1 | [13 empty] | 0 | DCP 439 Introduces new Paragraph 31.1
Schedule 18: Annex 1 | 1 | [13 empty] | 0
Schedule 18: Annex 1 | 1.1 | [13 empty] | 0
Schedule 18: Annex 1 | 2 | [13 empty] | 0
Schedule 18: Annex 1 | 2.1 | [13 empty] | 0
Schedule 18: Annex 1 | 2.2 | [13 empty] | 0
Schedule 18: Annex 1 | 2.3 | [13 empty] | 0
Schedule 18: Annex 1 | 2.4 | [13 empty] | 0
Schedule 18: Annex 1 | 2.5 | [13 empty] | 0
Schedule 18: Annex 1 | 3 | [13 empty] | 0
Schedule 18: Annex 1 | Definitions | [13 empty] | 0
Schedule 18: Annex 1 | 4 | [13 empty] | 0
Schedule 18: Annex 1 | 4.1 | [13 empty] | 0
Schedule 18: Annex 1 | 4.2 | [13 empty] | 0
Schedule 18: Annex 1 | 4.3 | [13 empty] | 0
Schedule 18: Annex 1 | 4.4 | [13 empty] | 0
Schedule 18: Annex 1 | 4.5 | [13 empty] | 0
Schedule 18: Annex 1 | 4.6 | [13 empty] | 0
Schedule 18: Annex 1 | 4.7 | [13 empty] | 0
Schedule 18: Annex 1 | 4.8 | [13 empty] | 0
Schedule 18: Annex 1 | 4.9 | [13 empty] | 0
Schedule 18: Annex 1 | 5 | [13 empty] | 0
Schedule 18: Annex 1 | 5.1 | [13 empty] | 0
Schedule 18: Annex 1 | 5.2 | [13 empty] | 0
Schedule 18: Annex 1 | 5.3 | [13 empty] | 0
Schedule 18: Annex 1 | 5.4 | [13 empty] | 0
Schedule 18: Annex 1 | 5.5 | [13 empty] | 0
Schedule 18: Annex 1 | 5.6 | [13 empty] | 0
Schedule 18: Annex 1 | 5.7 | [13 empty] | 0
Schedule 18: Annex 1 | 5.8 | [13 empty] | 0
Schedule 18: Annex 1 | 5.9 | [13 empty] | 0
Schedule 18: Annex 1 | 5.1 | [13 empty] | 0
Schedule 18: Annex 1 | 5.11 | [13 empty] | 0
Schedule 18: Annex 1 | 5.12 | [13 empty] | 0
Schedule 18: Annex 1 | 5.13 | [13 empty] | 0
Schedule 18: Annex 1 | 5.14 | [13 empty] | 0
Schedule 18: Annex 1 | 5.15 | [13 empty] | 0
Schedule 18: Annex 1 | 5.16 | [13 empty] | 0
Schedule 18: Annex 1 | 5.17 | [13 empty] | 0
Schedule 18: Annex 1 | 5.18 | [13 empty] | 0
Schedule 18: Annex 1 | 5.19 | [13 empty] | 0
Schedule 18: Annex 1 | 5.2 | [13 empty] | 0
Schedule 18: Annex 1 | 5.21 | [13 empty] | 0
Schedule 18: Annex 1 | 5.22 | [13 empty] | 0
Schedule 18: Annex 1 | 5.23 | [13 empty] | 0
Schedule 18: Annex 1 | 5.24 | [13 empty] | 0
Schedule 18: Annex 1 | 5.25 | [13 empty] | 0
Schedule 18: Annex 1 | 5.26 | [13 empty] | 0
Schedule 18: Annex 1 | 5.27 | [13 empty] | 0
Schedule 18: Annex 1 | 5.28 | [13 empty] | 0
Schedule 18: Annex 1 | 5.29 | [13 empty] | 0
Schedule 18: Annex 1 | 5.3 | [13 empty] | 0
Schedule 18: Annex 1 | 5.31 | [13 empty] | 0
Schedule 18: Annex 1 | 5.32 | [13 empty] | 0
Schedule 18: Annex 1 | 5.33 | [13 empty] | 0
Schedule 18: Annex 1 | 5.34 | [13 empty] | 0
Schedule 18: Annex 1 | 5.35 | [13 empty] | 0
Schedule 18: Annex 1 | 5.36 | [13 empty] | 0
Schedule 18: Annex 1 | 5.37 | [13 empty] | 0
Schedule 18: Annex 1 | 5.38 | [13 empty] | 0
Schedule 18: Annex 1 | 5.39 | [13 empty] | 0
Schedule 18: Annex 1 | 5.4 | [13 empty] | 0
Schedule 18: Annex 1 | 5.41 | [13 empty] | 0
Schedule 18: Annex 1 | 5.42 | [13 empty] | 0
Schedule 18: Annex 1 | 6 | [13 empty] | 0
Schedule 18: Annex 1 | 6.1 | [13 empty] | 0
Schedule 18: Annex 1 | 6.2 | [13 empty] | 0
Schedule 18: Annex 1 | 6.3 | [13 empty] | 0
Schedule 18: Annex 1 | 6.4 | [13 empty] | 0
Schedule 18: Annex 1 | 6.5 | [13 empty] | 0
Schedule 18: Annex 1 | 6.6 | [13 empty] | 0
Schedule 18: Annex 1 | 6.7 | [13 empty] | 0
Schedule 18: Annex 1 | 6.8 | [13 empty] | 0
Schedule 18: Annex 1 | 6.9 | [13 empty] | 0
Schedule 18: Annex 1 | 6.1 | [13 empty] | 0
Schedule 18: Annex 1 | 6.11 | [13 empty] | 0
Schedule 18: Annex 1 | 6.12 | [13 empty] | 0
Schedule 18: Annex 1 | 6.13 | [13 empty] | 0
Schedule 18: Annex 1 | 6.14 | [13 empty] | 0
Schedule 18: Annex 1 | 6.15 | [13 empty] | 0
Schedule 18: Annex 1 | 6.16 | [13 empty] | 0
Schedule 18: Annex 1 | 6.17 | [13 empty] | 0
Schedule 18: Annex 1 | 6.18 | [13 empty] | 0
Schedule 18: Annex 1 | 6.19 | [13 empty] | 0
Schedule 18: Annex 1 | 6.2 | [13 empty] | 0
Schedule 18: Annex 1 | 6.21 | [13 empty] | 0
Schedule 18: Annex 1 | 6.22 | [13 empty] | 0
Schedule 18: Annex 1 | 6.23 | [13 empty] | 0
Schedule 18: Annex 1 | 6.24 | [13 empty] | 0
Schedule 18: Annex 1 | 6.25 | [13 empty] | 0
Schedule 18: Annex 1 | 6.26 | [13 empty] | 0
Schedule 18: Annex 1 | 6.27 | [13 empty] | 0
Schedule 18: Annex 1 | 6.28 | [13 empty] | 0
Schedule 18: Annex 1 | 6.29 | [13 empty] | 0
Schedule 18: Annex 1 | 6.3 | [13 empty] | 0
Schedule 18: Annex 1 | 6.31 | [13 empty] | 0
Schedule 18: Annex 1 | 6.32 | [13 empty] | 0
Schedule 18: Annex 1 | 6.33 | [13 empty] | 0
Schedule 18: Annex 1 | 6.34 | [13 empty] | 0
Schedule 18: Annex 1 | 7 | [13 empty] | 0
Schedule 18: Annex 1 | 7.1 | [13 empty] | 0
Schedule 18: Annex 1 | 7.2 | [13 empty] | 0
Schedule 18: Annex 1 | 7.3 | [13 empty] | 0
Schedule 18: Annex 1 | 7.4 | [13 empty] | 0
Schedule 18: Annex 1 | 7.5 | [13 empty] | 0
Schedule 18: Annex 1 | 8 | [13 empty] | 0
Schedule 18: Annex 1 | 8.1 | [13 empty] | 0
Schedule 18: Annex 1 | 8.2 | [13 empty] | 0
Schedule 18: Annex 1 | 8.3 | [13 empty] | 0
Schedule 18: Annex 1 | 8.4 | [13 empty] | 0
Schedule 18: Annex 1 | 8.5 | [13 empty] | 0
Schedule 18: Annex 1 | 8.6 | [13 empty] | 0
Schedule 18: Annex 1 | 8.7 | [13 empty] | 0
Schedule 18: Annex 1 | 8.8 | [13 empty] | 0
Schedule 18: Annex 1 | 8.9 | [13 empty] | 0
Schedule 18: Annex 1 | 8.1 | [13 empty] | 0
Schedule 18: Annex 1 | 8.11 | [13 empty] | 0
Schedule 18: Annex 1 | 8.12 | [13 empty] | 0
Schedule 18: Annex 1 | 8.13 | [13 empty] | 0
Schedule 18: Annex 1 | 8.14 | [13 empty] | 0
Schedule 18: Annex 1 | 8.15 | [13 empty] | 0
Schedule 18: Annex 1 | 8.16 | [13 empty] | 0
Schedule 18: Annex 1 | 8.17 | [13 empty] | 0
Schedule 18: Annex 1 | 8.18 | [13 empty] | 0
Schedule 18: Annex 1 | 8.19 | [13 empty] | 0
Schedule 18: Annex 1 | 8.2 | [13 empty] | 0
Schedule 18: Annex 1 | 8.21 | [13 empty] | 0
Schedule 18: Annex 1 | Attachment 1 | [9 empty] | YES |  |  |  | 1
Schedule 18: Annex 1 | Attachment 2 | [13 empty] | 0
Schedule 18: Annex 1 | Attachment 3 | [13 empty] | 0
Schedule 18: Annex 2 | Annex 2 | [13 empty] | 0
0
Schedule 20 | Introduction |  |  | YES | [10 empty] | 1
Schedule 20 | 1.1 |  |  | YES | [10 empty] | 1
Schedule 20 | 2.1 |  |  | YES | [10 empty] | 1
Schedule 20 | 3.1 |  |  | YES | [10 empty] | 1
Schedule 20 | 3.2 |  |  | YES | [10 empty] | 1
0
Schedule 29 | Introduction | [13 empty] | 0
Schedule 29 | 1 | [13 empty] | 0
Schedule 29 | 1A | [13 empty] | 0
Schedule 29 | 2 | [13 empty] | 0
Schedule 29 | 3 | [13 empty] | 0
Schedule 29 | 4 | [13 empty] | 0
Schedule 29 | 5 | [13 empty] | 0
Schedule 29 | 6 | [13 empty] | 0
Schedule 29 | 7 | [13 empty] | 0
Schedule 29 | 8 | [13 empty] | 0
Schedule 29 | 9 | [13 empty] | 0
Schedule 29 | 10 | [13 empty] | 0
Schedule 29 | 11 | [13 empty] | 0
Schedule 29 | 11A | [13 empty] | 0
Schedule 29 | 12 | [13 empty] | 0
Schedule 29 | 13 | [13 empty] | 0
Schedule 29 | 14 | [13 empty] | 0
Schedule 29 | 15 | [13 empty] | 0
Schedule 29 | 16 | [13 empty] | 0
Schedule 29 | 17 | [13 empty] | 0
Schedule 29 | 18 | [13 empty] | 0
Schedule 29 | 19 | [13 empty] | 0
Schedule 29 | 20 | [13 empty] | 0
Schedule 29 | 21 | [13 empty] | 0
Schedule 29 | 22 | [13 empty] | 0
Schedule 29 | 23 | [13 empty] | 0
Schedule 29 | 24 | [13 empty] | 0
Schedule 29 | 25 | [13 empty] | 0
Schedule 29 | 26 | [13 empty] | 0
Schedule 29 | 27 | [13 empty] | 0
Schedule 29 | 28 | [13 empty] | 0
Schedule 29 | 29 | [13 empty] | 0
Schedule 29 | 30 | [13 empty] | 0
Schedule 29 | 31 | [13 empty] | 0
Schedule 29 | 32 | [13 empty] | 0
Schedule 29 | 33 | [13 empty] | 0
Schedule 29 | 34 | [13 empty] | 0
Schedule 29 | 35 | [13 empty] | 0
Schedule 29 | 36 | [13 empty] | 0
Schedule 29 | 37 | [13 empty] | 0
Schedule 29 | 38 | [13 empty] | 0
Schedule 29 | 39 | [13 empty] | 0
Schedule 29 | 40 | [13 empty] | 0
Schedule 29 | 41 | [13 empty] | 0
Schedule 29 | 42 | [13 empty] | 0
Schedule 29 | 43 | [13 empty] | 0
Schedule 29 | 44 | [13 empty] | 0
Schedule 29 | 45 | [13 empty] | 0
Schedule 29 | 46 | [13 empty] | 0
Schedule 29 | 46A | [13 empty] | 0
Schedule 29 | 47 | [13 empty] | 0
0
Schedule 32 | 1 | [13 empty] | 0
Schedule 32 | 1.1 | [13 empty] | 0
Schedule 32 | 1.2 | [13 empty] | 0
Schedule 32 | 1.2A | [13 empty] | 0
Schedule 32 | 1.3 | [13 empty] | 0
Schedule 32 | 1.4 | [13 empty] | 0
Schedule 32 | 1.5 | [13 empty] | 0
Schedule 32 | 1.6 | [13 empty] | 0
Schedule 32 | 1.7 | [13 empty] | 0
Schedule 32 | 1.8 | [5 empty] | YES | [7 empty] | 1
Schedule 32 | 1.9 | [13 empty] | 0
Schedule 32 | 1.10 | [5 empty] | YES | [7 empty] | 1
Schedule 32 | 2 | [13 empty] | 0
Schedule 32 | 2.1 | [13 empty] | 0
Schedule 32 | 2.2 | [13 empty] | 0
Schedule 32 | 2.3 | [13 empty] | 0
Schedule 32 | 2.4 | [13 empty] | 0
Schedule 32 | 2.5 | [13 empty] | 0
Schedule 32 | 3 | [13 empty] | 0
Schedule 32 | 3.1 | [5 empty] | YES | [7 empty] | 1
Schedule 32 | 3.2 | [13 empty] | 0
Schedule 32 | 3.3 | [13 empty] | 0
Schedule 32 | 3.4 | [13 empty] | 0
Schedule 32 | 3.5 | [13 empty] | 0
Schedule 32 | 3.6 | [13 empty] | 0
Schedule 32 | 4 | [13 empty] | 0
Schedule 32 | 4.1 | [5 empty] | YES | [7 empty] | 1
Schedule 32 | 4.2 | [5 empty] | YES | [7 empty] | 1
Schedule 32 | 4.2A | [5 empty] | YES | [7 empty] | 1
Schedule 32 | 4.3 | [13 empty] | 0
Schedule 32 | 4.4 | [13 empty] | 0
Schedule 32 | 4.5 | [5 empty] | YES | [7 empty] | 1
Schedule 32 | 4.6 | [13 empty] | 0
Schedule 32 | 5 | [13 empty] | 0
Schedule 32 | 5.1 | [13 empty] | 0
Schedule 32 | 5.2 | [13 empty] | 0
Schedule 32 | 5.3 | [13 empty] | 0
Schedule 32 | 5A. | [5 empty] | YES | [7 empty] | 1
Schedule 32 | 5A.1 | [13 empty] | 0
Schedule 32 | 5A.1A | [13 empty] | 0
Schedule 32 | 5A.2 | [13 empty] | 0
Schedule 32 | 6 | [13 empty] | 0
Schedule 32 | 6.1 | [6 empty] | YES | [6 empty] | 1
Schedule 32 | 6.2 | [6 empty] | YES | [6 empty] | 1
Schedule 32 | 6.3 | [5 empty] | YES | [7 empty] | 1
Schedule 32 | 6.4 | [10 empty] | YES |  |  | 1
Schedule 32 | 6.4A | [13 empty] | 0
Schedule 32 | 6.5 | [5 empty] | YES | [7 empty] | 1
Schedule 32 | 6.6 | [13 empty] | 0
Schedule 32 | 6.7 | [13 empty] | 0
Schedule 32 | 6.8 | [13 empty] | 0
Schedule 32 | 6.9 | [13 empty] | 0
Schedule 32 | 6.10 | [8 empty] | YES |  |  |  |  | 1
Schedule 32 | 6.11 | [8 empty] | YES |  | YES |  |  | 2
Schedule 32 | 6.12 | [8 empty] | YES |  |  |  |  | 1
Schedule 32 | 7 | [13 empty] | 0
Schedule 32 | 7.1 | [13 empty] | 0
Schedule 32 | 7.2 | [13 empty] | 0
Schedule 32 | 7.3 | [13 empty] | 0
Schedule 32 | 7.4 | [13 empty] | 0
Schedule 32 | 7.5 | [13 empty] | 0
Schedule 32 | 7.6 | [13 empty] | 0
Schedule 32 | 7.7 | [13 empty] | 0
Schedule 32 | 7.8 | [13 empty] | 0
Schedule 32 | 7.9 | [13 empty] | 0
Schedule 32 | 7.1 | [13 empty] | 0
Schedule 32 | 7.11 | [13 empty] | 0
Schedule 32 | 7.12 | [13 empty] | 0
Schedule 32 | 7.13 | [13 empty] | 0
Schedule 32 | 7.14 | [13 empty] | 0
Schedule 32 | 7.15 | [13 empty] | 0
Schedule 32 | 7.16 | [13 empty] | 0
Schedule 32 | 7.17 | [10 empty] | YES |  |  | 1
Schedule 32 | 8 | [13 empty] | 0
Schedule 32 | 8.1 | [13 empty] | 0
Schedule 32 | 8.2 | [13 empty] | 0
Schedule 32 | Definitions | [5 empty] | YES | YES | [6 empty] | 2
Charging Methodology CPs Legal Text Overlap Tracker