## Horizon Scan
DCUSA Horizon Scan 2024 - 2027
YEAR | [8 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
MONTH | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
DUoS Charges SCR | Work paused over winter period - with Ofgem focusing on other areas of work | Progress DUoS charging reform under a dedicated SCR (Phases: Discovery; Options definition and analysis; and Minded-to policy positions) | [20 empty] | Ofgem Final Decision and Direction on DUoS SCR | Industry to raise and progress DCUSA Change Proposals following DUoS Charges SCR Final Decision |  |  |  |  | Ofgem Decision on Change Proposals | Production of models and DNOs to set tariffs |  | 15 Months Notice Period | [14 empty] | Go Live
Market Wide HH Settlement | Physical Baseline and Detailed Design and Code Change recommendations delivered | The Code drafting timeline has been extended to allow sufficient time for drafting and actioning of consultation comments as well as adding contingency | [15 empty] | System Integration Testing Start |  |  |  |  | Start of 1 yr migration for UMS / Advanced + Start of 1 yr migration for Smart / Non-Smart + Load Shaping Service switched on | [7 empty] | Central systems ready for migrating MPANs |  |  |  | All suppliers must be able to accept MPANs under the new TOM (one way gate) | [6 empty] | Full transition complete |  | Cut over to new settlement timetable
BEIS Smart Systems and Flexibility Plan | BEIS Smart Systems and Flexibility Plan
Smart Meter Rollout | Smart Meter Rollout
ENA Open Networks Project | ENA Open Networks Project
BEIS Energy Codes Review | BEIS Energy Codes Review
Ofgem’s Decarbonisation Action Plan | Ofgem’s Decarbonisation Action Plan
Future of local energy institutions and governance | Focus will be on evaluating reform options, with a view to arriving at conclusions by early 2023. |  | Work to enter its implementation phase
Review of Electricity Market Arrangements | Review of Electricity Market Arrangements
Future System Operator | Future System Operator
Future reform to the electricity connections process | Short-term action (2023) | [7 empty] | Medium-term improvements (now – 2025) | [23 empty] | Longer-term outlook (2025 – 2030+)
Ofgem letter on strategic transmission charging reform |  |  |  |  | Ofgem letter on strategic transmission charging reform
Ofgem Proposal to introduce the Future Regulation Sandbox |  |  |  |  | Responses to Ofgem letter on strategic transmission charging reform |  |  |  |  | Ofgem reviews responses and considers implementation |  |  |  | Potential implementation period if Ofgem decide to move ahead with proposal (indicative only)
Open letter on regulatory arrangements for IDNOs |  |  |  |  | Responses Ofgem letter on strategic transmission charging reform |  |  |  | Next steps following Open letter on regulatory arrangements for IDNOs
Ofgem Consultation on SoLR Offset Levy | [9 empty] | Consultation runs until 5 April 2024 |  |  | Ofgem reviews responses |  | Next steps if Ofgem decide to move ahead with proposal (indicative only)
Ofgem Open Letter regarding Data Best Practice and its future in Codes | [10 empty] | Ofgem publishes Open Letter regarding Data Best Practice and its future in Codes (https://www.ofgem.gov.uk/publications/open-letter-regarding-data-best-practice-and-its-future-codes)] | Ofgem to engage with industry and other relevant parties over Summer 2024 | [5 empty] | Next steps to include consultation and potential formation of new steering group (indicative only) | [6 empty] | Implementation period (indicative only)
Note on A11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be updated once a review of new information has been carried out: https://www.ofgem.gov.uk/publications/consultation-future-local-energy-institutions-and-governance
Note on A12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be updated once new information has been reviewed: Review of electricity market arrangements: summary of responses

## Commentary
Horizon Item | Commentary | Update
DUoS Charging SCR | Area of development Detail Principles based topics 1 Updated case for change • Current shortcomings of DUoS methodology + Desired key outcomes of DUoS reform + Alignment with other charging reforms + Alignment with relevant wider market reforms + Consideration of interactions with the delivery of a net zero electricity system 2 Principles and trade-offs in network charging • Understand trade-offs in network charging principles + Prioritise and fully understand how options serve various principles 3 Role of DUoS in the emerging energy system (including decarbonisation) • Reference cases we want to test options against – both in terms of market arrangements and future energy scenarios + The size of the signal we have at our disposal to induce behavioural response 4 What signals to send and to whom? • What signals to send and the way that those signals are passed on to users of the network 5 Distributional impacts, vulnerability, and fairness • How big a signal are we willing to send + What are the distributional impacts and are there particular consumer archetypes we need to pay attention to Technical topics 6 Outstanding issues from phase 1 Access SCR reforms • Reviewing and assessing locational signals removed from connection charges + Ensuring DUoS arrangements are compatible with new non-firm/time-profiled access rights 7 Linkages to flexibility • How DUoS works in practice in enabling and achieving the benefits of flexibility, sitting alongside other signals/mechanisms + Linkages with wider full-chain flexibility work 8 Choice of cost model • What cost model is appropriate at each voltage level considering path dependency and future adaptability + Addressing the boundary distortion between EHV and HV/LV created by the current methodologies 9 Locational granularity • How the cost models need to evolve and developing options for introducing more locational granularity 10 Charge design/cost allocation • Based on the above technical choices what is the appropriate way to charge customers + Balance between usage-based and capacity based charges On 25 February 2022 Ofgem published their Decision (https://www.ofgem.gov.uk/publications/distribution-use-system-charges-significant-code-review-launch) to take forward the reform of Distribution Use of System charges under a separate Significant Code Review on revised timescales. Following consultation in November 2021, Ofgem decided to descope the wide-ranging review of Distribution Use of System (‘DUoS’) charges from the current Electricity Network Access and Forward-Looking Charges Significant Code Review (‘Access SCR’) and take it forward under a dedicated DUoS SCR with a revised timescale. This decision retains the overall objective of DUoS reform from the Access SCR - to ensure electricity networks are used efficiently and flexibly, reflecting users’ needs and allowing consumers to benefit from new technologies and services while avoiding unnecessary costs on energy bills in general. The DUoS SCR will directly mirror the scope of the DUoS review set out in the original Access SCR. This would include but not be limited to the following issues: - A review of the charging methodologies for Extra-High Voltage (EHV), as well as High Voltage/Low Voltage (HV/LV) - The balance between usage-based and capacity-based charges, as well as charges that could vary by time-of-use - Improvements to signals about how network costs and benefits vary by location - Improved predictability of charges for EHV users - The potential need for mitigating measures such as a basic charging threshold to protect small users (and vulnerable customers) from sharper charging signals | 8 November 2022 - Open Letter regarding Prioritisation of Electricity Network Charging Reforms A letter was published that sets out Ofgem’s approach to prioritising work on electricity network charging and connections over the coming months. It covers how Ofgem will deploy their teams to focus on areas most likely to protect consumers this winter and where Ofgem have slowed the delivery of some longer term policy work which they look to resume as soon as they are able to. Update 31 October 2023 – CFF Distribution Charging Reforms (key points) Ofgem have restarted DUoS reform work. During the CFF session, Ofgem shared some initial areas of interest and provided a space for industry to feed in its views on these areas. Amidst their ongoing conversations with stakeholders across industry, Ofgem have identified a shortlist of reforms to DUoS arrangements that they hope will ensure the arrangements are fit for purpose and fully support the energy transition. In the near term, Ofgem will examine: • Issues with the stability of EHV charges; and • The costs and benefits of DUoS credit arrangements for generation. In the longer term, Ofgem will focus on: • Inconsistencies in charging signals depending on voltage and location of connection across T&D; • The locational and temporal granularity of the DUoS charges at all levels; and • How costs are allocated between the residual and forward-looking charges. Ofgem are also considering: • Some work on future-proofing the IDNO model; and • A post-implementation review of our residual reforms CFF Held in March 2024 - DUoS charging reform – update on prioritisation of reform options Near term now = • Issues with existing CDCM and EDCM related to negative residuals •A framework for a longer term reform of DUoS charges Near term Long term now = • Inconsistencies in charging signals depending on voltage and location of connection across T&D •The locational and temporal granularity of the DUoS charges at all levels Current plan Q1 - Q2 2024 - Issue discovery - Work with ENA & DNOs to understand problems - Publish notes providing detail & obtain feedback from industry - Assess options - Aim: informal consultation on options Q3 – Q4 2024 - Review feedback - Aim: minded-to position on solution for 2026/27 charges Call for input - Distribution Use of System Charging – Managing the effects of surplus residual charges -25 July 2024 to 06 September 2024 In this call for input Ofgem outline the proposed approaches for managing the effects of surplus residual charges. Explanatory notes of the charging methodology issues as presented at the March 2024 Charging Futures Forum are found on the ESO Charging Futures Forum webpage. Ofgem are publishing this call for input to signal to relevant parties that they are considering their approach to address these issues. It includes Ofgem's assessment of options for resolving the issues and their proposed approach to implementation. Ofgem invite views from stakeholders on these developments ahead of identifying any preferred solution or solutions.
Market Wide HH Settlement | FBC Decision - Apr-21 - Publication of the Full Business Case, which includes the transition plan and decision on the TOM. Architecture Working Group (AWG) Recommendation delivered - Jun-21 - The AWG will deliver recommendations providing guidance for the solution architecture required to enable the DWG’s TOM which will set the framework for subsequent IT system design. DB Start - Aug-21 - The DB (Design and Build) phase will commence in August 2021 with Elexon's Central System, followed by DCC in Feb 2022 and other parties in May 2022. PMO/PPC/SI/IPA fully functioning - Oct-21 - PMO/SI/PPC/IPA have stood up their team and are fully operational with all programme management processes and governance forums established. Physical baseline delivered - Apr-22 - In order for the other parties to commence the DBT phase a complete Physical Baseline, aligning both technical and regulatory designs, will be delivered. Code change and detailed design recommendations delivered - Apr-22 - The CCDG will deliver the recommendations aimed at addressing any outstanding areas of the DWG’s TOM design, and will deliver the recomendations for the changes to the Industry Codes and subsidiary documents necessary to enable the TOM. Smart Meters Act powers enabled - May-22 - Time limited (5 year) powers in Primary Legislation for Ofgem to make changes to Industry Codes for the purposes of MHHS are activated. Code changes delivered - Nov-22 - All changes to regulation (licences, industry codes (including BSC, SEC, REC, DCUSA)) have been made setting out the regulatory baseline. System Integration Testing Start - Aug-23 - System Integration Testing (SIT) will commence in August 2023. This test phase involves the central parties (Elexon, DCC, comms network providers and the registration system providers) along with a small number of agents and suppliers. Central systems ready for migrating MPANs - Sep-24 - Following completion of the testing phase (excluding TE18 Security Testing), the Central Systems (BSC central systems, registration, DCC and communication systems) will be ready to initiate migration of Meter Point Administration Numbers (MPANs) from the current market roles into the new market roles. Start of 1 year migration for UMS/Advanced - Oct-24 - Start of migration window for suppliers to move all UMS and advanced meter points to be settled in the new arrangements. Start of 1 year migration for Smart/Non-smart - Nov-24 - Start of migration window for suppliers to move all smart and non-smart meter points to be settled in the new arrangements. Load Shaping Service switched on - Nov-24 - The LSS will be switched on after a period used to gather and validate settlement period level data from the smart meter data service. All suppliers must be able to accept MPANs under the new TOM (one way gate) - Feb-25 - Deadline by which all suppliers must have the systems and services in place to accept MPANs under the new TOM. From this point MPANs cannot be moved back into NHH regime on change of supplier. Full transition complete - Oct-25 - Completion of implementation activities including 1 year migration. Cut over to new settlement timetable - Nov-25 - The date of the cut over to the new settlement timetable will occur after the end of migration. The decision on when the settlement timetable should be reduced should be taken nearer the time, and on market monitoring against trigger points. We think that industry should ensure that the new settlement timetable is introduced as soon as practical after the end of migration, but if this is longer than 4 months after the end of migration then this decision should be brought to Ofgem. | DWG’s final report to Ofgem = August 2019 The Design Working Group (DWG) for Market-Wide Half Hourly Settlement (MHHS) issued its final report to Ofgem on Saturday 31 August. The report confirms the DWG’s preferred Target Operating Model (TOM), which it said captures all essential settlement data and processes and is not a barrier to future market innovation. The preferred transition approach has also been confirmed, with the DWG recommending that improvements to the elective HHS process are progressed under the existing change process as a “quick win”. Other areas to be considered that have been identified include the rationalisation of industry data items, and the detailed approach to the settlement run “run-off” arrangements under the new TOM. The CCDG has been established to develop, consult on and recommend solutions for the detailed areas of the Target Operating Model design which the Design Working Group (DWG) and/or Ofgem identified as outstanding when the DWG delivered its final report in August 2019. The CCDG will identify the changes required to relevant industry Codes and subsidiary documents and will review and consult on draft legal text developed for each Code by the relevant Code Administrators.The Code Administrators will attend the CCDG meetings when requested and have a monthly telecon meeting with Ofgem on progress to date relating to the development of the respective Code changes. CCDG consultation on detailed areas of TOM design (Q4 2020) AWG consultation on reference architecture (Q2 2021) CCDG consultation on detailed transition approach (Q2 2021) AWG final report to Ofgem for approval (Q2 2021) CCDG consultation on Industry Codes legal drafting (Q1 2022) CCDG final report to Ofgem for approval (Q2 2022) 2021/22 Ofgem Forward Workplan indicates the following: Q1 – Publish full business case Q2 – Consult on implementation governance and obligations Q2 – Decide on implementation governance and obligations Q3 – Make code and licence changes as necessary
BEIS Smart Systems and Flexibility Plan | In July 2017 BEIS issued a paper on Smart Systems and their Flexibility Plan which contains a number of recommendations that could have impacts on DCUSA, such as removing barriers for electricity storage on the network, linking microgeneration and smart metering and modifying industry codes on a wholesale level to incorporate energy storage. The plan detailed key focus areas in response to an electricity system undergoing changes such as: • increased use of low-carbon sources, • increased uptake of electric vehicles (EVs) and smart technologies, • the growth of distributed energy and the role of flexibility. The initial plan set out 29 specific actions for BEIS and Ofgem to carry out to achieve a smart and flexible future energy system. On 16 October 2018, BEIS and Ofgem released a progress report that said, to date, 15 of the 29 actions in the plan have been implemented across the three fields: • removing barriers to smart technologies • enabling smart homes and businesses, and • making markets work for flexibility. The report committed to delivering the remaining 14 forward actions by 2022. In addition, BEIS and Ofgem have identified nine related actions beyond those set out in the plan since its publication. For instance, the BEIS intends to consult on the treatment of electricity storage facilities with respect to the current national planning threshold to ensure they face no barriers to deployment. Some of these issues are expected to impact DCUSA in 2019. 19 July 2022 - a report was published -Delivering a Digitalised Energy System (https://es.catapult.org.uk/report/delivering-a-digitalised-energy-system/) - which laid out next steps | 29 July 2024 - Flexibility Market Asset Registration Consultation Opened - Closing date is 23 September 2024 Ofgem are seeking views on delivering common Flexibility Market Asset Registration as the first step in achieving the overall Flexibility Digital Infrastructure vision. In this current consultation, Ofgem set out how their Flexibility Digital Infrastructure policy has evolved. Ofgem welcome responses to their proposals for achieving common Flexibility Market Asset Registration for distributed flexibility assets to access Electricity System Operator (ESO) and Distribution System Operator (DSO) markets. Ofgem are seeking views and input from stakeholders on: - prioritising common Flexibility Market Asset Registration as the first step in achieving the overall Flexibility Digital Infrastructure vision - the scope of the digital infrastructure solution, as well as the functions and principles it should deliver - the Market Facilitator being responsible for delivering enablers and design activities, through Working Groups - the advantages and disadvantages of a range of delivery body options for the digital infrastructure itself - aligning in the long term with the policy vision for general asset visibility
Smart Meter Rollout | Ofgem's Smart Meter Rolliut programme has placed obligations on Suppliers to complete rollout of SMETS compliant meters by the end of 2020. Smart Meter Rollout Profiles are collated via DCUSA to aid Meter Operators in their resource allocations for rollout activites. The existing obligation on energy suppliers to take all reasonable steps to install smart meters expires on 31 December 2020. The Government is consulting on a new regulatory framework that will see the rollout continue beyond 2020. Under the proposed new obligation, Ofgem will continue to provide the regulatory oversight of energy suppliers’ compliance with the smart meter rollout. This consultation sets out proposals for the reporting requirements energy suppliers would be subject to under the proposed new obligation. The post-2020 obligation: In its consultation, Government has set out its proposals for a new regulatory framework that will continue to drive market-wide rollout of smart and advanced meters to domestic and smaller non-domestic premises. The proposals would mean that all suppliers in the market would have binding annual installation targets (referred to as Energy Supplier Annual Milestones in the Government consultation) to roll out smart and advanced meters to their remaining non-smart customer base until they reach a minimum smart coverage of 85% in their trajectory towards market wide rollout by 31 December 2024. Each year the annual milestones would be re-set based on the proportion of a supplier’s customer base without a Qualifying Metering System as of 31 December of the previous year. | Overarching Principles 1.1 Reporting requirements for energy suppliers: Minded-to position: For reporting purposes, we are minded to define large suppliers as those with 150,000 or more gas and/or electricity customer accounts as of 31 December of each year from 2020 to 2023; those with less than 150,000 gas and/or electricity customer accounts as of 31 December of each year from 2020 to 2023 will be defined as small suppliers. 1.2 Annual Reporting: Minded-to position: We are minded to require all suppliers to report to Ofgem annually their annual milestones for both gas and electricity as well as their performance against these milestones. 1.3 Timing for reporting: Minded-to position: We are minded to require all suppliers to report their annual milestones for the year ahead as well as their performance for the previous year to Ofgem on 31 January of each relevant year. Beginning of Year Reporting 2.1 Content of Beginning of Year Report – All suppliers: Minded-to position: For Beginning of Year Reporting purposes, we are minded to require all suppliers to submit by 31 January in each of the four years from 2021 their calculated annual milestones for both gas and electricity for the upcoming year. This would include confirmation of their Qualifying Relevant Premises for both gas and electricity as well as total customer base as of 31 December of the preceding year. 2.2 Additional Reporting for Large Suppliers: Minded-to position: In addition to the information set out in section 2.1, we are minded to require large suppliers to submit the following additional infomation as part of their Beginning of Year reporting: • The planned split of their annual milestone delivery to credit and pre-payment customers for both gas and electricity. • The planned split of their annual milestone delivery to domestic and non-domestic customers for both gas and electricity. • Projected installer capacity, productivity and abort rates for the upcoming year. • Key dependencies and risks for the upcoming year. 2.3 Process for managing Beginning of Year Submissions: Minded-to position: For large suppliers, upon receipt of their Beginning of Year Reporting, we are minded to review and respond to suppliers with relevant observations; For small suppliers, upon receipt of their Beginning of Year Report, we are minded to review the submission but only respond where we have a query about the calculation of the annual milestones. End of Year Performance Reporting 3.1 Content of End of Year Performance Report – All suppliers Minded-to position: For End of Year Performance Reporting, we are minded to require all suppliers to submit by 31 January in each of the four years from 2022 their annual installation milestones for the preceding year for both gas and electricity as well as the number of installations for Qualifying Relevant Premises for both gas and electricity for the previous year. All suppliers should also provide a narrative setting out their performance for the previous year. 3.2 Additional End of Year Performance Reporting for Large Suppliers: Minded-to position: In addition to the information set out in section 3.1, we are minded to require large suppliers1 to submit additional information in the following areas as part of their End of Year Performance Reporting: • Number of installations delivered to credit and pre-payment customers for both gas and electricity in the preceding year. • Number of installations delivered to domestic and non-domestic customers for both gas and electricity in the preceding year. 4.1 Publication of Information – All Suppliers: Minded-to position: We are minded to require all suppliers to publish, on their website: • their annual milestones for both gas and electricity for the upcoming year; and • performance against these binding milestones for the preceding year. We are minded to require this information to be published at the same time as suppliers submit their reports to Ofgem in January of each year. Suppliers should also provide a link to their website to Ofgem as to where the information is published. 4.2 Additional Information to be Published – Large suppliers: Minded-to position: In addition to publication of information set out in section 4.1, we are minded to require large suppliers to publish, on their website: • the planned split of their annual milestone delivery to credit, pre-payment, domestic and non-domestic customers; and • their delivery performance against Beginning of Year Report as set out in their End of Year Performance report. We are minded to require this information to be published at the same time as suppliers submit their reports to Ofgem on 31 January and suppliers should also provide a link to Ofgem to where the information is published on the supplier website. Rollout minimum annual installation targets for energy suppliers were introduced at the beginning of 2022 to drive rollout momentum. This Targets Framework will be in place until the end of 2025, with installation targets for the final two years of the policy to be set during 2023.
ENA Open Networks Project | The objectives of the Open Networks Project for the first phase of work in 2017 are to: 1. Develop improved T-D processes around connections, planning, shared TSO/DSO services and operation 2. Assess the gaps between the experience our customers currently receive and what they would like and identify any further changes to close the gaps within the context of ‘level playing field’ and common T & D approach 3. Develop a more detailed view of the required transition from DNO to DSO including the impacts on existing organisation capability 4. Consider the charging requirements of enduring electricity transmission/distribution systems Second Phase in 2018 and then beyond to RIIO ED2/T2 (2023): Phase 2: Impact Assessment of Options and Preferred Design Phase 3: Regulatory Enactment Phase 4: Design, Build and Test | (https://www.energynetworks.org/creating-tomorrows-networks/open-networks/ ) In 2023, Open Networks will focus on increasing participation and volume in the local flexibility market in line with actions from BEIS’ and Ofgem’s Smart Systems and Flexibility plan (2021). Open Networks aims to allow flexibility providers to easily engage with the market while having transparency of network planning and decision-making and make energy networks more coordinated and aligned.
Ofgem/DESNZ Energy Codes Reform | Government and Ofgem launched a joint comprehensive review into the codes which govern the energy system. The aim of the review is to consider options for improving the existing arrangements, including scope for fundamental reform. Published 22 July 2019 - Energy Codes Review Consultation Government and Ofgem are seeking views on changes proposed to the energy codes governance framework. Many of the detailed rules that facilitate the gas and electricity markets are set out in ‘codes’ or rules governed by industry-led processes and overseen by Ofgem. These rules need to adapt much more rapidly to enable the transition towards a more flexible energy system with net zero emissions, while minimising costs and protecting consumers. Reforming the code governance framework could therefore better facilitate strategic changes in the sector, unlocking innovation and significant benefits to consumers. This joint Ofgem and BEIS consultation seeks views on their proposals for reforming the code governance framework.The consultation closes at 11:45pm on 16 September 2019 Energy codes review workshops September 2019 BEIS and Ofgem will hold 2 identical workshops on these proposed reforms on Monday 2 September and Wednesday 4 September. A webinar may also be held in the same week if there is enough interest • 2021/22 Ofgem Forward Workplan indicates the following: Activity: Energy Codes Review - With BEIS, carry out a second energy codes consultation - Begin to implement energy codes reforms Activity: Engineering standards 6 April 2022 The Government provided its response to the consultation on Energy Code Reform and the following is an overview of their d6 April 2022 the Government provided its response to the consultation on Energy Code Reform and the following is an overview of their decisions: Government has decided to implement preferred option (Option 1), where Ofgem will be given new strategic code functions, including the ability to establish and regulate (via licence) one or more code manager(s). For the sake of regulatory and legislative simplicity, this decision will result in an expansion of Ofgem’s existing functions rather than the creation of a distinct entity known as the ‘strategic body’. This means that the strategic code functions will constitute new roles for Ofgem, rather than a new body that Ofgem is taking on. | 14 December 2022 - Energy Code Governance Reform Call for input Ofgem issued a call for input following the government response on Energy Code Reform published in April 2022. Ofgem are seeking initial views from all interested stakeholders on potential code consolidation as part of Ofgem’s approach to implementing the reforms. They were also seeking views on the content of the code manager licence conditions, and the role of stakeholders in the new governance framework. Alongside the call for input Ofgem published an independent report on potential code consolidation options prepared by Cornwall Insight in April 2022. This report was commissioned by Ofgem to assess a range of high-level options for code consolidation which are discussed further in the call for input. 30 January 2024 - Consultation on the implementation of energy code reform - Response deadline: 23 April 2024 Section 2: Designation of codes and central systems This section recaps on the scope of code reform and sets out which codes and central systems Ofgem intend to recommend the Secretary of State should designate as “qualifying documents” and “qualifying central systems” for the purposes of the use of the transitional powers conferred to Ofgem by virtue of Schedule 12 of the Act. Section 3: Code consolidation This section sets out Ofgem’s approach to assessing a shortlist of code consolidation options and presents their preferred options. This section should be read in conjunction with the accompanying draft impact assessment, which they published alongside the consultation, where they set out further detail on the quantitative and qualitative analysis used to inform these proposals. Section 4: Strategic direction This section sets out Ofgem’s proposed approach to implementing their Strategic Direction Statement (SDS), including proposed process and timings. Section 5: Code governance arrangements March 2024: Energy Code Reform: Joint DESNZ/Ofgem Consultation on Code Manager Licensing and Secondary Legislation Closing date: 5 May 2024 The document is ordered into chapters, each of which covers one primary policy area and contains our related proposals and a set of questions that we seek your views on. The final two chapters provide an overview of planned next steps and a recap of all the consultation questions. The policy chapters are as follows: • Chapter 1: Code manager licence • Chapter 2: Not-for-profit requirement • Chapter 3: Setting code manager budgets • Chapter 4: Code manager funding and cost recovery • Chapter 5: Code manager incentivisation • Chapter 6: Conflicts of interest and independence • Chapter 7: Financial and operational controls • Chapter 8: Code maintenance and modification • Chapter 9: Code manager selection DCUSA Ltd has responded to this consultation This section sets out Ofgem’s proposed approach to establishing the role of Stakeholder Advisory Forums. It includes Ofgem’s proposal to create a workgroup to help them identify what an updated code modification process should look like. Ofgem also explain their intention to review the existing code objectives, and harmonise the code modification prioritisation processes under the existing arrangements. Section 6: Transition This section sets out Ofgem’s proposed approach to transitioning the codes to the new governance framework. It presents and seeks views on Ofgem’s proposal to phase the transition. Ofgem also set out an indicative order in which Ofgem have proposed to transition the codes to the new arrangements (subject to decisions on code consolidation). 22 August 2024 - Implementation of energy code reform: consultation decision published In January 2024 Ofgem published a consultation on their approach to implementing the industry code governance reforms set out in the Energy Act 2023. The decision document summarises the responses to that consultation and outlines Ofgem's policy decisions on the proposals that they sought views on, including code consolidation and Ofgem’s approach to transitioning to the new code governance framework. Ofgem intend to consult further on detailed implementation proposals in due course, including statutory consultations where applicable. This decision confirmed the decision to consolidate the DCUSA and the CUSC together.
Ofgem’s Decarbonisation Action Plan | In this action plan, Ofgem build on their existing work and outline their next steps in making rapid, low-cost decarbonisation of the energy sector a reality. Industry are on a decades-long journey to set zero, and they will continue to adapt and develop this programme, as opportunities arise and to reflect changes in government policy and circumstances in the energy market. The high-level items in the plan are as follows: Preparing the networks to deliver 1. Designing cost effective networks for net zero 2. Long-term planning and innovation 3. More effective coordination to deliver low cost offshore networks 4. Preparing for low-carbon heat Ensuring the electricity system is ready 5. Preparing system operators for a net zero future 6. Supporting flexibility 7. Enabling electric vehicles at low cost Opening up retail innovation and driving behaviour change 8. Opening up retail innovation Reforming the organisation – How we will change 9. Adapting the organisation | 2021/22 Ofgem Forward Workplan indicates the following: Activity: Distribution System Operation (DSO) and Whole System regulations (Supporting Decarbonisation Action Plan Action Five) Q1 – Publish decision on Whole Electricity Systems licence change Q1 - Review the Distribution Network Operator (DNO) flexibility report Q2 – Working groups commence for the Long-Term Development Statement changes Q2/Q3 – Consult on CLASS ancillary services Q3 – Finalise Network Development Plan requirements Review Open Networks progress, including on coordinated development of DNO/ESO markets, cost transparency, data sharing, etc Outcome: Net-zero transition goals are met through system operation (Supporting Decarbonisation Action Plan Action Five) Activity: Distribution System Operator (DSO) governance review Q1 – Review Distribution Network Operator arrangements Q2 – Assess and evaluate DSO model options Q3/4 – Assess costs and benefits and prepare for consultation Activity: Engineering standards Q1/Q2 – With BEIS, assess and consider how to take forward the recommendations from the Engineering Standards Review
Future of local energy institutions and governance | 26 April 2022 - Call for Input: Future of local energy institutions and governance Background: As we transition to net zero, we will see rapid decarbonisation and decentralisation of generation and demand. Transforming the ways in which we generate electricity, heat our homes and power our vehicles will require radical changes across the energy system, with particular focus on the electricity distribution system. Electricity distribution network operators (DNOs) have been building capabilities in planning, operating and market facilitation of flexible resources to drive more efficient development and use of the decarbonising electricity system. These capabilities are currently referred to as Distribution System Operation (DSO) roles. However, other institutions also play a role in facilitating the energy system transition at a sub-national level, including Gas Distribution Networks (GDNs) and Local Government, including local and combined authorities as well as other supporting bodies. As the energy system undergoes the unprecedented transition to net zero, it is imperative that key energy system functions are performed by institutions with the competence, appropriate skillset and incentives to drive net zero at least cost, and that there is clear accountability and coordination in the delivery of these. This Call for Input begins our review into the effectiveness of institutional and governance arrangements at a sub-national level to support delivery of net zero at least cost, and the case for alternative approaches. Purpose and scope • The purpose of this Call for Input is to examine the institutional and governance arrangements needed to deliver the functions Ofgem consider are required at a sub-national level to drive the evolving energy system, in order to achieve a timely and cost effective net zero transition. • Ofgem think the right place to start is with the planning of the energy system at a sub-national level to drive the most cost-effective decarbonisation outcomes, and as part of this on the relationships between planning, markets and operation. Ofgem believe the electricity distribution system is a key starting point due to the clear changes in demand and generation we are seeing and will continue to see. However, in this Call for Input Ofgem acknowledge that changes to the electricity system will both drive and respond to changes in other energy systems, and so have widened their focus on planning to consider electricity, gas(es) and heat. • In this Call for Input, Ofgem set out and seek input from stakeholders on: - The energy system functions needed at a sub-national level to facilitate the transition to net zero at least cost and the criteria we consider need to be met for effective delivery of these functions; - The suitability of current and planned institutional and governance arrangements for delivering these functions; and - The opportunities and risks of change, and possible options for alternative arrangements. • Responses are due by 07 June 2022. | 29 July 2024 - Decision: Market facilitator delivery body Ofgem's review into local governance and institutional arrangements started with a call for input in April 2022, followed by a consultation published in March 2023 where they proposed a new role for the market facilitation of flexible resources, to be assigned to a single expert entity capable of delivering more accessible, transparent and coordinated flexibility markets. Ofgem confirmed their decision to create a market facilitator in November 2023. Ofgem published a consultation in December 2023 on whether Elexon or National Energy System Operator (NESO) should be the market facilitator delivery body. This document contains Ofgem's decision that Elexon will be the market facilitator delivery body. In this decision document Ofgem summarise consultation responses, set out the rationale for their decision and explain next steps. Ofgem will carry out further work to develop and establish the market facilitator, working with Elexon and wider stakeholders across three workstreams:
Review of Electricity Market Arrangements | Review of Electricity Market Arrangements BEIS Consultation Closing date: 10 October 2022 Purpose The purpose of REMA is to identify, assess, and – where necessary – implement options for reforming our market arrangements in GB, to ensure that they are fit for the purpose of meeting our commitment to a fully decarbonised electricity system by 2035, subject to security of supply. There are three main stages to achieving this purpose: • Setting out a clear statement of the case for reform (this consultation) • Developing options and determining what reforms are needed through extensive engagement with the energy sector (2022-23) • Establishing a full delivery plan and overseeing implementation (from the mid-2020s) in time to contribute to our 2035 commitment. This Review will focus on delivering the enduring market arrangements needed to deliver a fully decarbonised electricity system by 2035. A broad range of options are in scope of this Review, from medium-term changes to existing arrangements that can be delivered from the mid-2020s, to longer-term transformational reforms, as well as low regret ‘quick wins’ which could be pursued on accelerated timelines and implemented regardless of the end package of reform. We will do this in a way that ensures continued investor confidence in our energy system and assets. Any changes to the core mechanisms that drive investment - the CfD and Capacity Market - will be considered carefully with this in mind and whilst this programme runs, all existing schemes will continue. Any reforms would be subject to further consultation. | 12 March 2024: Review of electricity market arrangements (REMA): second consultation From: Department for Energy Security and Net Zero Summary This second consultation is an opportunity to provide feedback to government on the ongoing review of electricity market arrangements (REMA). This consultation ran from 9am on 12 March 2024 to 11:59pm on 7 May 2024 Consultation description This consultation seeks views on a narrowed range of options to deliver an enduring electricity market framework that will work for businesses, industry, and households. The consultation document is accompanied by: - an Options Assessment - a set of technical research reports
Future System Operator | Original consultation - 20 July 2021 to 28 September 2021 Summary BEIS/Ofgem were seeking views on proposals for the future role, organisational design and phased implementation of a Future System Operator with responsibilities across both the electricity and gas systems. Detail of outcome The government / Ofgem’s response to this consultation sets out a summary of responses, and our key decisions, including the commitment to proceed with the creation of an expert, impartial Future System Operator (FSO). The new Operator will: • have a duty to facilitate net zero while maintaining security of supply, and an efficient, coordinated and economical system • take on all the main existing Electricity System Operator (ESO) roles and the longer-term elements of the Gas System Operator (GSO), enabling more coordinated, strategic and whole systems planning • be a public corporation, inside the public sector, but with operational independence from government • be funded by consumers through price control arrangements regulated by Ofgem, but with the operational freedom to manage and organise itself to effectively deliver its roles and objectives • have a duty to provide advice on request to government and Ofgem to inform key policy decisions • take an increasingly significant role in shaping the energy system, including driving competition across the energy sector The response also sets out our implementation approach to ensure a smooth transition to the new arrangements, and next steps. | Next steps We set out our next steps for establishing and implementing the FSO below: • Primary Legislation - As set out above, creating the FSO and its associated duties and powers will require primary legislation, which the government plans to introduce when parliamentary time allows. • Secondary legislation, licensing and code amendments - Assuming the primary legislation has been enacted, a limited amount of secondary legislation will be needed in a number of areas. New licensing arrangements will be required to ensure that the FSO is properly licensed and can be funded to undertake its activities, and other industry licences and codes will need to be modified where necessary to take account of the new arrangements, with consultation of industry stakeholders where appropriate. • Discussions with NG Plc, NGESO and NGG - We will continue discussions with the key affected parties to make sure there is a plan in place for smooth transition to the new arrangements, avoiding disruption to the crucial services that NGESO and NGG currently provide. Subject to these discussions and legislation, there will be transactions between government and NG Plc and any other relevant parties, to transfer the relevant elements of their businesses into the FSO. • Engagement with the wider energy industry - We will also engage with industry participants at the appropriate points, to make sure all stakeholders affected by the changes have access to the information they need to prepare for the transition to the FSO. • Elexon consultation – In parallel to the above we also plan on publishing a separate consultation on Elexon ownership that will set out in more detail the options under consideration. We would welcome stakeholder responses to this consultation. We are aiming to deliver as soon as practicable, while maintaining the safety and stability of the energy systems. Depending on a number of factors, including timings of legislation and discussing timelines with key parties, the FSO could be established by, or in, 2024. Government will be working closely with Ofgem to take preliminary steps to smooth the transition. FSO Codes Change Programme – Response to statutory consultation on modifications to industry codes to implement the Independent System Operator and Planner (ISOP) Publication date: 29/08/2024 ((Ofgem and Department for Energy Security and Net Zero) The response document sets out Ofgem’s and the Department’s responses to the statutory consultation on modifications to industry codes to implement the Independent System Operator and Planner (ISOP), published in May 2024. In the statutory consultation Ofgem/Government stated they would assess responses before making decisions on final modifications. Having considered and taken account of stakeholder feedback received in response to that consultation, this response document sets out decisions taken by both organisations on the modifications to the following industry codes and their associated documents (collectively referred to as the “Codes”) on which the Relevant Authorities intend to exercise powers under section 169 of the Energy Act 2023 in order to modify directly these Codes which includes the DCUSA Ofgem / DESNZ intend for the Relevant Authorities to exercise powers, respectively, under section 169 of the Energy Act 2023 in order to modify directly these Codes. The Gas and Electricity Markets Authority (GEMA) and the Secretary of State of the Department will each act as the respective Relevant Authority for respective parts of the modifications. The intention is for GEMA to be the Relevant Authority for all the code modifications, excluding those related to National Security. In the case of the latter, the intention is for the Secretary of State to be the Relevant Authority.
Changes to Department for Business, Energy & Industrial Strategy (BEIS) - creation of four new Departments | The Government has announced the creation of four new Departments, which will divide the responsibilities of the former Department for Business, Energy & Industrial Strategy (BEIS) 7 February 2023: https://www.gov.uk/government/news/making-government-deliver-for-the-british-people The new departments to be: - Department for Energy Security and Net Zero: tasked with securing the nation's long-term energy supply, bringing down bills and halving inflation. - Department for Science, Innovation and Technology: which will drive innovation behind delivering improved public services, creating new and better-paid jobs and growing the economy. - A combined Department for Business and Trade: this will support growth by backing British businesses at home and abroad, promoting investment and championing free trade. - A re-focused Department for Culture, Media and Sport: this will recognise the importance of these industries to our economy and build on the UK’s position as a global leader in the creative arts. | Next steps Monitor future developments. Current workstreams are likely to continue within their new departments, but new developments may arise as these become more established.
Open letter on future reform to the electricity connections process | Proposed objective, outcomes and principles for reform Ofgem's objective for connections reform is to see electricity connection offers with shorter average connection dates which better meet customers’ needs and enable a timely transition to net zero. This should be part of a transparent and auditable process, underpinned by standardised and accessible data. This objective is underpinned by Ofgem's principal objective to protect the interests of current and future GB energy consumers (and their other statutory duties). It is also guided by Ofgem's Consumer Interests framework and strategic priorities, by ensuring connections arrangements are fit for the future and support a timely and efficient transition to a secure and resilient net zero future system, in line with government decarbonisation and energy security objectives. Ofgem have identified a set of reform outcomes which they consider are key to delivering their aims for connections arrangements and will continue to consider any potential for more specific supporting target outcomes or indicators of success and welcome stakeholder views: • Transparent, consistent data giving applicants advance, granular insight into expected grid capacity and level of network investment needed – to equip parties across the system with information on when and where is optimal to connect, enabling streamlined, well-informed applications. • More robust connection applications, enabling well-progressed projects to proceed – to ensure well-developed connection projects, including new technologies and business models, can deliver when ready and are not unduly delayed by projects which are not ready to proceed. • Reforms deliver improvements swiftly, enabling shorter average connection dates to be offered to customers – at both transmission and distribution, to meet net zero pathways for a secure, resilient low carbon system, through improved connection processes and planning assumptions and approaches. • Greater coordination and consistency across system boundaries, supporting more consistent outcomes and efficient and coordinated approaches - particularly across transmission and distribution, and to support the planning of network expansion and efficient use of network capacity on a whole systems basis. | Short-term action (2023): Ofgem will continue to work with and challenge the network companies, ESO and industry stakeholders to drive forward targeted measures at pace to address key issues. These improvements are being progressed primarily by two industry bodies: the Energy Networks Association (ENA) and the Electricity System Operator. Their work programmes (covering both distribution and transmission) are taking forward initiatives that include better connections queue management and improved network modelling assumptions underpinning connection offers. More detail on these initiatives can be found in Annex B and in associated industry updates. Ofgem are pushing forward this work, providing regulatory guidance and direction, to ensure rapid and material progress and expect that these targeted improvements will deliver tangible benefits to customers, removing projects which are not progressing from the queue, improving connection dates and enabling shovel-ready projects to connect ahead of those who may not be. At distribution, initial proposals on queue management have the potential to remove over 1GW of older projects in the connections queue and bring forward connection dates for up to 6GW capacity, while other initiatives are expected to bring additional benefits. Ofgem confirm their explicit support for Distribution Queue Management at Annex D of the letter. Ofgem are monitoring the impact of these changes closely to determine the extent of further interventions needed. Medium-term improvements (now – 2025): While targeted near-term measures should deliver swift improvements, Ofgem expect industry initiatives, with support from Ofgem and government, to consider wider reform options across transmission and distribution. The ESO’s Connections Reform Project and the ENA’s Strategic Connections Group are working collaboratively to consider the case for change, and exploring options for more substantial reform of connections processes. Ofgem are closely engaged in this important work and will assess the progress made and emerging direction to ensure any gaps are identified, rapid and substantial progress is delivered and any further areas for reform can be identified. Ofgem will provide regulatory guidance and direction on strategic questions and the emerging direction of reform as needed, informed by their own work to identify the scale and type of reform required to deliver a more fit-for-purpose electricity connections framework. Over this timeframe, Ofgem expect to see a revised connections process alongside wider coordinated improvements to the connections regime, and substantial shifts in the quality and transparency of data available to connecting parties. This, in tandem with the wider work underway to accelerate network investment, will collectively deliver tangible benefits for connecting customers in the shape of earlier connection dates, while ensuring the connections processes keep pace with developments on the system and are fit for the future to manage the changing nature and scale of applications. Longer-term outlook (2025 – 2030+): For the longer-term, Ofgem have stated that they will need to ensure the connections regime and access arrangements develop in line with wider system changes. Wide-ranging energy market and system planning reforms are under consideration on this timeframe: through REMA, the introduction of the Future System Operator (FSO), network charging and access reforms, work on regional system planners (RSPs), and evolving strategic planning approaches. The Electricity Networks Commissioner’s findings on how to accelerate progress on network infrastructure are also anticipated to inform the future direction.
Ofgem letter on strategic transmission charging reform | (https://www.ofgem.gov.uk/sites/default/files/2023-09/Open%20letter%20STC_110923.pdf) This letter on strategic transmission charging reform sets out Ofgem's initial thinking on the future role and design of electricity transmission network charging and why reform may be required. Ofgem consider these issues in the context of fundamental system change and policy reform, such as that being considered as part of the government’s Review of Electricity Market Arrangements. Ofgem welcome stakeholder engagement on their initial thinking and to facilitate this, have set out some questions where they would particularly welcome stakeholder input. | Questions for stakeholder feedback: • How should charges for large generators and large demand users at different voltages account for the increasing proportion of distributed generation and the changing nature of network flows? • Should there be greater alignment of charging obligations and methodologies for transmission- and distribution-connected assets, to encourage efficient connection voltage choices by generation and storage assets?
Ofgem Proposal to introduce the Future Regulation Sandbox | Proposal to introduce the Future Regulation Sandbox https://www.ofgem.gov.uk/publications/proposal-introduce-future-regulation-sandbox Publication date: 31st October 2023 Response deadline: 19th January 2024 Ofgem are seeking input on their proposal to introduce the Future Regulation Sandbox (FRS), an innovative policy instrument, to test and trial changes to the energy rulebook that need to happen to enable or respond to innovation that supports GB’s journey to a smarter, decarbonised energy system. Ofgem particularly welcome responses from those innovating in the energy sector, whether licensed by them or not, parties interested in driving innovation in the energy sector, consumer representatives, and rule owners such as Code Administrators in the energy system. They would also welcome responses from other stakeholders and the public, including those working in the field of agile regulation. Ofgem want to continue to adapt their decision-making tools and approaches to ensure their rulebook remains fit for purpose for a rapidly changing society and energy sector. The document has set out Ofgem’s proposal to introduce the Future Regulation Sandbox (FRS) as a tool to trial changes to the energy rulebook in an agile way so that they can unlock or respond to innovation that aligns with net zero in the interest of consumers. The introduction of this new FRS would be in addition to the current Energy Regulation Sandbox (ERS). Ofgem see value in running both the innovator-led ERS, which helps innovators to trial and bring their ideas to market, and the regulator led FRS, which would inform changes to the rules governing the energy sector. This call for input asks for stakeholders’ feedback Ofgem’s proposal, in particular they are interested in whether stakeholders see value in introducing the FRS, and views on how it could be implemented in a way that maximises benefits for the sector, and suggestions on what topics it could explore. The call for input will remain open until mid-January 2024 to allow sufficient time to think about the details and application of this idea. In the interim, Ofgem will continue to engage with industry.
Open letter on regulatory arrangements for IDNOs | Open letter on regulatory arrangements for independent distribution network operators https://www.ofgem.gov.uk/publications/open-letter-regulatory-arrangements-independent-distribution-network-operators Publication date: 19 October 2023 Response deadline: 01 December 2023 In this letter Ofgem outline some recent developments in the activities of independent distribution network operators (IDNOs). These developments have contributed to Ofgem’s view that the benefits of competition from IDNOs in extra high voltage (EHV) connections (including those directly connected to the transmission network) may need to be reviewed. Ofgem have published the letter now to signal to relevant parties that they are considering reviewing these arrangements. Ofgem also invite views from stakeholders on these developments ahead of initiating any review. Potential upcoming review of regulatory arrangements In light of the evolving nature of the LDNO arrangements, and the recent developments relating to serving EHV customers and connecting directly to the transmission network in particular, Ofgem are considering a review of the benefits of competition from LDNOs in EHV connections (including those directly to the transmission network). While Ofgem note some of the benefits that the LDNO regime has brought, they consider that a consideration of these benefits now could be timely. The regime was originally introduced around 20 years ago and the energy system has changed radically since then and continues to evolve as we move towards Net Zero. Indeed, their original decision on the regulation of LDNOs indicated their intention to consider regulatory arrangements from 2016 onwards, in 2011. The full scope of any such review is yet to be determined, and will be informed by the responses received to the questions at the end of the letter. Ofgem have issued the open letter to alert parties, in particular current and prospective LDNOs and their EHV customers, that the existing regulatory arrangements may evolve to reflect the changing role of LDNOs. This was always Ofgem’s intention when setting up the regime and it means that any arrangements in place now may not be enduring. Ofgem would seek to ensure that any such review improves arrangements in terms of their principal objective and statutory duties. Ofgem have said that they are also aware of the value of innovation and competition in seeking to meet government’s ambitious Net Zero targets. Ofgem will communicate further on this matter in due course. In the meantime, they would welcome initial thoughts on the questions below. Questions 1. What do you consider to be the pros/cons of IDNOs connecting EHV customers embedded within distribution networks? 2. What do you consider to be the pros/cons of IDNOs connecting directly to the transmission network? | 21 March 2024 - Response to open letter on regulatory arrangements for independent distribution network operators In this document we summarise the responses to our October 2023 open letter on regulatory arrangements for independent distribution networks operators (IDNOs) and outline next steps. That open letter signalled some concerns we had with the current arrangements, particularly for extra high voltage (EHV) connections. We acknowledge the benefits of IDNO connections at EHV, but consider that regulatory arrangements should be clarified given EHV activity was not originally envisioned for IDNOs when the arrangements were set up. In light of responses to the open letter, we are prioritising clarifying arrangements for EHV charging for IDNOs both embedded in a distribution network and for those directly connected to the transmission network. We want to act swiftly to address key areas of uncertainty, so the initial focus of our review will be targeted on EHV: • Examining options to make EHV charging more transparent, and • Clarifying charging arrangements for IDNOs connecting to the transmission network, particularly for the recovery of residual costs. Our open letter and Draft Forward Work Programme sought views on a possible wider review of the regulatory framework for IDNOs. The responses to the open letter and Draft Forward Work Programme will help inform the scope of on any wider review. The remainder of this document provides key background, summarises the responses and explains how we reached these conclusions. The annex includes a summary of responses to the two specific questions we posed. We have published non-confidential responses alongside this document.
Ofgem Consultation on SoLR Offset Levy | SoLR Levy Offset Policy Consultation https://www.ofgem.gov.uk/publications/solr-levy-offset-policy-consultation Publication Date: 9 February 2024 Response Deadline: 5 April 2024 In this consultation, Ofgem notes that the SoLR process was used heavily during the 2021 energy crisis to ensure that customers received undisrupted gas and electrity supplies when their supplier failed. Since the energy crisis, Ofgem has strengthened the rules to ensure that suppliers are more resilent to shocks and less likely to fail, and to ensure that certain funds are ringfunded to reduce the cost of mutualisation in the event of their failure. Ofgem is now further consulting on proposals that would further reduce the costs to consumers upon the failure of a supplier by allowing some of these costs to be recovered through the insolvency process. | Potential impact of these proposals: This consultation proposes creating licence and contractual arrangements such that another party would have a legitimate claim for SoLR Levy costs against a failed supplier. The debt would rank as an unsecured claim in supplier insolvencies. If funds are available to pay the claim, it could provide significant benefit to consumers by enabling any recovered funds to flow back to consumers through lower network charges, and therefore lower bills. The proposed mechanism for implementing this would be to require suppliers to enter a deed that would be recovered by the network in the event of the supplier failing and entering into the SoLR process. This would rank ahead of any distribution to creditors in the insolvency waterfall and would offset the cost of the SoLR process to consumers Ofgem does not anticipate that this would result in material costs for the network operators. They note that this obligation might have a detrimental effect upon the ability of suppliers to obtain investment or borrow money. Next steps Monitor future developments.
Ofgem Open Letter regarding Data Best Practice and its future in Codes | Ofgem Open Letter regarding Data Best Practice and its future in Codes https://www.ofgem.gov.uk/publications/open-letter-regarding-data-best-practice-and-its-future-codes Publication Date: 14 March 2024 This letter notes the importance of Data Best Practice for any organisations that handle data, and outlines Ofgem's proposed approach by which Code Managers will integrate this into their respective Codes Potential impact of these proposals: Ofgem are still at the start of this process but have announced their intention to engage with code managers with the intention of creating a standardised approach. To date, this is still a statement of intention and they have not launched a formal consultation. The intended workschedule is to consult with industry parties over Summer 2024 and to form a steering group off the back of this work. Next steps Monitor future developments. Ofgem have said that they will expect Code Managers and other parties to familiarise themselves with the DBP Guidance and Supporting Information as published, and to review these principles with a view to how they would affect business as usual processes. They will also be forming working groups in due course. | On 11 July 2024, the DCUSA Code Administrator attended a bilateral meeting with Ofgem about their plans regarding the planned Cross Code Digitalisation Steering Group. It was confirmed, that whilst the DCUSA doesn’t hold much industry data, that Ofgem would still want a representative from the DCUSA Code Administrator to attend on the basis that they’ll want to ascertain what data is held/managed under the DCUSA, and whether it might be considered to be within scope of the data best practice guidance and if so, how best to ensure that it is managed accordingly. The focus of the CCDSG will be on sharing good practices and learning across code bodies, increasing data interoperability while working together to examine and mitigate blockers and barriers to implementing Data Best Practice across codes. Ofgem are also seeking to understand where valuable datasets that can benefit the energy system are held. Members of this group will contribute to the shaping of DBP in their respective organisations and play a significant role within the industry. This first event was held on Thursday, August 15, 2024, from 10:00 to 13:00. Subsequently, it will be held on the 4th Thursday of every month. It will be an interactive event to ensure maximum benefit, with the aim of gathering stakeholders' input. The Terms of Reference will be sent for group approval one week prior to the first meeting and discussed in the initial set-up meeting. Agendas will be sent one week prior to each meeting. Ofgem hope to run this until the summer of next year, when they will decide the way forward for the group. Initial thinking includes handing ownership of the group over to the industry, to provide an enduring forum to drive digitalisation efforts evolving from industry improvements.Potential impact of these proposals: The Board have approved for the DCUSA Code Administrator to attend future sessions.