## Open
DCMDG Actions Log
Action Ref. | Action | Owner | Notes | Update
DCMDG_09/06: | Chair to include an official agenda item each April for discussions on the annual review of the Charging Methodologies and to issue out the DCUSA Issue Form prior to this in case there are any items to be added to the agenda. | Chair | Standing Action | Rolling agenda item for each April.
DCMDG_78/01 | The Secretariat to set up a subgroup to support the import capacity charges for storage facilities issue raised by OH from Thrive Renewables. | ElectraLink | Open | 15/08/2024 - New
DCMDG_78/02 | The secretariat to schedule a further meeting for the Private Network Subgroup at which Ofgem will attend to assist in agreeing next steps | ElectraLink | Open | 15/08/2024 - New

## Closed
Action Ref. | Action | Owner | Notes | Update
055/01 | Submit any comments they may have in respect of the LC14 Charging Statement to the Secretariat, in advance of the 26th April 2017 meeting | All | Closed | No additional comments have yet been received. If there are any comments then email them to DCMDG@electralink.co.uk. The final verisons have been circulated
056/01 | To obtain more detail regarding the contingency plan for the transition of the embedded benefits if generators are undergoing a judicial review | Tim Aldridge | Closed | Ofgem confirmed that the CMP264/CMP265 decision will be taken to Judicial Review. Industry should expect a decision by the court by early-mid 2018. Action Closed.
056/02 | To submit the Distribution Charging Methodologies Review Stage 2 Report to Ofgem | ElectraLink | Closed | Closed.
056/03 | To provide further information about the DCUSA Panel members | ElectraLink | Closed | Closed.
MIG/01 | Follows the discussion at the December MIG meeting regarding the eligibility criteria for EDCM generators to receive credits. A RFI was issued to determine how DNOs decide whether generators are eligible for credits within the EDCM and whether a consistent approach is adopted. | MIG | Closed | DCP 291 was raised. Action closed.
Closed
DCMDG_001/01 | Ofgem to obtain an update regarding BSUoS Charging to share with DCMDG Members | Tim Aldridge | Closed | Ofgem informed the DCMDG that they have published two working papers. They expect any changes regarding BSUoS to be conducted through the normal Code change process
DCMDG_001/02 | Ofgem to draft a paragraph for inclusion within the DCMDG TOR to determine the official communication channel between the CFF and the DCMDG and send to ElectraLink | Tim Aldridge | Closed | Included as section 15 in the TORs
DCMDG_001/03 | ElectraLink to update the TOR as per the discussions held. These will then be circulated to DCMDG members that were in attendance at the meeting | ElectraLink | Closed | Presented at 2nd meeting
DCMDG_001/04 | DCMDG members that attended the first meeting to provide amendments/comments on any drafting errors on the TOR and send to ElectraLink before submission to the DCUSA Panel for approval | DCMDG Members | Closed | Completed and ElectraLink incorporated in the final version which was submitted to Panel
DCMDG_001/05 | The Secretariat agreed to ask for clarification from the DCUSA Panel regarding the formation of sub-groups under the DCMDG | ElectraLink | Closed | Panel agreed DCMDG could do this
DCMDG_001/06 | ElectraLink to invite National Grid to a future DCMDG meeting to discuss current changes within the CUSC and Grid Codes that will potentially have an impact on distribution charging | ElectraLink | Closed | No developments in GC mods. Awaiting update regarding CUSC mods
DCMDG_001/07 | DNO DCMDG Members to provide an update on how they currently classify storage systems as intermittent or non-intermittent so the topic can be discussed at the next DCMDG Meeting | DNO DCMDG Members | Closed | All DNOs consider storage to be non-intermittent and have a non-zero F-factor
055/03 | To respectively review and update the CDCM and EDCM user manual. | Claire Campbell / Chris Ong / ElectraLink | Closed | A link to the CDCM/EDCM user manuals to be put on the DCMDG web page
DCMDG_002/01 | ElectraLink to amend the previous minutes to reflect the suggested amendments | ElectraLink | Closed | Circulated with Meeting_002 minutes
DCMDG_002/02 | ElectraLink to update the DCMDG Actions Log in line with discussions held | ElectraLink | Closed | Circulated with Meeting_002 minutes
DCMDG_002/03 | Ofgem representative to investigate whether there will be any slippage to the Task Forces envisaged output date | Edda Dirks | Closed | No slippage. Committed to the timescales previously published
DCMDG_002/04 | ElectraLink to engage with Ofgem to invite the Ofgem representative who attends the CMP280 and CMP281 Workgroups to attend a future DCMDG meeting to provide an update | ElectraLink | Closed | Presented at 3rd meeting
DCMDG_002/05 | ElectraLink to state in the TORs which parts are a copy of Schedule 28 in the DCUSA | ElectraLink | Closed | Presented at 3rd meeting
DCMDG_002/06 | ElectraLink to draft a strawman guidance document on a pre-mod process | ElectraLink | Closed | Presented at 3rd meeting
DCMDG_002/07 | ElectraLink to draft a section on the Forward Work Plan of the DCMDG | ElectraLink | Closed | Presented at 3rd meeting
DCMDG_002/08 | ElectraLink to circulate NHH/HH spreadsheet to all DNOs | ElectraLink | Closed | Circulated following 2nd meeting
DCMDG_002/09 | ElectraLink to circulate the 2018 DCMDG meeting dates | ElectraLink | Closed | Circulated with Meeting_002 minutes
DCMDG_002/10 | ElectraLink to request Panel formally reissue the CDCM/EDCM models and ask Reckon to update the ARP | ElectraLink | Closed | Completed following 2nd meeting
DCMDG_002/11 | DNOs to consider what customer groups would be affected by the additional adjustment on a fixed charge due to Co-Op’s last resort supply payments | DNO representatives | Closed | DNOs indiscussions with Ofgem. Ultimately an Ofgem decision.
DCMDG_003/01 | To amend the previous minutes to reflect the suggested amendments | ElectraLink | Closed
DCMDG_003/02 | To update the DCMDG Actions Log in line with discussions held | ElectraLink | Closed
DCMDG_003/03 | To clarify if those who attended the CFF last time need to sign up again to attend future meetings | Ofgem | Closed | Confirm that if attended then will get an invite to the next one
DCMDG_003/05 | Put the DCMDG Issues Form on the DCMDG website | ElectraLink | Closed | Link can be found under 'Notes' on the DCMDG Webpage
DCMDG_003/04 | Amend TORs and FWP as per discussions in the meeting | ElectraLink | Closed
DCMDG_003/06 | Investigate how other meetings and groups TORs reference the DCUSA | ElectraLink | Closed
DCMDG_003/07 | Investigate whether IDNOs would be expected to pass through charges if DNOs increased IDNO tariffs | Ofgem | Closed | IDNOs should not expect to see a claim from Cooperative Energy. If a DNO influences an IDNO charge, that IDNO may choose to pass through the charge within the one month window. Action to remain open until further updates emerge following the Ofgem decision
DCMDG_004/02: | The Secretariat to pursue DNOs yet to send through refreshed HH/NHH data for HHS and send the responses to Elexon | ElectraLink | Closed
DCMDG_004/01: | Ofgem to engage with IDNOs ahead of the decision regarding Cooperative Energy’s claim for a last resort supply payment | Ofgem | Closed
DCMDG_004/03: | SY, DW and AE to work with KH offline and update the DCMDG in the February meeting | ST, DW, AE, KH | Closed
DCMDG_004/04: | DNOs to send their 2019/20 LC14 charging statements to Tim Aldridge at Ofgem | DNOs | Closed | Confirmed all have been received
DCMDG_005/01: | The Chair to ask the DCUSA Panel if there should DCMDG specific “Competition Law Do’s and Don’ts”. | Chair | Closed | Confirmed that specific "Do's and Don'ts" are needed
DCMDG_005/02: | The Ofgem representative to look into setting up a meeting between the DCMDG delegates on this issue and key Ofgem representatives. | Ofgem | Closed | Confirmed the meeting would be held in the beginning of March
DCMDG_005/03: | The Secretariat to further amend the FWP in line with discussions held. | ElectraLink | Closed | Updated in line with discussions
DCMDG_005/04: | DNO representatives to forward the link of their 2018/19 losses to the Secretariat once the document is published | DNOs | Closed | Completed
DCMDG_005/05: | DNO representative to forward the link of the DNO guidance note on the treatment of storage. | Andrew Enzor | Closed | Link received
DCMDG_006/01: | Secretariat to forward the link of the guidance note on the treatment of storage to the DCMDG mailing list | ElectraLink | Closed | Completed
DCMDG_006/02: | Secretariat to forward the link of DNO’s 2018/19 losses to the DCMDG mailing list. | ElectraLink | Closed | All received
DCMDG_006/03: | The Ofgem representative to look into sharing the slides presented at the CFF with the DCMDG | Ofgem | Closed | Slides were published
DCMDG_006/06: | The Secretariat to contact Tom Chevalier and an Elexon representative and invite them to discuss the matter regarding competition in supply on private networks at the next DCMDG meeting. | ElectraLink | Closed | Completed
DCMDG_006/04: | The Ofgem representative to investigate whether Stephen Perry and Baringa would be able to present at the April or May DCMDG meeting. | Ofgem | Closed
DCMDG_006/05: | The Secretariat to input more information in the FWP, in particular the DCUSA Change Proposals and External tabs. | ElectraLink | Closed
DCMDG_007/01: | ElectraLink to update the DCMDG FWP in line with discussions held. | ElectraLink | Closed | Completed - Relevant items moved
DCMDG_007/02: | AE to take the competition in supply issue offline and draft a Change Proposal. | Andrew Enzor | Closed | Completed - draft CP issued
DCMDG_007/03: | DCMDG members to review the CP regarding the residual charging of storage and respond to DCUSA@electralink.co.uk with any comments or suggestions. | DCMDG Memebrs | Closed | No suggestions were received
DCMDG_007/04: | The Secretariat to contact a National Grid representative to organise a presenting slot at the TCMF regarding residual charging for storage generation. | Secretariat | Closed | Contacted. AE presented at the TCMF on 09 May
DCMDG_007/05: | The Chair to investigate whether there have been any Change Proposals raised regarding reactive power in the last few years. | Chair | Closed | DCP 143, DCP 222 and DCP 292
DCMDG_007/06: | The Secretariat to investigate the changes needed to incorporate the new Statement of Works and liaise with DNO representatives and determine if changes to the DCUSA are necessary. | Secretariat | Closed | To be reffered to Brian Hoy by the chair
DCMDG_008/02: | The Ofgem representative to engage with colleagues internally and at Elexon in order to establish if a presentation on Settlement Reform could be given at the next meeting. | Ofgem | Closed | Completed - agenda item at July meeting
DCMDG_008/03: | Ofgem to investigate internally to determine the delay of the DCP 243 decision. The update will be sent to the Secretariat and circulated around the DCMDG mailing list. | Ofgem | Closed | Completed - verbal update provided
DCMDG_008/05: | AE to define the issue more accurately and put forward a high-level solution. Once complete, the Secretariat to send round a Subgroup member request. | Andrew Enzor/Secretariat | Closed | Completed - agenda item at July meeting
DCMDG_008/08: | DCMDG members to circulate any comments regarding the proposed CP intending to remove residual charging from generation in the EDCM by 13 June 2018 | All DCMDG members | Closed | Completed - DCP 321 raised
DCMDG_008/07: | DCMDG members to review the assumptions log and to consider the best way of progressing the changes to the DCUSA legal text | All DCMDG members | Closed | Closed - Supersceded by Action DCMDG 010/02
DCMDG_009/01: | ElectraLink to amend the FWP by removing the Archived CPs tab and updating the DCUSA Change Proposals tab so that it provides status change updates for Charging Methodology CPs. | ElectraLink | Closed | Closed
DCMDG_009/02: | ElectraLink to amend the External Activities tab in the Forward Work Plan to align to the consolidated timelines published on the charging futures website. | ElectraLink | Closed | Closed
DCMDG_009/03: | AE to amend the CP form related to merging Schedule 15 with the ARP by making an adjustment to intent and will circulate to the Secretariat who will issue to the group for any final comments by 10 July 2018. | Andrew Enzor | Closed | Closed - DCP 325 raised and put into the change process
DCMDG_009/04: | AE to continue to develop the issue related to Competition in Supply of private networks and place into a CP form and bring back to DCMDG for further discussion. | Andrew Enzor | Closed | Closed
DCMDG_009/05: | CO, AE and CC to review the modelling assumptions log together outside of the DCMDG and to report back to the DCMDG on the results of their categorisation so that the DCMDG can decide on the next steps. The assumptions should split into two categories along the lines of whether a particular assumption could be considered relatively minor in nature that could be captured as housekeeping or something that might be considered more significant that requires further discussion/development. These can be further split to differentiate between different models (CDCM, EDCMs and PCDM). | Chris Ong, Andrew Enzor and Claire Campbell | Closed | Closed - Supersceded by Action DCMDG 010/02
DCMDG_008/01: | The Chair to refer the overlap of National Grid’s Statement of Works with the DCUSA to Brian Hoy | Chair | Closed | DCMDG members agreed to close this action
DCMDG_008/04: | WJ to raise DCMDG Issue 3 as a Change Proposal | William Jago | Closed | Closed - discussed at meeting 11
DCMDG_008/06: | The Chair to ask the proposer of the reactive power issue how they would like to further the matter (whilst keeping AE in circulation) | Chair | Closed | Closed - issue discussed at meeting 11
DCMDG_009/07: | The Chair to ensure that 1hr is allotted on the September DCMDG agenda for Stephen Perry to present to the group on the CFF meeting. | Chair | Closed | Closed
DCMDG_010/01: | John Parsons to share infomration on Brussels' new Renewable Energy Directive | John Parsons | Closed | Closed
DCMDG_010/02: | DCMDG members to review the Modelling Assumptions log and provide comments on the outstanding issues by close of play on 24 August 2018 | DCMDG members | Closed | Closed - Supersceded by new Actions
DCMDG_011/01: | JP to raise reactive power charges as a formal DCMDG issue for discussion at the October DCMDG meeting | John Parsons | Closed | Closed - discussed at meeting 12
DCMDG_011/05: | CEPA/TNEI to provide further clarification on the outstanding assumptions to allow members to fully understand them before developing their solutions. | CEPA/TNEI | Closed | Closed
DCMDG_011/03: | AE to work with CEPA/TNEI to resolve assumptions 36 and 68 on the modelling assumptions log | Andrew Enzor | Closed
DCMDG_011/06: | WJ to work with CO to refine the Alignment of Capacity Value Calculations and Exceeded Capacity Billing Periods CP and re-submit to the October DCMDG meeting to review further | William Jago/Chris Ong | Closed | WJ has decided to not progress with this propsoal.
DCMDG_012/01: | The Secretariat to update the FWP to reflect the discussions held | ElectraLink | Closed
DCMDG_012/02: | DCMDG members to review the draft SoLR CPs and provide any comments to Lee Wells by close of play on Friday 12 October 2018 | DCMDG Members | Closed | No comments received
DCMDG_013/01: | AE to submit recovery of eligible use of system bad debt CP | Andrew Enzor | Closed
DCMDG_011/02: | SY to work with CEPA/TNEI to resolve assumptions 19 and 21 on the modelling assumptions log | Dave Wornell | Closed | Soltions provided and forwarded to CEPA/TNEI for their review
DCMDG_012/03: | AE and JP to establish what needs to be investigated to determine whether reactive power charges are cost-reflective, to ultimately either inform Ofgem's proposed SCR or to lead to a CP. | Andrew Enzor/John Parsons | Closed | Agreed that it can only be dealt with under the ongoing SCR
DCMDG_014/01: | AE to raise the Nominated Calculation Agent Change Proposal to the DCUSA Panel | Andrew Enzor | Closed | Closed
DCMDG_014/02: | KH to raise SECMP0046 as an official DCMDG Issue | Kyran Hanks | Closed | Closed - will be raised again (if necessary) when the SECMP has developed further and any DCUSA impacts are recognised
DCMDG_015/01: | ElectraLink to update the DCMDG Forward Work Plan to reflect the discussion held | ElectraLink | Closed | Closed
DCMDG_015/02: | The Chair to follow up with the DCP 287 Proposer to inform them of the DCMDG members’ view of the interaction with the SCR. | ElectraLink | Closed | Closed
DCMDG_017/01: | Ofgem to obtain an update regarding the DCP 314 decision and the implementation of the Supplier of Last Resort licence changes. | Ankita Mehra | Closed | Update provided in meeting 18 minutes
DCMDG_017/02: | CO to raise the Change Proposals relating to the Modelling Assumptions Log that was produced as part of the development of the new Charging Models built by CEPA/TNEI, depending on an internal resource review at UKPN. | Chris Ong | Closed | CO unfortunately is unable to draft the CPs and therefore a paper will be being sent to the DCUSA Panel to propose that the DCUSA Secretariat draft this on behalf of the group if nobody else volunteers
DCMDG_018/01: | Ofgem to obtain an update from the Targeted Charging Review Team to determine the work that Frontier are completing includes residual charges. | Ankita Mehra | Closed | Update provided at meeting on 05 September 2019
DCMDG_018/02: | Ofgem to obtain an update regarding DCP 313 and whether industry can expect a decision or whether the decision will be deferred until the conclusion of the SCR. | Ankita Mehra | Closed | Update provided at meeting on 05 September 2019
DCMDG_018/03: | The Chair to ensure that CEPA/TNEI conduct a new impact assessment for DCP 268 using the 2021 charges. | Angelo Fitzhenry | Closed | AF - completed the action and the new impact assessment is on the DCUSA Website
DCMDG_011/04: | DP to work with CEPA/TNEI to find a solution for issue 93 of the Modelling Assumptions Log | Donald Preston | Closed | Four CPs have been raised to cover the Modelling Assumptions Log - DCMDG members agreed that this outstanding issues can be covered in the development of the CPs when they are accepted into the Change Process by the DCUSA Panel
DCMDG_019/02: | The DNOs to review and revise load factor and coincidence factor percentages regarding DCP 268 impact assessment and update as necessary. | DNOs | Closed
DCMDG_019/03: | CO to provide TCh with a current copy of the draft charging statement | Chris Ong | Closed
DCMDG_020/01: | Ofgem to obtain an update regarding the outstanding DCP 314 decision | Ofgem | Closed | No longer required - full solution in licence mod. It has been determined that DCP 314 is no longer required. This is because DCP 314 was only a partial solutin and Ofgem made the decision to provide a full solution in the licence modification, dealing with other SOLR issues. This licence condition has now gone into force and Ofgem will be issuing a decision to reject DCP 314 shortly.
DCMDG_020_02: | SSEN to check whether they are able to share the letter received from Ofgem regarding their derogation with other DNO Parties | SSEN | Closed | Members stated that they no longer need this letter. They are waiting on a decision from Ofgem as to whether a derogation is needed or not. Action closed.
DCMDG_021/01: | The Chair to find out further detail regarding the certification of assets by Supplier Parties for DCPs 341 and DCP 342 | ElectraLink | Closed | Email send to DCMDG members to set out what was discussed within the DCP 341/342 Working Group meetings.
DCMDG_021/02: | The Secretariat to contact SSEN to check on progress of providing the necessary information to Suppliers following implementation of DCP 326. Additional information included LLFCs, SSCs and available SSCs. | ElectraLink | Closed | Email sent to DCMDG members to explain that DNOs are aware of what they need to send to Suppliers and they should receive te info imminently.
DCMDG_023/01: | Ofgem to obtain updates on the Smart Systems and Flexibility Plan, Electric Vehicles and the Dieter Helm cost of energy review projects so that the DCMDG Forward Work Plan can be updated. | Ankita Mehra | Closed | Forward Work Plan updated
DCMDG_023/02: | The Chair to obtain an update from Energy Networks Association regarding their planned consultation on the Electricity Network Innovation Strategy. | Angelo Fitzhenry | Closed | Forward Work Plan updated
DCMDG_023/03: | One DCMDG Member to provide an update on the European Renewable Energy Directive | John Parsons | Closed | Forward Work Plan updated
DCMDG_023/04: | Ofgem to obtain an update on the publication of which of the access options will be taken forward in regard to the Access and Forward-Looking Charging SCR | Ankita Mehra | Closed | Ofgem provided an update and details can be found in the minutes of DCMDG Meeting 24
DCMDG_023/05: | A note to be circulated around DCMDG Members to explain how the Working Groups for the TCR Implementation CPs will be established. | Lee Wells | Closed | Note circulated following the January meeting
DCMDG_026/01: | The Secretariat to update the DCMDG Forward Work Plan to reflect the discussions held | ElectraLink | Closed | Action completed
DCMDG_026/02: | The Ofgem representative to provide feedback on whether Ofgem still believe that the tight timescales associated with the TCR implementation are still achievable due to the COVID-19 pandemic. | Ankita Mehra | Closed | Action completed - covered as part of the Ofgem uodate in agenda item 4.
DCMDG_026/03: | DCMDG members to send any specific discussion points related to the TCR CPs that they wish to discuss a the May 2020 DCMDG meeting to the DCMDG inbox so that the relevant updated can be obtained. | DCMDG members | Closed | Action closed - no emails received. The Chair provided an update within agenda item 6.
DCMDG_028/01: | DNOs to review their charging statements and if Profile Class 0 is missing to reinstate it in time for the next publication (to solve DCMDG Issue 007) | DNOs | Closed | DNOs to include this within their next charging statements if they do not already.
DCMDG_028/02: | The Secretariat to provide DCMDG members a copy of the certification process for the new storage tariffs that will be included in the new LC14 statements | ElectraLink | Closed | Provided after meeting 28.
DCMDG_028/03: | Ofgem to look in to publishing the total amount of relief that has been taken up in regard to COVID-19 so that Suppliers are able to forecast their risks | Ofgem | Closed | Ofgem noted that the scheme had some uptake but are still deciding on whether to publish the data and when.
DCMDG_029/01: | The Ofgem representative to obtain an update on the decision for DCP 266. | Ofgem | Closed
DCMDG_019/01: | Circulate the draft Change Proposal regarding P2/7 and ERP 130/3 documents to DCMDG for opportunity to comment. | Northern Powergrid | Closed | ENWL have expressed an interest in potentially picking up this draft DCP, however this cannot be confirmed until they have undertaken an internal review first.
DCMDG_020/03: | TC to chase SSEN and ENWL for their Whole Current and Current Transformer customer numbers. | Tom Chevalier | Closed | SSEN and ENWL still outstanding.
DCMDG_029/02: | SSEN representative to confirm whether their latest Cost Information Tables included the impact of the change in capitalisation rate for SSE Hydro | SSEN | Closed
DCMDG_032/01: | JH agreed to contact Ofgem to provide a steer to DNOs and Suppliers on the migration of MPANs for new and old LLFs, so Parties have greater visibility on the process. | Julia Haughey | Closed | Completed
DCMDG_032/02: | Where appropriate, members agreed to write to Elexon about plans for the settlement process and for MDD. | All | Closed | Completed
DCMDG_034/01: | CO to initiate the formal process of withdrawing DCPs 352 to 355 inclusive. | CO | Closed | Completed
DCMDG_034/02: | Chair to arrange to the BEIS License Exemptions: call for evidence to be reviewed in relation to DCP 328 impacts and advise/recommended to the DCUSA Panel if a formal response from DCUSA is appropriate. | Chair | Closed | Completed
DCMDG_034/03: | Chair to forward the Disputes Committee Nominations & Elections communication issued to DCUSA Contract Managers to DCMDG members. | Chair | Closed | Completed
DCMDG_035/01: | Chair to send the BEIS Call for Evidence on Electricity Licence Exemptions report undertaken for DCUSA to the DCP328 Working Group members. | Chair | Closed | Completed
DCMDG_035/02: | Chair to confirm the conflict-of-interest process with any Banding Dispute Committee Panel hearing. | Chair | Closed | Completed
DCMDG_035/03: | Chair to arrange for Energy White Paper to be reviewed and relevant aspects added to the Forward Work Plan. | Chair | Closed | Completed
DCMDG_038/01: | Chair to update LS and Matthew Tucker of the Ofgem’s recommendation to keep the Reactive Power and Mixed Use Sites as separate CPs. | Chair | Closed | Completed
DCMDG_039/01: | Ofgem to provide document highlighting any information set out in TCR consultations/decision document that is linked to what are now called ‘mixed use sites' that had originally been labelled as ‘complex sites’ and means sites with a mix and Final and Non-Final Demand. | Ofgem | Closed | First raised at meeting 38 and noted as work in progress during meeting 39 and subsequently chased during meeting 40
DCMDG_042/01: | The Secretariat check whether the DCMDG is allowed to form sub-groups and confirm answer back to members. | Secretariat | Closed
DCMDG_042/02: | DCMDG members to inform the Secretariat if they would like to join a DCMDG Sub-Group to review the issue ‘Application of fixed DUoS charges on a per-MPAN basis’ and develop a possible solution for inclusion in a CP. | All | Closed
DCMDG_042/03: | The Secretariat to raise the issue related to lack of Ofgem representation at recent DCMDG meetings during the next Panel meeting. | Secretariat | Closed
DCMDG_043/01: | Member to provide details of the question to seek clarity from the TCR Implementation Steering Group with respect to redundant capacity connections and the application of the TCR. | GM & Secretariat | Closed | GM provided the question to the Chair and this was further discussed at the October DCMDG meeting.
DCMDG_043/02: | All to provide any further comments on the draft Change Proposal - Implementation of Banding Allocation on an Annual Basis & Proposer to review internally whether to proceed with the Change Proposal given the initial feedback received. | DCMDG Members & Proposer | Closed | No further feedback was received and this Change Proposal will no longer be pursued.
DCMDG_043/03: | The Secretariat to issue a survey to the DCMDG on options to change dates/times of the meeting. | Secretariat | Closed | The group agreed to amend the meetings to the 3rd Thursday of every month.
DCMDG_044/01: | The Secretariat to circulate an updated version of the DCMDG Meeting 43 to the group post-meeting as v2.0. | Secretariat | Closed | This will be provided within the post-meeting pack for meeting 44.
DCMDG_044/04: | The Secretariat to circulate the Half-Hourly Settlement Governance Framework update to members of the group post-meeting. | Secretariat | Closed | This will be provided within the post-meeting pack for meeting 44.
DCMDG_044/07: | The Secretariat to circulate updated DCMDG meeting invites for the third Thursday of every month. | Secretariat | Closed | Updated meeting invites for November & December 2021, and 2022 meetings have been circulated to the group.
DCMDG_44/06: | The Secretariat to send communications to the group seeking feedback around using the CDCM model Version 8 for the upcoming charging period (including timeline). | Secretariat | Closed | Feedback was received and has now been passed to the modellers.
DCMDG_44/02: | Members to discuss whether Sites with redundant capacity should be billed a residual charge or not with the TCR Implementation Steering Group and bring back for further discussion at the November DCMDG meeting. | DCMDG Members & Proposer | Closed | GM has provided examples to ElectraLink and provided permission to share with Ofgem and the Implementation Steering Group. Feedback from the TCR Implementation Group meeting being held on 23 November 2021 will be provided to the DCMDG prior to the next meeting in December 2021. AF informed the group that this has now progressed and a draft CP will be provided to the group during the December DCMDG meeting for further discussion as AOB.
DCMDG_44/03: | The Secretariat to discuss the DCMDG query around why the TCR Implementation Steering Group do not allow wider access to meeting papers and minutes with the ENA. | Secretariat | Closed | Explanation was provide to the group and happy to close this action.
DCMDG_44/05: | The Secretariat to raise the communications issue regarding Market-Wide Half-Hourly Settlement groups at the next CACoP meeting. | Secretariat | Closed | This was discussed with the relevant people at Elexon and will be taken to the next CACoP meeting for further discussion. Feedback has now been received.
DCMDG_45/01: | The Secretariat to ensure that the example described under Action DCMDG/44/02 and the new example provided during meeting 45 related to backup connections (redundant capacity) are taken to the TCR Implementation Steering Group for feedback on how such sites will be treated under the arrangements that have been introduced as a result of the TCR Implementation. Secretariat to then pass this feedback on to DCMDG members prior to the next DCMDG meeting. | Secretariat | Closed
DCMDG_45/02: | The Ofgem representative to review the example described under Action DCMDG/44/02 and the new example provided during meeting 45 related to backup connections (redundant capacity) and provide any views on the treatment of such sites to the DCMDG. | Ofgem (SM) | Closed
DCMDG_46/01: | The Secretariat to seek DCUSA Panel approval for early legal advice for the draft Change Proposal around TCR Application of Residual Charges prior to a Working Group being created. | Secretariat | Closed | The Chair explained that the request had been taken to the Panel but that the Panel did not agree for legal advice to sought and that it expected such advice might be requested during the Working Group phase, should the change be raised.
DCMDG_47/01: | SM to pass feedback on internally regarding the request for a clearer indication of the expected decisions related to code modifications set out in Ofgems 'Code Modifications with Ofgem for Decision' publication, and if possible provide further updates at the next DCMDG meeting. | Shannon Murray | Closed | SM advised that she had passed on the groups feedback however was unable to provide any further updates on the modifications marked TBC 2022. SM noted that they hope to be able to confirm clearer timelines in the next few months.
DCMDG_47/02: | SM to seek some views internally on the question of whether the normal mechanism for how the recovery of costs related to SoLR will be used with respect to the Special Administration Regime (SAR) that has been brought in due the failure of Bulb or if some other process may be used. | Shannon Murray | Closed | SM provided a response to the group. This is included in the meeting minutes.
DCMDG_47/03: | DNO members to consider and provide their views/understanding on the interpretation of the issue raised under the AOB item, related to the application of the ‘LV Sub tariff’ as described in ‘Note 3’ under ‘Table 5 Site Specific Tariffs’ of paragraph 141 of Schedule 16. | DNO Members | Closed | Some feedback was received and a number DNOs also attended the SIG meeting at which this issue was formally discussed.
DCMDG_48/01: | SM to provide update at the next meeting regarding the Ofgem trial on providing target dates for CP Authority decisions rather than responding within the 25 Working Day SLA. | Shannon Murray | Closed | MP advised that the trial was extended by 6 months, therefore the decision will be made in April 2022.
DCMDG_48/03: | SM to invite representative of Ofgem Acess team to next DCMDG meeting. | Shannon Murray | Closed | DB attended and provided an update under agenda item 5.
DCMDG_50/01: | AF to refer to CEPA requesting further columns are added to the LRIC EDCM model. | Chair | Closed | Email sent to CEPA on 21 April 2022. CEPA confirmed they are investigating the request and discussing with CB directly. Agreed to close during DCMDG meeting 51.
DCMDG_51/01: | Secretariat to update the Issues Log and Forward Work Plan: • Adding DCP 403 to the Change Proposals tab; • Separating the Access and Forward-Looking Charging SCR into two, within the External Activities tab; • Removing the TCR SCR from the External Activities tab; and • Adding the EBSS to the External Activities tab. | ElectraLink | Closed | Updated Issues Log and Forward Work Plan provided with minutes to meeting 51.
DCMDG_51/02: | Secretariat to issue an email to members proposing to amend the timing of the DCMDG meetings going forward to 9am - 10am. | ElectraLink | Closed | Email issued on 25 May 2022.
DCMDG_48/02: | SM to provide further information on the cost recovery mechanism for the SAR arrangements (applicable to Bulb), and to confirm whether the mechanism uses an existing or a new charge. | Shannon Murray | Closed | SM advised that this mechanism is likely to use an existing charge, however discussions are ongoing as to which charge this will be. SM noted that this is a decision for BEIS.
DCMDG_54/01: | The Chair to resend the DCP 404, 405, 406 and 407 consultation email with links to the consultations on the website rather than attachments | Chair | Closed | Consultation email resent on 18 August 2022.
DCMDG_48/02: | SM to provide further information on the cost recovery mechanism for the SAR arrangements (applicable to Bulb), and to confirm whether the mechanism uses an existing or a new charge. | Shannon Murray | Closed | SM advised that this mechanism is likely to use an existing charge, however discussions are ongoing as to which charge this will be. SM noted that this is a decision for BEIS. 18/08/2022 - Group agreed to reopen action. Ofgem agreed to provide updates when possible 15/12/2022 - No further updates on which existing charge will be used. 19/01/2023 - Group agree to close.
DCMDG_56/01: | SM to provide update on SoLR decisions. | Shannon Murray | Closed | 20/10/2022 - New action 17/11/2022 - SM to investigate and issue relevant document to members 15/12/2022 - No update as of yet, final decision will be issued shortly. 19/01/2023 - Group agree to close.
DCMDG _57/01: | The Chair to feedback the DCMDG’s views on BSC Modification P441 ‘Creation of Complex Site Classes’ to Elexon. | Chair | Closed | 17/11/2011 - New action 15/12/2022 - Action ongoing, Chair to hold discussions with Elexon. 19/01/2023 - Chair confirmed that feedback had been provided.
DCMDG_59/02: | The Chair to send the DCMDG Issue 010 form to John Lawton and to set up a call to discuss referring the issue to the MHHS DCUSA stakeholder group. | Chair | Closed | 19/01/2023 - New action 16/02/2023 - Completed.
DCMDG_59/03: | The Chair to contact the ENA to ensure they hold up to date DCUSA contacts for communications relating to the DNO cost information tables meetings. | Chair | Closed | 19/01/2023 - New action 16/02/2023 - The Chair confirmed that this action is still ongoing, however noted that there is a meeting schedule on 24 February 2023. 16/03/2023 - The Chair confirmed that this is still ongoing. This was further discussed in AOB and was agreed to be closed.
DCMDG_59/01: | SM to seek an update on the BEIS Call for Evidence on Electricity Licence Exemptions. | SM | Closed | 19/01/2023 - New action 16/02/2023 - SM will continue to look into this and will provide an update once received. 16/03/2023 - SM does not have an update as of yet, but will continue to chase. 20/04/2023 - BEIS have stated there are no updates pending on this. SM does not believe there will be any updates in the neart future, however the group will be updated as and when.
DCMDG_61/01: | The Chair to see if JL (the Chair of the MHHS Stakeholder Group) can provide updates to the DMCDG. | Chair | Closed | 16/03/2023 - Ongoing. 20/04/2023 - The Chair informed the group that the MHHS Stakeholder Group is likely to come to a close in the neat future and therefore may not be of much benefit attending the DCMDG as there will be limited updates. It was agreed to keep this action open, and the Chair will seek an update from the MHHS Stakeholder Group and feed this back to the DCMDG at the May meeting. 18/05/2023 - No further update. The Working Gorup agreed to close this action and it can be re-visited should the DUoS SCR provide clarity around the interactions it would have with the Market Wide SCR .
DCMDG_61/02: | The Chair to ask all DNOs/IDNOs what their assumptions are going to be in the next charging year (regarding Customer contributions) and feedback to the April DCMDG meeting. | Chair | Closed | 16/03/2023 - New. 20/04/2023 - The Chair infomed the group that this request has been sent and four DNO response has been received thus far stating that they will be setting their Customer Constributions input to zero. Will be further discussed at the May DCMDG meeting. 18/05/2023 - No further update. 1 DNO response outstanding and the Chair agreed to follow this up post meeting. 15/06/2022 - All bar one DNO will make their outputs zero based on the responses received. The responses will be collated and fedback to members. CLOSED.
DCMDG_63/01: | The Secretariat to review the implementation dates for the four new CPs (DCP 421/422/423/424) and update as necessary. | Secretariat | Closed | 18/05/2023 - New. 24/05/2023 - Updated. CLOSED
DCMDG_63/02: | The Secretariat to add an item for ‘Connections reform’ to the Forward Work Plan & Issues Log. | Secretariat | Closed | 18/05/2023 - New. 24/05/2023 - Added to the log. CLOSED.
DCMDG_63/03: | The Chair to follow up with the remaining DNO for a response relating to Customer Contributions post-meeting. | Secretariat | Closed | 18/05/2023 - New. 15/06/2022 - this was followed up and the remaining response has now been received. CLOSED.
DCMDG_64/05: | The Secretariat to circulate the presentation by ENWL to the group post-meeting. | Secretariat | Closed | 15/06/2023 - New. 16/06/2023 - circualted to the group. CLOSED.
DCMDG_64/06: | The Secretariat to seek authorisation from the Panel to obtain the data required by DNOs and IDNOs to carry out their annual allocation review for sites that had been banded based on either no data or data that was a best estimate. | Secretariat | Closed | 15/06/2023 - New. 20/07/2023 - This has been requested. Closed.
DCMDG_64/01: | The Secretariat to collate the DNO responses (regarding Customer Contributions) and circulate to members post-meeting. | Secretariat | Closed | 15/06/2023 - New. 20/07/2023 - will be circualted to the group shortly. 5/6 DNOs confirmed that they will be using zero on Customer Contributions 17/08/2023 - Closed.
DCMDG_64/02: | The Secretariat to seek further information around the recent Energy Code Review Workshops and update the log post-meeting. | Secretariat | Closed | 15/06/2023 - New. 20/07/2023 - further info needed. Consultation is due in the Winter of 2023. 17/08/2023 - Closed.
DCMDG_64/04: | SM to speak internally with AM around Customer Contributions. | Secretariat | Closed | 15/06/2023 - New. 17/08/2023 - Closed
DCMDG_65/01: | The Secretariat to issue an invitation to DCMDG to join a DCMDG Subgroup to further discuss next steps in relation to DCP 328. | Secretariat | Closed | 20/07/2023 - New. 17/08/2023 - The Secretariat has issued the invite - Closed.
DCMDG_65/02: | The Secretariat to arrange for a call between AM, ED and CB to discuss thoughts/concerns related to the treatment of Customer Contributions moving forward. | Secretariat | Closed | 20/07/2023 - New. 17/08/2023 - Closed.
DCMDG_66/01: | The Secretariat to include Ofgem (AM) within the DCMDG Subgroup distribution list. | Secretariat | Closed | 17/08/2023 - Ongoing. 21/08/2023 - Added and doodle poll sent to AM. Closed
DCMDG_64/03: | The Secretariat to seek further information in relation to Connection Reforms and invite an ENA representative to provide an update at the next DCMDG meeting. | Secretariat | Closed | 15/06/2023 - Ongoing. 20/07/2023 - No further update as of yet. Will seek ENA attendance for August DCMDG meeting. 17/08/2023 - The Chair has reached out to ENA, but no response has been received as of yet. 21/09/2023 - The Chair confirmed there has been no further update, and will reach out to other ENA members for a response. 19/10/23 - The Chair is actively looking for an ENA representative. Information on ENA Webinar has been shared in the DCMDG 68 minutes.
DCMDG_66/02: | The Secretariat to add Schedule 32 related changes to the legal text overlap tracker on the DCMDG Forward Work Plan and Issues Log. | Secretariat | Closed | 17/08/2023 - Ongoing. 21/09/2023 - Updated version will be circualted to the WG prior to the next meeting. 19/10/2023 - Agreed action was completed and can be closed.
DCMDG_66/03: | AM to confirm whether a derogation is needed for the chosen option in regard to the DCP 414 decision. | AM (Ofgem) | Closed | 17/08/2023 - Ongoing. 21/09/2023 - AM will follow-up post meeting as no update has been received as of yet. 19/10/23 - AM to confirm there will be no need for a derogation. 18/01/24 - Ongoing. 15/02/24 - Closed.
DCMDG_67/01: | The Secretariat to update the DCMDG 66 minutes and re-upload to the DCUSA website. | Secretariat | Closed | 21/09/2023 - New. 19/10/23 - This had been done. Action now closed.
DCMDG_68/01: | The Secretariat to include updates for changes currently with the Authority for decision based on the updates provided to the DCUSA Panel in the minutes for this meeting (DCMDG 68 Minutes). | Secretariat | Closed | 21/09/2023 - New. 19/10/2023 - Agreed action was completed and can be closed.
DCMDG_68/02: | The Secretariat to include DCMDG Subgroup 01 - Meeting 02 to the DCMDG 68 Minutes | Secretariat | Closed | 21/09/2023 - New. 19/10/2023 - Agreed action was completed and can be closed.
DCMDG_68/03: | The Secretariat to include ENA shared links to the DCMDG 68 Minutes | Secretariat | Closed | 21/09/2023 - New. 19/10/2023 - Agreed action was completed and can be closed.
DCMDG_68/04: | Notification of Updated Charging Statement Addendums - The Chair to set out potential resolutions as discussed during DCMDG 68 and present this back to DCMDG members during the next DCMDG meeting. | Secretariat | Closed | 21/09/2023 - New. 19/10/2023 - Agreed action was completed and can be closed.
DCMDG_68/05: | DUoS Charges for Phased Capacity Sites - The Chair to draft potential text changes as discussed during DCMDG 68 and present this back to DCMDG members during the next DCMDG meeting. | Secretariat | Closed | 21/09/2023 - New. 19/10/2023 - Agreed action was completed and can be closed.
DCMDG_68/06: | Impacts on LLFs due to Annual Allocation Review - The Chair to reply to the person who had sent enquiry through to the DCUSA Code Admin team and explain the outcome of the DCMDG discussions. | Secretariat | Closed | 21/09/2023 - New. 19/10/2023 - Agreed action was completed and can be closed.
DCMDG_69/03: | The Secretariat to include exact dates re Ofgem new added external activities letter on strategic transmission reform. | Secretariat | Closed | 16/11/2023 - New 21/12/2023 - Agreed action was completed and can be closed.
DCMDG_69/01: | The Secretariat to include action 68/01 in the DCMDG 68 minutes and re upload updated post meeting pack version to the DCUSA website. | Secretariat | Closed | 16/11/2023 - New 18/01/2024 - Agreed action was completed and can be closed.
DCMDG_69/02: | The Secretariat to update the DCMDG 68 minutes actions boxes and the action log to add clarity to what each action refers to. | Secretariat | Closed | 16/11/2023 - New 18/01/2024 - Agreed action was completed and can be closed.
DCMDG_70/01: | Minutes of the November meeting: The Secretariat to update the minutes for meeting 69 to remove the final sentence in the second to last bullet point under paragraph 4.1 and to ensure the hyperlink to CMP 425 looks like a hyperlink. | Secretariat | Closed | 21/12/2023 - New 18/01/2024 - Agreed action was completed and can be closed.
DCMDG_70/02: | Timelines for revision of Charging Bands and Allocation of sites to those bands: The Chair to issue all DNOs/IDNOs an email, setting out the two options which had been discussed for the first time in November and ask that they reply to the email confirming the 24 month period they intend on using for the allocation of sites to charging bands for the next transmission price control period and report these findings back to the DCMDG. | Secretariat | Closed | 21/12/2023 - New 18/01/2024 - Agreed action was completed and can be closed.
DCMDG_71/01 | DNOs have taken an action to discuss the 24-month window associated with the allocation of sites to residual charging bands between themselves and to come to an agreement on the approach to take and to feedback the outcome of this to the next DCMDG meeting. | DNOs | Closed | 18/01/2024 - New 15/02/2024 - Agreed action was completed and can be closed.
DCMDG_72/01 | The Secretariat to update the DCMDG 71 Minutes to include: • An action be captured for the text in paragraph 7.4, whereby the DNOs should have taken an action to discuss the 24-month window associated with the allocation of sites to residual charging bands between themselves and to come to an agreement on the approach to take; • A suggestion that an action be captured for the text in paragraph 7.4, whereby the Secretariat should have taken an action to: o Provide the ESO with the approach agreed by the DNOs, so that they are aware of what has been agreed for the distribution residual banding allocation window; and o To seek similar confirmation from the ESO with respect to the Transmission Demand Residual banding allocation of sites to residual charging bands; | ElectraLink | Closed | 15/02/2024 - New 18/04/2024 - Agreed action was completed and accepted by DCMDG memebers and can be closed.
ACTION 72/02 | The Secretariat to circulate to members the DCMDG Issues Form for members to use if wanting to raised anything as part of the annual review of the Charging Methodologies in April. | ElectraLink | Closed | 15/02/2024 - New 18/04/2024 - Agreed action was completed and can be closed.
DCMDG_73/01 | The Secretariat to update the DCMDG 71 Action Log | ElectraLink | Closed | 28/03/2024 - New 18/04/2024 - Agreed action was completed and accepted by DCMDG members and can be closed.
DCMDG_72/03 | MC to look into DCP 392 and DCP 411 to see if an update with respect to when a decision is likely to be made can be provided. | Ofgem | Closed | 15/02/2024 - New 18/04/2024 - Ongoing. Update provided by Chair during meeting 73 confirming that a decision to reject DCP 392 had been made by Ofgem on 16 February 2024 and that the latest update for DCP 411 from Ofgem that had been provided to the Panel meeting on 20 March was that the expected decision date is now 08 April 2024. Ofgem Decision to Reject DCP 411 was published on 19 April 2024. 16/05/2024 - Agreed action was completed and can be closed.
DCMDG_74/02 | The Secretariat to update the DCMDG External Activities with the latest information for the following items: • DUoS SCR update, including the March CFF update • Strategic transmission charging update; • FSO implementation; • Open letter on regulatory arrangements for IDNOs, and; • Code Governance Reform update. | ElectraLink | Closed | 18/04/2024 - New 09/05/2024 - Updated DCMDG External Activities with Forward Work Plan and circulated with meeting pack for meeting 75 16/05/2024 - Agreed action was completed and can be closed.
DCMDG_71/02 | Secretariat to provide the ESO with the approach agreed by the DNOs, so that they are aware of what has been agreed for the distribution residual banding allocation window and to seek similar confirmation from the ESO with respect to the Transmission Demand Residual banding allocation of sites to residual charging bands. | ElectraLink | Closed | 18/01/2024 - New 15/02/2024 - Agreed action but is ongoing.This was completed but further information is desireable in terms of the actual window of data to be used by the ESO as response to date was "From a Transmission perspective the ESO doesn’t require any input of data from any DNO/IDNO. We will be setting the transmission banding threshold in line with the DNO/IDNO timelines so that the whole of the UK banding thresholds are done at the same time. However because of our the TNUoS tariff setting process, we will not be finalising the allocation of sites to bands until closer to Final tariff publication 2026/27 in January 2026." 18/04/2024 - Ongoing. The information of the actual window of data to be used by ESO is yet to be presented to the DCMDG members. 16/05/2024 - The Chair noted that ESO has been contacted prior to the DCMDG 75 meeting and is yet to respond and clarify the missing information regarding the banning allocation for the transmission demand residual. 20/06/24 - The Chair reiterated that ESO is yet to respond and clarify the missing information regarding the banning allocation for the transmission demand residual. DCMDG members noted they’re okay for this action to be closed and for the response to be circulated once received. Agreed action was completed and can be closed.
DCMDG_75/01 | The Secretariat to set a Sub-Group for a discussion on the process for the annual allocation review and specifically what distributors were providing to suppliers and to see if agreement can be reached on the use of a template for this purpose. | ElectraLink | Closed | 16/052024 - New 20/06/24 - The Chair confirmed that a subgroup has been created from this action. The Chair gave a brief updated on the DCMDG ‘AAR Lessons Learnt’ Subgroup, this being that a brief RFI and a guidance document being produced. An item will be added to the agenda to keep the DCMDG members up to date with the subgroup’s progress. Agreed action was completed and can be closed.
DCMDG_76/01 | The Chair to contact Ofgem regarding the statement that was expected from them at the end of June 2024. | ElectraLink | Closed | 20/06/2024 - New 18/07/2024 - It was noted that this item was covered in the Ofgem update during DCMDG meeting 77. Agreed action was completed and can be closed.
DCMDG_76/02 | The Secretariat to circulate to the DCMDG members the material related to the structure for Line Loss Factor (LLF) IDs moving forward that was presented during the meeting. | ElectraLink | Open | 20/06/2024 - New 18/07/2024 - It was nother that an updated version of the material related to the structure for Line Loss Factor (LLF) IDs moving forward had been circulated to the DCMDG members with the minutes of DCMDG meeting 77. Agreed action was completed and can be closed.
DCMDG_72/04 | The Secretariat to: • Draft and send an email to all DCUSA Contract Managers providing them with the agreed approach that the DNOs will use for the 24-month window for the allocation of sites to charging bands; and • produce and subsequently uploaded to the DCUSA website a document which will set out the agreed approach that the DNOs will use for the 24-month window for the allocation of sites to charging bands. | ElectraLink | Open | 15/02/2024 - New 18/04/2024 - Ongoing. The Chair confirmed that the document which will set out the agreed approach that the DNOs will use for the 24-month window for the allocation of sites to charging bands has now been uploaded to the DCUSA website, however needs more time to send out the email to All DCUSA Contract Managers. DCMDG members noted the urgency of this action being closed. 16/05/2024 - The Chair reassured the DCMDG members that an email will be issued to contract managers before the DCMDG 76 meeting. 20/06/24 - The Chair reassured The DCMDG members that the information will be published by the end of June 2024; The Chair asked the room if they would be interested in the new banding thresholds being published in the DCUSA Website, to which members agreed that it would be useful, this was updated live during the meeting and can be found in the DCUSA Website. 15/08/2024 - The Chair confirmed this has been issued prior to DCMDG 78 meeting, it was also included information regarding the upcoming annual allocation review processes that should be followed as it ties into the discussions that were had in the AAR Sub-Group. This action is therefore closed.
DCMDG_74/01 | The Chair to update the Legal Text Overlap Tracker with any of the new DCPs that have recently entered into the DCUSA change control process. | ElectraLink | Open | 18/04/2024 - New 16/05/2024 - The Chair informed the DCMDG members that more time is needed to complete this action and it will be done before DCMDG 76 meeting 20/06/24 - The Chair informed the DCMDG members that more time is needed to complete this action and it will be done before DCMDG 77 meeting. 18/07/24 - The Chair informed the DCMDG members that more time is needed to complete this action and it will be done before DCMDG 78 meeting. 15/08/2024 - The Chair confirmed that the updated version will be circulated with the minutes and can be reviewed during the September meeting. This action is therefore closed.
DCMDG_77/01 | The Secretariat ti expand on point 3.2 of the DCMDG 76 minutes, regarding the NESO (National Energy System Operator) fot he benefit of readers. | ElectraLink | Open | 18/07/2024 - New 15/08/2024 - The Chair informed the members this had been done and the DCMDG members were happy with the final text added to expand on the NESO in the DCMDG 77 Minutes. This action is therefore closed.