## CPs
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Current Status | Status Changed in the last month | Date Issued to Ofgem | Original Expected Decision Date | Latest Expected Decision Date
STATUS - INITIAL ASSESSMENT
DCP 446 | Emergency Disconnections | To enable distributors to charge customers covered by section 2 of the National Terms of Connection for emergency disconnections that have been caused by their act or omission. | General | 1 | Craig Booth | N/A | 2024-11-07 | 0 | No | Next scheduled release following approval | Being presented to the Panel for approval to progress to Working Group on 20 November 2024. | INITIAL ASSESSMENT | INITIAL ASSESSMENT
DCP 447 | NTC Section Footers | This is a housekeeping change to add the Section Number into the Footers within Schedule 2B so the reader can be sure the terms they are reading are for the intended section. | General | 2 |  | N/A | 2024-11-11 | 0 | No | Next scheduled release following approval | Being presented to the Panel for approval to progress to Change Report on 20 November 2024. | INITIAL ASSESSMENT | INITIAL ASSESSMENT
DCP 448 | Supercustomer Billing | This is a housekeeping change to align DCUSA text to what happens in the supercustomer process by amending Clause 20.4 to replace “different from those included in an Initial Account” with “different from those previously billed”. | General | 2 |  | N/A | 2024-11-11 | 0 | No | 2025-04-01 | Being presented to the Panel for approval to progress to Change Report on 20 November 2024. | INITIAL ASSESSMENT | INITIAL ASSESSMENT
STATUS - DEFINITION
DCP 325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20. | The intent of this Change Proposal is to combine, review and if appropriate, amend the requirements of Section 35A, Section 35B, Schedule 15 and Schedule 20 to improve transparency and efficiency in the data published by DNOs | General | 2 | Richard Colwill / Melissa Kendal | N/A | 2018-11-07 | 15 | No | Next scheduled release following approval | The Working Group is next due to meet on 12 December 2024 where they will review the consultation responses and determine next steps. | CONSULTATION | CONSULTATION
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | The intent of this modification is to define “Mixed Demand” Sites and apply a proportionate Residual charge where a Site meets the mixed demand definition. | General | 1 | John Lawton / Andy Green | Andrew Malley | 2021-04-14 | 17 | No | TBC | The Working Group met on 02 October to review the need for a BSC change. It was agreed that a BSC change was required and that DCP 388 couldn’t be progressed until the BSC modification had been defined so DCP 388 has been paused until the Proposer raises the required BSC modification. | DEFINITION | N/A
DCP 412 | Allocation of banding for TCR Charges for ‘Peaky’ Final Demand Customers | The intent of this CP is to consider the residual charge for ‘peaky’ customers, removing the disproportionate impact of allocating residual charges on the basis of the Agreed Supply Capacity. | CDCM / EDCM | 1 | Craig Booth / Richard Colwill | Andrew Malley | 2022-10-11 | 37 | No | TBC | The DCP 412 Working Group last met on 23 October, where they reviewed a draft of the Change Report and the legal text and are planning to meet later in November, to finalise the legal and Change Report. The aim is for the Change Report to be issued to the Panel in December. | DEFINITION | N/A
DCP 415 | Replacement of D0242/D0315 for MHHS | To create a new DCUSA owned DIP data message for supercustomer billing statements using MHHS data. | Billing | 2 | Hannah Proffitt / Craig Booth | N/A | 10/22/2022 | 3 | Yes | TBC (dependent on date required for DIP testing) | The Change Report was submitted to the Panel for review in the February 2023 Panel meeting. The Panel agreed that it would not progress to Party voting and that it should be sent back to the Working Group but that the Working Group won’t need to meet until the MHHS Programme have been able to carry out an Impact Assessment for the solution they developed. It was noted that even then, no further work may be required but that it was too early to know that for sure. | DEFINITION | N/A
DCP 416 | Electronic Invoicing Post MHHS | To create a new DCUSA owned DIP data message for electronic Distributor billing post MHHS. | Billing | 2 | Melissa Kendal / Andy Green | N/A | 2022-11-14 | 5 | Yes | TBC (dependent on date required for DIP testing) | The Working Group have reviewed the consultation responses and met on 23 June 2023 to finalise the conclusions to the second consultation. A decision on whether or not a Change Report is to be produced is to be made by the Panel but the Proposer has initated a MHHS Change Request for the CP to be impact assessed and so it is expected that DCP 416 will be put on hold, pending outcome of the MHHS Change Request. | DEFINITION | N/A
DCP 419 | Pre-Notifications of Planned Supply De-Energisations | This change seeks to ensure that all DCUSA Parties, that de-energise metering equipment as part of any planned work, provide the Distributor with advance notification of the supply interruption. | General | 1 | Alysson Pena / Richard Colwill | TBC | 2023-03-06 | 13 | No | Next scheduled release following approval | The DCP 419 Working Group last met on 25 September 2024 where they explored the feasability of using a DCC service request. Further analysis was needed for this solution and once this has been confirmed to be completed, the next meeting of the Working Group will be set up. | DEFINITION | N/A
DCP 420 | Provide targeted relief from residual charges for electric vehicle charging sites | The intent of this Change Proposal is to provide targeted relief from residual charges to publicly accessible electric vehicle (“EV”) charging sites. This may be a temporary fix to be put in place until the charging stations included are commercially viable. | General | 1 | Craig Booth / Richard Colwill | TBC | 2023-03-29 | 15 | No | TBC | The DCP 420 Working Group issued a consultation on 9 October 2024 and are due to meet next on 19 November to review responses and determine next steps. | DEFINITION | N/A
DCP 423 | LDNO Discounts for negative scaling | The purpose of this change proposal is to set a floor on the LDNO discount applied to negative tariff components, after scaling, for demand tariffs. The intent of this change proposal is to seek to remedy what the proposer believes is an unintended outcome of the implementation of Ofgem’s Targeted Charging Review where LDNO tariffs can be higher than the equivalent all-the-way tariff i.e. the LDNO margin is negative for that component. | CDCM | 1 | Melissa Kendal / Andy Green | TBC | 2023-05-09 | 7 | No | 2025-04-01 | The proposer is considering withdrawing DCP 423. | DEFINITION | N/A
DCP 424 | Use of System charging for complex sites | This change proposal enables the correct DUoS to be paid by meters that are class F or G within a Class 5 or Class 6 Complex Site as described in BSC Modification P441 (where netting of Import and Export takes place for BSC Settlement purposes) in a practical manner. Under p441 where generation and demand are netted before settlement, the gross values must be added to the D0036 or D0275 to ensure the correct DUoS is charged. However, for class F and G the MPAN counts are included on the D0030 data flows but the volumes are zero. In order for the volumes to be correctly charged DUoS it is proposed that these volumes are included in the D0036 or D0275 using a pseudo MPAN for the gross value. | CDCM | 1 | Andy Green / Craig Booth | TBC | 2023-05-10 | 7 | Yes | Aligned to BSC Mod P441 Implementation Date | DCP 424 has been delayed due a request by Ofgem for further impact analysis on the proposed BSC solution (P441 - Creation of Complex Site Classes). The DCP 424 consultation is now estimated to be released in Q3 2024. | DEFINITION | N/A
DCP 440 | Consuming “de-energised” sites | To ensure all consuming “de-energised” sites are charged DUoS. | CDCM | 1 | Hannah Proffitt / Andy Green | TBC | 2024-03-14 | 6 | No | 2026-04-01 | The DCP 440 Working Group is due to meet on 13 November 2024, where they will review RFI responses and Change Report, with the aim of issuing to the December Panel. | DEFINITION | N/A
DCP 442 | Aligning enduring flexible connections | The intent of this Change Proposal is to align (and clarify) the two approaches that currently may result in a flexible connection being provided on an enduring basis. A flexible connection on an enduring basis is an arrangement that allows a Customer’s import/export of electricity via a connection to be restricted by a DNO/IDNO Party in perpetuity. This CP proposes that such a connection shall be a Flexible Connection rather than a Curtailable Connection. | General | 1 | Melissa Kendall / Craig Booth | TBC | 2024-07-01 | 2 | No | 2025-04-01 | The DCP 442 Working Group is due to meet on 14 November to review RFI responses and determine next steps. | DEFINITION | N/A
DCP 443 | Excess Capacity | The purpose of this Change Proposal is to drive the correct customer behaviour regarding exceeding capacity. | CDCM / EDCM | 1 | Melissa Kendal / Andy Green | TBC | 2024-07-09 | 6 | No | 2026-04-01 | The DCP 433 Working Group is due to meet next on 22 November with the aim of finalising an RFI to be issued to industry. | DEFINITION | N/A
STATUS - CHANGE REPORT
N/A
N/A
STATUS - AWAITING AUTHORITY CONSENT
DCP 417 | Ability for the DCUSA Secretariat to Raise Change Proposals | This change seeks to grant the ability to the Secretariat to raise Change Proposals where it identifies a change that would better facilitate the DCUSA Objectives and to introduce an obligation for the Secretariat to raise Change Proposals in certain circumstances, such as at the direction of the Authority. | General | 1 | Melissa Kendal / Richard Colwill | Nadir Hafeez | 2022-12-14 | 12 | No | Next scheduled release following approval | The Working Group met on 23 April, with a representative from Gowling WLG in attendance, in order to finalise the legal text. The legal text was agreed with the legal representative from Gowling WLG. The Change Report presented to the Panel during their May 2024 meeting, where it was approved and was subsequently issued for voting following the May Panel meeting for a period of 15 Working Days. The outcome of the Party voting was a recommendation that Ofgem Accept DCP 417 and the Change Declaration was issued to Authority for approval on 11 June 2024. | AWAITING AUTHORITY CONSENT | N/A | 2024-06-11 | 2024-10-30 | 2024-10-30
DCP 433 | Limitation for backdating of rebates/charges under Schedule 32 | The intent of this Change Proposal is to amend Schedule 32 to ensure that processes which may result in the backdating of rebates/charges are reflective of the limitations within the current industry arrangements. | General | 1 | Craig Booth | TBC | 2024-01-05 | 5 | No | 2024-06-27 | The Change Report was presented to the Panel during their May 2024 meeting, where it was approved and was subsequently issued for voting following the May Panel meeting for a period of 15 Working Days. The outcome of the Party voting was a recommendation that Ofgem Accept DCP 433 and the Change Declaration was issued to Authority for approval on 10 June 2024. | AWAITING AUTHORITY CONSENT | N/A | 2024-06-10 | 2024-11-08 | 2024-11-08
DCP 438 | Rate of Return Change Proposal | This change proposal aims to update the rate of return as the previous legal text is out of date | CDCM | 1 | Hannah Proffitt / Craig Booth | TBC | 2024-02-27 | 2 | No | 2025-04-01 | The Working Group met in April and agreed to issue a consultation for DCP 438. The consultation was issued on 07 May, with responses due by 29 May 2024. The second Working Group meeting was held on 04 June 2024 to review responses and the draft Change Report. The Change Report was issued to the Panel during the June Panel meeting, where it was approved to be issued for Party voting. | AWAITING AUTHORITY CONSENT | N/A | 2024-07-15 | 2024-12-11 | 2024-12-11
DCP 441 | Proposal to increase the number of allowed Change Report alternative variations from two to three | This Change Proposal seeks to change the number of alternative variations that can be added by the Panel to a Change Report from two to three. | General | 1 | Alysson Pena | N/A | 2024-01-05 | 2 | No | 2024-06-27 | DCP 441 was submitted to the Panel for Initial Assessment during their May meeting. The Panel approved for DCP 441 to progress to the Change Report Phase. The Change Report was issued to the Panel during the June Panel meeting, where it was approved to be issued for Party voting. | AWAITING AUTHORITY CONSENT | N/A | 2024-07-18 | 2024-12-06 | 2024-12-06
DCP 439 | Backdating Tariff Changes | This change proposal seeks to add a sensible backstop to backdating. | CDCM | 1 | Hannah Proffitt / Andy Green | TBC | 2024-03-14 | 4 | No | 2025-04-01 | The DCP 439 Change Report was issued to the August Panel meeeting for approval to progress to voting. During their meeting, the Panel requested for some amendments to be made and agreed to consider the the Change Report ex-committee. Approval was subsequently obtained via email and the Change Report was issued for voting for a period of 15 Working Days. | AWAITING AUTHORITY CONSENT | N/A | 2024-09-18
DCP 445 | Implementation of Market-wide Half Hourly Settlement (MHHS) Arrangements | This Change Proposal will ensure that the appropriate obligations, processes and provisions for the new MHHS arrangements, which have been developed and consulted on as part of the MHHS Programme, are introduced into the DCUSA. | General | 1 | Dylan Townsend | N/A | 2024-09-04 | 0 | No | Will be the date determined by the Authority in line with the MHHS Programme milestone, M8 ‘Code changes delivered’ | DCP 445 was submitted to the Panel for Initial Assessment during their September meeting. The Panel approved for DCP 445 to progress to the Change Report Phase. The Change Report is being issued to the Panel during the October Panel meeting. | AWAITING AUTHORITY CONSENT | AWAITING AUTHORITY CONSENT | 2024-11-08
DCP 437 | To Shorten the DUoS Pricing Notice Periods | This change proposal aims to shorten the DUoS Pricing Notice Periods so there is longer period between the publication of the PCFM where OFGEM have the option to make changes to our allowed revenue at short notice and the setting of the prices | CDCM | 1 | Hannah Proffitt / Richard Colwill | TBC | 2024-02-13 | 4 | No | 1 Working Day following approval | Voting for DCP 437 ended on 9 October 2024. A Change Declaration was issued to industry and the Authority on 10 October 2024, with a recommendation to accept the proposed solution and implementation date. | AWAITING AUTHORITY CONSENT | AWAITING AUTHORITY CONSENT | 2024-10-10
STATUS - AWAITING IMPLEMENTATION
2025-04-01
DCP 428 | Zero REP-002/A Data | To specify how parties should deal with zero or blank data in the supercustomer/aggregated billing messages when sending daily statements or raising invoices. | General | 2 | Richard Colwill/ Alysson Peña | N/A | 2023-07-25 | 4 | No | 2025-04-01 | The DCP 428 Working Group finalised their review of the legal text to confirm it was fit for purpose and the Change Report was approved by the Panel ex-committee and subsequently issued for voting on 10 April 2024. The outcome of the Party voting was to Accept DCP 428 and therefore the change will be implemented. | AWAITING IMPLEMENTATION | N/A
STATUS - SENT BACK
N/A | N/A | [7 empty] | No |  |  |  | N/A
STATUS - IMPLEMENTED
DCP 435 | Party Novation Process | To add a process within DCUSA to enable a Party to transfer its rights and obligations to another Party via a novation agreement. | General | 1 | Craig Booth | N/A | 2024-02-09 | 0 | No | Next release after approval. | The Change Report was issued for voting following the March Panel meeting for a period of three weeks. The outcome of the Party voting was a recommendation that Ofgem Accept DCP 435 and the Change Declaration was issued to Authority for approval. | IMPLEMENTED | IMPLEMENTED
STATUS - REJECTED
N/A | N/A | [7 empty] | No |  |  |  | N/A
STATUS - WITHDRAWN
DCP 444 | Additional Settlement Runs | To describe how settlement runs, that will cause Supercustomer DUoS Reports (REP-002/A/B) to be created and sent under MHHS, that were not previously created as D0030/D0314 flows, will be handled. | General | 2 | Hannah Proffitt / Richard Colwill | N/A | 2024-09-03 | 2 | No | 2025-04-01 | The DCP 444 Working Group have met twice and have developed a consultation document which was issued on 08 October 2024 for a period of 2 weeks. The Working Group is scheduled to meet again on 25 October 2024 to review the consultation responses. | WITHDRAWN | WITHDRAWN
Change Register - November 2024

## Status Changes
[14 empty] | AWAITING IMPLEMENTATION | 1
[14 empty] | IMPLEMENTED | 1
[14 empty] | REJECTED | 0
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status | Status Changed in the last month | DEFINITION | 11
DCP 446 | Emergency Disconnections | To enable distributors to charge customers covered by section 2 of the National Terms of Connection for emergency disconnections that have been caused by their act or omission. | General | 1 | Craig Booth | N/A | 2024-11-07 | 0 | No | Next scheduled release following approval | Being presented to the Panel for approval to progress to Working Group on 20 November 2024. | #VALUE! | INITIAL ASSESSMENT
DCP 447 | NTC Section Footers | This is a housekeeping change to add the Section Number into the Footers within Schedule 2B so the reader can be sure the terms they are reading are for the intended section. | General | 2 |  | N/A | 2024-11-11 | 0 | No | Next scheduled release following approval | Being presented to the Panel for approval to progress to Change Report on 20 November 2024. | #VALUE! | INITIAL ASSESSMENT
DCP 448 | Supercustomer Billing | This is a housekeeping change to align DCUSA text to what happens in the supercustomer process by amending Clause 20.4 to replace “different from those included in an Initial Account” with “different from those previously billed”. | General | 2 |  | N/A | 2024-11-11 | 0 | No | 2025-04-01 | Being presented to the Panel for approval to progress to Change Report on 20 November 2024. | #VALUE! | INITIAL ASSESSMENT
DCP 325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20. | The intent of this Change Proposal is to combine, review and if appropriate, amend the requirements of Section 35A, Section 35B, Schedule 15 and Schedule 20 to improve transparency and efficiency in the data published by DNOs | General | 2 | Richard Colwill / Melissa Kendal | N/A | 2018-11-07 | 15 | No | Next scheduled release following approval | The Working Group is next due to meet on 12 December 2024 where they will review the consultation responses and determine next steps. | CONSULTATION | CONSULTATION
DCP 445 | Implementation of Market-wide Half Hourly Settlement (MHHS) Arrangements | This Change Proposal will ensure that the appropriate obligations, processes and provisions for the new MHHS arrangements, which have been developed and consulted on as part of the MHHS Programme, are introduced into the DCUSA. | General | 1 | Dylan Townsend | N/A | 2024-09-04 | 0 | No | Will be the date determined by the Authority in line with the MHHS Programme milestone, M8 ‘Code changes delivered’ | DCP 445 was submitted to the Panel for Initial Assessment during their September meeting. The Panel approved for DCP 445 to progress to the Change Report Phase. The Change Report was issued to the Panel during the October Panel meeting where it was approved to be issued for Party Voting. Party Voting closed on 07 November 2024 and a Change Declaration being issued to industry and the Authority on 08 November 2024, with a recommendation to accept the proposed solution and implementation date. | CONSULTATION | AWAITING AUTHORITY CONSENT
DCP 437 | To Shorten the DUoS Pricing Notice Periods | This change proposal aims to shorten the DUoS Pricing Notice Periods so there is longer period between the publication of the PCFM where OFGEM have the option to make changes to our allowed revenue at short notice and the setting of the prices | CDCM | 1 | Hannah Proffitt / Richard Colwill | TBC | 2024-02-13 | 4 | No | 1 Working Day following approval | Voting for DCP 437 ended on 9 October 2024. A Change Declaration was issued to industry and the Authority on 10 October 2024, with a recommendation to accept the proposed solution and implementation date. | CONSULTATION | AWAITING AUTHORITY CONSENT
DCP 435 | Party Novation Process | To add a process within DCUSA to enable a Party to transfer its rights and obligations to another Party via a novation agreement. | General | 1 | Craig Booth | N/A | 2024-02-09 | 0 | No | Next release after approval. | The Change Report was issued for voting following the March Panel meeting for a period of three weeks. The outcome of the Party voting was a recommendation that Ofgem Accept DCP 435 and the Change Declaration was issued to Authority for approval. | CONSULTATION | IMPLEMENTED
DCP 444 | Additional Settlement Runs | To describe how settlement runs, that will cause Supercustomer DUoS Reports (REP-002/A/B) to be created and sent under MHHS, that were not previously created as D0030/D0314 flows, will be handled. | General | 2 | Hannah Proffitt / Richard Colwill | N/A | 2024-09-03 | 2 | No | 2025-04-01 | The DCP 444 Working Group have met twice and have developed a consultation document which was issued on 08 October 2024 for a period of 2 weeks. The Working Group is scheduled to meet again on 25 October 2024 to review the consultation responses. | #REF! | WITHDRAWN
Status Change - November 2024

## Timetables
DCP | Title | Part 1/ Part 2 Matter | Standard/ Urgent | Proposer | Party | Technical Secretariat | Chair | Timetable Change | [6 empty] | Notes
[9 empty] | Nov | Dec | Jan | Feb | Mar | Apr
444 | Additional Settlement Runs | Part 2 | Standard | Peter Waymont | UKPN | Melissa Kendall | Andy Green | N | [6 empty] | DCP 444 has been withdrawn | bar: Nov
443 | Excess Capacity | Part 1 | Standard | Peter Waymont | UKPN | Melissa Kendall | Andy Green | N | Nov: DEF; Dec: DEF; Jan: CR
442 | Aligning enduring flexible connections | Part 1 | Standard | Lee Wells | NPg | Melissa Kendall | Craig Booth | Y | Nov: DEF; Dec: CR | Need for an RFI and a cancelled meeting at the request of the proposer
442 | New timetable | [7 empty] | RFI | CON | DEF | CR
440 | Consuming “de-energised” sites | Part 1 | Standard | Peter Waymont | UKPN | Hannah Proffitt | Andy Green | Y | [6 empty] | The Working Group identified the need to issue an RFI to DNOs requesting data, as data previously provided may not have been sufficient. | bar: Nov
440 | New timetable | [7 empty] | Nov: DEF; Dec: CR
424 | Use of System charging for complex sites | Part 1 | Standard | Mary Gillie | NPg | Craig Booth | Andy Green | N | Nov: O/H
423 | LDNO Discounts for negative scaling | Part 1 | Standard | Tom Cadge | ENC | Melissa Kendall | Andy Green | N | [6 empty] | Proposer considering withdrawing CP as it creates an issue with the SOLR process within the modelling. | bar: Nov
420 | Include Car Charging Stations In The Definition For Non Final Demand | Part 1 | Standard | Dave Wornell | NGED | Craig Booth | Richard Colwill | Y | [6 empty] | This timetable was included in error last month. | bar: Nov
420 | New timetable | [7 empty] | DEF | DEF | CON | DEF | DEF | CR
419 | Pre-notification of Planned Supply De-energisations | Part 1 | Standard | Nikhel Jethwa | SSEN | Alysson Peña | Richard Colwill | N | Nov: DEF; Dec: DEF; Jan: CR
416 | Electronic Invoicing Post MHHS | Part 2 | Standard | Peter Waymont | UKPN | Craig Booth | Andy Green | N | Nov: O/H
415 | Replacement of D0242/D0315 for MHHS | Part 2 | Standard | Peter Waymont | UKPN | Melissa Kendall | Craig Booth | N | Nov: O/H
412 | Discounts from TCR charges for ‘peaky’ final demand customers | Part 1 | Standard | Lee Stone | E.ON | Craig Booth | Richard Colwill | Y | [6 empty] | Working Group needed more time to finalise the Change Report based on some legal text amendments after legal review. | bar: Nov
412 | New timetable | [7 empty] | Nov: DEF; Dec: CR
388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | Part 1 | Standard | Lee Stone | E.on | Andy Green | John Lawton | N | Nov: O/H
325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20 | Part 1 | Standard | Kara Burke | NPg | Craig Booth | Andy Green | Y | [6 empty] | This timetable was included in error last month. | bar: Nov
325 | New timetable | [7 empty] | CON | DEF | DEF | CR
| DEFINITION | DEF
| RFI | RFI
| CONSULTATION | CON/ CON 2
| CHANGE REPORT | CR
| ON HOLD | O/H

## Legal Text Overlap Tracker
YES
|  | MHHS | DCP 424 | DCP 325 | DCP 423 | DCP 388 | DCP 412 | DCP 420 | DCP 433 | DCP 438 | DCP 439 | DCP 440 | DCP 443
|  | Unknown | 2024-11-21 | Next Scheduled | 2025-04-01 | TBC | TBC | 2025-04-01 | 2024-11-07 | 2024-11-07 | 2025-04-01 | 2026-04-01 | TBC |  | NOTES TO ASSIST
Schedules | Paragraph Number | Change Report | On Hold | Definition | Definition | On Hold | Change Report | Consultation | Awaiting Consent | Awaiting Consent | Awaiting Consent | Change Report | Definition | Number of CPs Impacting Paragraph
Schedule 15 | Table 1 |  |  | YES | [9 empty] | 1 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 2 |  |  | YES | [9 empty] | 1 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 3 |  |  | YES | [9 empty] | 1 | The WGs for DCP 325 and DCP 421 are aware of the interactions
0
Schedule 16 | Introduction | [12 empty] | 0
Schedule 16 | 1 | [12 empty] | 0
Schedule 16 | 2 | [12 empty] | 0
Schedule 16 | 3 | [12 empty] | 0 | Model reference number and date
Schedule 16 | 4 | [12 empty] | 0
Schedule 16 | 5 | [12 empty] | 0
Schedule 16 | 6 | [12 empty] | 0
Schedule 16 | 7 | [12 empty] | 0
Schedule 16 | 7A | [12 empty] | 0
Schedule 16 | 8 | [12 empty] | 0
Schedule 16 | 9 | [12 empty] | 0
Schedule 16 | 10 | [12 empty] | 0
Schedule 16 | 10A | [12 empty] | 0
Schedule 16 | 11 | [12 empty] | 0
Schedule 16 | 12 | [12 empty] | 0
Schedule 16 | 13 | [12 empty] | 0
Schedule 16 | 14 | [12 empty] | 0
Schedule 16 | 15 | [12 empty] | 0
Schedule 16 | 16 | [12 empty] | 0
Schedule 16 | 17 | [12 empty] | 0
Schedule 16 | 18 | [12 empty] | 0
Schedule 16 | 19 | [12 empty] | 0
Schedule 16 | 20 | [12 empty] | 0
Schedule 16 | 21 | [12 empty] | 0
Schedule 16 | 22 | [12 empty] | 0
Schedule 16 | 23 | [12 empty] | 0
Schedule 16 | 24 | [12 empty] | 0
Schedule 16 | 25 | [12 empty] | 0
Schedule 16 | 26 | [12 empty] | 0
Schedule 16 | 27 | [12 empty] | 0
Schedule 16 | 28 | [12 empty] | 0
Schedule 16 | 29 | [12 empty] | 0
Schedule 16 | 30 | [12 empty] | 0
Schedule 16 | 31 | [12 empty] | 0
Schedule 16 | 32 | [12 empty] | 0
Schedule 16 | 33 | [12 empty] | 0
Schedule 16 | 34 | [12 empty] | 0
Schedule 16 | 35 | [12 empty] | 0
Schedule 16 | 36 | [12 empty] | 0
Schedule 16 | 37 | [12 empty] | 0
Schedule 16 | 38 | [12 empty] | 0
Schedule 16 | 39 | [12 empty] | 0
Schedule 16 | 40 | [12 empty] | 0
Schedule 16 | 41 | [12 empty] | 0
Schedule 16 | 41A | [12 empty] | 0
Schedule 16 | 41B | [12 empty] | 0
Schedule 16 | 42 | [12 empty] | 0
Schedule 16 | 42A | YES | [11 empty] | 1
Schedule 16 | 43 | [12 empty] | 0
Schedule 16 | 44 | YES | [11 empty] | 1
Schedule 16 | 45 | [12 empty] | 0
Schedule 16 | 46 | [12 empty] | 0
Schedule 16 | 47 | [12 empty] | 0
Schedule 16 | 48 | [12 empty] | 0
Schedule 16 | 49 | [12 empty] | 0
Schedule 16 | 50 | [12 empty] | 0
Schedule 16 | 51 | [12 empty] | 0
Schedule 16 | 52 | [12 empty] | 0
Schedule 16 | 52A | [12 empty] | 0
Schedule 16 | 53 | [12 empty] | 0
Schedule 16 | 54 | [12 empty] | 0
Schedule 16 | 55 | [12 empty] | 0
Schedule 16 | 56 | [12 empty] | 0
Schedule 16 | 57 | [12 empty] | 0
Schedule 16 | 58 | [12 empty] | 0
Schedule 16 | 59 | [12 empty] | 0
Schedule 16 | 60 | [12 empty] | 0
Schedule 16 | 61 | [12 empty] | 0
Schedule 16 | 62 | [12 empty] | 0
Schedule 16 | 63 | [12 empty] | 0
Schedule 16 | 64 | [12 empty] | 0
Schedule 16 | 65 | [12 empty] | 0
Schedule 16 | 66 | [12 empty] | 0
Schedule 16 | 67 | [12 empty] | 0
Schedule 16 | 68 | [12 empty] | 0
Schedule 16 | 69 | [12 empty] | 0
Schedule 16 | 70 | YES | [11 empty] | 1
Schedule 16 | 71 | [12 empty] | 0
Schedule 16 | 72 | [12 empty] | 0
Schedule 16 | 72A | [12 empty] | 0
Schedule 16 | 73 | [12 empty] | 0
Schedule 16 | 74 | [12 empty] | 0
Schedule 16 | 75 | [12 empty] | 0
Schedule 16 | 76 | [12 empty] | 0
Schedule 16 | 77 | [12 empty] | 0
Schedule 16 | 78 | [12 empty] | 0
Schedule 16 | 79 | [12 empty] | 0
Schedule 16 | 80 | YES | [11 empty] | 1
Schedule 16 | 81 | [12 empty] | 0
Schedule 16 | 82 | [12 empty] | 0
Schedule 16 | 83 | [12 empty] | 0
Schedule 16 | 84 | [12 empty] | 0
Schedule 16 | 85 | [12 empty] | 0
Schedule 16 | 86 | [12 empty] | 0
Schedule 16 | 87 | [12 empty] | 0
Schedule 16 | 88 | [12 empty] | 0
Schedule 16 | 89 | [12 empty] | 0
Schedule 16 | 90 | [12 empty] | 0
Schedule 16 | 91 | [12 empty] | 0
Schedule 16 | 92 | [12 empty] | 0
Schedule 16 | 92A | [12 empty] | 0
Schedule 16 | 92B | [12 empty] | 0
Schedule 16 | 92C | [12 empty] | 0
Schedule 16 | 93 | [12 empty] | 0
Schedule 16 | 94 | [12 empty] | 0
Schedule 16 | 95 | [12 empty] | 0
Schedule 16 | 96 | [12 empty] | 0
Schedule 16 | 97 | [12 empty] | 0
Schedule 16 | 98 |  |  |  | YES | [8 empty] | 1
Schedule 16 | 99 | [12 empty] | 0
Schedule 16 | 100 | [12 empty] | 0
Schedule 16 | 101 | [12 empty] | 0
Schedule 16 | 102 | [12 empty] | 0
Schedule 16 | 102A | [12 empty] | 0
Schedule 16 | 102B | [12 empty] | 0
Schedule 16 | 103 | [12 empty] | 0
Schedule 16 | 104 | [12 empty] | 0
Schedule 16 | 105 | [12 empty] | 0
Schedule 16 | 106 | [12 empty] | 0
Schedule 16 | 107 | [12 empty] | 0
Schedule 16 | 108 | [12 empty] | 0
Schedule 16 | 108A | [12 empty] | 0
Schedule 16 | 109 | [12 empty] | 0
Schedule 16 | 110 | [12 empty] | 0
Schedule 16 | 111 | [12 empty] | 0
Schedule 16 | 112 | [12 empty] | 0
Schedule 16 | 112A | [12 empty] | 0
Schedule 16 | 113 | [12 empty] | 0
Schedule 16 | 113A | [12 empty] | 0
Schedule 16 | 113B | [12 empty] | 0
Schedule 16 | 113C | [12 empty] | 0
Schedule 16 | 113D | [12 empty] | 0
Schedule 16 | 113E | [12 empty] | 0
Schedule 16 | 114 | [12 empty] | 0
Schedule 16 | 115 | [12 empty] | 0
Schedule 16 | 116 | [12 empty] | 0
Schedule 16 | 117 | [12 empty] | 0
Schedule 16 | 118 | [12 empty] | 0
Schedule 16 | 119 | [12 empty] | 0
Schedule 16 | 120 | [12 empty] | 0
Schedule 16 | 121 | [12 empty] | 0
Schedule 16 | 122 | [12 empty] | 0
Schedule 16 | 123 | [12 empty] | 0
Schedule 16 | 124 | [12 empty] | 0
Schedule 16 | 125 | [12 empty] | 0
Schedule 16 | 126 | [12 empty] | 0
Schedule 16 | 127 | [12 empty] | 0
Schedule 16 | 127A | [12 empty] | 0
Schedule 16 | 128 | YES | YES | [10 empty] | 2
Schedule 16 | 129 | YES | [11 empty] | 1
Schedule 16 | 130 | YES | [11 empty] | 1
Schedule 16 | 131 | [12 empty] | 0
Schedule 16 | 132 | YES | [11 empty] | 1
Schedule 16 | 132A | [12 empty] | 0
Schedule 16 | 132B | [12 empty] | 0
Schedule 16 | 132C | YES | [11 empty] | 1
Schedule 16 | 132D | [12 empty] | 0
Schedule 16 | 133 | YES | [11 empty] | 1
Schedule 16 | 134 | [12 empty] | 0
Schedule 16 | 135 | [12 empty] | 0
Schedule 16 | 135A | YES | [11 empty] | 1 | MHHS CP seeks to remove the last column containing applicable Measurement Class
Schedule 16 | 135B | [12 empty] | 0
Schedule 16 | 136 | [12 empty] | 0
Schedule 16 | 137 | [12 empty] | 0
Schedule 16 | 138 | [12 empty] | 0
Schedule 16 | 139 | [12 empty] | 0
Schedule 16 | 140 | [10 empty] | YES |  | 1
Schedule 16 | 140A | YES | [11 empty] | 1
Schedule 16 | 140B | YES | [11 empty] | 1
Schedule 16 | 140C | YES | [11 empty] | 1
Schedule 16 | 140D | [12 empty] | 0
Schedule 16 | 140E | [12 empty] | 0
Schedule 16 | 141 | [12 empty] | 0
Schedule 16 | 142 | YES | [11 empty] | 1
Schedule 16 | 143 | YES | [11 empty] | 1
Schedule 16 | 144 | YES | [11 empty] | 1
Schedule 16 | 145 | [12 empty] | 0
Schedule 16 | 146 | [12 empty] | 0
Schedule 16 | 147 | [12 empty] | 0
Schedule 16 | 148 | [12 empty] | 0
Schedule 16 | 149 | [12 empty] | 0
Schedule 16 | 150 | [12 empty] | 0
Schedule 16 | 151 | [12 empty] | 0
Schedule 16 | 152 | [12 empty] | 0
Schedule 16 | 153 | [11 empty] | YES | 1
Schedule 16 | 154 | [12 empty] | 0
Schedule 16 | 155 | [12 empty] | 0
Schedule 16 | 156 | [12 empty] | 0
Schedule 16 | 157 | [8 empty] | YES |  |  |  | 1
Schedule 16 | 158 | [12 empty] | 0
Schedule 16 | 159 | [12 empty] | 0
Schedule 16 | 160 | [12 empty] | 0
Schedule 16 | 161 | [12 empty] | 0
Schedule 16 | 162 | [12 empty] | 0
Schedule 16 | 163 | [12 empty] | 0
Schedule 16 | 164 | [12 empty] | 0
Schedule 16 | 165 | [12 empty] | 0
Schedule 16 | 166 | [12 empty] | 0
Schedule 16 | 167 | [12 empty] | 0
Schedule 16 | 168 | [12 empty] | 0
Schedule 16 | 169 | [12 empty] | 0
Schedule 16 | 170 | [12 empty] | 0
Schedule 16 | 171 | [12 empty] | 0
Schedule 16 | 172 | [12 empty] | 0
Schedule 16 | 173 | [12 empty] | 0
Schedule 16 | 173A | [9 empty] | YES |  |  | 1 | DCP 439 Introduces new Paragraph 173A
Schedule 16 | 174 | [12 empty] | 0
Schedule 16 | 175 | [12 empty] | 0
Schedule 16 | 176 | [12 empty] | 0
Schedule 16 | 177 | [12 empty] | 0
Schedule 16 | 178 | [12 empty] | 0
Schedule 16 | 179 | [12 empty] | 0
Schedule 16 | 180 | [12 empty] | 0
Schedule 16 | 181 | [12 empty] | 0
Schedule 16 | 182 | [12 empty] | 0
Schedule 16 | 183 | [12 empty] | 0
Schedule 16 | 184 | [12 empty] | 0
Schedule 16 | Glossary | YES | [11 empty] | 1
0
Schedule 17 | Introduction | [12 empty] | 0
Schedule 17 | 1 | [12 empty] | 0
Schedule 17 | 1.1 | [12 empty] | 0
Schedule 17 | 1.2 | [12 empty] | 0
Schedule 17 | 1.3 | [12 empty] | 0 | Model reference number and date
Schedule 17 | 1.3A | [12 empty] | 0
Schedule 17 | 1.4 | [12 empty] | 0
Schedule 17 | 1.5 | [12 empty] | 0
Schedule 17 | 1.6 | [12 empty] | 0
Schedule 17 | 1.7 | [12 empty] | 0
Schedule 17 | 1.8 | [12 empty] | 0
Schedule 17 | 1.9 | [12 empty] | 0
Schedule 17 | 2 | [12 empty] | 0
Schedule 17 | 2.1 | [12 empty] | 0
Schedule 17 | 2.2 | [12 empty] | 0
Schedule 17 | 2.3 | [12 empty] | 0
Schedule 17 | 2.4 | [12 empty] | 0
Schedule 17 | 2.5 | [12 empty] | 0
Schedule 17 | 2.6 | [12 empty] | 0
Schedule 17 | 2.7 | [12 empty] | 0
Schedule 17 | 2.8 | [12 empty] | 0
Schedule 17 | 2.9 | [12 empty] | 0
Schedule 17 | 2.1 | [12 empty] | 0
Schedule 17 | 2.11 | [12 empty] | 0
Schedule 17 | 2.12 | [12 empty] | 0
Schedule 17 | 2.13 | [12 empty] | 0
Schedule 17 | 2.14 | [12 empty] | 0
Schedule 17 | 2.15 | [12 empty] | 0
Schedule 17 | 2.16 | [8 empty] | YES |  |  |  | 1
Schedule 17 | 2.17 | [12 empty] | 0
Schedule 17 | 2.18 | [12 empty] | 0
Schedule 17 | 2.19 | [12 empty] | 0
Schedule 17 | 3 | [12 empty] | 0
Schedule 17 | 3.1 | [12 empty] | 0
Schedule 17 | 3.2 | [12 empty] | 0
Schedule 17 | 3.3 | [12 empty] | 0
Schedule 17 | 3.4 | [12 empty] | 0
Schedule 17 | 3.5 | [12 empty] | 0
Schedule 17 | 3.6 | [12 empty] | 0
Schedule 17 | 3.7 | [12 empty] | 0
Schedule 17 | 4 | [12 empty] | 0
Schedule 17 | 4.1 | [12 empty] | 0
Schedule 17 | 5 | [12 empty] | 0
Schedule 17 | 5.1 | [12 empty] | 0
Schedule 17 | 6 | [12 empty] | 0
Schedule 17 | 6.1 | [12 empty] | 0
Schedule 17 | 6.2 | [12 empty] | 0
Schedule 17 | 6.3 | [12 empty] | 0
Schedule 17 | 7 | [12 empty] | 0
Schedule 17 | 7.1 | [12 empty] | 0
Schedule 17 | 8 | [12 empty] | 0
Schedule 17 | 8.1 | [12 empty] | 0
Schedule 17 | 8.2 | [12 empty] | 0
Schedule 17 | 8.3 | [12 empty] | 0
Schedule 17 | 8.4 | [12 empty] | 0
Schedule 17 | 9 | [12 empty] | 0
Schedule 17 | 9.1 | [12 empty] | 0
Schedule 17 | 9.2 | [12 empty] | 0
Schedule 17 | 9.3 | [12 empty] | 0
Schedule 17 | 10 | [12 empty] | 0
Schedule 17 | 10.1 | [12 empty] | 0
Schedule 17 | 10.2 | [12 empty] | 0
Schedule 17 | 10.3 | [12 empty] | 0
Schedule 17 | 10.4 | [12 empty] | 0
Schedule 17 | 11 | [12 empty] | 0
Schedule 17 | 11.1 | [12 empty] | 0
Schedule 17 | 12 | [12 empty] | 0
Schedule 17 | 12.1 | [12 empty] | 0
Schedule 17 | 12.2 | [12 empty] | 0
Schedule 17 | 12.3 | [12 empty] | 0
Schedule 17 | 13 | [12 empty] | 0
Schedule 17 | 13.1 | [12 empty] | 0
Schedule 17 | 13.2 | [12 empty] | 0
Schedule 17 | 13.3 | [12 empty] | 0
Schedule 17 | 13.4 | [12 empty] | 0
Schedule 17 | 14 | [12 empty] | 0
Schedule 17 | 14.1 | [12 empty] | 0
Schedule 17 | 14.2 | [12 empty] | 0
Schedule 17 | 14.3 | [12 empty] | 0
Schedule 17 | 14.4 | [12 empty] | 0
Schedule 17 | 14.5 | [12 empty] | 0
Schedule 17 | 15 | [12 empty] | 0
Schedule 17 | 15.1 | [12 empty] | 0
Schedule 17 | 15.2 | [12 empty] | 0
Schedule 17 | 15.3 | [12 empty] | 0
Schedule 17 | 15.4 | [12 empty] | 0
Schedule 17 | 15.5 | [12 empty] | 0
Schedule 17 | 15.6 | [12 empty] | 0
Schedule 17 | 15.7 | [12 empty] | 0
Schedule 17 | 15.8 | [12 empty] | 0
Schedule 17 | 15.9 | [12 empty] | 0
Schedule 17 | 15.1 | [12 empty] | 0
Schedule 17 | 15.11 | [12 empty] | 0
Schedule 17 | 15.12 | [12 empty] | 0
Schedule 17 | 15.15 | [12 empty] | 0
Schedule 17 | 16 | [12 empty] | 0
Schedule 17 | 16.1 | [12 empty] | 0
Schedule 17 | 16.2 | [12 empty] | 0
Schedule 17 | 16.3 | [12 empty] | 0
Schedule 17 | 16.4 | [12 empty] | 0
Schedule 17 | 16.5 | [12 empty] | 0
Schedule 17 | 16.6 | [12 empty] | 0
Schedule 17 | 16.7 | [12 empty] | 0
Schedule 17 | 16.8 | [12 empty] | 0
Schedule 17 | 16.9 | [12 empty] | 0
Schedule 17 | 16.1 | [12 empty] | 0
Schedule 17 | 17 | [12 empty] | 0
Schedule 17 | 17.1 | [12 empty] | 0
Schedule 17 | 17.2 | [12 empty] | 0
Schedule 17 | 17.3 | [12 empty] | 0
Schedule 17 | 18 | [12 empty] | 0
Schedule 17 | 18.1 | [12 empty] | 0
Schedule 17 | 18.2 | [12 empty] | 0
Schedule 17 | 18.3 | [12 empty] | 0
Schedule 17 | 18.4 | [12 empty] | 0
Schedule 17 | 18.5 | [12 empty] | 0
Schedule 17 | 18.6 | [12 empty] | 0
Schedule 17 | 18.7 | [12 empty] | 0
Schedule 17 | 18.8 | [12 empty] | 0
Schedule 17 | 18.9 | [12 empty] | 0
Schedule 17 | 18.1 | [12 empty] | 0
Schedule 17 | 18.11 | [12 empty] | 0
Schedule 17 | 18.12 | [12 empty] | 0
Schedule 17 | 18.13 | [12 empty] | 0
Schedule 17 | 18.14 | [12 empty] | 0
Schedule 17 | 18.15 | [12 empty] | 0
Schedule 17 | 18.16 | [12 empty] | 0
Schedule 17 | 18.17 | [12 empty] | 0
Schedule 17 | 18.18 | [12 empty] | 0
Schedule 17 | 18.19 | [12 empty] | 0
Schedule 17 | 18.2 | [12 empty] | 0
Schedule 17 | 18.21 | [12 empty] | 0
Schedule 17 | 19 | [12 empty] | 0
Schedule 17 | 19.1 | [12 empty] | 0
Schedule 17 | 19.2 | [12 empty] | 0
Schedule 17 | 19.3 | [12 empty] | 0
Schedule 17 | 19.4 | [12 empty] | 0
Schedule 17 | 19.5 | [12 empty] | 0
Schedule 17 | 19.6 | [12 empty] | 0
Schedule 17 | 19.7 | [12 empty] | 0
Schedule 17 | 19.8 | [12 empty] | 0
Schedule 17 | 19.9 | [12 empty] | 0
Schedule 17 | 19.1 | [12 empty] | 0
Schedule 17 | 19.11 | [12 empty] | 0
Schedule 17 | 20 | [12 empty] | 0
Schedule 17 | 20.1 | [12 empty] | 0
Schedule 17 | 20.2 | [12 empty] | 0
Schedule 17 | 20.3 | [12 empty] | 0
Schedule 17 | 20.4 | [12 empty] | 0
Schedule 17 | 20.5 | [12 empty] | 0
Schedule 17 | 20.6 | [11 empty] | YES | 1
Schedule 17 | 20.7 | [11 empty] | YES | 1
Schedule 17 | 20.8 | [12 empty] | 0
Schedule 17 | 20.9 | [11 empty] | YES | 1
Schedule 17 | 21 | [12 empty] | 0
Schedule 17 | 21.1 | [12 empty] | 0
Schedule 17 | 21.2 | [12 empty] | 0
Schedule 17 | 22 | [12 empty] | 0
Schedule 17 | 22.1 | [12 empty] | 0
Schedule 17 | 22.2 | [12 empty] | 0
Schedule 17 | 22.3 | [12 empty] | 0
Schedule 17 | 22.4 | [12 empty] | 0
Schedule 17 | 23 | [12 empty] | 0
Schedule 17 | 23.1 | [12 empty] | 0
Schedule 17 | 23.2 | [12 empty] | 0
Schedule 17 | 23.3 | [12 empty] | 0
Schedule 17 | 23.4 | [12 empty] | 0
Schedule 17 | 23.5 | [12 empty] | 0
Schedule 17 | 24 | [12 empty] | 0
Schedule 17 | 24.1 | [12 empty] | 0
Schedule 17 | 24.2 | [12 empty] | 0
Schedule 17 | 24.3 | [12 empty] | 0
Schedule 17 | 24.4 | [12 empty] | 0
Schedule 17 | 24.5 | [12 empty] | 0
Schedule 17 | 24.6 | [12 empty] | 0
Schedule 17 | 24.7 | [12 empty] | 0
Schedule 17 | 24.8 | [12 empty] | 0
Schedule 17 | 24.9 | [12 empty] | 0
Schedule 17 | 25 | [12 empty] | 0
Schedule 17 | 25.1 | [12 empty] | 0
Schedule 17 | 25.2 | [12 empty] | 0
Schedule 17 | 25.3 | [12 empty] | 0
Schedule 17 | 25.4 | [12 empty] | 0
Schedule 17 | 25.5 | [12 empty] | 0
Schedule 17 | 25.6 | [12 empty] | 0
Schedule 17 | 25.7 | [12 empty] | 0
Schedule 17 | 25.8 | [12 empty] | 0
Schedule 17 | 25.9 | [12 empty] | 0
Schedule 17 | 25.1 | [12 empty] | 0
Schedule 17 | 25.11 | [12 empty] | 0
Schedule 17 | 25.12 | [12 empty] | 0
Schedule 17 | 25.13 | [12 empty] | 0
Schedule 17 | 25.14 | [12 empty] | 0
Schedule 17 | 25.15 | [12 empty] | 0
Schedule 17 | 25.16 | [12 empty] | 0
Schedule 17 | 25.17 | [12 empty] | 0
Schedule 17 | 25.18 | [12 empty] | 0
Schedule 17 | 25.19 | [12 empty] | 0
Schedule 17 | 26 | [12 empty] | 0
Schedule 17 | 26.1 | [12 empty] | 0
Schedule 17 | 26.2 | [12 empty] | 0
Schedule 17 | 26.3 | [12 empty] | 0
Schedule 17 | 26.4 | [12 empty] | 0
Schedule 17 | 26.5 | [12 empty] | 0
Schedule 17 | 26.6 | [12 empty] | 0
Schedule 17 | 26.7 | [12 empty] | 0
Schedule 17 | 26.8 | [12 empty] | 0
Schedule 17 | 26.9 | [12 empty] | 0
Schedule 17 | 26.1 | [12 empty] | 0
Schedule 17 | 26.11 | [12 empty] | 0
Schedule 17 | 27 | [12 empty] | 0
Schedule 17 | 27.1 | [12 empty] | 0
Schedule 17 | 27.2 | [12 empty] | 0
Schedule 17 | 27.3 | [12 empty] | 0
Schedule 17 | 27.4 | [12 empty] | 0
Schedule 17 | 28 | [12 empty] | 0
Schedule 17 | 28.1 | [12 empty] | 0
Schedule 17 | 28.2 | [12 empty] | 0
Schedule 17 | 29 | [12 empty] | 0
Schedule 17 | 29.1 | [12 empty] | 0
Schedule 17 | 29.2 | [12 empty] | 0
Schedule 17 | 29.3 | [12 empty] | 0
Schedule 17 | 29.4 | [12 empty] | 0
Schedule 17 | 30 | [12 empty] | 0
Schedule 17 | 30.1 | [12 empty] | 0
Schedule 17 | 30.2 | [12 empty] | 0
Schedule 17 | 30.3 | [12 empty] | 0
Schedule 17 | 30.4 | [12 empty] | 0
Schedule 17 | 30.5 | [12 empty] | 0
Schedule 17 | 30.6 | [12 empty] | 0
Schedule 17 | 30.7 | [12 empty] | 0
Schedule 17 | 30.8 | [12 empty] | 0
Schedule 17 | 30.9 | [12 empty] | 0
Schedule 17 | 30.1 | [12 empty] | 0
Schedule 17 | 30.11 | [12 empty] | 0
Schedule 17 | 31 | [9 empty] | YES |  |  | 1 | DCP 439 Introduces new Paragraph 31
Schedule 17 | 31.1 | [9 empty] | YES |  |  | 1 | DCP 439 Introduces new Paragraph 31.1
Schedule 17: Annex 1 | 1 | [12 empty] | 0
Schedule 17: Annex 1 | 2 | [12 empty] | 0
Schedule 17: Annex 1 | 2.1 | [12 empty] | 0
Schedule 17: Annex 1 | 2.2 | [12 empty] | 0
Schedule 17: Annex 1 | 2.3 | [12 empty] | 0
Schedule 17: Annex 1 | 2.4 | [12 empty] | 0
Schedule 17: Annex 1 | 2.5 | [12 empty] | 0
Schedule 17: Annex 1 | 3 | [12 empty] | 0
Schedule 17: Annex 1 | Definitions | [12 empty] | 0
Schedule 17: Annex 1 | 4 | [12 empty] | 0
Schedule 17: Annex 1 | 4.1 | [12 empty] | 0
Schedule 17: Annex 1 | 4.2 | [12 empty] | 0
Schedule 17: Annex 1 | 4.3 | [12 empty] | 0
Schedule 17: Annex 1 | 4.4 | [12 empty] | 0
Schedule 17: Annex 1 | 4.5 | [12 empty] | 0
Schedule 17: Annex 1 | 4.6 | [12 empty] | 0
Schedule 17: Annex 1 | 4.7 | [12 empty] | 0
Schedule 17: Annex 1 | 4.8 | [12 empty] | 0
Schedule 17: Annex 1 | 4.9 | [12 empty] | 0
Schedule 17: Annex 1 | 4.1 | [12 empty] | 0
Schedule 17: Annex 1 | 5 | [12 empty] | 0
Schedule 17: Annex 1 | 5.1 | [12 empty] | 0
Schedule 17: Annex 1 | 5.2 | [12 empty] | 0
Schedule 17: Annex 1 | 5.3 | [12 empty] | 0
Schedule 17: Annex 1 | 5.4 | [12 empty] | 0
Schedule 17: Annex 1 | 5.5 | [12 empty] | 0
Schedule 17: Annex 1 | 5.6 | [12 empty] | 0
Schedule 17: Annex 1 | 5.7 | [12 empty] | 0
Schedule 17: Annex 1 | 5.8 | [12 empty] | 0
Schedule 17: Annex 1 | 5.9 | [12 empty] | 0
Schedule 17: Annex 1 | 5.1 | [12 empty] | 0
Schedule 17: Annex 1 | 5.11 | [12 empty] | 0
Schedule 17: Annex 1 | 5.12 | [12 empty] | 0
Schedule 17: Annex 1 | 5.13 | [12 empty] | 0
Schedule 17: Annex 1 | 5.14 | [12 empty] | 0
Schedule 17: Annex 1 | 5.15 | [12 empty] | 0
Schedule 17: Annex 1 | 5.16 | [12 empty] | 0
Schedule 17: Annex 1 | 5.17 | [12 empty] | 0
Schedule 17: Annex 1 | 5.18 | [12 empty] | 0
Schedule 17: Annex 1 | 5.19 | [12 empty] | 0
Schedule 17: Annex 1 | 5.2 | [12 empty] | 0
Schedule 17: Annex 1 | 5.21 | [12 empty] | 0
Schedule 17: Annex 1 | 5.22 | [12 empty] | 0
Schedule 17: Annex 1 | 5.23 | [12 empty] | 0
Schedule 17: Annex 1 | 5.24 | [12 empty] | 0
Schedule 17: Annex 1 | 5.25 | [12 empty] | 0
Schedule 17: Annex 1 | 5.26 | [12 empty] | 0
Schedule 17: Annex 1 | 5.27 | [12 empty] | 0
Schedule 17: Annex 1 | 5.28 | [12 empty] | 0
Schedule 17: Annex 1 | 5.29 | [12 empty] | 0
Schedule 17: Annex 1 | 5.3 | [12 empty] | 0
Schedule 17: Annex 1 | 5.31 | [12 empty] | 0
Schedule 17: Annex 1 | 5.32 | [12 empty] | 0
Schedule 17: Annex 1 | 5.33 | [12 empty] | 0
Schedule 17: Annex 1 | 5.34 | [12 empty] | 0
Schedule 17: Annex 1 | 5.35 | [12 empty] | 0
Schedule 17: Annex 1 | 5.36 | [12 empty] | 0
Schedule 17: Annex 1 | 5.37 | [12 empty] | 0
Schedule 17: Annex 1 | 5.38 | [12 empty] | 0
Schedule 17: Annex 1 | 5.39 | [12 empty] | 0
Schedule 17: Annex 1 | 5.4 | [12 empty] | 0
Schedule 17: Annex 1 | 5.41 | [12 empty] | 0
Schedule 17: Annex 1 | 5.42 | [12 empty] | 0
Schedule 17: Annex 1 | 5.43 | [12 empty] | 0
Schedule 17: Annex 1 | 5.44 | [12 empty] | 0
Schedule 17: Annex 1 | 5.45 | [12 empty] | 0
Schedule 17: Annex 1 | 6 | [12 empty] | 0
Schedule 17: Annex 1 | 6.1 | [12 empty] | 0
Schedule 17: Annex 1 | 6.2 | [12 empty] | 0
Schedule 17: Annex 1 | 6.3 | [12 empty] | 0
Schedule 17: Annex 1 | 6.4 | [12 empty] | 0
Schedule 17: Annex 1 | 6.5 | [12 empty] | 0
Schedule 17: Annex 1 | 6.6 | [12 empty] | 0
Schedule 17: Annex 1 | 6.7 | [12 empty] | 0
Schedule 17: Annex 1 | 6.8 | [12 empty] | 0
Schedule 17: Annex 1 | 7 | [12 empty] | 0
Schedule 17: Annex 1 | 7.1 | [12 empty] | 0
Schedule 17: Annex 1 | 7.2 | [12 empty] | 0
Schedule 17: Annex 1 | 7.3 | [12 empty] | 0
Schedule 17: Annex 1 | 7.4 | [12 empty] | 0
Schedule 17: Annex 1 | 7.5 | [12 empty] | 0
Schedule 17: Annex 1 | 7.6 | [12 empty] | 0
Schedule 17: Annex 1 | 7.7 | [12 empty] | 0
Schedule 17: Annex 1 | 7.8 | [12 empty] | 0
Schedule 17: Annex 1 | 8 | [12 empty] | 0
Schedule 17: Annex 1 | 8.1 | [12 empty] | 0
Schedule 17: Annex 1 | 8.2 | [12 empty] | 0
Schedule 17: Annex 1 | 8.3 | [12 empty] | 0
Schedule 17: Annex 1 | 8.4 | [12 empty] | 0
Schedule 17: Annex 1 | 9 | [12 empty] | 0
Schedule 17: Annex 1 | 9.1 | [12 empty] | 0
Schedule 17: Annex 1 | 9.2 | [8 empty] | YES |  |  |  | 1
Schedule 17: Annex 1 | 9.3 | [12 empty] | 0
Schedule 17: Annex 1 | 9.4 | [12 empty] | 0
Schedule 17: Annex 1 | 9.5 | [12 empty] | 0
Schedule 17: Annex 1 | 9.6 | [12 empty] | 0
Schedule 17: Annex 1 | 9.7 | [12 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [12 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [12 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [12 empty] | 0
Schedule 17: Annex 1 | Attachment 3 | [12 empty] | 0
Schedule 17: Annex 2 | Annex 2 | [8 empty] | YES |  |  |  | 1
0
Schedule 18 | Introduction | [12 empty] | 0
Schedule 18 | 1 | [12 empty] | 0
Schedule 18 | 1.1 | [12 empty] | 0
Schedule 18 | 1.2 | [12 empty] | 0
Schedule 18 | 1.3 | [12 empty] | 0 | Model reference number and date
Schedule 18 | 1.3A | [12 empty] | 0
Schedule 18 | 1.4 | [12 empty] | 0
Schedule 18 | 1.5 | [12 empty] | 0
Schedule 18 | 1.6 | [12 empty] | 0
Schedule 18 | 1.7 | [12 empty] | 0
Schedule 18 | 1.8 | [12 empty] | 0
Schedule 18 | 1.9 | [12 empty] | 0
Schedule 18 | 2 | [12 empty] | 0
Schedule 18 | 2.1 | [12 empty] | 0
Schedule 18 | 2.2 | [12 empty] | 0
Schedule 18 | 2.3 | [12 empty] | 0
Schedule 18 | 2.4 | [12 empty] | 0
Schedule 18 | 2.5 | [12 empty] | 0
Schedule 18 | 2.6 | [12 empty] | 0
Schedule 18 | 2.7 | [12 empty] | 0
Schedule 18 | 2.8 | [12 empty] | 0
Schedule 18 | 2.9 | [8 empty] | YES |  |  |  | 1
Schedule 18 | 2.1 | [12 empty] | 0
Schedule 18 | 2.11 | [12 empty] | 0
Schedule 18 | 2.12 | [12 empty] | 0
Schedule 18 | 2.13 | [12 empty] | 0
Schedule 18 | 2.14 | [12 empty] | 0
Schedule 18 | 2.15 | [12 empty] | 0
Schedule 18 | 2.16 | [12 empty] | 0
Schedule 18 | 2.17 | [12 empty] | 0
Schedule 18 | 2.18 | [12 empty] | 0
Schedule 18 | 2.19 | [12 empty] | 0
Schedule 18 | 2.2 | [12 empty] | 0
Schedule 18 | 2.21 | [12 empty] | 0
Schedule 18 | 2.22 | [12 empty] | 0
Schedule 18 | 2.23 | [12 empty] | 0
Schedule 18 | 2.24 | [12 empty] | 0
Schedule 18 | 2.25 | [12 empty] | 0
Schedule 18 | 2.26 | [12 empty] | 0
Schedule 18 | 2.27 | [12 empty] | 0
Schedule 18 | 2.28 | [12 empty] | 0
Schedule 18 | 2.29 | [12 empty] | 0
Schedule 18 | 2.3 | [12 empty] | 0
Schedule 18 | 3 | [12 empty] | 0
Schedule 18 | 3.1 | [12 empty] | 0
Schedule 18 | 3.2 | [12 empty] | 0
Schedule 18 | 3.3 | [12 empty] | 0
Schedule 18 | 3.4 | [12 empty] | 0
Schedule 18 | 3.5 | [12 empty] | 0
Schedule 18 | 3.6 | [12 empty] | 0
Schedule 18 | 3.7 | [12 empty] | 0
Schedule 18 | 4 | [12 empty] | 0
Schedule 18 | 4.1 | [12 empty] | 0
Schedule 18 | 5 | [12 empty] | 0
Schedule 18 | 5.1 | [12 empty] | 0
Schedule 18 | 6 | [12 empty] | 0
Schedule 18 | 6.1 | [12 empty] | 0
Schedule 18 | 6.2 | [12 empty] | 0
Schedule 18 | 6.3 | [12 empty] | 0
Schedule 18 | 6.4 | [12 empty] | 0
Schedule 18 | 6.5 | [12 empty] | 0
Schedule 18 | 7 | [12 empty] | 0
Schedule 18 | 7.1 | [12 empty] | 0
Schedule 18 | 8 | [12 empty] | 0
Schedule 18 | 8.1 | [12 empty] | 0
Schedule 18 | 8.2 | [12 empty] | 0
Schedule 18 | 8.3 | [12 empty] | 0
Schedule 18 | 8.4 | [12 empty] | 0
Schedule 18 | 9 | [12 empty] | 0
Schedule 18 | 9.1 | [12 empty] | 0
Schedule 18 | 9.2 | [12 empty] | 0
Schedule 18 | 10 | [12 empty] | 0
Schedule 18 | 10.1 | [12 empty] | 0
Schedule 18 | 10.2 | [12 empty] | 0
Schedule 18 | 10.3 | [12 empty] | 0
Schedule 18 | 10.4 | [12 empty] | 0
Schedule 18 | 10.5 | [12 empty] | 0
Schedule 18 | 11 | [12 empty] | 0
Schedule 18 | 11.1 | [12 empty] | 0
Schedule 18 | 12 | [12 empty] | 0
Schedule 18 | 12.1 | [12 empty] | 0
Schedule 18 | 12.2 | [12 empty] | 0
Schedule 18 | 12.3 | [12 empty] | 0
Schedule 18 | 12.4 | [12 empty] | 0
Schedule 18 | 12.5 | [12 empty] | 0
Schedule 18 | 12.6 | [12 empty] | 0
Schedule 18 | 13 | [12 empty] | 0
Schedule 18 | 13.1 | [12 empty] | 0
Schedule 18 | 13.2 | [12 empty] | 0
Schedule 18 | 13.3 | [12 empty] | 0
Schedule 18 | 13.4 | [12 empty] | 0
Schedule 18 | 14 | [12 empty] | 0
Schedule 18 | 14.1 | [12 empty] | 0
Schedule 18 | 14.2 | [12 empty] | 0
Schedule 18 | 14.3 | [12 empty] | 0
Schedule 18 | 14.4 | [12 empty] | 0
Schedule 18 | 14.5 | [12 empty] | 0
Schedule 18 | 15 | [12 empty] | 0
Schedule 18 | 15.1 | [12 empty] | 0
Schedule 18 | 15.2 | [12 empty] | 0
Schedule 18 | 15.3 | [12 empty] | 0
Schedule 18 | 15.4 | [12 empty] | 0
Schedule 18 | 15.5 | [12 empty] | 0
Schedule 18 | 15.6 | [12 empty] | 0
Schedule 18 | 15.7 | [12 empty] | 0
Schedule 18 | 15.8 | [12 empty] | 0
Schedule 18 | 15.9 | [12 empty] | 0
Schedule 18 | 15.1 | [12 empty] | 0
Schedule 18 | 15.11 | [12 empty] | 0
Schedule 18 | 15.12 | [12 empty] | 0
Schedule 18 | 15.15 | [12 empty] | 0
Schedule 18 | 16 | [12 empty] | 0
Schedule 18 | 16.1 | [12 empty] | 0
Schedule 18 | 16.2 | [12 empty] | 0
Schedule 18 | 16.3 | [12 empty] | 0
Schedule 18 | 16.4 | [12 empty] | 0
Schedule 18 | 16.5 | [12 empty] | 0
Schedule 18 | 16.6 | [12 empty] | 0
Schedule 18 | 16.7 | [12 empty] | 0
Schedule 18 | 16.8 | [12 empty] | 0
Schedule 18 | 16.9 | [12 empty] | 0
Schedule 18 | 16.1 | [12 empty] | 0
Schedule 18 | 17 | [12 empty] | 0
Schedule 18 | 17.1 | [12 empty] | 0
Schedule 18 | 17.2 | [12 empty] | 0
Schedule 18 | 17.3 | [12 empty] | 0
Schedule 18 | 18 | [12 empty] | 0
Schedule 18 | 18.1 | [12 empty] | 0
Schedule 18 | 18.2 | [12 empty] | 0
Schedule 18 | 18.3 | [12 empty] | 0
Schedule 18 | 18.4 | [12 empty] | 0
Schedule 18 | 18.5 | [12 empty] | 0
Schedule 18 | 18.6 | [12 empty] | 0
Schedule 18 | 18.7 | [12 empty] | 0
Schedule 18 | 18.8 | [12 empty] | 0
Schedule 18 | 18.9 | [12 empty] | 0
Schedule 18 | 18.1 | [12 empty] | 0
Schedule 18 | 18.11 | [12 empty] | 0
Schedule 18 | 18.12 | [12 empty] | 0
Schedule 18 | 18.13 | [12 empty] | 0
Schedule 18 | 18.14 | [12 empty] | 0
Schedule 18 | 18.15 | [12 empty] | 0
Schedule 18 | 18.16 | [12 empty] | 0
Schedule 18 | 18.17 | [12 empty] | 0
Schedule 18 | 18.18 | [12 empty] | 0
Schedule 18 | 18.19 | [12 empty] | 0
Schedule 18 | 18.2 | [12 empty] | 0
Schedule 18 | 18.21 | [12 empty] | 0
Schedule 18 | 19 | [12 empty] | 0
Schedule 18 | 19.1 | [12 empty] | 0
Schedule 18 | 19.2 | [12 empty] | 0
Schedule 18 | 19.3 | [12 empty] | 0
Schedule 18 | 19.4 | [12 empty] | 0
Schedule 18 | 19.5 | [12 empty] | 0
Schedule 18 | 19.6 | [12 empty] | 0
Schedule 18 | 19.7 | [12 empty] | 0
Schedule 18 | 19.8 | [12 empty] | 0
Schedule 18 | 19.9 | [12 empty] | 0
Schedule 18 | 19.1 | [12 empty] | 0
Schedule 18 | 19.11 | [12 empty] | 0
Schedule 18 | 20 | [12 empty] | 0
Schedule 18 | 20.1 | [12 empty] | 0
Schedule 18 | 20.2 | [12 empty] | 0
Schedule 18 | 20.3 | [12 empty] | 0
Schedule 18 | 20.4 | [12 empty] | 0
Schedule 18 | 20.5 | [12 empty] | 0
Schedule 18 | 20.6 | [11 empty] | YES | 1
Schedule 18 | 20.7 | [11 empty] | YES | 1
Schedule 18 | 20.8 | [12 empty] | 0
Schedule 18 | 20.9 | [11 empty] | YES | 1
Schedule 18 | 21 | [12 empty] | 0
Schedule 18 | 21.1 | [12 empty] | 0
Schedule 18 | 21.2 | [12 empty] | 0
Schedule 18 | 22 | [12 empty] | 0
Schedule 18 | 22.1 | [12 empty] | 0
Schedule 18 | 22.2 | [12 empty] | 0
Schedule 18 | 22.3 | [12 empty] | 0
Schedule 18 | 22.4 | [12 empty] | 0
Schedule 18 | 23 | [12 empty] | 0
Schedule 18 | 23.1 | [12 empty] | 0
Schedule 18 | 23.2 | [12 empty] | 0
Schedule 18 | 23.3 | [12 empty] | 0
Schedule 18 | 23.4 | [12 empty] | 0
Schedule 18 | 23.5 | [12 empty] | 0
Schedule 18 | 24 | [12 empty] | 0
Schedule 18 | 24.1 | [12 empty] | 0
Schedule 18 | 24.2 | [12 empty] | 0
Schedule 18 | 24.3 | [12 empty] | 0
Schedule 18 | 24.4 | [12 empty] | 0
Schedule 18 | 24.5 | [12 empty] | 0
Schedule 18 | 24.6 | [12 empty] | 0
Schedule 18 | 24.7 | [12 empty] | 0
Schedule 18 | 24.8 | [12 empty] | 0
Schedule 18 | 24.9 | [12 empty] | 0
Schedule 18 | 25 | [12 empty] | 0
Schedule 18 | 25.1 | [12 empty] | 0
Schedule 18 | 25.2 | [12 empty] | 0
Schedule 18 | 25.3 | [12 empty] | 0
Schedule 18 | 25.4 | [12 empty] | 0
Schedule 18 | 25.5 | [12 empty] | 0
Schedule 18 | 25.6 | [12 empty] | 0
Schedule 18 | 25.7 | [12 empty] | 0
Schedule 18 | 25.8 | [12 empty] | 0
Schedule 18 | 25.9 | [12 empty] | 0
Schedule 18 | 25.1 | [12 empty] | 0
Schedule 18 | 25.11 | [12 empty] | 0
Schedule 18 | 25.12 | [12 empty] | 0
Schedule 18 | 25.13 | [12 empty] | 0
Schedule 18 | 25.14 | [12 empty] | 0
Schedule 18 | 25.15 | [12 empty] | 0
Schedule 18 | 25.16 | [12 empty] | 0
Schedule 18 | 25.17 | [12 empty] | 0
Schedule 18 | 25.18 | [12 empty] | 0
Schedule 18 | 25.19 | [12 empty] | 0
Schedule 18 | 26 | [12 empty] | 0
Schedule 18 | 26.1 | [12 empty] | 0
Schedule 18 | 26.2 | [12 empty] | 0
Schedule 18 | 26.3 | [12 empty] | 0
Schedule 18 | 26.4 | [12 empty] | 0
Schedule 18 | 26.5 | [12 empty] | 0
Schedule 18 | 26.6 | [12 empty] | 0
Schedule 18 | 26.7 | [12 empty] | 0
Schedule 18 | 26.8 | [12 empty] | 0
Schedule 18 | 26.9 | [12 empty] | 0
Schedule 18 | 26.1 | [12 empty] | 0
Schedule 18 | 26.11 | [12 empty] | 0
Schedule 18 | 27 | [12 empty] | 0
Schedule 18 | 27.1 | [12 empty] | 0
Schedule 18 | 27.2 | [12 empty] | 0
Schedule 18 | 27.3 | [12 empty] | 0
Schedule 18 | 27.4 | [12 empty] | 0
Schedule 18 | 28 | [12 empty] | 0
Schedule 18 | 28.1 | [12 empty] | 0
Schedule 18 | 28.2 | [12 empty] | 0
Schedule 18 | 29 | [12 empty] | 0
Schedule 18 | 29.1 | [12 empty] | 0
Schedule 18 | 29.2 | [12 empty] | 0
Schedule 18 | 29.3 | [12 empty] | 0
Schedule 18 | 29.4 | [12 empty] | 0
Schedule 18 | 30 | [12 empty] | 0
Schedule 18 | 30.1 | [12 empty] | 0
Schedule 18 | 30.2 | [12 empty] | 0
Schedule 18 | 30.3 | [12 empty] | 0
Schedule 18 | 30.4 | [12 empty] | 0
Schedule 18 | 30.5 | [12 empty] | 0
Schedule 18 | 30.6 | [12 empty] | 0
Schedule 18 | 30.7 | [12 empty] | 0
Schedule 18 | 30.8 | [12 empty] | 0
Schedule 18 | 30.9 | [12 empty] | 0
Schedule 18 | 30.1 | [12 empty] | 0
Schedule 18 | 30.11 | [12 empty] | 0
Schedule 18 | 31 | [12 empty] | 0 | DCP 439 Introduces new Paragraph 31
Schedule 18 | 31.1 | [12 empty] | 0 | DCP 439 Introduces new Paragraph 31.1
Schedule 18: Annex 1 | 1 | [12 empty] | 0
Schedule 18: Annex 1 | 1.1 | [12 empty] | 0
Schedule 18: Annex 1 | 2 | [12 empty] | 0
Schedule 18: Annex 1 | 2.1 | [12 empty] | 0
Schedule 18: Annex 1 | 2.2 | [12 empty] | 0
Schedule 18: Annex 1 | 2.3 | [12 empty] | 0
Schedule 18: Annex 1 | 2.4 | [12 empty] | 0
Schedule 18: Annex 1 | 2.5 | [12 empty] | 0
Schedule 18: Annex 1 | 3 | [12 empty] | 0
Schedule 18: Annex 1 | Definitions | [12 empty] | 0
Schedule 18: Annex 1 | 4 | [12 empty] | 0
Schedule 18: Annex 1 | 4.1 | [12 empty] | 0
Schedule 18: Annex 1 | 4.2 | [12 empty] | 0
Schedule 18: Annex 1 | 4.3 | [12 empty] | 0
Schedule 18: Annex 1 | 4.4 | [12 empty] | 0
Schedule 18: Annex 1 | 4.5 | [12 empty] | 0
Schedule 18: Annex 1 | 4.6 | [12 empty] | 0
Schedule 18: Annex 1 | 4.7 | [12 empty] | 0
Schedule 18: Annex 1 | 4.8 | [12 empty] | 0
Schedule 18: Annex 1 | 4.9 | [12 empty] | 0
Schedule 18: Annex 1 | 5 | [12 empty] | 0
Schedule 18: Annex 1 | 5.1 | [12 empty] | 0
Schedule 18: Annex 1 | 5.2 | [12 empty] | 0
Schedule 18: Annex 1 | 5.3 | [12 empty] | 0
Schedule 18: Annex 1 | 5.4 | [12 empty] | 0
Schedule 18: Annex 1 | 5.5 | [12 empty] | 0
Schedule 18: Annex 1 | 5.6 | [12 empty] | 0
Schedule 18: Annex 1 | 5.7 | [12 empty] | 0
Schedule 18: Annex 1 | 5.8 | [12 empty] | 0
Schedule 18: Annex 1 | 5.9 | [12 empty] | 0
Schedule 18: Annex 1 | 5.1 | [12 empty] | 0
Schedule 18: Annex 1 | 5.11 | [12 empty] | 0
Schedule 18: Annex 1 | 5.12 | [12 empty] | 0
Schedule 18: Annex 1 | 5.13 | [12 empty] | 0
Schedule 18: Annex 1 | 5.14 | [12 empty] | 0
Schedule 18: Annex 1 | 5.15 | [12 empty] | 0
Schedule 18: Annex 1 | 5.16 | [12 empty] | 0
Schedule 18: Annex 1 | 5.17 | [12 empty] | 0
Schedule 18: Annex 1 | 5.18 | [12 empty] | 0
Schedule 18: Annex 1 | 5.19 | [12 empty] | 0
Schedule 18: Annex 1 | 5.2 | [12 empty] | 0
Schedule 18: Annex 1 | 5.21 | [12 empty] | 0
Schedule 18: Annex 1 | 5.22 | [12 empty] | 0
Schedule 18: Annex 1 | 5.23 | [12 empty] | 0
Schedule 18: Annex 1 | 5.24 | [12 empty] | 0
Schedule 18: Annex 1 | 5.25 | [12 empty] | 0
Schedule 18: Annex 1 | 5.26 | [12 empty] | 0
Schedule 18: Annex 1 | 5.27 | [12 empty] | 0
Schedule 18: Annex 1 | 5.28 | [12 empty] | 0
Schedule 18: Annex 1 | 5.29 | [12 empty] | 0
Schedule 18: Annex 1 | 5.3 | [12 empty] | 0
Schedule 18: Annex 1 | 5.31 | [12 empty] | 0
Schedule 18: Annex 1 | 5.32 | [12 empty] | 0
Schedule 18: Annex 1 | 5.33 | [12 empty] | 0
Schedule 18: Annex 1 | 5.34 | [12 empty] | 0
Schedule 18: Annex 1 | 5.35 | [12 empty] | 0
Schedule 18: Annex 1 | 5.36 | [12 empty] | 0
Schedule 18: Annex 1 | 5.37 | [12 empty] | 0
Schedule 18: Annex 1 | 5.38 | [12 empty] | 0
Schedule 18: Annex 1 | 5.39 | [12 empty] | 0
Schedule 18: Annex 1 | 5.4 | [12 empty] | 0
Schedule 18: Annex 1 | 5.41 | [12 empty] | 0
Schedule 18: Annex 1 | 5.42 | [12 empty] | 0
Schedule 18: Annex 1 | 6 | [12 empty] | 0
Schedule 18: Annex 1 | 6.1 | [12 empty] | 0
Schedule 18: Annex 1 | 6.2 | [12 empty] | 0
Schedule 18: Annex 1 | 6.3 | [12 empty] | 0
Schedule 18: Annex 1 | 6.4 | [12 empty] | 0
Schedule 18: Annex 1 | 6.5 | [12 empty] | 0
Schedule 18: Annex 1 | 6.6 | [12 empty] | 0
Schedule 18: Annex 1 | 6.7 | [12 empty] | 0
Schedule 18: Annex 1 | 6.8 | [12 empty] | 0
Schedule 18: Annex 1 | 6.9 | [12 empty] | 0
Schedule 18: Annex 1 | 6.1 | [12 empty] | 0
Schedule 18: Annex 1 | 6.11 | [12 empty] | 0
Schedule 18: Annex 1 | 6.12 | [12 empty] | 0
Schedule 18: Annex 1 | 6.13 | [12 empty] | 0
Schedule 18: Annex 1 | 6.14 | [12 empty] | 0
Schedule 18: Annex 1 | 6.15 | [12 empty] | 0
Schedule 18: Annex 1 | 6.16 | [12 empty] | 0
Schedule 18: Annex 1 | 6.17 | [12 empty] | 0
Schedule 18: Annex 1 | 6.18 | [12 empty] | 0
Schedule 18: Annex 1 | 6.19 | [12 empty] | 0
Schedule 18: Annex 1 | 6.2 | [12 empty] | 0
Schedule 18: Annex 1 | 6.21 | [12 empty] | 0
Schedule 18: Annex 1 | 6.22 | [12 empty] | 0
Schedule 18: Annex 1 | 6.23 | [12 empty] | 0
Schedule 18: Annex 1 | 6.24 | [12 empty] | 0
Schedule 18: Annex 1 | 6.25 | [12 empty] | 0
Schedule 18: Annex 1 | 6.26 | [12 empty] | 0
Schedule 18: Annex 1 | 6.27 | [12 empty] | 0
Schedule 18: Annex 1 | 6.28 | [12 empty] | 0
Schedule 18: Annex 1 | 6.29 | [12 empty] | 0
Schedule 18: Annex 1 | 6.3 | [12 empty] | 0
Schedule 18: Annex 1 | 6.31 | [12 empty] | 0
Schedule 18: Annex 1 | 6.32 | [12 empty] | 0
Schedule 18: Annex 1 | 6.33 | [12 empty] | 0
Schedule 18: Annex 1 | 6.34 | [12 empty] | 0
Schedule 18: Annex 1 | 7 | [12 empty] | 0
Schedule 18: Annex 1 | 7.1 | [12 empty] | 0
Schedule 18: Annex 1 | 7.2 | [12 empty] | 0
Schedule 18: Annex 1 | 7.3 | [12 empty] | 0
Schedule 18: Annex 1 | 7.4 | [12 empty] | 0
Schedule 18: Annex 1 | 7.5 | [12 empty] | 0
Schedule 18: Annex 1 | 8 | [12 empty] | 0
Schedule 18: Annex 1 | 8.1 | [12 empty] | 0
Schedule 18: Annex 1 | 8.2 | [12 empty] | 0
Schedule 18: Annex 1 | 8.3 | [12 empty] | 0
Schedule 18: Annex 1 | 8.4 | [12 empty] | 0
Schedule 18: Annex 1 | 8.5 | [12 empty] | 0
Schedule 18: Annex 1 | 8.6 | [12 empty] | 0
Schedule 18: Annex 1 | 8.7 | [12 empty] | 0
Schedule 18: Annex 1 | 8.8 | [12 empty] | 0
Schedule 18: Annex 1 | 8.9 | [12 empty] | 0
Schedule 18: Annex 1 | 8.1 | [12 empty] | 0
Schedule 18: Annex 1 | 8.11 | [12 empty] | 0
Schedule 18: Annex 1 | 8.12 | [12 empty] | 0
Schedule 18: Annex 1 | 8.13 | [12 empty] | 0
Schedule 18: Annex 1 | 8.14 | [12 empty] | 0
Schedule 18: Annex 1 | 8.15 | [12 empty] | 0
Schedule 18: Annex 1 | 8.16 | [12 empty] | 0
Schedule 18: Annex 1 | 8.17 | [12 empty] | 0
Schedule 18: Annex 1 | 8.18 | [12 empty] | 0
Schedule 18: Annex 1 | 8.19 | [12 empty] | 0
Schedule 18: Annex 1 | 8.2 | [12 empty] | 0
Schedule 18: Annex 1 | 8.21 | [12 empty] | 0
Schedule 18: Annex 1 | Attachment 1 | [8 empty] | YES |  |  |  | 1
Schedule 18: Annex 1 | Attachment 2 | [12 empty] | 0
Schedule 18: Annex 1 | Attachment 3 | [12 empty] | 0
Schedule 18: Annex 2 | Annex 2 | [12 empty] | 0
0
Schedule 20 | Introduction |  |  | YES | [9 empty] | 1
Schedule 20 | 1.1 |  |  | YES | [9 empty] | 1
Schedule 20 | 2.1 |  |  | YES | [9 empty] | 1
Schedule 20 | 3.1 |  |  | YES | [9 empty] | 1
Schedule 20 | 3.2 |  |  | YES | [9 empty] | 1
0
Schedule 29 | Introduction | [12 empty] | 0
Schedule 29 | 1 | [12 empty] | 0
Schedule 29 | 1A | [12 empty] | 0
Schedule 29 | 2 | [12 empty] | 0
Schedule 29 | 3 | [12 empty] | 0
Schedule 29 | 4 | [12 empty] | 0
Schedule 29 | 5 | [12 empty] | 0
Schedule 29 | 6 | [12 empty] | 0
Schedule 29 | 7 | [12 empty] | 0
Schedule 29 | 8 | [12 empty] | 0
Schedule 29 | 9 | [12 empty] | 0
Schedule 29 | 10 | [12 empty] | 0
Schedule 29 | 11 | [12 empty] | 0
Schedule 29 | 11A | [12 empty] | 0
Schedule 29 | 12 | [12 empty] | 0
Schedule 29 | 13 | [12 empty] | 0
Schedule 29 | 14 | [12 empty] | 0
Schedule 29 | 15 | [12 empty] | 0
Schedule 29 | 16 | [12 empty] | 0
Schedule 29 | 17 | [12 empty] | 0
Schedule 29 | 18 | [12 empty] | 0
Schedule 29 | 19 | [12 empty] | 0
Schedule 29 | 20 | [12 empty] | 0
Schedule 29 | 21 | [12 empty] | 0
Schedule 29 | 22 | [12 empty] | 0
Schedule 29 | 23 | [12 empty] | 0
Schedule 29 | 24 | [12 empty] | 0
Schedule 29 | 25 | [12 empty] | 0
Schedule 29 | 26 | [12 empty] | 0
Schedule 29 | 27 | [12 empty] | 0
Schedule 29 | 28 | [12 empty] | 0
Schedule 29 | 29 | [12 empty] | 0
Schedule 29 | 30 | [12 empty] | 0
Schedule 29 | 31 | [12 empty] | 0
Schedule 29 | 32 | [12 empty] | 0
Schedule 29 | 33 | [12 empty] | 0
Schedule 29 | 34 | [12 empty] | 0
Schedule 29 | 35 | [12 empty] | 0
Schedule 29 | 36 | [12 empty] | 0
Schedule 29 | 37 | [12 empty] | 0
Schedule 29 | 38 | [12 empty] | 0
Schedule 29 | 39 | [12 empty] | 0
Schedule 29 | 40 | [12 empty] | 0
Schedule 29 | 41 | [12 empty] | 0
Schedule 29 | 42 | [12 empty] | 0
Schedule 29 | 43 | [12 empty] | 0
Schedule 29 | 44 | [12 empty] | 0
Schedule 29 | 45 | [12 empty] | 0
Schedule 29 | 46 | [12 empty] | 0
Schedule 29 | 46A | [12 empty] | 0
Schedule 29 | 47 | [12 empty] | 0
0
Schedule 32 | 1 | [12 empty] | 0
Schedule 32 | 1.1 | [12 empty] | 0
Schedule 32 | 1.2 | [12 empty] | 0
Schedule 32 | 1.2A | [12 empty] | 0
Schedule 32 | 1.3 | [12 empty] | 0
Schedule 32 | 1.4 | [12 empty] | 0
Schedule 32 | 1.5 | [12 empty] | 0
Schedule 32 | 1.6 | [12 empty] | 0
Schedule 32 | 1.7 | [12 empty] | 0
Schedule 32 | 1.8 |  |  |  |  | YES | [7 empty] | 1
Schedule 32 | 1.9 | [12 empty] | 0
Schedule 32 | 1.10 |  |  |  |  | YES | [7 empty] | 1
Schedule 32 | 2 | [12 empty] | 0
Schedule 32 | 2.1 | [12 empty] | 0
Schedule 32 | 2.2 | [12 empty] | 0
Schedule 32 | 2.3 | [12 empty] | 0
Schedule 32 | 2.4 | [12 empty] | 0
Schedule 32 | 2.5 | [12 empty] | 0
Schedule 32 | 3 | [12 empty] | 0
Schedule 32 | 3.1 |  |  |  |  | YES | [7 empty] | 1
Schedule 32 | 3.2 | [12 empty] | 0
Schedule 32 | 3.3 | [12 empty] | 0
Schedule 32 | 3.4 | [12 empty] | 0
Schedule 32 | 3.5 | [12 empty] | 0
Schedule 32 | 3.6 | [12 empty] | 0
Schedule 32 | 4 | [12 empty] | 0
Schedule 32 | 4.1 |  |  |  |  | YES | [7 empty] | 1
Schedule 32 | 4.2 |  |  |  |  | YES | [7 empty] | 1
Schedule 32 | 4.2A |  |  |  |  | YES | [7 empty] | 1
Schedule 32 | 4.3 | [12 empty] | 0
Schedule 32 | 4.4 | [12 empty] | 0
Schedule 32 | 4.5 |  |  |  |  | YES | [7 empty] | 1
Schedule 32 | 4.6 | [12 empty] | 0
Schedule 32 | 5 | [12 empty] | 0
Schedule 32 | 5.1 | [12 empty] | 0
Schedule 32 | 5.2 | [12 empty] | 0
Schedule 32 | 5.3 | [12 empty] | 0
Schedule 32 | 5A. |  |  |  |  | YES | [7 empty] | 1
Schedule 32 | 5A.1 | [12 empty] | 0
Schedule 32 | 5A.1A | [12 empty] | 0
Schedule 32 | 5A.2 | [12 empty] | 0
Schedule 32 | 6 | [12 empty] | 0
Schedule 32 | 6.1 | [5 empty] | YES | [6 empty] | 1
Schedule 32 | 6.2 | [5 empty] | YES | [6 empty] | 1
Schedule 32 | 6.3 |  |  |  |  | YES | [7 empty] | 1
Schedule 32 | 6.4 | [9 empty] | YES |  |  | 1
Schedule 32 | 6.4A | [12 empty] | 0
Schedule 32 | 6.5 |  |  |  |  | YES | [7 empty] | 1
Schedule 32 | 6.6 | [12 empty] | 0
Schedule 32 | 6.7 | [12 empty] | 0
Schedule 32 | 6.8 | [12 empty] | 0
Schedule 32 | 6.9 | [12 empty] | 0
Schedule 32 | 6.10 | [7 empty] | YES |  |  |  |  | 1
Schedule 32 | 6.11 | [7 empty] | YES |  | YES |  |  | 2
Schedule 32 | 6.12 | [7 empty] | YES |  |  |  |  | 1
Schedule 32 | 7 | [12 empty] | 0
Schedule 32 | 7.1 | [12 empty] | 0
Schedule 32 | 7.2 | [12 empty] | 0
Schedule 32 | 7.3 | [12 empty] | 0
Schedule 32 | 7.4 | [12 empty] | 0
Schedule 32 | 7.5 | [12 empty] | 0
Schedule 32 | 7.6 | [12 empty] | 0
Schedule 32 | 7.7 | [12 empty] | 0
Schedule 32 | 7.8 | [12 empty] | 0
Schedule 32 | 7.9 | [12 empty] | 0
Schedule 32 | 7.1 | [12 empty] | 0
Schedule 32 | 7.11 | [12 empty] | 0
Schedule 32 | 7.12 | [12 empty] | 0
Schedule 32 | 7.13 | [12 empty] | 0
Schedule 32 | 7.14 | [12 empty] | 0
Schedule 32 | 7.15 | [12 empty] | 0
Schedule 32 | 7.16 | [12 empty] | 0
Schedule 32 | 7.17 | [9 empty] | YES |  |  | 1
Schedule 32 | 8 | [12 empty] | 0
Schedule 32 | 8.1 | [12 empty] | 0
Schedule 32 | 8.2 | [12 empty] | 0
Schedule 32 | Definitions |  |  |  |  | YES | YES | [6 empty] | 2
Charging Methodology CPs Legal Text Overlap Tracker