## Summary
MHHS Programme M8 Code Change Control
Owner | MHHS Code Workstream
Purpose | A central deposit and change control for all Programme related Code change post M6 (August '24)
Input Owners | MHHS Code, Balancing Settlement Code, Retail Energy Code, Distribution and Connection Use of System Agreement
and DIP Manager
Governance Control | MHHS Cross Code Advisory Group (CCAG) and L5 Cross Code Change Control Subgroup (CCCCSG)
Publication | MHHS Code Governance Collaboration Base Page
Please note this is a live document and will continue to be regularly updated
The Date logged will display the date the line item was last updated

## Control Log
M8 Change Control Log
Change Ref | Date Logged | Input Category | Source Ref | Source Title / Release | Related Design Artefact | Subject | Description | Code owner | Code Artefact | Version | Status | Delivery Vehicle | Validated (Y/N)
M8-001 | 2024-12-09 | Programme CR | CR54 | CR054 Change to Non-Functional Requirements for LDSOs | E2E Non Functional Requirements | LDSO Non Functional design/code changes | Amend LDSO Non functional requirements for system processing volumes | DIP | DIP Rules |  | Design and Code update required | TBD
M8-002 | 2024-12-09 | DIN log | DIN-1077 | 8.2 | DES138 | Code Correction | Adding II enumeration to Settlement Code Data Item (DI-160) | BSC | EMDS | 1.2 | Code update required | PYYY
M8-003 | 2024-12-09 | DIN log | DIN-1120 | 8.3 | ERI011B | Code Correction | DI-533 Distributor Billing Email - change data type to DT-036 | DCUSA | EMDS | 1.2 | Code update required | DCPXXX
M8-004 | 2024-12-09 | DIN log | DIN-1120 | 8.3 | ERI011B | Code Correction | DI-600 Total Charge For Charge Type ex VAT - change MHHS data type to DT-025 | DCUSA | EMDS | 1.2 | Code update required | DCPXXX
M8-005 | 2024-12-09 | DIN log | DIN-1114 | 8.3 | ERI011B | Code Correction | Boolean update to true/false for the following data items: DI-021 - Customer Direct Contract Metering Service DI-022 - Customer Direct Contract Data Service DI-486 - DUoS Tariff Domestic Premise Indicator DI-567 - Misaligned Multi Mpan Site DI-837 - Supplier Proposed Domestic Indicator | BSC | EMDS | 1.2 | Code update required | PYYY
M8-006 | 12/9/2024 Soln update 27/02/25 | DIN log | DIN-1114 | 8.3 | ERI011B | Code Correction | DI-127 Metered Indicator Boolean update - this includes the removal of the association with J2252 which is set to T/F | BSC | EMDS | 1.2 | Code update required | PYYY
M8-007 | 12/9/2024 Soln update 27/02/25 | DIN log | DIN-1114 | 8.3 | ERI011B | Code Correction | DI-357 Default BM Unit Flag Boolean update - this includes the removal of the association with J1631 which is set to T/F | BSC | EMDS | 1.2 | Code update required | PYYY
M8-008 | 2024-12-09 | DIN log | DIN-1114 | 8.3 | DES138 | Code Correction | DI-030 Domestic Premise Indicator Boolean update - create new data item for DI-030 and remove link to DI90016 | REC | EMDS | 1.2 | Code update required | RXXX
M8-009 | 2024-12-09 | DIN log | DIN-1072 | 8.2 | DES138 | Code Correction | Reflecting Load Shape DPI (DI-031) is nullable | BSC | EMDS | 1.2 | Code update required | PYYY
M8-010 | 2024-12-09 | DIN log | ? | 8.3 | DES138 | Code Correction | Addition of words 'where available in Registration' against the MAP block B075 Not required as change reversed in later IR | BSC | None |  |  | Not required | N/A
M8-011 | 2024-12-09 | DIN log | DIN-1115 | 8.3 | DES138 | Code Correction | DI 988 Replay Indicator amended to no nulls / mandatory. Data item also amended to Mandatory in the DIP Common tab, group D0 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-012 | 2024-12-09 | DIN log | DIN-1117 | 8.3 | DES138 | Code Correction | Removing routing to MDS in IF-021 to save duplication | BSC | EMDS | 1.2 | Code update required | PYYY
M8-013 | 2024-12-09 | DIN log | DIN-1128 | 8.4 | DES138 | Code Correction | IF008 (REC – DIN1128) Adding an exclusion against correlation id and in the notes box to clarify the correlation id is not required where the SMRS auto de-energises | REC | EMDS | 1.2 | Code update required | RXXX
M8-014 | 2024-12-09 | DIN log | DIN-1135 | 8.4 | DES138 | Code Correction | IF035 (BSC – DIN1135) as per the IF008 - Adding an exclusion against correlation id and in the notes box to clarify the correlation id is not required for Linked / Related MPANs | BSC | EMDS | 1.2 | Code update required | PYYY
M8-015 | 2024-12-09 | DIN log | DIN-1112 | 8.4 | DES138 | Code Correction | IF036 (BSC – DIN1112) additional value of ‘inherited’ for correlation id with additional interface notes to support Linked / Relate MPANs | BSC | EMDS | 1.2 | Code update required | PYYY
M8-016 | 2024-12-09 | DIN log | DIN-1136 | 8.5 | DES138 | Code Correction | (BSC – DIN1136) – removal of the caveat which made B075 group optional in IR8.3. Should mean no change to EMDS from existing M6 version. Fix from previous DIN | BSC | None |  |  | not required | N/A
M8-017 | 2024-12-09 | DIN log | DIN-1142 | 8.5 | DES138 | Code Correction | IF034 (BSC – DIN1142) removal of statement in flow notes regarding validation against DCC service flag | BSC | EMDS | 1.2 | Code update required | PYYY
M8-018 | 2024-12-09 | Code only |  | MHHS internal report definitions |  | Code Correction | Internal reports in BSCP703 are not defined, because EMDS only holds external / DIP delivered reports. These need to be either changed to 'internal interface' or defined elsewhere in the BSC | BSC | BSCP703 |  | Code update required | PYYY
M8-019 | 2024-12-09 | Code only |  | Agent response code enumerations |  | Code Correction | Agent response codes (DI-0143) to be added for agent response codes in IF-034, and possibly referenced in BSCP706. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-020 | 2024-12-09 | Code only |  | Additional redlining to BSC Section K |  | Additional BSC legal text | Clarifications in respect of Shared SVA Metering Systems where these are explicitly defined as Half Hourly Metering Equipment. | BSC | Section K |  | Code update required | PXXX
M8-021 | 2024-12-09 | Code only |  | Additional redlining to BSC Section S |  | Additional BSC legal text | Clarifications in respect of the SVA Metering Systems Register (S10) to allow MHHS Metering Systems to participate in the BM. | BSC | Section S |  | Code update required | PXXX
M8-022 | 2024-12-09 | Code only |  | Additional redlining to BSC Section X-1 |  | Additional BSC legal text | Clarifications to Definitions to remove ambiguity and support the additional redlining in Sections K and S above. | BSC | Section X, Annex X-1 |  | Code update required | PXXX
M8-023 | 2024-12-09 | Code only |  | MHHS update to SVA Data Catalogue |  | Supporting Change | Adding business context for IF/PUB, REP and D-flows to the SVA Data Catalogue Volume 1, Appendix A | BSC | SVA DC Vol 1 |  | Code update required | CPZZZZ
M8-024 | 2024-12-09 | Code only | CR055 | Updates to Annex S-4 to account for later M8 implementation |  | Code Correction | Annex S-4 has a number of hardcoded dates for activities at known points in the calendar year. These were drafted on the basis of the original M8 implementation date, and some dates will have passed when the P478 code goes live. Review needed. | BSC | Section S, Annex S-4 |  | Code update required | PYYY
M8-025 | 2024-12-09 | Code only |  | BSCP 65 alignment with BSCP707 Appendix for BSC Party Name |  | Code Correction | In BSCP707 Appendix 1 and 2, the allowed character limit for the company name is 160, while in BSCP65, it remains at 30. | BSC | BSCP65 |  | Code update required | TBD
M8-026 | 2024-12-09 | Code only | CR059 | Replacement of REP-020 with D0357 |  | Code Correction | Update code to reflect the use of D0357 instead of the REP-020 | BSC | BSCP703 |  | Code update required | PYYY
M8-027 | 2024-12-16 | Code only | Code review | Ownership of new/amended message/data items |  | code ommision at M6 | the code needs to incorporate new and amended messages/data items introduced by the Programme on similar lines to how the BSC intridcued them at M6 | DCUSA | EMDS | 1.2 | reference made in the change proposal | DCPXXX
M8-028 | 2024-12-16 | Code only | DCP445 voting response | Implementation of Market-wide Half Hourly Settlement (MHHS) Arrangements |  | Code Correction to error in DCP445 | In re Schedule 16, paragraph 128 there is a reference to “REP-002” which should be to “REP-002B” to align with the definition of “Supercustomer DUoS Report”. | DCUSA | Schedule 16, paragraph 128 |  | Code update required | DCPXXX
M8-029 | 2024-12-16 | Code only | DCP433 | Limitation for backdating of rebates/charges under Schedule 32 |  | additional MHHS text required | DCP433 introduces a term that has an equivent term introduced by DCP445. | DCUSA | Schedule 32, paragraphs 6.10 and 6.11 |  | Code update required | DCPXXX
M8-030 | 2024-12-16 | Programme CR | CR-056 & DIN-1138 | 8.5 |  | Code alignment | 7.3B The ERDA shall provide Supplier Agent and SMDR Appointment data in a single CSS00200 Market Message per Metering Point by 23:00 hours on the day the agent appointment is issued by the equivalent SMRA. | REC | ERDS Service Definition |  | Code update required | RXXX
M8-031 | 2024-12-16 | Code only | EES API - 1 | EES API - 1 |  | Code Correction | Removal of capitalisation from the return detail tables (API returns will always be lower case) | REC | EES API Technical Specification |  | Code update required | RXXX
M8-032 | 2024-12-16 | Code only | EES API - 2 | EES API - 2 |  | Code Correction | Removal of the MHHS Indicator and EFD from the SearchAddress Method. | REC | EES API Technical Specification |  | Code update required | RXXX
M8-033 | 2025-01-06 | DIN log | DIN-1063 | 8.2 | EDI021 ISD Entities METH001 (SDS) METH002 (ADS) METH004 (UMSDS) METH005 (LSS) METH006 (VAS) | Code Correction | Measurement Quantity data item changes to Measurement Quantity ID in BSCP707 and Appendices | BSC | BSCP707 & Appendices |  | Code update required | PYYY
M8-034 | 2025-01-06 | DIN log | DIN-1155 | 8.7 | MHHSP-EM021 ISD Entity Map | Code Correction | Change required to Annex S4 of BSC to amend detail of which MDD Entities are frozen at the end of Transition and to add 'Standard Settlement Configuration' which is missing. Changes to be rolled up into BSC Mod. | BSC | Section S, Annex S-4 |  | Code update required | PYYY
M8-035 | 31/1/25 | DIN log | DIN-1165 | 8.7 | DES196 DEL1712 | Code Correction | Additional scenario variants added to D0294, D0295, D0297 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-036 | 31/1/25 | DIN log | DIN-1166 | 8.7 | DES196 DEL1712 ERI011B | Code Correction | Removal of REP-020 from ECS Reporting Catalogue and addition of new scenario variants for D0357. Plus removal of erroneous scenario variants for D0354, D0355, D0356 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-037 | 31/01/2025 | EMDS Review | D0001 | N/A | DES196 and redlined D Flows | Code Correction | Add scenario variant for Meter Reading Service to Smart Data Service | BSC | EMDS | 1.2 | Code update required | PYYY
M8-038 | 31/01/2025 | EMDS Review | D0001 | N/A | DES196 and redlined D Flows | Code Correction | Add the following condition against Additional Information data item in group 003: "Additional Information is Mandatory if Reason for Request data item value does not provide sufficient information to identify the reason for the suspected fault." | BSC | EMDS | 1.2 | Code update required | PYYY
M8-039 | 31/01/2025 | EMDS Review | D0002 | N/A | DES196 and redlined D Flows | Code Correction | Amend SV00630 to Advanced MEM to Advanced MEM Add new scenario variant Smart MEM to Smart MEM | BSC | EMDS | 1.2 | Code update required | PYYY
M8-040 | 31/01/2025 | EMDS Review | D0002 | N/A | DES196 and redlined D Flows | Code Correction | Add the following condition against Additional Information data item in group 760:"If Site Visit Check Code equals 88 then Additional information is Mandatory." | BSC | EMDS | 1.2 | Code update required | PYYY
M8-041 | 31/01/2025 | EMDS Review | D0003 | N/A | DES196 and redlined D Flows | Code Correction | Amend scenario variant SV00635 target from Smart MEM to Advanced MEM | BSC | EMDS | 1.2 | Code update required | PYYY
M8-042 | 31/01/2025 | EMDS Review | D0004 | N/A | DES196 and redlined D Flows | Code Correction | Amend scenario variant SV00640 source from Data Retriever to Meter Reading Service | BSC | EMDS | 1.2 | Code update required | PYYY
M8-043 | 31/01/2025 | EMDS Review | D0005 | N/A | DES196 and redlined D Flows | Code Correction | Add the following scenario variants: • Smart Data Service to Electricity Smart Meter Equipment Manager • Electricity Smart Meter Equipment Manager to Smart Data Service • Electricity Supplier to Smart Data Service | BSC | EMDS | 1.2 | Code update required | PYYY
M8-044 | 31/01/2025 | EMDS Review | D0126 | N/A | DES196 and redlined D Flows | Code Correction | Remove erronous text introduced into the HTML where certain symbols such as quotation marks are used in the message and data item descriptions and notes | REC | EMDS | 1.2 | Code update required | RXXX
M8-045 | 31/01/2025 | EMDS Review | D0126 | N/A | DES196 and redlined D Flows | Code Correction | Amend the ownership on scenario variants SV00015 and 16 from BSC to REC | REC | EMDS | 1.2 | Code update required | RXXX
M8-046 | 31/01/2025 | EMDS Review | D0126 | N/A | DES196 and redlined D Flows | Code Correction | Add the following condition against Additional Information data item in group 250: "Additional Information is Mandatory if Asset Condition Code equals D, R or U; for any other value, Additional Information is Optional." | REC | EMDS | 1.2 | Code update required | RXXX
M8-047 | 31/01/2025 | EMDS Review | D0134 | N/A | DES196 and redlined D Flows | Code Correction | Amend message description to: "A request for the energisation status of a metering point to be changed." | REC | EMDS | 1.2 | Code update required | RXXX
M8-048 | 31/01/2025 | EMDS Review | D0134 | N/A | DES196 and redlined D Flows | Code Correction | Amend message notes to remove the following sentence to reflect redlined changes: "Half hour Data Collectors are not involved in the change of energisation process. This flow is not for use with prepayment meters." | REC | EMDS | 1.2 | Code update required | RXXX
M8-049 | 31/01/2025 | EMDS Review | D0135 | N/A | DES196 and redlined D Flows | Code Correction | Add scenario variant for Meter Reading Service to Smart Data Service | REC | EMDS | 1.2 | Code update required | RXXX
M8-050 | 31/01/2025 | EMDS Review | D0136 | N/A | DES196 and redlined D Flows | Code Correction | Add scenario variant for Meter Reading Service to Smart Data Service | REC | EMDS | 1.2 | Code update required | RXXX
M8-051 | 31/01/2025 | EMDS Review | D0142 | N/A | DES196 and redlined D Flows | Code Correction | Amend message description to reflect the correct baseline version: "Request is being made and information provided to allow removal, replacement or installation of a meter. " | REC | EMDS | 1.2 | Code update required | RXXX
M8-052 | 31/01/2025 | EMDS Review | D0149 | N/A | DES196 and redlined D Flows | Code Correction | Update to reflect the agreed redlined changes to the data item rules. This includes references to Non Half Hourly Meter Technical Details Message which should be Traditional Meter Technical Details Message and typo corrections of reciept to receipt. | REC | EMDS | 1.2 | Code update required | RXXX
M8-053 | 31/01/2025 | EMDS Review | D0150 | N/A | DES196 and redlined D Flows | Code Correction | Amend message description to: "Meter Technical Details for Traditional Metering Assets" | REC | EMDS | 1.2 | Code update required | RXXX
M8-054 | 31/01/2025 | EMDS Review | D0150 | N/A | DES196 and redlined D Flows | Code Correction | Amend message notes to: "Used for all Non Half Hourly Meters for Non-MHHS Migrated Metering Points or Traditional Metering Assets for MHHS Migrated Metering Points" | REC | EMDS | 1.2 | Code update required | RXXX
M8-055 | 31/01/2025 | EMDS Review | D0150 | N/A | DES196 and redlined D Flows | Code Correction | Remove Data Item rule against MPAN Core as it is not part of the current baseline | REC | EMDS | 1.2 | Code update required | RXXX
M8-056 | 31/01/2025 | EMDS Review | D0150 | N/A | DES196 and redlined D Flows | Code Correction | Amend the Data Item rules to match the approved redline drafting against the following data items: Effective from Settlement Date {MSMTD}Measurement Class Id Standard Settlement Configuration Id Effective from Settlement Date {SCON} Metering System Non Settlement Functionality Code Effective From Settlement Date {MSNSFC} Meter Id (Serial Number) Meter Register Id Meter Register Type Measurement Quantity Id Meter Register Multiplier Number of Register Digits | REC | EMDS | 1.2 | Code update required | RXXX
M8-057 | 31/01/2025 | EMDS Review | D0150 | N/A | DES196 and redlined D Flows | Code Correction | Amend optionality of data items marked as N to be 0 for optional | REC | EMDS | 1.2 | Code update required | RXXX
M8-058 | 31/01/2025 | EMDS Review | D0179 | N/A | DES196 and redlined D Flows | Code Correction | Add missing data item condition to Tariff Code: "Tariff Code is Mandatory within a message generated for a Token Meter or a Smart Card Meter, or Optional for any other meter type." | REC | EMDS | 1.2 | Code update required | RXXX
M8-059 | 31/01/2025 | EMDS Review | D0180 | N/A | DES196 and redlined D Flows | Code Correction | Add missing data item conditions throughout the message | REC | EMDS | 1.2 | Code update required | RXXX
M8-060 | 31/01/2025 | EMDS Review | D0222 | N/A | DES196 and redlined D Flows | Code Correction | Add scenario variant for Meter Reading Service to Smart Data Service | BSC | EMDS | 1.2 | Code update required | PYYY
M8-061 | 31/01/2025 | EMDS Review | D0222 | N/A | DES196 and redlined D Flows | Code Correction | Update owner for scenario variant SV00122 to REC | BSC/REC | EMDS | 1.2 | Code update required | PYYY / RXXX
M8-062 | 31/01/2025 | EMDS Review | D0222 | N/A | DES196 and redlined D Flows | Code Correction | Update owner for scenario variant SV00125 to BSC | BSC/REC | EMDS | 1.2 | Code update required | PYYY / RXXX
M8-063 | 31/01/2025 | EMDS Review | D0225 | N/A | DES196 and redlined D Flows | Code Correction | Add missing data item conditions throughout the message. Note that a BAU issue has been raised to consider an alternative approach to defining conditions against address data items | REC | EMDS | 1.2 | Code update required | RXXX
M8-064 | 31/01/2025 | EMDS Review | D0268 | N/A | DES196 and redlined D Flows | Code Correction | Amend message description to reflect redlined change: "Half Hourly Advanced Meter Technical Details are transferred when there is a change in equipment, configuration or upon change of Agent." | BSC/REC | EMDS | 1.2 | Code update required | PYYY / RXXX
M8-065 | 31/01/2025 | EMDS Review | D0268 | N/A | DES196 and redlined D Flows | Code Correction | Update flow notes to remove Annex C reference: "See Annex C for Flow Notes. Where an AMVLP (Asset Metering Virtual Lead Party) is involved and for SV00690, the MPAN Core must contain an AMSID (Asset Metering System Identifier) and not an MPAN." | BSC/REC | EMDS | 1.2 | Code update required | PYYY / RXXX
M8-066 | 31/01/2025 | EMDS Review | D0268 | N/A | DES196 and redlined D Flows | Code Correction | Add missing data item conditions throughout the message | BSC/REC | EMDS | 1.2 | Code update required | PYYY / RXXX
M8-067 | 31/01/2025 | EMDS Review | D0290 | N/A | DES196 and redlined D Flows | Code Correction | Amend scenario variant SV00673 to target Meter Reading Service rather than Data Retriever | BSC | EMDS | 1.2 | Code update required | PYYY
M8-068 | 31/01/2025 | EMDS Review | D0290 | N/A | DES196 and redlined D Flows | Code Correction | Add missing data item conditions throughout the message | BSC | EMDS | 1.2 | Code update required | PYYY
M8-069 | 31/01/2025 | EMDS Review | D0300 | N/A | DES196 and redlined D Flows | Code Correction | Amend message description to: "Notification of a disputed/missing Meter Reading on Change of Supplier and the associated details" | REC | EMDS | 1.2 | Code update required | RXXX
M8-070 | 31/01/2025 | EMDS Review | D0303 | N/A | DES196 and redlined D Flows | Code Correction | Add missing data item rule to Effective from Settlement Date {REGI}: "Data Item may not be populated for Smart Metering Assets where the Smart Metering Equipment Manager does not hold this data." | REC | EMDS | 1.2 | Code update required | RXXX
M8-071 | 31/01/2025 | EMDS Review | D0303 | N/A | DES196 and redlined D Flows | Code Correction | Add missing data item condition to Date of Installation / Removal of Timing Device / Associated Equipment: "Date of Installation / Removal of Timing Device / Associated Equipment is Mandatory if message generation related to install or removal event, for any other event the data item must be Null." | REC | EMDS | 1.2 | Code update required | RXXX
M8-072 | 31/01/2025 | EMDS Review | D0303 | N/A | DES196 and redlined D Flows | Code Correction | Add missing data item condition to Date of Meter Installation: "Date of Meter Installation is Mandatory when the message is generated following the installation of that meter, or the data item is Optional if the message is generated for any other purpose." | REC | EMDS | 1.2 | Code update required | RXXX
M8-073 | 31/01/2025 | EMDS Review | D0388 | N/A | DES196 and redlined D Flows | Code Correction | Correct target in SV00681 scenario variant to Unmetered Supplies Data Service | BSC | EMDS | 1.2 | Code update required | PYYY
M8-074 | 31/01/2025 | EMDS Review | D0389 | N/A | DES196 and redlined D Flows | Code Correction | Correct source in scenario variant SV00682 to Unmetered Supplies Data Service | BSC | EMDS | 1.2 | Code update required | PYYY
M8-075 | 31/01/2025 | EMDS Review | D0399 | N/A | DES196 and redlined D Flows | Code Correction | Amend message description to: "Report of consumption component class totals for each GSP group." | BSC | EMDS | 1.2 | Code update required | PYYY
M8-076 | 31/01/2025 | EMDS Review | D0400 | N/A | DES196 and redlined D Flows | Code Correction | Amend the range of group TLD/03Z to 0-* | BSC | EMDS | 1.2 | Code update required | PYYY
M8-077 | 31/01/2025 | EMDS Review | D0400 | N/A | DES196 and redlined D Flows | Code Correction | Amend order of data items in MCC group to ensure Consumption Component Indicator is above Connection Type (currently they have been transposed in the EMDS). | BSC | EMDS | 1.2 | Code update required | PYYY
M8-078 | 31/01/2025 | EMDS Review | D0401 | N/A | DES196 and redlined D Flows | Code Correction | Move group 88J above 87J and correct parent/ child formatting in levels | BSC | EMDS | 1.2 | Code update required | PYYY
M8-079 | 31/01/2025 | EMDS Review | D0401 | N/A | DES196 and redlined D Flows | Code Correction | Amend the J numbers linked to the following data items: MSID Count - Actuals (DI51607) should be J2377 rather than J2320 MSID Count - Estimates (DI51608) should be J2378 rather than J2321 MSID Count - Defaults (DI51609) should be J2379 rather than J2322 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-080 | 31/01/2025 | EMDS Review | D0402 | N/A | DES196 and redlined D Flows | Code Correction | Amend data item names: DI20282 to "Supplier Smart and Unmetered Demand Disconnection Volume" DI20283 to "Supplier Smart and Unmetered Demand Disconnection Volume Losses" This will impact data item names in group 19Z | BSC | EMDS | 1.2 | Code update required | PYYY
M8-081 | 31/01/2025 | EMDS Review | D0402 | N/A | DES196 and redlined D Flows | Code Correction | Amend data item names: DI20284 to "Daily Supplier Smart and Unmetered Demand Disconnection Volume" DI20285 to "Daily Supplier Smart and Unmetered Demand Disconnection Volume Losses" This will impact data item names in group 20Z | BSC | EMDS | 1.2 | Code update required | PYYY
M8-082 | 31/01/2025 | EMDS Review | DI-018 Consent Granularity Effective From Date | N/A | DES138 | Code Correction | Amend data item description to: "The date and time from which the consent granularity was in effect", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-083 | 31/01/2025 | EMDS Review | DI-019 Contract Reference Metering Service | N/A | DES138 | Code Correction | Amend data item description to: "The unique reference of the contractual agreement between a supplier and the Metering Service", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-084 | 31/01/2025 | EMDS Review | DI-020 Contract Reference Data Service | N/A | DES138 | Code Correction | Amend data item description to: "The unique reference of the contractual agreement between a supplier and the Data Service", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-085 | 31/01/2025 | EMDS Review | DI-021 Customer Direct Contract Metering Service | N/A | DES138 | Code Correction | Amend data item description to: "An indicator to show if a direct customer contract exists between the customer and the Metering Service", as agreed in CR024 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-086 | 31/01/2025 | EMDS Review | DI-022 Customer Direct Contract Data Service | N/A | DES138 | Code Correction | Amend data item description to: "An indicator to show if a direct customer contract exists between the customer and the Data Service", as agreed in CR024 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-087 | 31/01/2025 | EMDS Review | DI-031 Load Shape Domestic Premise Indicator | N/A | DES138 | Code Correction | Correct typo in the data item description - Domectic | BSC | EMDS | 1.2 | Code update required | PYYY
M8-088 | 31/01/2025 | EMDS Review | DI-032 Domestic Premise Indicator Effective From Date | N/A | DES138 | Code Correction | Amend data item description to: "The date and time from which the metering point Domestic Premise Indicator is in effect", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-089 | 31/01/2025 | EMDS Review | DI-033 Energisation Status | N/A | DES138 | Code Correction | Add the following enumerations: 'D De-Energised' 'E Energised' | BSC | EMDS | 1.2 | Code update required | PYYY
M8-090 | 31/01/2025 | EMDS Review | DI-048 Manufacturers Make and Type | N/A | DES138 | Code Correction | Remove duplicate apostrophe from data item description | REC | EMDS | 1.2 | Code update required | RXXX
M8-091 | 31/01/2025 | EMDS Review | DI-051 Market Segment Indicator Effective From Date | N/A | DES138 | Code Correction | Amend data item description to: "The date and time from which the metering point Market Segment is in effect", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-092 | 31/01/2025 | EMDS Review | DI-059 Meter Type | N/A | DES138 | Code Correction | Amend data item description to: "Indicates the type of meter", as agreed in CR024. | REC | EMDS | 1.2 | Code update required | RXXX
M8-093 | 31/01/2025 | EMDS Review | DI-061 Metering Service Effective From Date | N/A | DES138 | Code Correction | Amend description to reflect DES138 update for CR036: "The date and time from when a metering service will be responsible for a metering point. Initially assumed to be midnight UTC." | BSC | EMDS | 1.2 | Code update required | PYYY
M8-094 | 31/01/2025 | EMDS Review | DI-077 CSS RMP DeActivation Date | N/A | DES138 | Code Correction | Amend data item description to: "The data and time from which the CSS Registration is made Inactive within CSS", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-095 | 31/01/2025 | EMDS Review | DI-084 | N/A | DES138 | Code Correction | Delete DI-084 from the EMDS | BSC | EMDS | 1.2 | Code update required | PYYY
M8-096 | 31/01/2025 | EMDS Review | DI-093 Additional Information | N/A | DES138 | Code Correction | Unmatch this DI with the J0012 in the HTML and create a standalone data item with format matching the DES138 | REC | EMDS | 1.2 | Code update required | RXXX
M8-097 | 31/01/2025 | EMDS Review | DI-121 Supplier Effective To Date | N/A | DES138 | Code Correction | Amend data item description to: "The last inclusive settlement date and time after which a Supplier's registration to a metering system ceases to be valid", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-098 | 31/01/2025 | EMDS Review | DI-145 Customer Direct Contract MS EffectiveTo Date | N/A | DES138 | Code Correction | Amend data item description to: "The date and time on which an existing Metering Service Customer Direct Contract is due to expire", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-099 | 31/01/2025 | EMDS Review | DI-146 Customer Direct Contract DS EffectiveTo Date | N/A | DES138 | Code Correction | Amend data item description to: "The date and time on which an existing Data Service Customer Direct Contract is due to expire", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-100 | 31/01/2025 | EMDS Review | DI-148 Annual Consumption | N/A | DES138 | Code Correction | Amend data item description to: "Calculated Annual Consumption (kWh)" which removes reference to ECS, as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-101 | 31/01/2025 | EMDS Review | DI-149 Annual Consumption EffectiveFrom Date | N/A | DES138 | Code Correction | Amend data item description to: "The date and time on which the Annual Consumption was calculated/is effective from", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-102 | 31/01/2025 | EMDS Review | DI-150 Annual Consumption Quality Indicator | N/A | DES138 | Code Correction | Amend data item description to: "Calculated Annual Consumption Quality Indicator" which removes reference to ECS, as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-103 | 31/01/2025 | EMDS Review | DI-152 Supplier Nominated Annual Consumption | N/A | DES138 | Code Correction | Amend data item description: "Supplier Nominated Annual Consumption Value, to be used as required by Data Service in preference to the Annual Consumption" which removes reference to ECS calculated, as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-104 | 31/01/2025 | EMDS Review | DI-196 MDR Reference Date | N/A | DES138 | Code Correction | Amend data item ownership to BSC | DCUSA / BSC | EMDS | 1.2 | Code update required | PYYY
M8-105 | 31/01/2025 | EMDS Review | DI-218 Current Supplier DIP ID | N/A | DES138 | Code Correction | Amend data item ownership to BSC | DCUSA / BSC | EMDS | 1.2 | Code update required | PYYY
M8-106 | 31/01/2025 | EMDS Review | DI-219 Current Supplier MPID | N/A | DES138 | Code Correction | Amend data item ownership to BSC | DCUSA / BSC | EMDS | 1.2 | Code update required | PYYY
M8-107 | 31/01/2025 | EMDS Review | DI-305 Settlement Date | N/A | ERI011B | Code Correction | Create new data item for DI-305 rather than linking to J0073 / DI50034 as they have different formats | BSC | EMDS | 1.2 | Code update required | PYYY
M8-108 | 31/01/2025 | EMDS Review | DI-364 Daily Uncorrected BM Unit's Period Level Consumption Losses | N/A | ERI011B | Code Correction | Amend MHHS DataType for DI-364 Daily Uncorrected BM Unit's Period Level Consumption Losses to DT-022N | BSC | EMDS | 1.2 | Code update required | PYYY
M8-109 | 31/01/2025 | EMDS Review | DI-367 Daily Uncorrected Period BM Unit Total Allocated Volume | Solution update 27/02/25 | ERI011B | Code Correction | Add DI-367 Daily Uncorrected Period BM Unit Total Allocated Volume to the EMDS | BSC | EMDS | 1.2 | Code update required | PYYY
M8-110 | 31/01/2025 | EMDS Review | DI-368 Daily Period BM Unit Total Allocated Volume | Solution update 27/02/25 | ERI011B | Code Correction | Add DI-368 Daily Period BM Unit Total Allocated Volume to the EMDS | BSC | EMDS | 1.2 | Code update required | PYYY
M8-111 | 31/01/2025 | EMDS Review | DI-375 Daily Uncorrected BM Unit's Period Level Consumption | N/A | ERI011B | Code Correction | Amend MHHS DataType for DI-375 Daily Uncorrected BM Unit's Period Level Consumption Losses to DT-022N | BSC | EMDS | 1.2 | Code update required | PYYY
M8-112 | 31/01/2025 | EMDS Review | DI-411 Supplier Demand Disconnection Volume | N/A | ERI011B | Code Correction | Amend name to: "Supplier Smart and Unmetered Demand Disconnection Volume" as per D0402 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-113 | 31/01/2025 | EMDS Review | DI-412 Supplier Demand Disconnection Volume Losses | N/A | ERI011B | Code Correction | Amend name to: "Supplier Smart and Unmetered Demand Disconnection Volume Losses" as per D0402 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-114 | 31/01/2025 | EMDS Review | DI-417 Daily Supplier Demand Disconnection Volume | N/A | ERI011B | Code Correction | Amend name to: "Daily Supplier Smart and Unmetered Demand Disconnection Volume" as per D0402 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-115 | 31/01/2025 | EMDS Review | DI-418 Daily Supplier Demand Disconnection Volume Losses | N/A | ERI011B | Code Correction | Amend name to: "Daily Supplier Smart and Unmetered Demand Disconnection Volume Losses" as per D0402 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-116 | 31/01/2025 | EMDS Review | DI-432 Period Metering System Metered Data | N/A | ERI011B | Code Correction | Create new data item for DI-432 Period Metering System Metered Data rather than linking to J1872 / DI51168 as they have different formats | BSC | EMDS | 1.2 | Code update required | PYYY
M8-117 | 31/01/2025 | EMDS Review | DI-441 Daily GSP Group Take | N/A | ERI011B | Code Correction | Create new data item for DI-441 Daily GSP Group Take rather than linking to J0899 / DI50441 as they have different formats | BSC | EMDS | 1.2 | Code update required | PYYY
M8-118 | 31/01/2025 soln update 18/02/25 | EMDS Review | DI-512 MHHS Consumption Component Class | N/A | ERI011B | Code Correction | Create new data item for DI-512 MHHS Consumption Component Class | BSC | EMDS | 1.2 | Code update required | PYYY
M8-119 | 31/01/2025 | EMDS Review | DI-516 Aggregated BM Unit Energy | N/A | ERI011B | Code Correction | Add DI-516 to DI50955 / J1629 and remove second sentence from the data item description | BSC | EMDS | 1.2 | Code update required | PYYY
M8-120 | 31/01/2025 | EMDS Review | DI-517 Aggregarted BM Unit Line Losses | N/A | ERI011B | Code Correction | Add DI-517 to DI50956 / J1630 and remove second sentence from the data item description | BSC | EMDS | 1.2 | Code update required | PYYY
M8-121 | 31/01/2025 | EMDS Review | DI-518 Corrected BM Unit Energy | N/A | ERI011B | Code Correction | Add DI-518 to DI50964 / J1638 and remove second sentence from the data item description | BSC | EMDS | 1.2 | Code update required | PYYY
M8-122 | 31/01/2025 | EMDS Review | DI-519 Corrected BM Unit Line Losses | N/A | ERI011B | Code Correction | Add DI-519 to DI50965 / J1639 and remove second sentence from the data item description | BSC | EMDS | 1.2 | Code update required | PYYY
M8-123 | 31/01/2025 | EMDS Review | DI-612 LDSO Billing DUoS Tariff ID | N/A | ERI011B | Code Correction | Amend data item ownership to DCUSA | DCUSA/SEC | EMDS | 1.2 | Code update required | DCPXXX
M8-124 | 31/01/2025 | EMDS Review | DI-618 Daily Uncorrected Period BM Unit Total Allocated Volume | N/A | ERI011B | Code Correction | Amend data format to logical length 14, decimal length 4 and physical length 16. And remove MHHS Data Type DT-022 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-125 | 31/01/2025 | EMDS Review | DI-619 Daily Period BM Unit Total Allocated Volume | N/A | ERI011B | Code Correction | Amend data format to logical length 14, decimal length 4 and physical length 16. And remove MHHS Data Type DT-022 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-126 | 31/01/2025 | EMDS Review | DI-620 GSP Group Take Report Value | N/A | ERI011B | Code Correction | Remove MHHS Data Type DT-003 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-127 | 31/01/2025 Soln update 27/02/25 | EMDS Review | DI-621 Uncorrected Period BM Unit Total Allocated Volume | N/A | ERI011B | Code Correction | Add new data item for DI-621 with logical length 16, decimal length 6 and physical length 18 and remove this from DI50962 which is linked to J1636 (which has a different format with 4 decimal places). Retain the J1636 within the D0400. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-128 | 31/01/2025 Soln update 27/02/25 | EMDS Review | DI-622 Period BM Unit Total Allocated Volume | N/A | ERI011B | Code Correction | Add new data item for DI-622 with logical length 16, decimal length 6 and physical length 18 and remove this from DI50963 which is linked to J1637 (which has a different format with 4 decimal places). Retain the J1636 within the D0400. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-129 | 31/01/2025 | EMDS Review | DI-800 Service Provider Appointment Scenario | N/A | DES138 | Code Correction | Amend data item description to: "Code used to identify the scenario around a Metering Service or Data Service Appointment", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-130 | 31/01/2025 | EMDS Review | DI-800 Service Provider Appointment Scenario | N/A | DES138 | Code Correction | Amend enumeration code from MSC to MCS | BSC | EMDS | 1.2 | Code update required | PYYY
M8-131 | 31/01/2025 | EMDS Review | DI-815 Metering Service EffectiveTo Date | N/A | DES138 | Code Correction | Amend data item description to: "Date and time on which a Metering Service's period of appointment comes to an end", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-132 | 31/01/2025 | EMDS Review | DI-818 Data Service EffectiveTo Date | N/A | DES138 | Code Correction | Amend data item description to: "Date and time on which a Data Service's period of appointment comes to an end", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-133 | 31/01/2025 | EMDS Review | DI-819 De-Appointment Reason Code | N/A | DES138 | Code Correction | Amend data item description to: " A code indicating reason for termination of a Metering Service or Data Service appointment", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-134 | 31/01/2025 | EMDS Review | DI-824 Incoming (Next) Metering Service EffectiveFrom Date | N/A | DES138 | Code Correction | Amend data item description to: "Date and time from which next/incoming Metering Service appointment is/was effective", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-135 | 31/01/2025 | EMDS Review | DI-827 Incoming (Next) Data Service EffectiveFrom Date | N/A | DES138 | Code Correction | Amend data item description to: "Date and time from which next/incoming Data Service appointment is/was effective", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-136 | 31/01/2025 | EMDS Review | DI-830 Proposed / Prospective MS DIP EffectiveFromDate | N/A | DES138 | Code Correction | Amend data item description to: "Date and time from which the Supplier would like proposed Metering Service appointment to take effect", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-137 | 31/01/2025 | EMDS Review | DI-833 Proposed / Prospective DS DIP EffectiveFromDate | N/A | DES138 | Code Correction | Amend data item description to: " Date and time from which the Supplier would like proposed Data Service appointment to take effect", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-138 | 31/01/2025 | EMDS Review | DI-836 Supplier Nominated MDR EffectiveFrom Date | N/A | DES138 | Code Correction | Amend data item description to: "Date and time from which the Supplier would like the Nominated MDR to take effect", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-139 | 31/01/2025 | EMDS Review | DI-837 Supplier Proposed Domestic Indicator | N/A | DES138 | Code Correction | Amend data item description to: "Proposed Domestic Indicator for a period of Supplier Agent Appointment", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-140 | 31/01/2025 | EMDS Review | DI-838 Supplier Proposed Consent Granularity | N/A | DES138 | Code Correction | Amend Nullable field to Mandatory No Nulls | BSC | EMDS | 1.2 | Code update required | PYYY
M8-141 | 31/01/2025 | EMDS Review | DI-841 SDS Nominated MDR Requested Effective From Date | N/A | DES138 | Code Correction | Amend data item description to: "Date and time from which the SDS would like the MDR to be assigned to an MPAN", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-142 | 31/01/2025 | EMDS Review | DI-844 Assigned MDR Effective From Date | N/A | DES138 | Code Correction | Amend data item description to: "Date and time from which the MDR is effective for an MPAN", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-143 | 31/01/2025 | EMDS Review | DI-847 Service Provider App Requesting Supplier DIP ID | N/A | DES138 | Code Correction | Amend data item description to: "DIP ID of the Supplier requesting a Metering Service or Data Service Appointment", as agreed in CR024. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-144 | 31/01/2025 | EMDS Review | DI-850 MDR Effective To Date | N/A | DES138 | Code Correction | Amend data item ownership to BSC | DCUSA / BSC | EMDS | 1.2 | Code update required | PYYY
M8-145 | 31/01/2025 | EMDS Review | DI-960 - DI-999 | N/A | DES138 | Code Correction | Add MHHS Data Classification as 'Public' in DI-960 to DI-999 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-146 | 31/01/2025 | EMDS Review | DI-978 Msg Service Ticket URL | N/A | DES138 | Code Correction | Amend length to 250 to reflect DES138 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-147 | 31/01/2025 | EMDS Review | DI-980 Response Message | N/A | DES138 | Code Correction | Add missing sentence from data item description: "Note: it is possible to provide an array of [Response Message]'s , if it is desirable to send multiple failure texts" | BSC | EMDS | 1.2 | Code update required | PYYY
M8-148 | 31/01/2025 | EMDS Review | IF common blocks | N/A | DES138 | Code Correction | DIP Common tab defines the A0 Addressing group as optional for non Primary Routing. Should be set to 0-1 within the EMDS with condition stated in all IF messages. | BSC/REC | EMDS | 1.2 | Code update required | PYYY / RXXX
M8-149 | 31/01/2025 | EMDS Review | IF-001 | N/A | DES138 | Code Correction | IF-001 -Remove SUPO from the list of Primary recipients in the EMDS | BSC | EMDS | 1.2 | Code update required | PYYY
M8-150 | 31/01/2025 | EMDS Review | IF-002 | N/A | DES138 | Code Correction | IF-002- Add "most recent record only" as a condition against all instances of the B075 group in the EMDS and amend the cardinality to 1-1 as this is mandatory where a parent group is provided | BSC | EMDS | 1.2 | Code update required | PYYY
M8-151 | 31/01/2025 | EMDS Review | IF-003 | N/A | DES138 | Code Correction | IF-003 - Add security category and update version to 11 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-152 | 31/01/2025 | EMDS Review | IF-003 | N/A | DES138 | Code Correction | IF-003 - add condition "mandatory where available in SMRS" in the groups B095 and B096 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-153 | 31/01/2025 | EMDS Review | IF-003 | N/A | DES138 | Code Correction | IF-003 - Update flow notes in EMDS: "It is possible that in some circumstances the SMRS will not yet be aware of the Incoming MOP/DC, at the point it is necessary and required to issue the Notification of De-Appointment to the incumbent Supplier Agent(s). In such cases the message will be issued with section(s) B095 and B096 not present. Once known the incoming MOP/DC will be notified, via a second follow up IF-003 with event code [MSDeAppUpdateRM] or [DSDeAppUpdateRM], as appropriate to the relevent outgoing Supplier Agent, this time with blocks B095/B096 fully populated. During the migration / qualification period not all parties will have an active DIP ID, where it is not possible to populate a participants DIP ID - the SMRS will use a default DIP ID value. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-154 | 31/01/2025 | EMDS Review | IF-003 | N/A | DES138 | Code Correction | IF-003 - Add SUPC as Primary routing for all scenario variants in the EMDS | BSC | EMDS | 1.2 | Code update required | PYYY
M8-155 | 31/01/2025 | EMDS Review | IF-003 | N/A | DES138 | Code Correction | IF-003 - Record LDSO as Secondary routing rather than Always routing in the Reverse Migration scenario SV20745 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-156 | 31/01/2025 | EMDS Review | IF-005 | N/A | DES138 | Code Correction | IF-005 - Amend cardinality of New Meter Information group B033 and Meter MAP Info group B034 to 0-0 in Meter Removal scenario variant SV20716 and amend cardinality of Removed Meter Information group B039 to 0-0 in Meter Install scenario variant SV20715 | REC | EMDS | 1.2 | Code update required | RXXX
M8-157 | 31/01/2025 Soln update 11/02/2025 | EMDS Review | IF-006 | N/A | DES138 | Code Correction | IF-006 - Amend cardinality of New Meter Information group B033 and Meter MAP Info group B034 to 0-0 in Meter Removal scenario variant SV20413 and amend cardinality of Removed Meter Information group B039 to 0-0 in Meter Install scenario variant SV20383 | REC | EMDS | 1.2 | Code update required | RXXX
M8-158 | 31/01/2025 Soln update 25/02/2025 | EMDS Review | IF-006 | N/A | DES138 | Code Correction | IF-006 - Amend condition against all instances of the B075 group in the EMDS to: 'Most recent record only' and amend cardinality to 1-1 as only the most recent should be provided. | REC | EMDS | 1.2 | Code update required | RXXX
M8-159 | 31/01/2025 | EMDS Review | IF-009 | N/A | DES138 | Code Correction | IF-009 - Remove SUPC from the list of Primary recipients for MPAN Reconnection scenario variant SV20310 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-160 | 31/01/2025 | EMDS Review | IF-009 | N/A | DES138 | Code Correction | IF-009 - Amend the cardinality of MPAN Reconnection scenario variant SV20310 groups B041 and B042 to 0-1 to align to other scenatio variants | BSC | EMDS | 1.2 | Code update required | PYYY
M8-161 | 31/01/2025 | EMDS Review | IF-009 | N/A | DES138 | Code Correction | IF-009 - Amend optionality of data items marked as C to be M or O within groups B041 and B042 in the MPAN Reconnection scenario variant SV20310 to align to the DES138 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-162 | 31/01/2025 Soln Update 11/02/2025 | EMDS Review | IF-013 | N/A | DES138 | Code Correction | IF013 - Amend Primary routing from SUPS to SUPC for both scenario variants | BSC | EMDS | 1.2 | Code update required | PYYY
M8-163 | 31/01/2025 | EMDS Review | IF-016 | N/A | DES138 | Code Correction | IF-016 - Amend message name to: " UTC Settlement Period Consumption Data - REPLAY" to align to the IF-016 tab rather than the List tab | BSC | EMDS | 1.2 | Code update required | PYYY
M8-164 | 31/01/2025 | EMDS Review | IF-016 | N/A | DES138 | Code Correction | IF016 - remove notes from the EMDS as these are no longer included in the DES138 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-165 | 31/01/2025 | EMDS Review | IF-018 | N/A | DES138 | Code Correction | IF018 - remove duplicate data items from GSPChg scenario variant SV20256 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-166 | 31/01/2025 | EMDS Review | IF-019 | N/A | DES138 | Code Correction | IF-019 - Amend message name to: " Manage Meterpoint Relationship" to align to the IF-019 tab rather than the List tab | BSC | EMDS | 1.2 | Code update required | PYYY
M8-167 | 31/01/2025 | EMDS Review | IF-019 | N/A | DES138 | Code Correction | IF-019 - Remove the following sentence from the message notes in the EMDS: "Where there are multiple Related Import MPANs, the Export MPAN will only be linked with the Primary MPAN in the relationship." | BSC | EMDS | 1.2 | Code update required | PYYY
M8-168 | 31/01/2025 | EMDS Review | IF-020 | N/A | DES138 | Code Correction | Amend message name to: " Manage Meterpoint Relationships Response" to align to the IF-020 tab rather than the List tab | BSC | EMDS | 1.2 | Code update required | PYYY
M8-169 | 31/01/2025 | EMDS Review | IF-020 | N/A | DES138 | Code Correction | IF-020 - remove spurious double quotation marks from scenario variant titles in the EMDS | BSC | EMDS | 1.2 | Code update required | PYYY
M8-170 | 31/01/2025 | EMDS Review | IF-020 | N/A | DES138 | Code Correction | IF-020 - add LDSO as source for linked import export rejection scenario SV20214 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-171 | 31/01/2025 | EMDS Review | IF-020 | N/A | DES138 | Code Correction | IF-020 - Update notes to reflect latest version of the DES138 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-172 | 31/01/2025 | EMDS Review | IF-024 | N/A | DES138 | Code Correction | IF-024 - amend the EMDS to use DI-093 for the additional information data item. The hyperlink currently links to DI-120 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-173 | 31/01/2025 | EMDS Review | IF-025 | N/A | DES138 | Code Correction | IF-025 Amend SV20191 SSC and Profile Class scenario group B032 to mandatory 1-1 in the EMDS | BSC | EMDS | 1.2 | Code update required | PYYY
M8-174 | 31/01/2025 | EMDS Review | IF-026 | N/A | DES138 | Code Correction | IF-026 remove double quotation marks from SV20187 name | BSC | EMDS | 1.2 | Code update required | PYYY
M8-175 | 31/01/2025 | EMDS Review | IF-027 | N/A | DES138 | Code Correction | IF-027 Amend scenario variant name in SV20163 to just Consumption Amendment - delete the word request | BSC | EMDS | 1.2 | Code update required | PYYY
M8-176 | 31/01/2025 | EMDS Review | IF-028 | N/A | DES138 | Code Correction | IF-028 - Amend SV name to just Consumption Amendment - delete the word request | BSC | EMDS | 1.2 | Code update required | PYYY
M8-177 | 31/01/2025 | EMDS Review | IF-031 | N/A | DES138 | Code Correction | IF-031 - Amend cardinality of group B13 to 0-1 with condition: "Mandatory if available" | BSC | EMDS | 1.2 | Code update required | PYYY
M8-178 | 31/01/2025 | EMDS Review | IF-031 | N/A | DES138 | Code Correction | IF-031 - amend DI838 Supplier Proposed Consent Granularity to mandatory rather than conditional in both scenario variants | BSC | EMDS | 1.2 | Code update required | PYYY
M8-179 | 31/01/2025 | EMDS Review | IF-032 | N/A | DES138 | Code Correction | IF-032 - amend DI838 Supplier Proposed Consent Granularity to mandatory rather than conditional in both scenario variants | BSC | EMDS | 1.2 | Code update required | PYYY
M8-180 | 31/01/2025 | EMDS Review | IF-033 | N/A | DES138 | Code Correction | IF-033 - Amend version number to 011 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-181 | 31/01/2025 | EMDS Review | IF-033 | N/A | DES138 | Code Correction | IF-033 - Amend condition against group B032 MPAN Legacy Info - Mandatory for Traditional Meters / Optional for other Meters or where not available in SMRS | BSC | EMDS | 1.2 | Code update required | PYYY
M8-182 | 31/01/2025 | EMDS Review | IF-033 | N/A | DES138 | Code Correction | IF-033 - amend DI838 Supplier Proposed Consent Granularity to mandatory rather than conditional in both scenario variants | BSC | EMDS | 1.2 | Code update required | PYYY
M8-183 | 31/01/2025 | EMDS Review | IF-033 | N/A | DES138 | Code Correction | IF-033 - amend cardinality of group B035 in both scenario variants to 0-* rather than 0-1 as its only populated where there are linked metering points and there may be multiple groups | BSC | EMDS | 1.2 | Code update required | PYYY
M8-184 | 31/01/2025 | EMDS Review | IF-033 | N/A | DES138 | Code Correction | IF-033 - amend cardinality of group B037 in both scenario variants to 0-* rather than 1-1 as its only populated where there are related metering points and there may be multiple groups | BSC | EMDS | 1.2 | Code update required | PYYY
M8-185 | 31/01/2025 | EMDS Review | IF-034 | N/A | DES138 | Code Correction | IF-034 - amend DI-838 Supplier Proposed Consent Granularity to mandatory rather than conditional in all scenario variants | BSC | EMDS | 1.2 | Code update required | PYYY
M8-186 | 31/01/2025 | EMDS Review | IF-034 | N/A | DES138 | Code Correction | IF-034 - Amend cardinality of B018 group in SDS-MDRUpdate scenario variant SV20151 to 0-1 with the condition that the group is mandatory where smart meters installed | BSC | EMDS | 1.2 | Code update required | PYYY
M8-187 | 31/01/2025 | EMDS Review | IF-035 | N/A | DES138 | Code Correction | IF-035 - Update notes to reflect latest version of the DES138 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-188 | 31/01/2025 | EMDS Review | IF-035 | N/A | DES138 | Code Correction | IF-035 - amend DI-838 Supplier Proposed Consent Granularity to mandatory rather than conditional in all scenario variants | BSC | EMDS | 1.2 | Code update required | PYYY
M8-189 | 31/01/2025 | EMDS Review | IF-035 | N/A | DES138 | Code Correction | IF035 - amend cardinality of group B019 in DSAppAccepted scenario SV20134 to 0-1 and amend condition to state its 'Mandatory for smart meters' | BSC | EMDS | 1.2 | Code update required | PYYY
M8-190 | 31/01/2025 | EMDS Review | IF-035 | N/A | DES138 | Code Correction | IF-035 - ensure cardinality of group B013 is 0-1 with condition 'Mandatory if available in SMRS' for all scenario variants. Note that it is currently correct in SV20125 and SV20128 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-191 | 31/01/2025 | EMDS Review | IF-036 | N/A | DES138 | Code Correction | IF-036 - Update notes to reflect latest version of the DES138 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-192 | 31/01/2025 | EMDS Review | IF-036 | N/A | DES138 | Code Correction | IF-036 - amend primary routing to include 'Custom' for both scenario variants and caveat of (Non Smart Segment) against SUPL in the DSAppActive SV20117 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-193 | 31/01/2025 | EMDS Review | IF-036 | N/A | DES138 | Code Correction | IF-036 - Add condition against group B019 in the MSAppActive scenario variant SV20109 that the group is for smart meters only | BSC | EMDS | 1.2 | Code update required | PYYY
M8-194 | 31/01/2025 | EMDS Review | IF-036 | N/A | DES138 | Code Correction | IF-036 - amend condition against B005 group in both scenario variants to state: mandatory where available in SMRS | BSC | EMDS | 1.2 | Code update required | PYYY
M8-195 | 31/01/2025 | EMDS Review | IF-036 | N/A | DES138 | Code Correction | IF-036 - Amend to ensure MS App group B016 should be 0-0 as there can be no partner MS. Similarly for DS App group B017 should be 0-0 as there can be no partner DS Amend to ensure MS App group B068 should be 0-0 as irrelevant and for DS App group B068 should be 0-1 with the condition 'mandatory if available in SMRS | BSC | EMDS | 1.2 | Code update required | PYYY
M8-196 | 31/01/2025 | EMDS Review | IF-036 | N/A | DES138 | Code Correction | IF-036 - Amend cardinality in DSApp scenario variant group B027 to 0-1 to match the condition | BSC | EMDS | 1.2 | Code update required | PYYY
M8-197 | 31/01/2025 Soln updated 11/02/2025 | EMDS Review | IF-037 | N/A | DES138 | Code Correction | IF-037 - Remove reference to XMSC and XDSC from primary routing for MSDeAppUpdate SV20103 and DSDeAppUpdate SV20106 scenario variants. Also amend reference to "Previously de-appointed Metering Data Service" in DSDeAppUpdate SV20106 scenario variant. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-198 | 31/01/2025 | EMDS Review | IF-037 | N/A | DES138 | Code Correction | IF-037 - Update the cardinality of groups B010 and B011 to reflect the following: MSDeApp scenario variant SV20091: B010 = 0-1 with condition: "Mandatory for Event MSDeApp where available in SMRS, provided DI-819 is not DEREG" and B011 = 0-0 DSDeApp scenario variant SV20097: B010 = 0-0 and B011 = 0-1 with condition "Mandatory for Event DSDeApp where available in SMRS, provided DI-819 is not DEREG" MSDeAppUpdate scenario variant SV20103: B010 = 1-1 and B011 = 0-0 DSDeAppUpdate scenario variant SV20106: B010 = 0-0 and B011 = 1-1 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-199 | 31/01/2025 | EMDS Review | IF-037 | N/A | DES138 | Code Correction | IF-037 - add condition: "Mandatory if available in SMRS' against group B013 in DSDeAppUpdate scenario variant SV20106 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-200 | 31/01/2025 | EMDS Review | IF-037 | N/A | DES138 | Code Correction | IF-037 - amend cardinality of group B002 in MSDeApp scenario variant SV20091 to 0-1 with condition that its mandatory where de-appointment reason is CSUPP | BSC | EMDS | 1.2 | Code update required | PYYY
M8-201 | 31/01/2025 | EMDS Review | IF-039 | N/A | DES138 | Code Correction | IF-039 - add data item note against DI-980 Response Message in group R0 in the first scenario variant SV20069 stating that the data item is 'required if [DI-979] - "R" | BSC | EMDS | 1.2 | Code update required | PYYY
M8-202 | 31/01/2025 | EMDS Review | IF-041 | N/A | DES138 | Code Correction | IF041 - remove duplicate scenario variant (SV20778) 'DS:Reading on site' | BSC | EMDS | 1.2 | Code update required | PYYY
M8-203 | 31/01/2025 | EMDS Review | IF-045 | N/A | DES138 | Code Correction | IF-045 - amend the EMDS to use DI-120 (DI20298) in the data item list for the additional information data item. Note that the hypelink in the message body correctly links to the DI-0120. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-204 | 31/01/2025 | EMDS Review | IF-047 | N/A | DES138 | Code Correction | IF-047 - amend the EMDS to use DI-120 (DI20298) in the data item list for the additional information data item. Note that the hypelink in the message body correctly links to the DI-0120. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-205 | 31/01/2025 | EMDS Review | IF-047 | N/A | DES138 | Code Correction | IF-047 - amend message description to align to DES138: " The purpose of this interface is to notify DIP Participants of the Publication of a Downloadable Asset, such as ISD or other Reports, and the URI that can be used to access the publication." | BSC | EMDS | 1.2 | Code update required | PYYY
M8-206 | 31/01/2025 | EMDS Review | IF-061 | N/A | DES138 | Code Correction | IF-061 - amend the EMDS to use DI-120 (DI20298) in the data item list for the additional information data item. Note that the hypelink in the message body correctly links to the DI-0120. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-207 | 31/01/2025 | EMDS Review | IF-062 | N/A | DES138 | Code Correction | IF-062 - amend the EMDS to use DI-120 (DI20298) in the data item list for the additional information data item. Note that the hypelink in the message body correctly links to the DI-0120. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-208 | 31/01/2025 | EMDS Review | IF-063 | N/A | DES138 | Code Correction | IF-063 - amend the EMDS to use DI-120 (DI20298) in the data item list for the additional information data item. Note that the hypelink in the message body correctly links to the DI-0120. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-209 | 31/01/2025 | EMDS Review | IF-064 | N/A | DES138 | Code Correction | IF-064 - Amend cardinality of the B046 group to 1-* | BSC | EMDS | 1.2 | Code update required | PYYY
M8-210 | 31/01/2025 | EMDS Review | IF-064 | N/A | DES138 | Code Correction | IF-064 - amend the EMDS to use DI-120 (DI20298) in the data item list for the additional information data item. Note that the hypelink in the message body correctly links to the DI-0120. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-211 | 31/01/2025 | EMDS Review | IF-065 | N/A | DES138 | Code Correction | IF-065 - Remove the condition against groups B076 and B065 for all scenario variants except the ReadingRemote scenario (SV20768) | BSC | EMDS | 1.2 | Code update required | PYYY
M8-212 | 31/01/2025 | EMDS Review | IF-065 | N/A | DES138 | Code Correction | IF-065 - amend the title of group B077 in the HTML to MDR Request Reference Date (rather than Data) | BSC | EMDS | 1.2 | Code update required | PYYY
M8-213 | 31/01/2025 | EMDS Review | IF-065 | N/A | DES138 | Code Correction | IF-065 - amend the EMDS to use DI-120 (DI20298) in the data item list for the additional information data item. Note that the hypelink in the message body correctly links to the DI-0120. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-214 | 31/01/2025 | EMDS Review | J0007 | N/A | DES196 and redlined J Items | Code Correction | Amend Enumeration descriptions for 24/25 to align to redlined drafting: 24 - Migration Metering Point (CoA) 25 - Migrated Metering Point (CoS). | BSC | EMDS | 1.2 | Code update required | PYYY
M8-215 | 31/01/2025 | EMDS Review | J0171 | N/A | DES196 and redlined J Items | Code Correction | Amend enumerations to align to the redlined drafting: U - Forward Migration CoA V - Forward Migration CoS X - Supplier Agreed Switch Read Y - Reverse Migration CoS | BSC | EMDS | 1.2 | Code update required | PYYY
M8-216 | 31/01/2025 | EMDS Review | J2256 | N/A | DES196 and redlined J Items | Code Correction | Add missing data item notes: " Meter Work refers to the date on which the meter work was undertaken (Metering System MTD EFD), i.e. meter installation date, rather than the date on which the update is processed by MPAS." | REC | EMDS | 1.2 | Code update required | RXXX
M8-217 | 31/01/2025 | EMDS Review | REP-003 | N/A | ERI011B | Code Correction | REP-003 - amend cardinality of group R024 to align to 1-* to align to REP-003A | BSC | EMDS | 1.2 | Code update required | PYYY
M8-218 | 31/01/2025 Soln update 25/02/2025 | EMDS Review | REP-003 | N/A | ERI011B | Code Correction | REP-003 - Add data item rule against DI- 339 and DI-370 in groups R022 and R023 stating "optional where disconnection event has impacted settlement period" and remove group condition from group R022 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-219 | 31/01/2025 | EMDS Review | REP-003 | N/A | ERI011B | Code Correction | Add DI-367 'Daily Uncorrected Period BM Unit Total Allocated Volume' to the EMDS and use this within REP-003 rather than DI-618 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-220 | 31/01/2025 | EMDS Review | REP-003A | N/A | ERI011B | Code Correction | Add DI-367 'Daily Uncorrected Period BM Unit Total Allocated Volume' to the EMDS and use this within REP-003A rather than DI-618 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-221 | 31/01/2025 | EMDS Review | REP-003A | N/A | ERI011B | Code Correction | REP-003A - Change 'Supplier' from Secondary to Primary routing. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-222 | 31/01/2025 | EMDS Review | REP-003A | N/A | ERI011B | Code Correction | REP-003A - Amend notes against DI BM Unit Demand Disconnection Volume Losses in group R022 to: "Only populate where a disconnection event has impacted the Settlement Period for the BM Unit within the GSP Group." | BSC | EMDS | 1.2 | Code update required | PYYY
M8-223 | 31/01/2025 | EMDS Review | REP-003A | N/A | ERI011B | Code Correction | REP-003A - Add notes against DI Daily BM Unit Demand Disconnection Volume Losses in group R023: "Only populate where a disconnection event has impacted the Settlement Period for the BM Unit within the GSP Group." | BSC | EMDS | 1.2 | Code update required | PYYY
M8-224 | 31/01/2025 | EMDS Review | REP-006 | N/A | ERI011B | Code Correction | REP-006 - Amend notes against DI "Supplier Advanced Demand Disconnection Volume Losses" in group R106 to: "If Settlement Run is for a Demand Disconnection Event, Mandatory if CCC ID is for consumption losses" | BSC | EMDS | 1.2 | Code update required | PYYY
M8-225 | 31/01/2025 | EMDS Review | REP-006 | N/A | ERI011B | Code Correction | REP-006 - Amend notes against DI "BM Unit Demand Disconnection Volume Losses" in group R106 to "If Settlement Run is for a Demand Disconnection Event, Mandatory if CCC ID is for consumption losses" | BSC | EMDS | 1.2 | Code update required | PYYY
M8-226 | 31/01/2025 | EMDS Review | REP-020 | N/A | ERI011B | Code Correction | Remove REP-020 from EMDS as replaced by a DTN flow via IR8.7 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-227 | 31/01/2025 | EMDS Review | REP-080 | N/A | ERI011B | Code Correction | REP080 - Amend version number to 008 | BSC | EMDS | 1.2 | Code update required | PYYY
M8-228 | 31/01/2025 | EMDS Review | REP-080 | N/A | ERI011B | Code Correction | REP-080 - Add notes to DI Daily Storage Corrected Components in group R083 stating : "Only where the Supplier has MPANs on the SVA Storage facilities register." | BSC | EMDS | 1.2 | Code update required | PYYY
M8-229 | 31/01/2025 | EMDS Review | REP-080 | N/A | ERI011B | Code Correction | REP-080 - Amend hierarchy of groups from R083 onwards within the EMDS. | BSC | EMDS | 1.2 | Code update required | PYYY
M8-230 | 31/01/2025 | EMDS Review | REP-080 | N/A | ERI011B | Code Correction | REP-080 - Four data items in group R080 with data item notes should be defined as C Conditional rather than 1 Mandatory | BSC | EMDS | 1.2 | Code update required | PYYY
M8-231 | 31/01/2025 | EMDS Review | REP-900 | N/A | ERI011B | Code Correction | REP-900 - In group R900-3 , change following Data Items to 'O' - LDSO Billing Site Address Line 1 - LDSO Billing Site Address Line 2 - LDSO Billing Site Address Line 3 - LDSO Billing Site Address Line 4 | DCUSA | EMDS | 1.2 | Code update required | DCPXXX
M8-232 | 31/01/2025 | EMDS Review | REP-900 | N/A | ERI011B | Code Correction | In group R900-4, change 'Tax Point Date' to '1' | DCUSA | EMDS | 1.2 | Code update required | DCPXXX
M8-233 | 31/01/2025 | EMDS Review | REP-900 | N/A | ERI011B | Code Correction | In group R900-4, change 'Invoice Date' to '1' | DCUSA | EMDS | 1.2 | Code update required | DCPXXX
M8-234 | 31/01/2025 | EMDS Review | REP-900 | N/A | ERI011B | Code Correction | In group R900-4, change 'Invoice Date Due' to '1' | DCUSA | EMDS | 1.2 | Code update required | DCPXXX
M8-235 | 31/01/2025 | EMDS Review | REP-900 | N/A | ERI011B | Code Correction | In group R900-4, change 'Site-Specific DUoS Invoice Type' to '0' | DCUSA | EMDS | 1.2 | Code update required | DCPXXX
M8-236 | 31/01/2025 | EMDS Review | REP-900 | N/A | ERI011B | Code Correction | In group R900-4, change 'Maximum Demand (in the) Invoice Period to '0' | DCUSA | EMDS | 1.2 | Code update required | DCPXXX
M8-237 | 31/01/2025 | EMDS Review | REP-900 | N/A | ERI011B | Code Correction | In group R900-4, change 'Total Invoice Amount ex VAT' to '1' | DCUSA | EMDS | 1.2 | Code update required | DCPXXX
M8-238 | 31/01/2025 | EMDS Review | REP-900 | N/A | ERI011B | Code Correction | In group 900-4, change 'Total Invoice VAT' to '1' | DCUSA | EMDS | 1.2 | Code update required | DCPXXX
M8-239 | 31/01/2025 | EMDS Review | REP-900 | N/A | ERI011B | Code Correction | In group R900-4, change 'Total Invoice Amount inc VAT' to '1' | DCUSA | EMDS | 1.2 | Code update required | DCPXXX
M8-240 | 31/01/2025 | EMDS Review | REP-900 | N/A | ERI011B | Code Correction | Change DIP Delivery Pattern from Pattern A JSON via DIP to Pattern A (Compressed String) | DCUSA | EMDS | 1.2 | Code update required | DCPXXX
M8-241 | 31/01/2025 | EMDS Review | REP-901 | N/A | ERI011B | Code Correction | Change DIP Delivery Pattern from Pattern A JSON via DIP to Pattern A (Compressed String) | DCUSA | EMDS | 1.2 | Code update required | DCPXXX
M8-242 | 31/01/2025 | EMDS Review | General | N/A | Generic | Code Correction | Remove spurious data items which are existing J items not linked to MHHS data items | Multiple | EMDS | 1.2 | Code update required | DCPXXX
M8-243 | 2025-02-05 | Code only | EES API - 3 | EES API - 3 |  | Code Correction | Addition of the MHHS Indicator and EFD to the ‘GetCSSMessage’ method | REC | EES API Technical Specification |  | Code update required | RXXX
M8-244 | 2025-02-05 | Code only | EES API - 4 | EES API - 4 |  | Code Correction | Removal of the ‘Metered Indicator ETD’ | REC | EES API Technical Specification |  | Code update required | RXXX
M8-245 | 2025-02-11 | EMDS Review | REP-006 | N/A | ERI011B | Code Correction | REP-006 - Add the following data item notes against DI "MHHS Consumption Component Class Id" and "Settlement Period" in group R106: "Only populate where a disconnection event has occurred" | BSC | EMDS | 1.2 | Code update required | PYYY
M8-246 | 2025-02-18 | DIN Log | DIN-1154 | 8.6 | DES138 | Code Correction | Remove REG1022 Advance segment IHD validation from IF-005 in DES138 | BSC | BSCP706 |  | Code update required | PYYY
M8-247 | 13/03/25 | Code only | EES API - 5 | EES API - 5 |  | Code Correction | Addition of missing value ‘True’ to the ‘GetAssociatedMPANs’ | REC | EES API Technical Specification |  | Code update required | RXXX
M8-248 | 13/03/2025 | Code only | DIN-0431 | D0386 validation – J2240 New enumeration | Migration Design Document | Code alignment | Add Enumeration Value to J2240: Y; Enumeration Description: Forward Migration Underway or MPAN is MHHS | REC | EMDS |  | Code update required | RXXX
M8-249 | 13/03/2025 | Code only | R0209 Consultation | Related Metering Points during Migration | Migration Design Document | Code alignment | Add clarification that a Metering Point relationship cannot be created between a Metering Point that is MHHS and one that is non-MHHS | REC | Schedule 28 |  | Code update required | RXXX
M8-250 | 13/03/2025 | Code only | BRS006 | N/A | MHHS-BR-EES-016.1&2 | Code alignment | Amend EES SLAs to clarify the different timescales for publishing data received from secured active processing versus other updates. | REC | EES Service Definition |  | Code update required | RXXX
M8-251 | 13/03/2025 | Code only | CR-039 | N/A | DES138 | Code alignment | CR039 removed the requirement on the Registration Service to receive Annual Consumption data. This led to the IF040 from BSC Central Systems being processed by EES. The EES Service Definition will be updated to recognise that data is being received from BSC Central Systems via the DIP. | REC | EES Service Definition |  | Code update required | RXXX
M8-252 | 2025-03-18 | DIN log | DIN-1162 | 8.8 | METH002 | Code alignment | Alignment with BSCP502 processes in respect of MAR and 'mini-MAR' requirements. | BSC | BSCP702 |  | Code update required | PYYY
M8-253 | 2025-03-18 | DIN log | DIN-1172 | 8.8 | DES138 | Code alignment | Update IF-041 routing rules for SDS/DS to reflect that both the incoming and outgoing Supplier will receive the read where required for a COS. Clarify on IF-041 routing that meter removal reads need to be sent by the SVA MOA prior to the segment change, and install reads need to be sent after the segment change. Add primary routing to Data Service to cover routing from a DS to another DS during a COS/ Change of Agent. | BSC | EMDS |  | Code update required | PYYY
M8-254 | 2025-03-18 | DIN log | DIN-1125 | 8.9 | BRS002 | Code alignment | Update BSCP704 to remove BR-MS-026 following removal from the UMSO tab | BSC | BSCP704 |  | Code update required | PYYY
M8-255 | 2025-03-18 | DIN log | DIN-1177 | 8.9 | EDI021 | Code alignment | Update BSCP707 to note that non-domestic/import/opt out combinations apply to micro businesses only, otherwise it could be deemed to apply to any non-domestic site | BSC | BSCP707 |  | Code update required | PYYY
M8-256 | 2025-03-18 | DIN log | DIN-1180 | 8.9 | BRS003 | Code alignment | Removal of IF-018 being sent in a COS scenario, placing reliance solely on IF-001/IF-036. Requirement BR-RS-117 (SMRS) to be updated to stipulate not to include on COS | BSC | BSCP706 |  | Code update required | PYYY
M8-257 | 2025-03-18 | DIN log | DIN-1181 | 8.9 | DES138 | Code alignment | Update REG1038 and 1039 Repeat for queue indicators to YES in IF-031 | BSC | BSCP706 |  | Code update required | PYYY
M8-258 | 2025-03-18 | DIN log | DIN-1183 | 8.10 | ERI011B | Code alignment | Update EMDS to show new HHDC to ADS scenario variant of the D0036 for migration | BSC | EMDS |  | Code update required | PYYY
M8-259 | 2025-03-18 | DIN log | DIN-1178 | 8.10 | ERI011B | Code alignment | Update D0397 data items to align with BSC solution document updated for IR8.10 | BSC | EMDS |  | Code update required | PYYY
M8-260 | 2025-03-18 | DIN log | DIN-1178 | 8.10 | ERI011B | Code alignment | Update D0398 data items to align with BSC solution document updated for IR8.10 | BSC | EMDS |  | Code update required | PYYY
M8-261 | 2025-03-18 | DIN log | DIN-1178 | 8.10 | ERI011B | Code alignment | Update D0399 data items to align with BSC solution document updated for IR8.10 | BSC | EMDS |  | Code update required | PYYY
M8-262 | 2025-03-18 | DIN log | DIN-1178 | 8.10 | ERI011B | Code alignment | Update D0400 data items to align with BSC solution document updated for IR8.10 | BSC | EMDS |  | Code update required | PYYY
M8-263 | 2025-03-18 | DIN log | DIN-1178 | 8.10 | ERI011B | Code alignment | Update D0401 data items to align with BSC solution document updated for IR8.10 | BSC | EMDS |  | Code update required | PYYY
M8-264 | 2025-03-18 | DIN log | DIN-1178 | 8.10 | ERI011B | Code alignment | Update D0402 data items to align with BSC solution document updated for IR8.10 | BSC | EMDS |  | Code update required | PYYY
M8-265 | 2025-03-18 | DIN log | DIN-1178 | 8.10 | ERI011B | Code alignment | Update D0403 data items to align with BSC solution document updated for IR8.10 | BSC | EMDS |  | Code update required | PYYY
M8-266 | 2025-03-18 | DIN log | DIN-1178 | 8.10 | ERI011B | Code alignment | Update D0404 data items to align with BSC solution document updated for IR8.10 | BSC | EMDS |  | Code update required | PYYY
Please note this is a live document and will be regularly updated
'Date Logged' shows the date the item was first added to the M8 log

## Field values (hidden)
Matrix Field Values - To be agreed
Ref | Input Category | Ref | Title | Subject | Description | Additional Commentary | Code Artefact | Code | Status | Delivery owner | Delivery solution | Mechanism | PCR status | Implementation Date | Agreed imp date | Milestone | MHHSP impact | Core Code | Priority | Status
| Programme CR | [6 empty] | BSC | Design and Code update required | BSC |  | SCR | PCR required |  |  | M8 | Yes | BSCP700 series | 1 | Open
| DIN log | [6 empty] | REC | Code update required | REC |  | BAU | PCR not required |  |  | Post-M8,M10 | No | REC Interfaces | 2 | Closed
| Code only | [6 empty] | DCUSA | Code correct, Design update required | DCUSA |  |  | PCR raised |  |  | Post M11 |  | BSC Section Appendix | 3
[8 empty] | BSC, REC |  | MHHS Programme | [7 empty] | N/A | 4
[8 empty] | BSC, DCUSA |  | BSC, REC | [8 empty] | 5
[8 empty] | REC, DCUSA |  | BSC, REC, DCUSA
[8 empty] | BSC, REC, DCUSA |  | DIP Manager
DIP
BSC, DIP,
Notes | [7 empty] | REC, DIP
BSC, REC, DIP
Unique ref | Change trigger | EG DIN/CR ref | Change title | Change subject | Change Description | Additional Commentary | Code Artefact | RACI | What is impacted | Change owner/lead | Change approach | Change mechanism | Programme CR required | Proposed Deliver Date | Deliver Date | Milestone | MHHSP impact | Core Code | Priority

## Pivot
Input Category | Code owner | Code Artefact | Count of Change Ref
Code only | BSC | BSCP65 | 1
|  | BSCP703 | 2
|  | EMDS | 1
|  | Section K | 1
|  | Section S | 1
|  | Section S, Annex S-4 | 1
|  | Section X, Annex X-1 | 1
|  | SVA DC Vol 1 | 1
| BSC Total |  | 9
| DCUSA | EMDS | 1
|  | Schedule 16, paragraph 128 | 1
|  | Schedule 32, paragraphs 6.10 and 6.11 | 1
| DCUSA Total |  | 3
| REC | EES API Technical Specification | 5
|  | EES Service Definition | 2
|  | EMDS | 1
|  | Schedule 28 | 1
| REC Total |  | 9
Code only Total |  |  | 21
DIN log | BSC | BSCP702 | 1
|  | BSCP704 | 1
|  | BSCP706 | 3
|  | BSCP707 | 1
|  | BSCP707 & Appendices | 1
|  | EMDS | 22
|  | None | 2
|  | Section S, Annex S-4 | 1
| BSC Total |  | 32
| DCUSA | EMDS | 2
| DCUSA Total |  | 2
| REC | EMDS | 2
| REC Total |  | 2
DIN log Total |  |  | 36
EMDS Review | BSC | EMDS | 156
| BSC Total |  | 156
| BSC/REC | EMDS | 6
| BSC/REC Total |  | 6
| DCUSA | EMDS | 11
| DCUSA Total |  | 11
| DCUSA / BSC | EMDS | 4
| DCUSA / BSC Total |  | 4
| DCUSA/SEC | EMDS | 1
| DCUSA/SEC Total |  | 1
| Multiple | EMDS | 1
| Multiple Total |  | 1
| REC | EMDS | 28
| REC Total |  | 28
EMDS Review Total |  |  | 207
Programme CR | DIP | DIP Rules | 1
| DIP Total |  | 1
| REC | ERDS Service Definition | 1
| REC Total |  | 1
Programme CR Total |  |  | 2
(blank) | (blank) | (blank)
(blank) Total
(blank) Total
Grand Total |  |  | 266

## Process (hidden)
M8 Workoff process - to be agreed
| Step | Activity
| 1 | Code change identified
| 2 | Code change added to Post - M6 Work off matrix
| 3 | Code triage committee convenes
| 4 | Code triage committee assesses change and updates control
| 5 | Code changes batched into change vehicles
| 6 | Target delivery date proposed
| 7 | Target delivery date agreed
| 8 | Publish/update the control
| 9 | *Progress to agreed change mechanisum
| * | Pre-M8 Code changes delivery via SCR/BAU Modification CP. Post-M10 change process to be defined