Draft MHHS M8 Timeline

Activity					Date			Alternative date

CDWG 					13 May			10 June

CCAG					28 May			25 June

Ofgem direction			04 June			03 July

Submit change report			04 June			03 July

Panel meeting 				18 June			11 July (ex Com)

Panel meeting (Change Report)	16 July			25 Jul (ex-com)

Vote					18Jul- 08Aug		29Jul-12Sep

Change declaration			12 August		14 August

Ofgem decision			05 September		05 September

M8 go live				22 September		22 September

Outstanding actions

Review by the DCUSA Panel (April 2025)

Ofgem review of change proposal and development of SCR direction

SCR direction timeline depends on when we propose to submit DCP (Prefer June)

Currently DCUSA change proposal aligns with EMDS v1.2. EDMS v1.3 expected at the end of April with no impact on DCUSA. DIN log doesn’t identify code impact.