## Sheet1
Change Ref | Input Category | Subject | CCAG slide Description | Expected EMDS Description | Code Artefact | DCUSA review of EMDS v1.4 first pass | DCUSA review of EMDS v1.4 post feedback | DCUSA review of EMDS v1.4 second pass
M8-295 | REP-900 | Code Correction | Distributor Registered Number: ECS Data Catalogue mismatch - Align to REP Tab | Amend DI20313 - Distributor Registered Number This should be a string to cater for Scottish version | EMDS v1.4 | match | match | match
M8-296 | REP-900 | Code Correction | Distributor Registered Address: ECS Data Catalogue mismatch - Align to REP Tab Add Population Notes as data Item Rule | Amend DI20314 - Distributor Registered Address Line 1: MHHS Nullable from Mandatory no nulls to Mandatory Nullable; and MHHS DataType reference from DT-001 to DT-001N Add to Data item Notes "an address is mandatory but all lines may not be populated" | EMDS v1.4 | MHHS Nullable - should this be Mandatory Nullable instead of Mandatory No Nulls to align with other address lines e.g. Distributor Billing Address Line 1 as agreed match not added - is this not required if we move to Mandatory Nullable, if not please add as agreed | Agreed to amend MHHS Nullable field Match Placed in REP-900 message under Data Item Rule rather than in the Data Item itself even though there is only one use of this Data Item so cannot see any reason not to place it under the Data Item itself. In addition, the address and its format will not change irrespective of whether it is used in multiple messages. | match Match All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. Personally I don’t think this change was needed since Mandatory Nullable covers this. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live
M8-296 | REP-900 | Code Correction |  | Amend DI20315 - Distributor Registered Address Line 2 MHHS Nullable from Mandatory no nulls to Mandatory Nullable; and MHHS DataType reference from DT-001 to DT-001N | EMDS v1.4 | see address line 1 Match | Agreed to amend MHHS Nullable field | match
M8-296 | REP-900 | Code Correction |  | Amend DI20316 - Distributor Registered Address Line 3 MHHS Nullable from Mandatory no nulls to Mandatory Nullable; and MHHS DataType reference from DT-001 to DT-001N | EMDS v1.4 | see address line 1 Match | Agreed to amend MHHS Nullable field | match
M8-296 | REP-900 | Code Correction |  | Amend DI20317 - Distributor Registered Address Line 4 MHHS Nullable from Mandatory no nulls to Mandatory Nullable; and MHHS DataType reference from DT-001 to DT-001N | EMDS v1.4 | see address line 1 Match | Agreed to amend MHHS Nullable field | match
M8-296 | REP-900 | Code Correction |  | Amend DI20318 - Distributor Registered Address Line 5 MHHS Nullable from Mandatory no nulls to Mandatory Nullable; and MHHS DataType reference from DT-001 to DT-001N | EMDS v1.4 | see address line 1 Match | Agreed to amend MHHS Nullable field | match
M8-296 | REP-900 | Code Correction |  | Amend DI20319 - Distributor Registered Address Line 6 MHHS Nullable from Mandatory no nulls to Mandatory Nullable; and MHHS DataType reference from DT-001 to DT-001N | EMDS v1.4 | see address line 1 Match | Agreed to amend MHHS Nullable field | match
M8-296 | REP-900 | Code Correction |  | Amend DI20320 - Distributor Registered Address Line 7 MHHS Nullable from Mandatory no nulls to Mandatory Nullable; and MHHS DataType reference from DT-001 to DT-001N | EMDS v1.4 | see address line 1 Match | Agreed to amend MHHS Nullable field | match
M8-296 | REP-900 | Code Correction |  | Amend DI20321 - Distributor Registered Address Line 8 MHHS Nullable from Mandatory no nulls to Mandatory Nullable; and MHHS DataType reference from DT-001 to DT-001N | EMDS v1.4 | see address line 1 Match | Agreed to amend MHHS Nullable field | match
M8-296 | REP-900 | Code Correction |  | Amend DI20322 - Distributor Registered Address Line 9 MHHS Nullable from Mandatory no nulls to Mandatory Nullable; and MHHS DataType reference from DT-001 to DT-001N | EMDS v1.4 | see address line 1 Match | Agreed to amend MHHS Nullable field | match
M8-297 | REP-900 | Code Correction | Distributor Billing Address address line 1: ECS Data Catalogue mismatch Add Population Notes as data Item Rule | Amend DI20327 - Distributor Billing Address Line 1 Add to Data Item Notes "an address is mandatory but all lines may not be populated" | EMDS v1.4 | not added - is this not required because it says Mandatory Nullable, if not please add as agreed | Placed in REP-900 message under Data Item Rule rather than in the Data Item itself even though there is only one use of this Data Item so cannot see any reason not to place it under the Data Item itself. In addition, the address and its format will not change irrespective of whether it is used in multiple messages. | All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. Personally I don’t think this change was needed since Mandatory Nullable covers this. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live.
M8-298 | REP-900 | Code Correction | Distributor Bank Sort Code22/05/2025 ECS Data Catalogue mismatch - Align to REP Tab | Amend DI20337 - Distributor Bank Sort Code Physical Length from 8 to 6 | EMDS v1.4 | match |  | match
M8-299 | REP-900 | Code Correction | LDSO Billing Supplier Bill address line 1: ECS Data Catalogue mismatch Add Population Notes as data Item Rule | Amend DI20344 - LDSO Billing Supplier Bill-To Address Line 1 Add to Data Item Notes "an address is mandatory but all lines may not be populated" | EMDS v1.4 | not added - is this not required because it says Mandatory Nullable, if not please add as agreed | Placed in REP-900 message under Data Item Rule rather than in the Data Item itself even though there is only one use of this Data Item so cannot see any reason not to place it under the Data Item itself. In addtion, the address and its format will not change irrespective of whether it is used in multiple messages. | All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. Personally I don’t think this change was needed since Mandatory Nullable covers this. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live
M8-300 | REP-900 | Code Correction | LDSO Billing Site ID: ECS Data Catalogue mismatch - Align to REP Tab Add Population Notes as data Item Rule | Amend DI20355 - LDSO Billing Site ID Data Type Replace "number" with "string"; and Add to Data Item notes "Site reference of billing account" | EMDS v1.4 | Match Not added | Placed in REP-900 message under Data Item Rule rather than in the Data Item itself even though there is only one use of this Data Item so cannot see any reason not to place it under the Data Item itself. | Match All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live
M8-301 | REP-900 | Code Correction | List of MPANS on site: Add Population Notes as data Item Rule | Amend DI20356 - List of MPANS on site Add to Data Items Notes add "list of MPANs each separated by a space (=14 String each)" | EMDS v1.4 | Not added | Placed in REP-900 message under Data Item Rule but there is only one use of this data item so cannot see any reason not to place it under the Data Item | All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live
M8-302 | REP-900 | Code Correction | LDSO Billing Site Capacity Add Population Notes as data Item Rule (with correct spelling) | Amend DI20358 - LDSO Billing Site Capacity Add to Data Item Notes "The total capacity of the site which may differ from the billed capacity" (for information this also corrects a spelling error relating to the missing c in 'c' in capacity) | EMDS v1.4 | Not added | Placed in REP-900 message under Data Item Rule but there is only one use of this data item so cannot see any reason not to place it under the Data Item | All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live
M8-303 | REP-900 | Code Correction | LDSO Billing Site Address Line 1: ECS Data Catalogue mismatch Add Population Notes as data Item Rule | Amend DI20359 - LDSO Billing Site Address Line 1 Add to Data Item Notes "an address is mandatory but all lines may not be populated" | EMDS v1.4 | not added - is this not required because it says Mandatory Nullable, if not please add as agreed | Placed in REP-900 message under Data Item Rule rather than in the Data Item itself even though there is only one use of this Data Item so cannot see any reason not to place it under the Data Item itself. In addtion, the address and its format will not change irrespective of whether it is used in multiple messages. | All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. Personally I don’t think this change was needed since Mandatory Nullable covers this. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live.
M8-304 | REP-900 | Code Correction | LDSO Billing Invoice Type Add Population Notes as data Item Rule - Not adding an enumeration rule at this stage DCUSA could progress a post M10 change. | Amend DI20369 - LDSO Billing Invoice Type Add to Data Item Notes "Site Specific DUoS" We understand this the spellling of "Specifc" was raised at testing due to the missing "i" but it is what is in the SWAGGER and should retained and only updated once this has been amended by the Programme. | EMDS v1.4 | Not added | Placed in REP-900 message under Data Item Rule but there is only one use of this data item so cannot see any reason not to place it under the Data Item | All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live
M8-305 | REP-900 | Code Correction | Site-Specific DUoS Invoice Type: Add Data Item Population Note - not adding enumerations at this stage. DCUSA could progress a post M10 change | Amend DI20374 - Site-Specific DUoS Invoice Type add to Data items notes "New= New, Can= Cancellation, Reb= Rebill" | EMDS v1.4 | Not added | Placed in REP-900 message under Data Item Rule but there is only one use of this data item so cannot see any reason not to place it under the Data Item | All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live
M8-306 | REP-900 | Code Correction | Maximum Demand (in the) Invoice Period: Add Population Notes as data Item Rule | Amend DI20379 - Maximum Demand (in the) Invoice Period Add to Data Item Notes "kVA, Set to zero if zero or Null consumption" | EMDS v1.4 | Not added | Placed in REP-900 message under Data Item Rule but there is only one use of this data item so cannot see any reason not to place it under the Data Item | All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live
M8-307 | REP-900 | Code Correction | Maximum Demand (in the) Invoice Period Date Time: Add Population Notes as data Item Rule | Amend DI20380 - Maximum Demand (in the) Invoice Period Date Time add to Data Item Notes "YYYY-MM-DD HH:MM (time is the start time of the relevant HH), Set to first HH in billing period if MD = 0." | EMDS v1.4 | Not added | Placed in REP-900 message under Data Item Rule but there is only one use of this data item so cannot see any reason not to place it under the Data Item | All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live
M8-308 | REP-900 | Code Correction | Charge Type: ECS Data Catalogue mismatch align to REP tab Add Population Notes as data Item Rule not adding enumerations at this stage. DCUSA could progress a post M10 change | Amend DI20384 - Charge Type add to Data Item Notes "Values = FIXED, CAPAC, XSCAP, REACT, RED, AMBER, GREEN, YELLO, BLACK, SUPER, ZERO" | EMDS v1.4 | Not added | Placed in REP-900 message under Data Item Rule but there is only one use of this data item so cannot see any reason not to place it under the Data Item | All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live
M8-309 | REP-900 | Code Correction | Number of Days Billed: ECS Data Catalogue mismatch align to REP tab Add Population Notes as data Item Rule | Amend DI20385 - Number of Days Billed Physical length replace "15" with "2". Add to Data Item Notes "Number of days in billing period up to 31 days" | EMDS v1.4 | Match Not added | Placed in REP-900 message under Data Item Rule but there is only one use of this data item so cannot see any reason not to place it under the Data Item | Match All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live
M8-310 | REP-900 | Code Correction | Quantity: Add Population Notes as data Item Rule | Amend DI20386 - Quantity Add to Data Item notes "If Charge type =CAPAC or XSCAP, shows a capacity value" | EMDS v1.4 | Not added | Placed in REP-900 message under Data Item Rule but there is only one use of this data item so cannot see any reason not to place it under the Data Item | All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live
M8-311 | REP-900 | Code Correction | VAT Rate Code Add Population Notes as data Item Rule not adding enumerations at this stage. DCUSA could progress a post M10 change | Amend DI20389 - VAT Rate Code Physical Length replace "5" with "1" Add to Data items Notes "E = exempt, S= standard rate, Z = zero rate, N = not applicable" | EMDS v1.4 | Match not added | Placed in REP-900 message under Data Item Rule but there is only one use of this data item so cannot see any reason not to place it under the Data Item | Match All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live
M8-312 | REP-901 | Code Correction | Charge Band Add Population Notes as data Item Rule not adding enumerations at this stage. DCUSA could progress a post M10 change | Amend DI20393 - Charge Band Add to Data items Notes "Has values red, amber, green, black, yellow" | EMDS v1.4 | Not added | Placed in REP-901 message under Data Item Rule but there is only one use of this data item so cannot see any reason not to place it under the Data Item | All agreed notes placed in REP900 and matches ECS Reports rather than in the specific Data Item. RTS have stated to amend in line with our suggestion may impact M8 go live because the changes may not be ready for DCUSA Panel Paper day. Also requested Programme approval to progress with an initial reaction not to support any changes that impact or increase the risk of M8 go live