## CPs
| CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Current Status | Status Changed in the last month | Date Issued to Ofgem | Original Expected Decision Date | Latest Expected Decision Date
STATUS - INITIAL ASSESSMENT
N/A
STATUS - DEFINITION
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | The intent of this modification is to define “Mixed Demand” Sites and apply a proportionate Residual charge where a Site meets the mixed demand definition. | General | 1 | John Lawton / Andy Green | Andrew Malley | 14/04/2021 | 17 | Yes - See comments in status column | TBC | The Working Group met on 02 October to review the need for a BSC change. It was agreed that a BSC change was required and that DCP 388 couldn’t be progressed until the BSC modification had been defined so DCP 388 has been paused until the Proposer raises the required BSC modification.
DCP 415 | Replacement of D0242/D0315 for MHHS | To create a new DCUSA owned DIP data message for supercustomer billing statements using MHHS data. | Billing | 2 | Hannah Proffitt / Craig Booth | N/A | 10/22/2022 | 3 | Yes - See comments in status column | TBC (dependent on date required for DIP testing) | The Change Report was submitted to the Panel for review in the February 2023 Panel meeting. The Panel agreed that it would not progress to Party voting and that it should be sent back to the Working Group but that the Working Group won’t need to meet until the MHHS Programme have been able to carry out an Impact Assessment for the solution they developed. It was noted that even then, no further work may be required but that it was too early to know that for sure. | DEFINITION
DCP 416 | Electronic Invoicing Post MHHS | To create a new DCUSA owned DIP data message for electronic Distributor billing post MHHS. | Billing | 2 | Melissa Kendal / Andy Green | N/A | 2022-11-14 | 5 | Yes - See comments in status column | TBC (dependent on date required for DIP testing) | The Working Group have reviewed the consultation responses and met on 23 June 2023 to finalise the conclusions to the second consultation. A decision on whether or not a Change Report is to be produced is to be made by the Panel but the Proposer has initated a MHHS Change Request for the CP to be impact assessed and so it is expected that DCP 416 will be put on hold, pending outcome of the MHHS Change Request. | DEFINITION
DCP 419 | Pre-Notifications of Planned Supply De-Energisations | This change seeks to ensure that all DCUSA Parties, that de-energise metering equipment as part of any planned work, provide the Distributor with advance notification of the supply interruption. | General | 1 | Alysson Pena / Richard Colwill | TBC | 2023-03-06 | 15 | No | Next scheduled release following approval | DCP 419 is likely to be withdrawn with a REC change progressing separately. | DEFINITION
DCP 420 | Provide targeted relief from residual charges for electric vehicle charging sites | The intent of this Change Proposal is to provide targeted relief from residual charges to publicly accessible electric vehicle (“EV”) charging sites. This may be a temporary fix to be put in place until the charging stations included are commercially viable. | General | 1 | Craig Booth / Richard Colwill | Thomas Holderness | 2023-03-29 | 18 | Yes - See comments in status column | TBC | The DCP 420 Working Group issued two RFIs, one to EV Charge Point Operators and one to DNOs and IDNOs. A good response to both RFIs was received with good engagement from DNOs and IDNOs in obtaining the necessary data. The data is to be used to perform an impact assessment and requires a "market share" figure for the responding EV CPOs, so that the national impact can be estimated, however we have encountered some challenges in obtaining this data. The Department for Transport initially suggested it would be able to help in this regard, however it has since advised DCUSA that its contract with the data provider prohibits it from sharing the raw data. DCUSA has since engaged with the data owner, ZapMap, however the dataset in question is a commercial dataset and will required funding. A paper will be presented to the Board relating to this (and to DCP 454). | DEFINITION
DCP 423 | LDNO Discounts for negative scaling | The purpose of this change proposal is to set a floor on the LDNO discount applied to negative tariff components, after scaling, for demand tariffs. The intent of this change proposal is to seek to remedy what the proposer believes is an unintended outcome of the implementation of Ofgem’s Targeted Charging Review where LDNO tariffs can be higher than the equivalent all-the-way tariff i.e. the LDNO margin is negative for that component. | CDCM | 1 | Melissa Kendal / Andy Green | TBC | 2023-05-09 | 7 | No | 2026-04-01 | The proposer has requested that this isn't withdrawn yet due to an Ofgem consultation on debt relief. This consultation is expected to deliver results in April and the proposer has advised that if the solution doesn’t involve network charge recovery of the debt, then they would be happy to withdraw the CP | DEFINITION
DCP 424 | Use of System charging for complex sites | This change proposal enables the correct DUoS to be paid by meters that are class F or G within a Class 5 or Class 6 Complex Site as described in BSC Modification P441 (where netting of Import and Export takes place for BSC Settlement purposes) in a practical manner. Under p441 where generation and demand are netted before settlement, the gross values must be added to the D0036 or D0275 to ensure the correct DUoS is charged. However, for class F and G the MPAN counts are included on the D0030 data flows but the volumes are zero. In order for the volumes to be correctly charged DUoS it is proposed that these volumes are included in the D0036 or D0275 using a pseudo MPAN for the gross value. | CDCM | 1 | Andy Green / Craig Booth | TBC | 2023-10-05 | 8 | Yes - See comments in status column | Aligned to BSC Mod P441 Implementation Date | The working group has restarted and a meeting took place on 08 August 2025 to agree the consulation document
DCP 442 | Aligning enduring flexible connections | The intent of this Change Proposal is to align (and clarify) the two approaches that currently may result in a flexible connection being provided on an enduring basis. A flexible connection on an enduring basis is an arrangement that allows a Customer’s import/export of electricity via a connection to be restricted by a DNO/IDNO Party in perpetuity. This CP proposes that such a connection shall be a Flexible Connection rather than a Curtailable Connection. | General | 1 | Melissa Kendall / Craig Booth | TBC | 2024-07-01 | 7 | Yes - See comments in status column | 2026-04-01 | The next Working Group is currently TBC - due to the Proposer's availability. Once the next meeting has been scheduled, the aim is to finalise the draft Consultation ready to issue to wider industry. | DEFINITION
DCP 443 | Excess Capacity | The purpose of this Change Proposal is to drive the correct customer behaviour regarding exceeding capacity. | CDCM / EDCM | 1 | Melissa Kendal / Andy Green | TBC | 2024-09-07 | 12 | No | 2026-01-04 | The modelling consultatnats attended the last working group to provide comments on the approach the working group were seeking to take. Next meeting to be agreed by doodle poll
DCP 452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | The intent of this Change Proposal is to correct an oversight in DCUSA which results in customers connecting directly to Grid Supply Point incorrectly facing a locational FCP charge relating to assets downstream of their connection. | EDCM | 1 | George Kestner / Dylan Townsend | Thomas Holderness | 2025-02-28 | 5 | No | 2027-04-01 | DCP 452 Working Group Meeting 09 was held on 28 August 2025, where the Working Group were provided with an update on progress of modelling and completion of Impact Assessment by DNOs, conducted a review of updated EDCM models and documentation, conducted a review of consultation document and draft legal text. It is hoped that a consultation will be issued within a week or two. | DEFINITION
DCP 454 | Provide enduring targeted relief from residual charges for electric vehicle charging sites | The intent of this CP is to provide enduring targeted relief from residual charges to publicly accessible electric vehicle (“EV”) charging sites. | CDCM | 1 | Craig Booth / Richard Colwill | Thomas Holderness | 2025-05-06 | 1 | Yes - See comments in status column | 2028-04-01 | The Working Group will need to perform an impact assessment using the same information as used by the DCP 420 Working Group. There is therefore a dependancy on obtaining the market share data under DCP 420 in order to progress this CP. | DEFINITION
DCP 458 | Amend DCP 414 process | To apply a default capacity of 71kVA following the 12 months non-applicability of capacity charging arising from DCP 414. | CDCM | 2 | Craig Booth / Andy Green | N/A | 17/07/2025 | 2 | No | 27/10/2025 | The DCP 458 consultation was issued on 18 August 2025 with a closing date of 02 September 2025 and a second Working Group meeting was held on 08/09/2025, with a third planned for 15 September. | DEFINITION | CONSULTATION
DCP 459 | DNO invoices to Embedded DNO | The intent of the Change Proposal is to require separate invoice backing data to be provided by DNO Parties when issuing invoices to EDNOs. | General | 2 | Hannah Proffitt / Andy Green | N/A | 2025-08-01 | 0 | No | 2026-02-26 | DCP 459 was presented to the DCUSA Panel for their initial assessment during their meeting on 20 August 2025. The DCUSA Panel agreed that it could be progressed to the definition phase and to be assessed by a Working Group which is in the process of being set up. |  | DEFINITION
DCP 461 | Reducing the Impact of Transmission Distribution Charges | This Change Proposal seeks to address a growing set of structural, economic, and policy misalignments that are actively hindering the UK’s energy transition. | CCCM | 1 | Melissa Kendall / Craig Booth | N/A | 2025-08-13 | 0 | No | TBC | DCP 461 was presented to the DCUSA Panel for their initial assessment during their meeting on 20 August 2025. The DCUSA Panel agreed that it could be progressed to the definition phase and to be assessed by a Working Group which is in the process of being set up. |  | DEFINITION
STATUS - CHANGE REPORT
DCP 460 | Updating Incorrect Company Names Referenced throughout the DCUSA | The intent of this CP is to ensure that any references to the company names of specific Parties within the DCUSA are correct and to explore the possibility of future proofing these against any future changes. | Standard | 2 | Dylan Townsend | N/A | 2025-08-12 | 9 | No | 2025-11-06 | DCP 460 was presented to the DCUSA Panel for their initial assessment during their meeting on 20 August 2025. The DCUSA Panel agreed that it could be progressed directly to the Change Report phase, with the caveat that should it be determined to require input from Parties post legal review, then the Panel may re-direct the Change Proposal to be assessed by a Working Group. | CHANGE REPORT | CHANGE REPORT
DCP 455 | Align RAV price-inflation with that used in ED2 | ED2 PCFM uses a combination of RPI and CPIH to uplift from 2020/21 to outturn prices. This change seeks to align the prescribed calculation of RAV in Schedule 1, to retain consistency of credit cover calculation with ED2 PCFM. | General | 2 | Hannah Proffitt / Richard Colwill | N/A | 2025-05-22 | 0 | No | 2025-12-01 | The DCP 455 consultation was issued on 08 August with a deadline of 29 August. The Working Group will meet on 01 September to review responses. | CHANGE REPORT | CHANGE REPORT
DCP 325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20. | The intent of this Change Proposal is to combine, review and if appropriate, amend the requirements of Section 35A, Section 35B, Schedule 15 and Schedule 20 to improve transparency and efficiency in the data published by DNOs | General | 2 | Richard Colwill / Melissa Kendal | N/A | 2018-07-11 | 19 | No | Next scheduled release following approval | Legal text finalised and the Change Report has been agreed. The modelling was approved by the DCUSA panel on 09 June 2025 and issued to CEPA/TNEI on the same day.
STATUS - VOTING
DCP 457 | Housekeeping Items | To fix housekeeping items 124, 125, 126, 128, 129, 130, 131. | Standard | 2 | Dylan Townsend | N/A | 2024-03-14 | 9 | No | 2026-04-01 | DCP 457 was presented to the DCUSA Panel for their initial assessment during their meeting on 17 July 2024. The DCUSA Panel agreed that DCP 457 be progressed directly to the Change Report phase. The Change Report was presented to the Panel at the Auigust meeting, where the Panel approved for it to be issued for voting on 20 August. | VOTING OPEN | VOTING OPEN
DCP 450 | Managing the effects of surplus residual charge in the CDCM | To determine the appropriate arrangements for managing the effects of large residual values in the CDCM. | CDCM | 1 | Hannah Proffitt / Craig Booth | James Harvey | 2025-02-10 | 3 | No | 2027-04-01 | The Change Report was presented to the Panel at the Auigust meeting, where the Panel approved for it to be issued for voting on 20 August. |  | VOTING OPEN
STATUS - AWAITING AUTHORITY CONSENT
DCP 412 | Allocation of banding for TCR Charges for ‘Peaky’ Final Demand Customers | The intent of this CP is to consider the residual charge for ‘peaky’ customers, removing the disproportionate impact of allocating residual charges on the basis of the Agreed Supply Capacity. | CDCM / EDCM | 1 | Craig Booth / Richard Colwill | Andrew Malley | 2022-10-11 | 39 | No | 10 Working Days following Authority Decision | The Working Group have finalised the change report and legal text and this is being tabled at the February Panel. DCP 412 was approved by the Panel during their meeting in February and subsequently issued to Parties for voting on 20 February 2025, with a deadline of 13 March 2025. A Change Declaration was issued to both Parties and Ofgem on 19 March 2025. | AWAITING AUTHORITY CONSENT |  | 2025-03-19 | TBC
DCP 446 | Emergency Disconnections | To enable distributors to charge customers covered by section 2 of the National Terms of Connection for emergency disconnections that have been caused by their act or omission. | General | 1 | Hannah Proffitt / Craig Booth | N/A | 2024-11-07 | 3 | No | Next scheduled release following approval | The Working Group has reviewed the legal text and change report both of which were subsequently submitted to the Panel in March, for their agreement for it to be progressed to the voting phase. The Change Report was approved at the March Panel and subsequently issued to Parties for voting. A Change Declaration was issued to both Parties and Ofgem on 17 April 2025. | AWAITING AUTHORITY CONSENT |  | 2025-04-17 | TBC
DCP 437 | To Shorten the DUoS Pricing Notice Periods | This change proposal aims to shorten the DUoS Pricing Notice Periods so there is longer period between the publication of the PCFM where OFGEM have the option to make changes to our allowed revenue at short notice and the setting of the prices | CDCM | 1 | Hannah Proffitt / Richard Colwill | James Harvey | 2024-02-13 | 7 | No | 1 Working Day following approval | The *Status* of DCP 437 was changed on 16 June 2025 to *Awaiting Authority Decision* following the collation/calculation of votes received and the issuing of a Change Declaration setting out the result of the Party vote. | AWAITING AUTHORITY CONSENT |  | 2025-06-16 | TBC
DCP 439 | Backdating Tariff Changes | This change proposal seeks to add a sensible backstop to backdating. | CDCM | 1 | Hannah Proffitt / Andy Green | James Harvey | 2024-03-14 | 9 | No | 2026-04-01 | The Change Report is due to be presented to the Panel at the July meeting. If approved it will be issued for voting on 17 July with a deadline of 08 August. | #REF! | AWAITING AUTHORITY CONSENT | 2025-08-12 | TBC
STATUS - AWAITING IMPLEMENTATION
2025-09-24
DCP 445 | Implementation of Market-wide Half Hourly Settlement (MHHS) Arrangements | This Change Proposal will ensure that the appropriate obligations, processes and provisions for the new MHHS arrangements, which have been developed and consulted on as part of the MHHS Programme, are introduced into the DCUSA. | General | 1 | Dylan Townsend | N/A | 2024-09-04 | N/A | No | 2025-09-22 | DCP 445 was submitted to the Panel for Initial Assessment during their September meeting. The Panel approved for DCP 445 to progress to the Change Report Phase and the Change Report was issued to the Panel during the October Panel meeting. Parties voted to appove DCP 445 and a Change Declaration that was issued to Ofgem on 08 November 2024. Ofgem's decision to approve DCP 445 was received on 26 November 2024. The implementation date for DCP 445 will be the same date as the M8 Milestone (‘Code Changes Delivered’) in the baselined MHHS Implementation Timetable which, following the Authority's approval of MHHS Programme Change Request (CR055), the M8 Milestone is now set for 24/09/2025. | AWAITING IMPLEMENTATION
DCP 456 | MHHS Incremental Changes for Go Live | MHHS Programme changes affecting DCUSA that have been identified post M6 (catered for by DCP445) and required by M8 (code implementation date). | General | 1 | Melissa Kendall | N/A | 2025-04-06 | N/A | No | 22/09/2025 | DCP 456 was submitted to the Panel for Initial Assessment during their June 2025 meeting. The Panel approved for DCP 456 to progress to the Change Report Phase and the Change Report is being issued to the Panel for approval to be issued for voting during the July 2025 Panel meeting. Following the Party Voting period, aChange Declaration was issued to Ofgem and then on 29 August 2025, Ofgem issued their decision to approve DCP 456. |  | AWAITING IMPLEMENTATION
2027-04-01
DCP 440 | Consuming “de-energised” sites | To ensure all consuming “de-energised” sites are charged DUoS. | CDCM | 1 | Hannah Proffitt / Andy Green | Shaun McRaith | 2024-03-14 | 10 | No | 2027-04-01 | The *Status* of DCP 440 was changed on 17 June 2025 to *Awaiting Authority Decision* following the collation/calculation of votes received and the issuing of a Change Declaration setting out the result of the Party vote. On 29 August 2025, Ofgem issued their decision to approve DCP 456. |  | AWAITING IMPLEMENTATION
STATUS - SENT BACK
N/A | N/A | [7 empty] | No
STATUS - IMPLEMENTED
N/A | N/A | [7 empty] | No
STATUS - REJECTED
N/A | N/A | [7 empty] | No
STATUS - WITHDRAWN
N/A | N/A | [7 empty] | No
Change Register - September 2025

## Status Changes
[14 empty] | AWAITING IMPLEMENTATION | 1
[14 empty] | IMPLEMENTED | 0
[14 empty] | REJECTED | 0
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status | Status Changed in the last month | DEFINITION | 9
DCP 458 | Amend DCP 414 process | To apply a default capacity of 71kVA following the 12 months non-applicability of capacity charging arising from DCP 414. | CDCM | 2 | Craig Booth / Andy Green | N/A | 17/07/2025 | 2 | No | 27/10/2025 | The DCP 458 consultation was issued on 18 August 2025 with a closing date of 02 September 2025 and a second Working Group meeting was held on 08/09/2025, with a third planned for 15 September. | DEFINITION | CONSULTATION
DCP 459 | DNO invoices to Embedded DNO | The intent of the Change Proposal is to require separate invoice backing data to be provided by DNO Parties when issuing invoices to EDNOs. | General | 2 | Hannah Proffitt / Andy Green | N/A | 2025-08-01 | 0 | No | 46079 | DCP 459 was presented to the DCUSA Panel for their initial assessment during their meeting on 20 August 2025. The DCUSA Panel agreed that it could be progressed to the definition phase and to be assessed by a Working Group which is in the process of being set up. | 0 | DEFINITION
DCP 461 | Reducing the Impact of Transmission Distribution Charges | This Change Proposal seeks to address a growing set of structural, economic, and policy misalignments that are actively hindering the UK’s energy transition. | CCCM | 1 | Melissa Kendall / Craig Booth | N/A | 2025-08-13 | 0 | No | TBC | DCP 461 was presented to the DCUSA Panel for their initial assessment during their meeting on 20 August 2025. The DCUSA Panel agreed that it could be progressed to the definition phase and to be assessed by a Working Group which is in the process of being set up. | 0 | DEFINITION
DCP 460 | Updating Incorrect Company Names Referenced throughout the DCUSA | The intent of this CP is to ensure that any references to the company names of specific Parties within the DCUSA are correct and to explore the possibility of future proofing these against any future changes. | Standard | 2 | Dylan Townsend | N/A | 2025-08-12 | 9 | No | 45967 | DCP 460 was presented to the DCUSA Panel for their initial assessment during their meeting on 20 August 2025. The DCUSA Panel agreed that it could be progressed directly to the Change Report phase, with the caveat that should it be determined to require input from Parties post legal review, then the Panel may re-direct the Change Proposal to be assessed by a Working Group. | CHANGE REPORT | CHANGE REPORT
DCP 455 | Align RAV price-inflation with that used in ED2 | ED2 PCFM uses a combination of RPI and CPIH to uplift from 2020/21 to outturn prices. This change seeks to align the prescribed calculation of RAV in Schedule 1, to retain consistency of credit cover calculation with ED2 PCFM. | General | 2 | Hannah Proffitt / Richard Colwill | N/A | 2025-05-22 | 0 | No | 2025-12-01 | The DCP 455 consultation was issued on 08 August with a deadline of 29 August. The Working Group will meet on 01 September to review responses. | CHANGE REPORT | CHANGE REPORT
DCP 457 | Housekeeping Items | To fix housekeeping items 124, 125, 126, 128, 129, 130, 131. | Standard | 2 | Dylan Townsend | N/A | 2024-03-14 | 9 | No | 46113 | DCP 457 was presented to the DCUSA Panel for their initial assessment during their meeting on 17 July 2024. The DCUSA Panel agreed that DCP 457 be progressed directly to the Change Report phase. The Change Report was presented to the Panel at the Auigust meeting, where the Panel approved for it to be issued for voting on 20 August. | VOTING OPEN | VOTING OPEN
DCP 450 | Managing the effects of surplus residual charge in the CDCM | To determine the appropriate arrangements for managing the effects of large residual values in the CDCM. | CDCM | 1 | Hannah Proffitt / Craig Booth | James Harvey | 2025-02-10 | 3 | No | 46478 | The Change Report was presented to the Panel at the Auigust meeting, where the Panel approved for it to be issued for voting on 20 August. | 0 | VOTING OPEN
DCP 439 | Backdating Tariff Changes | This change proposal seeks to add a sensible backstop to backdating. | CDCM | 1 | Hannah Proffitt / Andy Green | James Harvey | 2024-03-14 | 9 | No | 46113 | The Change Report is due to be presented to the Panel at the July meeting. If approved it will be issued for voting on 17 July with a deadline of 08 August. | #REF! | AWAITING AUTHORITY CONSENT
DCP 456 | MHHS Incremental Changes for Go Live | MHHS Programme changes affecting DCUSA that have been identified post M6 (catered for by DCP445) and required by M8 (code implementation date). | General | 1 | Melissa Kendall | N/A | 2025-04-06 | N/A | No | 22/09/2025 | DCP 456 was submitted to the Panel for Initial Assessment during their June 2025 meeting. The Panel approved for DCP 456 to progress to the Change Report Phase and the Change Report is being issued to the Panel for approval to be issued for voting during the July 2025 Panel meeting. Following the Party Voting period, aChange Declaration was issued to Ofgem and then on 29 August 2025, Ofgem issued their decision to approve DCP 456. | 0 | AWAITING IMPLEMENTATION
DCP 440 | Consuming “de-energised” sites | To ensure all consuming “de-energised” sites are charged DUoS. | CDCM | 1 | Hannah Proffitt / Andy Green | Shaun McRaith | 2024-03-14 | 10 | No | 46478 | The *Status* of DCP 440 was changed on 17 June 2025 to *Awaiting Authority Decision* following the collation/calculation of votes received and the issuing of a Change Declaration setting out the result of the Party vote. On 29 August 2025, Ofgem issued their decision to approve DCP 456. | 0 | AWAITING IMPLEMENTATION
Status Change - September 2025

## Timetables
DCP | Title | Part 1/ Part 2 Matter | Timetable Change | Sept | Oct | Nov | Dec | Jan | Feb
461 | Reducing the Impact of Transmission Distribution Charges | Part 1 | B | DEF | DEF | CON | DEF | DEF | CR
459 | DNO invoices to Embedded DNO | Part 1 | N | DEF | CON | DEF | CR
458 | Amend DCP 414 process | Part 2 | N | Sept: DEF; Oct: CR
455 | Align RAV price-inflation with that used in ED2 | Part 2 | N | bar: Sept
454 | Provide enduring targeted relief from residual charges for electric vehicle charging sites | Part 1 | N | DEF | CON | DEF | CR
452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | Part 1 | N | Sept: DEF; Oct: CR
443 | Excess Capacity | Part 1 | N | Sept: CON; Oct: DEF; Nov: CR
442 | Aligning enduring flexible connections | Part 1 | N | Sept: O/H
424 | Use of System charging for complex sites | Part 1 | N | Sept: O/H
423 | LDNO Discounts for negative scaling | Part 1 | N | Sept: O/H
420 | Include Car Charging Stations In The Definition For Non Final Demand | Part 1 | N | DEF | CON | DEF | CR
419 | Pre-notification of Planned Supply De-energisations | Part 1 | N | Sept: On hold
416 | Electronic Invoicing Post MHHS | Part 2 | N | Sept: O/H
415 | Replacement of D0242/D0315 for MHHS | Part 2 | N | Sept: O/H
388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | Part 1 | N | Sept: O/H
325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20 | Part 2 | Y | bar: Sept
| DEFINITION | DEF
| RFI | RFI
| CONSULTATION | CON/ CON 2
| CHANGE REPORT | CR
| ON HOLD | O/H

## Legal Text Overlap Tracker
YES
|  | MHHS | DCP 424 | DCP 325 | DCP 423 | DCP 388 | DCP 412 | DCP 420 | DCP 439 | DCP 440 | DCP 443
|  | 2025-09-25 | TBC | Next Scheduled | 2025-04-01 | TBC | TBC | 2025-04-01 | 2025-04-01 | 2026-04-01 | TBC |  | NOTES TO ASSIST
Schedules | Paragraph Number | Awaiting Implementation | On Hold | Change Report | Definition | On Hold | Awaiting Consent | Definition | Sent Back | Voting | Definition | Number of CPs Impacting Paragraph
Schedule 15 | Table 1 |  |  | YES | [7 empty] | 1 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 2 |  |  | YES | [7 empty] | 1 | The WGs for DCP 325 and DCP 421 are aware of the interactions
Schedule 15 | Table 3 |  |  | YES | [7 empty] | 1 | The WGs for DCP 325 and DCP 421 are aware of the interactions
0
Schedule 16 | Introduction | [10 empty] | 0
Schedule 16 | 1 | [10 empty] | 0
Schedule 16 | 2 | [10 empty] | 0
Schedule 16 | 3 | [10 empty] | 0 | Model reference number and date
Schedule 16 | 4 | [10 empty] | 0
Schedule 16 | 5 | [10 empty] | 0
Schedule 16 | 6 | [10 empty] | 0
Schedule 16 | 7 | [10 empty] | 0
Schedule 16 | 7A | [10 empty] | 0
Schedule 16 | 8 | [10 empty] | 0
Schedule 16 | 9 | [10 empty] | 0
Schedule 16 | 10 | [10 empty] | 0
Schedule 16 | 10A | [10 empty] | 0
Schedule 16 | 11 | [10 empty] | 0
Schedule 16 | 12 | [10 empty] | 0
Schedule 16 | 13 | [10 empty] | 0
Schedule 16 | 14 | [10 empty] | 0
Schedule 16 | 15 | [10 empty] | 0
Schedule 16 | 16 | [10 empty] | 0
Schedule 16 | 17 | [10 empty] | 0
Schedule 16 | 18 | [10 empty] | 0
Schedule 16 | 19 | [10 empty] | 0
Schedule 16 | 20 | [10 empty] | 0
Schedule 16 | 21 | [10 empty] | 0
Schedule 16 | 22 | [10 empty] | 0
Schedule 16 | 23 | [10 empty] | 0
Schedule 16 | 24 | [10 empty] | 0
Schedule 16 | 25 | [10 empty] | 0
Schedule 16 | 26 | [10 empty] | 0
Schedule 16 | 27 | [10 empty] | 0
Schedule 16 | 28 | [10 empty] | 0
Schedule 16 | 29 | [10 empty] | 0
Schedule 16 | 30 | [10 empty] | 0
Schedule 16 | 31 | [10 empty] | 0
Schedule 16 | 32 | [10 empty] | 0
Schedule 16 | 33 | [10 empty] | 0
Schedule 16 | 34 | [10 empty] | 0
Schedule 16 | 35 | [10 empty] | 0
Schedule 16 | 36 | [10 empty] | 0
Schedule 16 | 37 | [10 empty] | 0
Schedule 16 | 38 | [10 empty] | 0
Schedule 16 | 39 | [10 empty] | 0
Schedule 16 | 40 | [10 empty] | 0
Schedule 16 | 41 | [10 empty] | 0
Schedule 16 | 41A | [10 empty] | 0
Schedule 16 | 41B | [10 empty] | 0
Schedule 16 | 42 | [10 empty] | 0
Schedule 16 | 42A | YES | [9 empty] | 1
Schedule 16 | 43 | [10 empty] | 0
Schedule 16 | 44 | YES | [9 empty] | 1
Schedule 16 | 45 | [10 empty] | 0
Schedule 16 | 46 | [10 empty] | 0
Schedule 16 | 47 | [10 empty] | 0
Schedule 16 | 48 | [10 empty] | 0
Schedule 16 | 49 | [10 empty] | 0
Schedule 16 | 50 | [10 empty] | 0
Schedule 16 | 51 | [10 empty] | 0
Schedule 16 | 52 | [10 empty] | 0
Schedule 16 | 52A | [10 empty] | 0
Schedule 16 | 53 | [10 empty] | 0
Schedule 16 | 54 | [10 empty] | 0
Schedule 16 | 55 | [10 empty] | 0
Schedule 16 | 56 | [10 empty] | 0
Schedule 16 | 57 | [10 empty] | 0
Schedule 16 | 58 | [10 empty] | 0
Schedule 16 | 59 | [10 empty] | 0
Schedule 16 | 60 | [10 empty] | 0
Schedule 16 | 61 | [10 empty] | 0
Schedule 16 | 62 | [10 empty] | 0
Schedule 16 | 63 | [10 empty] | 0
Schedule 16 | 64 | [10 empty] | 0
Schedule 16 | 65 | [10 empty] | 0
Schedule 16 | 66 | [10 empty] | 0
Schedule 16 | 67 | [10 empty] | 0
Schedule 16 | 68 | [10 empty] | 0
Schedule 16 | 69 | [10 empty] | 0
Schedule 16 | 70 | YES | [9 empty] | 1
Schedule 16 | 71 | [10 empty] | 0
Schedule 16 | 72 | [10 empty] | 0
Schedule 16 | 72A | [10 empty] | 0
Schedule 16 | 73 | [10 empty] | 0
Schedule 16 | 74 | [10 empty] | 0
Schedule 16 | 75 | [10 empty] | 0
Schedule 16 | 76 | [10 empty] | 0
Schedule 16 | 77 | [10 empty] | 0
Schedule 16 | 78 | [10 empty] | 0
Schedule 16 | 79 | [10 empty] | 0
Schedule 16 | 80 | YES | [9 empty] | 1
Schedule 16 | 81 | [10 empty] | 0
Schedule 16 | 82 | [10 empty] | 0
Schedule 16 | 83 | [10 empty] | 0
Schedule 16 | 84 | [10 empty] | 0
Schedule 16 | 85 | [10 empty] | 0
Schedule 16 | 86 | [10 empty] | 0
Schedule 16 | 87 | [10 empty] | 0
Schedule 16 | 88 | [10 empty] | 0
Schedule 16 | 89 | [10 empty] | 0
Schedule 16 | 90 | [10 empty] | 0
Schedule 16 | 91 | [10 empty] | 0
Schedule 16 | 92 | [10 empty] | 0
Schedule 16 | 92A | [10 empty] | 0
Schedule 16 | 92B | [10 empty] | 0
Schedule 16 | 92C | [10 empty] | 0
Schedule 16 | 93 | [10 empty] | 0
Schedule 16 | 94 | [10 empty] | 0
Schedule 16 | 95 | [10 empty] | 0
Schedule 16 | 96 | [10 empty] | 0
Schedule 16 | 97 | [10 empty] | 0
Schedule 16 | 98 |  |  |  | YES | [6 empty] | 1
Schedule 16 | 99 | [10 empty] | 0
Schedule 16 | 100 | [10 empty] | 0
Schedule 16 | 101 | [10 empty] | 0
Schedule 16 | 102 | [10 empty] | 0
Schedule 16 | 102A | [10 empty] | 0
Schedule 16 | 102B | [10 empty] | 0
Schedule 16 | 103 | [10 empty] | 0
Schedule 16 | 104 | [10 empty] | 0
Schedule 16 | 105 | [10 empty] | 0
Schedule 16 | 106 | [10 empty] | 0
Schedule 16 | 107 | [10 empty] | 0
Schedule 16 | 108 | [10 empty] | 0
Schedule 16 | 108A | [10 empty] | 0
Schedule 16 | 109 | [10 empty] | 0
Schedule 16 | 110 | [10 empty] | 0
Schedule 16 | 111 | [10 empty] | 0
Schedule 16 | 112 | [10 empty] | 0
Schedule 16 | 112A | [10 empty] | 0
Schedule 16 | 113 | [10 empty] | 0
Schedule 16 | 113A | [10 empty] | 0
Schedule 16 | 113B | [10 empty] | 0
Schedule 16 | 113C | [10 empty] | 0
Schedule 16 | 113D | [10 empty] | 0
Schedule 16 | 113E | [10 empty] | 0
Schedule 16 | 114 | [10 empty] | 0
Schedule 16 | 115 | [10 empty] | 0
Schedule 16 | 116 | [10 empty] | 0
Schedule 16 | 117 | [10 empty] | 0
Schedule 16 | 118 | [10 empty] | 0
Schedule 16 | 119 | [10 empty] | 0
Schedule 16 | 120 | [10 empty] | 0
Schedule 16 | 121 | [10 empty] | 0
Schedule 16 | 122 | [10 empty] | 0
Schedule 16 | 123 | [10 empty] | 0
Schedule 16 | 124 | [10 empty] | 0
Schedule 16 | 125 | [10 empty] | 0
Schedule 16 | 126 | [10 empty] | 0
Schedule 16 | 127 | [10 empty] | 0
Schedule 16 | 127A | [10 empty] | 0
Schedule 16 | 128 | YES | YES | [8 empty] | 2
Schedule 16 | 129 | YES | [9 empty] | 1
Schedule 16 | 130 | YES | [9 empty] | 1
Schedule 16 | 131 | [10 empty] | 0
Schedule 16 | 132 | YES | [9 empty] | 1
Schedule 16 | 132A | [10 empty] | 0
Schedule 16 | 132B | [10 empty] | 0
Schedule 16 | 132C | YES | [9 empty] | 1
Schedule 16 | 132D | [10 empty] | 0
Schedule 16 | 133 | YES | [9 empty] | 1
Schedule 16 | 134 | [10 empty] | 0
Schedule 16 | 135 | [10 empty] | 0
Schedule 16 | 135A | YES | [9 empty] | 1 | MHHS CP seeks to remove the last column containing applicable Measurement Class
Schedule 16 | 135B | [10 empty] | 0
Schedule 16 | 136 | [10 empty] | 0
Schedule 16 | 137 | [10 empty] | 0
Schedule 16 | 138 | [10 empty] | 0
Schedule 16 | 139 | [10 empty] | 0
Schedule 16 | 140 | [8 empty] | YES |  | 1
Schedule 16 | 140A | YES | [9 empty] | 1
Schedule 16 | 140B | YES | [9 empty] | 1
Schedule 16 | 140C | YES | [9 empty] | 1
Schedule 16 | 140D | [10 empty] | 0
Schedule 16 | 140E | [10 empty] | 0
Schedule 16 | 141 | [10 empty] | 0
Schedule 16 | 142 | YES | [9 empty] | 1
Schedule 16 | 143 | YES | [9 empty] | 1
Schedule 16 | 144 | YES | [9 empty] | 1
Schedule 16 | 145 | [10 empty] | 0
Schedule 16 | 146 | [10 empty] | 0
Schedule 16 | 147 | [10 empty] | 0
Schedule 16 | 148 | [10 empty] | 0
Schedule 16 | 149 | [10 empty] | 0
Schedule 16 | 150 | [10 empty] | 0
Schedule 16 | 151 | [10 empty] | 0
Schedule 16 | 152 | [10 empty] | 0
Schedule 16 | 153 | [9 empty] | YES | 1
Schedule 16 | 154 | [10 empty] | 0
Schedule 16 | 155 | [10 empty] | 0
Schedule 16 | 156 | [10 empty] | 0
Schedule 16 | 157 | [10 empty] | 0
Schedule 16 | 158 | [10 empty] | 0
Schedule 16 | 159 | [10 empty] | 0
Schedule 16 | 160 | [10 empty] | 0
Schedule 16 | 161 | [10 empty] | 0
Schedule 16 | 162 | [10 empty] | 0
Schedule 16 | 163 | [10 empty] | 0
Schedule 16 | 164 | [10 empty] | 0
Schedule 16 | 165 | [10 empty] | 0
Schedule 16 | 166 | [10 empty] | 0
Schedule 16 | 167 | [10 empty] | 0
Schedule 16 | 168 | [10 empty] | 0
Schedule 16 | 169 | [10 empty] | 0
Schedule 16 | 170 | [10 empty] | 0
Schedule 16 | 171 | [10 empty] | 0
Schedule 16 | 172 | [10 empty] | 0
Schedule 16 | 173 | [10 empty] | 0
Schedule 16 | 173A | [7 empty] | YES |  |  | 1 | DCP 439 Introduces new Paragraph 173A
Schedule 16 | 174 | [10 empty] | 0
Schedule 16 | 175 | [10 empty] | 0
Schedule 16 | 176 | [10 empty] | 0
Schedule 16 | 177 | [10 empty] | 0
Schedule 16 | 178 | [10 empty] | 0
Schedule 16 | 179 | [10 empty] | 0
Schedule 16 | 180 | [10 empty] | 0
Schedule 16 | 181 | [10 empty] | 0
Schedule 16 | 182 | [10 empty] | 0
Schedule 16 | 183 | [10 empty] | 0
Schedule 16 | 184 | [10 empty] | 0
Schedule 16 | Glossary | YES | [9 empty] | 1
0
Schedule 17 | Introduction | [10 empty] | 0
Schedule 17 | 1 | [10 empty] | 0
Schedule 17 | 1.1 | [10 empty] | 0
Schedule 17 | 1.2 | [10 empty] | 0
Schedule 17 | 1.3 | [10 empty] | 0 | Model reference number and date
Schedule 17 | 1.3A | [10 empty] | 0
Schedule 17 | 1.4 | [10 empty] | 0
Schedule 17 | 1.5 | [10 empty] | 0
Schedule 17 | 1.6 | [10 empty] | 0
Schedule 17 | 1.7 | [10 empty] | 0
Schedule 17 | 1.8 | [10 empty] | 0
Schedule 17 | 1.9 | [10 empty] | 0
Schedule 17 | 2 | [10 empty] | 0
Schedule 17 | 2.1 | [10 empty] | 0
Schedule 17 | 2.2 | [10 empty] | 0
Schedule 17 | 2.3 | [10 empty] | 0
Schedule 17 | 2.4 | [10 empty] | 0
Schedule 17 | 2.5 | [10 empty] | 0
Schedule 17 | 2.6 | [10 empty] | 0
Schedule 17 | 2.7 | [10 empty] | 0
Schedule 17 | 2.8 | [10 empty] | 0
Schedule 17 | 2.9 | [10 empty] | 0
Schedule 17 | 2.1 | [10 empty] | 0
Schedule 17 | 2.11 | [10 empty] | 0
Schedule 17 | 2.12 | [10 empty] | 0
Schedule 17 | 2.13 | [10 empty] | 0
Schedule 17 | 2.14 | [10 empty] | 0
Schedule 17 | 2.15 | [10 empty] | 0
Schedule 17 | 2.16 | [10 empty] | 0
Schedule 17 | 2.17 | [10 empty] | 0
Schedule 17 | 2.18 | [10 empty] | 0
Schedule 17 | 2.19 | [10 empty] | 0
Schedule 17 | 3 | [10 empty] | 0
Schedule 17 | 3.1 | [10 empty] | 0
Schedule 17 | 3.2 | [10 empty] | 0
Schedule 17 | 3.3 | [10 empty] | 0
Schedule 17 | 3.4 | [10 empty] | 0
Schedule 17 | 3.5 | [10 empty] | 0
Schedule 17 | 3.6 | [10 empty] | 0
Schedule 17 | 3.7 | [10 empty] | 0
Schedule 17 | 4 | [10 empty] | 0
Schedule 17 | 4.1 | [10 empty] | 0
Schedule 17 | 5 | [10 empty] | 0
Schedule 17 | 5.1 | [10 empty] | 0
Schedule 17 | 6 | [10 empty] | 0
Schedule 17 | 6.1 | [10 empty] | 0
Schedule 17 | 6.2 | [10 empty] | 0
Schedule 17 | 6.3 | [10 empty] | 0
Schedule 17 | 7 | [10 empty] | 0
Schedule 17 | 7.1 | [10 empty] | 0
Schedule 17 | 8 | [10 empty] | 0
Schedule 17 | 8.1 | [10 empty] | 0
Schedule 17 | 8.2 | [10 empty] | 0
Schedule 17 | 8.3 | [10 empty] | 0
Schedule 17 | 8.4 | [10 empty] | 0
Schedule 17 | 9 | [10 empty] | 0
Schedule 17 | 9.1 | [10 empty] | 0
Schedule 17 | 9.2 | [10 empty] | 0
Schedule 17 | 9.3 | [10 empty] | 0
Schedule 17 | 10 | [10 empty] | 0
Schedule 17 | 10.1 | [10 empty] | 0
Schedule 17 | 10.2 | [10 empty] | 0
Schedule 17 | 10.3 | [10 empty] | 0
Schedule 17 | 10.4 | [10 empty] | 0
Schedule 17 | 11 | [10 empty] | 0
Schedule 17 | 11.1 | [10 empty] | 0
Schedule 17 | 12 | [10 empty] | 0
Schedule 17 | 12.1 | [10 empty] | 0
Schedule 17 | 12.2 | [10 empty] | 0
Schedule 17 | 12.3 | [10 empty] | 0
Schedule 17 | 13 | [10 empty] | 0
Schedule 17 | 13.1 | [10 empty] | 0
Schedule 17 | 13.2 | [10 empty] | 0
Schedule 17 | 13.3 | [10 empty] | 0
Schedule 17 | 13.4 | [10 empty] | 0
Schedule 17 | 14 | [10 empty] | 0
Schedule 17 | 14.1 | [10 empty] | 0
Schedule 17 | 14.2 | [10 empty] | 0
Schedule 17 | 14.3 | [10 empty] | 0
Schedule 17 | 14.4 | [10 empty] | 0
Schedule 17 | 14.5 | [10 empty] | 0
Schedule 17 | 15 | [10 empty] | 0
Schedule 17 | 15.1 | [10 empty] | 0
Schedule 17 | 15.2 | [10 empty] | 0
Schedule 17 | 15.3 | [10 empty] | 0
Schedule 17 | 15.4 | [10 empty] | 0
Schedule 17 | 15.5 | [10 empty] | 0
Schedule 17 | 15.6 | [10 empty] | 0
Schedule 17 | 15.7 | [10 empty] | 0
Schedule 17 | 15.8 | [10 empty] | 0
Schedule 17 | 15.9 | [10 empty] | 0
Schedule 17 | 15.1 | [10 empty] | 0
Schedule 17 | 15.11 | [10 empty] | 0
Schedule 17 | 15.12 | [10 empty] | 0
Schedule 17 | 15.15 | [10 empty] | 0
Schedule 17 | 16 | [10 empty] | 0
Schedule 17 | 16.1 | [10 empty] | 0
Schedule 17 | 16.2 | [10 empty] | 0
Schedule 17 | 16.3 | [10 empty] | 0
Schedule 17 | 16.4 | [10 empty] | 0
Schedule 17 | 16.5 | [10 empty] | 0
Schedule 17 | 16.6 | [10 empty] | 0
Schedule 17 | 16.7 | [10 empty] | 0
Schedule 17 | 16.8 | [10 empty] | 0
Schedule 17 | 16.9 | [10 empty] | 0
Schedule 17 | 16.1 | [10 empty] | 0
Schedule 17 | 17 | [10 empty] | 0
Schedule 17 | 17.1 | [10 empty] | 0
Schedule 17 | 17.2 | [10 empty] | 0
Schedule 17 | 17.3 | [10 empty] | 0
Schedule 17 | 18 | [10 empty] | 0
Schedule 17 | 18.1 | [10 empty] | 0
Schedule 17 | 18.2 | [10 empty] | 0
Schedule 17 | 18.3 | [10 empty] | 0
Schedule 17 | 18.4 | [10 empty] | 0
Schedule 17 | 18.5 | [10 empty] | 0
Schedule 17 | 18.6 | [10 empty] | 0
Schedule 17 | 18.7 | [10 empty] | 0
Schedule 17 | 18.8 | [10 empty] | 0
Schedule 17 | 18.9 | [10 empty] | 0
Schedule 17 | 18.1 | [10 empty] | 0
Schedule 17 | 18.11 | [10 empty] | 0
Schedule 17 | 18.12 | [10 empty] | 0
Schedule 17 | 18.13 | [10 empty] | 0
Schedule 17 | 18.14 | [10 empty] | 0
Schedule 17 | 18.15 | [10 empty] | 0
Schedule 17 | 18.16 | [10 empty] | 0
Schedule 17 | 18.17 | [10 empty] | 0
Schedule 17 | 18.18 | [10 empty] | 0
Schedule 17 | 18.19 | [10 empty] | 0
Schedule 17 | 18.2 | [10 empty] | 0
Schedule 17 | 18.21 | [10 empty] | 0
Schedule 17 | 19 | [10 empty] | 0
Schedule 17 | 19.1 | [10 empty] | 0
Schedule 17 | 19.2 | [10 empty] | 0
Schedule 17 | 19.3 | [10 empty] | 0
Schedule 17 | 19.4 | [10 empty] | 0
Schedule 17 | 19.5 | [10 empty] | 0
Schedule 17 | 19.6 | [10 empty] | 0
Schedule 17 | 19.7 | [10 empty] | 0
Schedule 17 | 19.8 | [10 empty] | 0
Schedule 17 | 19.9 | [10 empty] | 0
Schedule 17 | 19.1 | [10 empty] | 0
Schedule 17 | 19.11 | [10 empty] | 0
Schedule 17 | 20 | [10 empty] | 0
Schedule 17 | 20.1 | [10 empty] | 0
Schedule 17 | 20.2 | [10 empty] | 0
Schedule 17 | 20.3 | [10 empty] | 0
Schedule 17 | 20.4 | [10 empty] | 0
Schedule 17 | 20.5 | [10 empty] | 0
Schedule 17 | 20.6 | [9 empty] | YES | 1
Schedule 17 | 20.7 | [9 empty] | YES | 1
Schedule 17 | 20.8 | [10 empty] | 0
Schedule 17 | 20.9 | [9 empty] | YES | 1
Schedule 17 | 21 | [10 empty] | 0
Schedule 17 | 21.1 | [10 empty] | 0
Schedule 17 | 21.2 | [10 empty] | 0
Schedule 17 | 22 | [10 empty] | 0
Schedule 17 | 22.1 | [10 empty] | 0
Schedule 17 | 22.2 | [10 empty] | 0
Schedule 17 | 22.3 | [10 empty] | 0
Schedule 17 | 22.4 | [10 empty] | 0
Schedule 17 | 23 | [10 empty] | 0
Schedule 17 | 23.1 | [10 empty] | 0
Schedule 17 | 23.2 | [10 empty] | 0
Schedule 17 | 23.3 | [10 empty] | 0
Schedule 17 | 23.4 | [10 empty] | 0
Schedule 17 | 23.5 | [10 empty] | 0
Schedule 17 | 24 | [10 empty] | 0
Schedule 17 | 24.1 | [10 empty] | 0
Schedule 17 | 24.2 | [10 empty] | 0
Schedule 17 | 24.3 | [10 empty] | 0
Schedule 17 | 24.4 | [10 empty] | 0
Schedule 17 | 24.5 | [10 empty] | 0
Schedule 17 | 24.6 | [10 empty] | 0
Schedule 17 | 24.7 | [10 empty] | 0
Schedule 17 | 24.8 | [10 empty] | 0
Schedule 17 | 24.9 | [10 empty] | 0
Schedule 17 | 25 | [10 empty] | 0
Schedule 17 | 25.1 | [10 empty] | 0
Schedule 17 | 25.2 | [10 empty] | 0
Schedule 17 | 25.3 | [10 empty] | 0
Schedule 17 | 25.4 | [10 empty] | 0
Schedule 17 | 25.5 | [10 empty] | 0
Schedule 17 | 25.6 | [10 empty] | 0
Schedule 17 | 25.7 | [10 empty] | 0
Schedule 17 | 25.8 | [10 empty] | 0
Schedule 17 | 25.9 | [10 empty] | 0
Schedule 17 | 25.1 | [10 empty] | 0
Schedule 17 | 25.11 | [10 empty] | 0
Schedule 17 | 25.12 | [10 empty] | 0
Schedule 17 | 25.13 | [10 empty] | 0
Schedule 17 | 25.14 | [10 empty] | 0
Schedule 17 | 25.15 | [10 empty] | 0
Schedule 17 | 25.16 | [10 empty] | 0
Schedule 17 | 25.17 | [10 empty] | 0
Schedule 17 | 25.18 | [10 empty] | 0
Schedule 17 | 25.19 | [10 empty] | 0
Schedule 17 | 26 | [10 empty] | 0
Schedule 17 | 26.1 | [10 empty] | 0
Schedule 17 | 26.2 | [10 empty] | 0
Schedule 17 | 26.3 | [10 empty] | 0
Schedule 17 | 26.4 | [10 empty] | 0
Schedule 17 | 26.5 | [10 empty] | 0
Schedule 17 | 26.6 | [10 empty] | 0
Schedule 17 | 26.7 | [10 empty] | 0
Schedule 17 | 26.8 | [10 empty] | 0
Schedule 17 | 26.9 | [10 empty] | 0
Schedule 17 | 26.1 | [10 empty] | 0
Schedule 17 | 26.11 | [10 empty] | 0
Schedule 17 | 27 | [10 empty] | 0
Schedule 17 | 27.1 | [10 empty] | 0
Schedule 17 | 27.2 | [10 empty] | 0
Schedule 17 | 27.3 | [10 empty] | 0
Schedule 17 | 27.4 | [10 empty] | 0
Schedule 17 | 28 | [10 empty] | 0
Schedule 17 | 28.1 | [10 empty] | 0
Schedule 17 | 28.2 | [10 empty] | 0
Schedule 17 | 29 | [10 empty] | 0
Schedule 17 | 29.1 | [10 empty] | 0
Schedule 17 | 29.2 | [10 empty] | 0
Schedule 17 | 29.3 | [10 empty] | 0
Schedule 17 | 29.4 | [10 empty] | 0
Schedule 17 | 30 | [10 empty] | 0
Schedule 17 | 30.1 | [10 empty] | 0
Schedule 17 | 30.2 | [10 empty] | 0
Schedule 17 | 30.3 | [10 empty] | 0
Schedule 17 | 30.4 | [10 empty] | 0
Schedule 17 | 30.5 | [10 empty] | 0
Schedule 17 | 30.6 | [10 empty] | 0
Schedule 17 | 30.7 | [10 empty] | 0
Schedule 17 | 30.8 | [10 empty] | 0
Schedule 17 | 30.9 | [10 empty] | 0
Schedule 17 | 30.1 | [10 empty] | 0
Schedule 17 | 30.11 | [10 empty] | 0
Schedule 17 | 31 | [7 empty] | YES |  |  | 1 | DCP 439 Introduces new Paragraph 31
Schedule 17 | 31.1 | [7 empty] | YES |  |  | 1 | DCP 439 Introduces new Paragraph 31.1
Schedule 17: Annex 1 | 1 | [10 empty] | 0
Schedule 17: Annex 1 | 2 | [10 empty] | 0
Schedule 17: Annex 1 | 2.1 | [10 empty] | 0
Schedule 17: Annex 1 | 2.2 | [10 empty] | 0
Schedule 17: Annex 1 | 2.3 | [10 empty] | 0
Schedule 17: Annex 1 | 2.4 | [10 empty] | 0
Schedule 17: Annex 1 | 2.5 | [10 empty] | 0
Schedule 17: Annex 1 | 3 | [10 empty] | 0
Schedule 17: Annex 1 | Definitions | [10 empty] | 0
Schedule 17: Annex 1 | 4 | [10 empty] | 0
Schedule 17: Annex 1 | 4.1 | [10 empty] | 0
Schedule 17: Annex 1 | 4.2 | [10 empty] | 0
Schedule 17: Annex 1 | 4.3 | [10 empty] | 0
Schedule 17: Annex 1 | 4.4 | [10 empty] | 0
Schedule 17: Annex 1 | 4.5 | [10 empty] | 0
Schedule 17: Annex 1 | 4.6 | [10 empty] | 0
Schedule 17: Annex 1 | 4.7 | [10 empty] | 0
Schedule 17: Annex 1 | 4.8 | [10 empty] | 0
Schedule 17: Annex 1 | 4.9 | [10 empty] | 0
Schedule 17: Annex 1 | 4.1 | [10 empty] | 0
Schedule 17: Annex 1 | 5 | [10 empty] | 0
Schedule 17: Annex 1 | 5.1 | [10 empty] | 0
Schedule 17: Annex 1 | 5.2 | [10 empty] | 0
Schedule 17: Annex 1 | 5.3 | [10 empty] | 0
Schedule 17: Annex 1 | 5.4 | [10 empty] | 0
Schedule 17: Annex 1 | 5.5 | [10 empty] | 0
Schedule 17: Annex 1 | 5.6 | [10 empty] | 0
Schedule 17: Annex 1 | 5.7 | [10 empty] | 0
Schedule 17: Annex 1 | 5.8 | [10 empty] | 0
Schedule 17: Annex 1 | 5.9 | [10 empty] | 0
Schedule 17: Annex 1 | 5.1 | [10 empty] | 0
Schedule 17: Annex 1 | 5.11 | [10 empty] | 0
Schedule 17: Annex 1 | 5.12 | [10 empty] | 0
Schedule 17: Annex 1 | 5.13 | [10 empty] | 0
Schedule 17: Annex 1 | 5.14 | [10 empty] | 0
Schedule 17: Annex 1 | 5.15 | [10 empty] | 0
Schedule 17: Annex 1 | 5.16 | [10 empty] | 0
Schedule 17: Annex 1 | 5.17 | [10 empty] | 0
Schedule 17: Annex 1 | 5.18 | [10 empty] | 0
Schedule 17: Annex 1 | 5.19 | [10 empty] | 0
Schedule 17: Annex 1 | 5.2 | [10 empty] | 0
Schedule 17: Annex 1 | 5.21 | [10 empty] | 0
Schedule 17: Annex 1 | 5.22 | [10 empty] | 0
Schedule 17: Annex 1 | 5.23 | [10 empty] | 0
Schedule 17: Annex 1 | 5.24 | [10 empty] | 0
Schedule 17: Annex 1 | 5.25 | [10 empty] | 0
Schedule 17: Annex 1 | 5.26 | [10 empty] | 0
Schedule 17: Annex 1 | 5.27 | [10 empty] | 0
Schedule 17: Annex 1 | 5.28 | [10 empty] | 0
Schedule 17: Annex 1 | 5.29 | [10 empty] | 0
Schedule 17: Annex 1 | 5.3 | [10 empty] | 0
Schedule 17: Annex 1 | 5.31 | [10 empty] | 0
Schedule 17: Annex 1 | 5.32 | [10 empty] | 0
Schedule 17: Annex 1 | 5.33 | [10 empty] | 0
Schedule 17: Annex 1 | 5.34 | [10 empty] | 0
Schedule 17: Annex 1 | 5.35 | [10 empty] | 0
Schedule 17: Annex 1 | 5.36 | [10 empty] | 0
Schedule 17: Annex 1 | 5.37 | [10 empty] | 0
Schedule 17: Annex 1 | 5.38 | [10 empty] | 0
Schedule 17: Annex 1 | 5.39 | [10 empty] | 0
Schedule 17: Annex 1 | 5.4 | [10 empty] | 0
Schedule 17: Annex 1 | 5.41 | [10 empty] | 0
Schedule 17: Annex 1 | 5.42 | [10 empty] | 0
Schedule 17: Annex 1 | 5.43 | [10 empty] | 0
Schedule 17: Annex 1 | 5.44 | [10 empty] | 0
Schedule 17: Annex 1 | 5.45 | [10 empty] | 0
Schedule 17: Annex 1 | 6 | [10 empty] | 0
Schedule 17: Annex 1 | 6.1 | [10 empty] | 0
Schedule 17: Annex 1 | 6.2 | [10 empty] | 0
Schedule 17: Annex 1 | 6.3 | [10 empty] | 0
Schedule 17: Annex 1 | 6.4 | [10 empty] | 0
Schedule 17: Annex 1 | 6.5 | [10 empty] | 0
Schedule 17: Annex 1 | 6.6 | [10 empty] | 0
Schedule 17: Annex 1 | 6.7 | [10 empty] | 0
Schedule 17: Annex 1 | 6.8 | [10 empty] | 0
Schedule 17: Annex 1 | 7 | [10 empty] | 0
Schedule 17: Annex 1 | 7.1 | [10 empty] | 0
Schedule 17: Annex 1 | 7.2 | [10 empty] | 0
Schedule 17: Annex 1 | 7.3 | [10 empty] | 0
Schedule 17: Annex 1 | 7.4 | [10 empty] | 0
Schedule 17: Annex 1 | 7.5 | [10 empty] | 0
Schedule 17: Annex 1 | 7.6 | [10 empty] | 0
Schedule 17: Annex 1 | 7.7 | [10 empty] | 0
Schedule 17: Annex 1 | 7.8 | [10 empty] | 0
Schedule 17: Annex 1 | 8 | [10 empty] | 0
Schedule 17: Annex 1 | 8.1 | [10 empty] | 0
Schedule 17: Annex 1 | 8.2 | [10 empty] | 0
Schedule 17: Annex 1 | 8.3 | [10 empty] | 0
Schedule 17: Annex 1 | 8.4 | [10 empty] | 0
Schedule 17: Annex 1 | 9 | [10 empty] | 0
Schedule 17: Annex 1 | 9.1 | [10 empty] | 0
Schedule 17: Annex 1 | 9.2 | [10 empty] | 0
Schedule 17: Annex 1 | 9.3 | [10 empty] | 0
Schedule 17: Annex 1 | 9.4 | [10 empty] | 0
Schedule 17: Annex 1 | 9.5 | [10 empty] | 0
Schedule 17: Annex 1 | 9.6 | [10 empty] | 0
Schedule 17: Annex 1 | 9.7 | [10 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [10 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [10 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [10 empty] | 0
Schedule 17: Annex 1 | Attachment 3 | [10 empty] | 0
Schedule 17: Annex 2 | Annex 2 | [10 empty] | 0
0
Schedule 18 | Introduction | [10 empty] | 0
Schedule 18 | 1 | [10 empty] | 0
Schedule 18 | 1.1 | [10 empty] | 0
Schedule 18 | 1.2 | [10 empty] | 0
Schedule 18 | 1.3 | [10 empty] | 0 | Model reference number and date
Schedule 18 | 1.3A | [10 empty] | 0
Schedule 18 | 1.4 | [10 empty] | 0
Schedule 18 | 1.5 | [10 empty] | 0
Schedule 18 | 1.6 | [10 empty] | 0
Schedule 18 | 1.7 | [10 empty] | 0
Schedule 18 | 1.8 | [10 empty] | 0
Schedule 18 | 1.9 | [10 empty] | 0
Schedule 18 | 2 | [10 empty] | 0
Schedule 18 | 2.1 | [10 empty] | 0
Schedule 18 | 2.2 | [10 empty] | 0
Schedule 18 | 2.3 | [10 empty] | 0
Schedule 18 | 2.4 | [10 empty] | 0
Schedule 18 | 2.5 | [10 empty] | 0
Schedule 18 | 2.6 | [10 empty] | 0
Schedule 18 | 2.7 | [10 empty] | 0
Schedule 18 | 2.8 | [10 empty] | 0
Schedule 18 | 2.9 | [10 empty] | 0
Schedule 18 | 2.1 | [10 empty] | 0
Schedule 18 | 2.11 | [10 empty] | 0
Schedule 18 | 2.12 | [10 empty] | 0
Schedule 18 | 2.13 | [10 empty] | 0
Schedule 18 | 2.14 | [10 empty] | 0
Schedule 18 | 2.15 | [10 empty] | 0
Schedule 18 | 2.16 | [10 empty] | 0
Schedule 18 | 2.17 | [10 empty] | 0
Schedule 18 | 2.18 | [10 empty] | 0
Schedule 18 | 2.19 | [10 empty] | 0
Schedule 18 | 2.2 | [10 empty] | 0
Schedule 18 | 2.21 | [10 empty] | 0
Schedule 18 | 2.22 | [10 empty] | 0
Schedule 18 | 2.23 | [10 empty] | 0
Schedule 18 | 2.24 | [10 empty] | 0
Schedule 18 | 2.25 | [10 empty] | 0
Schedule 18 | 2.26 | [10 empty] | 0
Schedule 18 | 2.27 | [10 empty] | 0
Schedule 18 | 2.28 | [10 empty] | 0
Schedule 18 | 2.29 | [10 empty] | 0
Schedule 18 | 2.3 | [10 empty] | 0
Schedule 18 | 3 | [10 empty] | 0
Schedule 18 | 3.1 | [10 empty] | 0
Schedule 18 | 3.2 | [10 empty] | 0
Schedule 18 | 3.3 | [10 empty] | 0
Schedule 18 | 3.4 | [10 empty] | 0
Schedule 18 | 3.5 | [10 empty] | 0
Schedule 18 | 3.6 | [10 empty] | 0
Schedule 18 | 3.7 | [10 empty] | 0
Schedule 18 | 4 | [10 empty] | 0
Schedule 18 | 4.1 | [10 empty] | 0
Schedule 18 | 5 | [10 empty] | 0
Schedule 18 | 5.1 | [10 empty] | 0
Schedule 18 | 6 | [10 empty] | 0
Schedule 18 | 6.1 | [10 empty] | 0
Schedule 18 | 6.2 | [10 empty] | 0
Schedule 18 | 6.3 | [10 empty] | 0
Schedule 18 | 6.4 | [10 empty] | 0
Schedule 18 | 6.5 | [10 empty] | 0
Schedule 18 | 7 | [10 empty] | 0
Schedule 18 | 7.1 | [10 empty] | 0
Schedule 18 | 8 | [10 empty] | 0
Schedule 18 | 8.1 | [10 empty] | 0
Schedule 18 | 8.2 | [10 empty] | 0
Schedule 18 | 8.3 | [10 empty] | 0
Schedule 18 | 8.4 | [10 empty] | 0
Schedule 18 | 9 | [10 empty] | 0
Schedule 18 | 9.1 | [10 empty] | 0
Schedule 18 | 9.2 | [10 empty] | 0
Schedule 18 | 10 | [10 empty] | 0
Schedule 18 | 10.1 | [10 empty] | 0
Schedule 18 | 10.2 | [10 empty] | 0
Schedule 18 | 10.3 | [10 empty] | 0
Schedule 18 | 10.4 | [10 empty] | 0
Schedule 18 | 10.5 | [10 empty] | 0
Schedule 18 | 11 | [10 empty] | 0
Schedule 18 | 11.1 | [10 empty] | 0
Schedule 18 | 12 | [10 empty] | 0
Schedule 18 | 12.1 | [10 empty] | 0
Schedule 18 | 12.2 | [10 empty] | 0
Schedule 18 | 12.3 | [10 empty] | 0
Schedule 18 | 12.4 | [10 empty] | 0
Schedule 18 | 12.5 | [10 empty] | 0
Schedule 18 | 12.6 | [10 empty] | 0
Schedule 18 | 13 | [10 empty] | 0
Schedule 18 | 13.1 | [10 empty] | 0
Schedule 18 | 13.2 | [10 empty] | 0
Schedule 18 | 13.3 | [10 empty] | 0
Schedule 18 | 13.4 | [10 empty] | 0
Schedule 18 | 14 | [10 empty] | 0
Schedule 18 | 14.1 | [10 empty] | 0
Schedule 18 | 14.2 | [10 empty] | 0
Schedule 18 | 14.3 | [10 empty] | 0
Schedule 18 | 14.4 | [10 empty] | 0
Schedule 18 | 14.5 | [10 empty] | 0
Schedule 18 | 15 | [10 empty] | 0
Schedule 18 | 15.1 | [10 empty] | 0
Schedule 18 | 15.2 | [10 empty] | 0
Schedule 18 | 15.3 | [10 empty] | 0
Schedule 18 | 15.4 | [10 empty] | 0
Schedule 18 | 15.5 | [10 empty] | 0
Schedule 18 | 15.6 | [10 empty] | 0
Schedule 18 | 15.7 | [10 empty] | 0
Schedule 18 | 15.8 | [10 empty] | 0
Schedule 18 | 15.9 | [10 empty] | 0
Schedule 18 | 15.1 | [10 empty] | 0
Schedule 18 | 15.11 | [10 empty] | 0
Schedule 18 | 15.12 | [10 empty] | 0
Schedule 18 | 15.15 | [10 empty] | 0
Schedule 18 | 16 | [10 empty] | 0
Schedule 18 | 16.1 | [10 empty] | 0
Schedule 18 | 16.2 | [10 empty] | 0
Schedule 18 | 16.3 | [10 empty] | 0
Schedule 18 | 16.4 | [10 empty] | 0
Schedule 18 | 16.5 | [10 empty] | 0
Schedule 18 | 16.6 | [10 empty] | 0
Schedule 18 | 16.7 | [10 empty] | 0
Schedule 18 | 16.8 | [10 empty] | 0
Schedule 18 | 16.9 | [10 empty] | 0
Schedule 18 | 16.1 | [10 empty] | 0
Schedule 18 | 17 | [10 empty] | 0
Schedule 18 | 17.1 | [10 empty] | 0
Schedule 18 | 17.2 | [10 empty] | 0
Schedule 18 | 17.3 | [10 empty] | 0
Schedule 18 | 18 | [10 empty] | 0
Schedule 18 | 18.1 | [10 empty] | 0
Schedule 18 | 18.2 | [10 empty] | 0
Schedule 18 | 18.3 | [10 empty] | 0
Schedule 18 | 18.4 | [10 empty] | 0
Schedule 18 | 18.5 | [10 empty] | 0
Schedule 18 | 18.6 | [10 empty] | 0
Schedule 18 | 18.7 | [10 empty] | 0
Schedule 18 | 18.8 | [10 empty] | 0
Schedule 18 | 18.9 | [10 empty] | 0
Schedule 18 | 18.1 | [10 empty] | 0
Schedule 18 | 18.11 | [10 empty] | 0
Schedule 18 | 18.12 | [10 empty] | 0
Schedule 18 | 18.13 | [10 empty] | 0
Schedule 18 | 18.14 | [10 empty] | 0
Schedule 18 | 18.15 | [10 empty] | 0
Schedule 18 | 18.16 | [10 empty] | 0
Schedule 18 | 18.17 | [10 empty] | 0
Schedule 18 | 18.18 | [10 empty] | 0
Schedule 18 | 18.19 | [10 empty] | 0
Schedule 18 | 18.2 | [10 empty] | 0
Schedule 18 | 18.21 | [10 empty] | 0
Schedule 18 | 19 | [10 empty] | 0
Schedule 18 | 19.1 | [10 empty] | 0
Schedule 18 | 19.2 | [10 empty] | 0
Schedule 18 | 19.3 | [10 empty] | 0
Schedule 18 | 19.4 | [10 empty] | 0
Schedule 18 | 19.5 | [10 empty] | 0
Schedule 18 | 19.6 | [10 empty] | 0
Schedule 18 | 19.7 | [10 empty] | 0
Schedule 18 | 19.8 | [10 empty] | 0
Schedule 18 | 19.9 | [10 empty] | 0
Schedule 18 | 19.1 | [10 empty] | 0
Schedule 18 | 19.11 | [10 empty] | 0
Schedule 18 | 20 | [10 empty] | 0
Schedule 18 | 20.1 | [10 empty] | 0
Schedule 18 | 20.2 | [10 empty] | 0
Schedule 18 | 20.3 | [10 empty] | 0
Schedule 18 | 20.4 | [10 empty] | 0
Schedule 18 | 20.5 | [10 empty] | 0
Schedule 18 | 20.6 | [9 empty] | YES | 1
Schedule 18 | 20.7 | [9 empty] | YES | 1
Schedule 18 | 20.8 | [10 empty] | 0
Schedule 18 | 20.9 | [9 empty] | YES | 1
Schedule 18 | 21 | [10 empty] | 0
Schedule 18 | 21.1 | [10 empty] | 0
Schedule 18 | 21.2 | [10 empty] | 0
Schedule 18 | 22 | [10 empty] | 0
Schedule 18 | 22.1 | [10 empty] | 0
Schedule 18 | 22.2 | [10 empty] | 0
Schedule 18 | 22.3 | [10 empty] | 0
Schedule 18 | 22.4 | [10 empty] | 0
Schedule 18 | 23 | [10 empty] | 0
Schedule 18 | 23.1 | [10 empty] | 0
Schedule 18 | 23.2 | [10 empty] | 0
Schedule 18 | 23.3 | [10 empty] | 0
Schedule 18 | 23.4 | [10 empty] | 0
Schedule 18 | 23.5 | [10 empty] | 0
Schedule 18 | 24 | [10 empty] | 0
Schedule 18 | 24.1 | [10 empty] | 0
Schedule 18 | 24.2 | [10 empty] | 0
Schedule 18 | 24.3 | [10 empty] | 0
Schedule 18 | 24.4 | [10 empty] | 0
Schedule 18 | 24.5 | [10 empty] | 0
Schedule 18 | 24.6 | [10 empty] | 0
Schedule 18 | 24.7 | [10 empty] | 0
Schedule 18 | 24.8 | [10 empty] | 0
Schedule 18 | 24.9 | [10 empty] | 0
Schedule 18 | 25 | [10 empty] | 0
Schedule 18 | 25.1 | [10 empty] | 0
Schedule 18 | 25.2 | [10 empty] | 0
Schedule 18 | 25.3 | [10 empty] | 0
Schedule 18 | 25.4 | [10 empty] | 0
Schedule 18 | 25.5 | [10 empty] | 0
Schedule 18 | 25.6 | [10 empty] | 0
Schedule 18 | 25.7 | [10 empty] | 0
Schedule 18 | 25.8 | [10 empty] | 0
Schedule 18 | 25.9 | [10 empty] | 0
Schedule 18 | 25.1 | [10 empty] | 0
Schedule 18 | 25.11 | [10 empty] | 0
Schedule 18 | 25.12 | [10 empty] | 0
Schedule 18 | 25.13 | [10 empty] | 0
Schedule 18 | 25.14 | [10 empty] | 0
Schedule 18 | 25.15 | [10 empty] | 0
Schedule 18 | 25.16 | [10 empty] | 0
Schedule 18 | 25.17 | [10 empty] | 0
Schedule 18 | 25.18 | [10 empty] | 0
Schedule 18 | 25.19 | [10 empty] | 0
Schedule 18 | 26 | [10 empty] | 0
Schedule 18 | 26.1 | [10 empty] | 0
Schedule 18 | 26.2 | [10 empty] | 0
Schedule 18 | 26.3 | [10 empty] | 0
Schedule 18 | 26.4 | [10 empty] | 0
Schedule 18 | 26.5 | [10 empty] | 0
Schedule 18 | 26.6 | [10 empty] | 0
Schedule 18 | 26.7 | [10 empty] | 0
Schedule 18 | 26.8 | [10 empty] | 0
Schedule 18 | 26.9 | [10 empty] | 0
Schedule 18 | 26.1 | [10 empty] | 0
Schedule 18 | 26.11 | [10 empty] | 0
Schedule 18 | 27 | [10 empty] | 0
Schedule 18 | 27.1 | [10 empty] | 0
Schedule 18 | 27.2 | [10 empty] | 0
Schedule 18 | 27.3 | [10 empty] | 0
Schedule 18 | 27.4 | [10 empty] | 0
Schedule 18 | 28 | [10 empty] | 0
Schedule 18 | 28.1 | [10 empty] | 0
Schedule 18 | 28.2 | [10 empty] | 0
Schedule 18 | 29 | [10 empty] | 0
Schedule 18 | 29.1 | [10 empty] | 0
Schedule 18 | 29.2 | [10 empty] | 0
Schedule 18 | 29.3 | [10 empty] | 0
Schedule 18 | 29.4 | [10 empty] | 0
Schedule 18 | 30 | [10 empty] | 0
Schedule 18 | 30.1 | [10 empty] | 0
Schedule 18 | 30.2 | [10 empty] | 0
Schedule 18 | 30.3 | [10 empty] | 0
Schedule 18 | 30.4 | [10 empty] | 0
Schedule 18 | 30.5 | [10 empty] | 0
Schedule 18 | 30.6 | [10 empty] | 0
Schedule 18 | 30.7 | [10 empty] | 0
Schedule 18 | 30.8 | [10 empty] | 0
Schedule 18 | 30.9 | [10 empty] | 0
Schedule 18 | 30.1 | [10 empty] | 0
Schedule 18 | 30.11 | [10 empty] | 0
Schedule 18 | 31 | [10 empty] | 0 | DCP 439 Introduces new Paragraph 31
Schedule 18 | 31.1 | [10 empty] | 0 | DCP 439 Introduces new Paragraph 31.1
Schedule 18: Annex 1 | 1 | [10 empty] | 0
Schedule 18: Annex 1 | 1.1 | [10 empty] | 0
Schedule 18: Annex 1 | 2 | [10 empty] | 0
Schedule 18: Annex 1 | 2.1 | [10 empty] | 0
Schedule 18: Annex 1 | 2.2 | [10 empty] | 0
Schedule 18: Annex 1 | 2.3 | [10 empty] | 0
Schedule 18: Annex 1 | 2.4 | [10 empty] | 0
Schedule 18: Annex 1 | 2.5 | [10 empty] | 0
Schedule 18: Annex 1 | 3 | [10 empty] | 0
Schedule 18: Annex 1 | Definitions | [10 empty] | 0
Schedule 18: Annex 1 | 4 | [10 empty] | 0
Schedule 18: Annex 1 | 4.1 | [10 empty] | 0
Schedule 18: Annex 1 | 4.2 | [10 empty] | 0
Schedule 18: Annex 1 | 4.3 | [10 empty] | 0
Schedule 18: Annex 1 | 4.4 | [10 empty] | 0
Schedule 18: Annex 1 | 4.5 | [10 empty] | 0
Schedule 18: Annex 1 | 4.6 | [10 empty] | 0
Schedule 18: Annex 1 | 4.7 | [10 empty] | 0
Schedule 18: Annex 1 | 4.8 | [10 empty] | 0
Schedule 18: Annex 1 | 4.9 | [10 empty] | 0
Schedule 18: Annex 1 | 5 | [10 empty] | 0
Schedule 18: Annex 1 | 5.1 | [10 empty] | 0
Schedule 18: Annex 1 | 5.2 | [10 empty] | 0
Schedule 18: Annex 1 | 5.3 | [10 empty] | 0
Schedule 18: Annex 1 | 5.4 | [10 empty] | 0
Schedule 18: Annex 1 | 5.5 | [10 empty] | 0
Schedule 18: Annex 1 | 5.6 | [10 empty] | 0
Schedule 18: Annex 1 | 5.7 | [10 empty] | 0
Schedule 18: Annex 1 | 5.8 | [10 empty] | 0
Schedule 18: Annex 1 | 5.9 | [10 empty] | 0
Schedule 18: Annex 1 | 5.1 | [10 empty] | 0
Schedule 18: Annex 1 | 5.11 | [10 empty] | 0
Schedule 18: Annex 1 | 5.12 | [10 empty] | 0
Schedule 18: Annex 1 | 5.13 | [10 empty] | 0
Schedule 18: Annex 1 | 5.14 | [10 empty] | 0
Schedule 18: Annex 1 | 5.15 | [10 empty] | 0
Schedule 18: Annex 1 | 5.16 | [10 empty] | 0
Schedule 18: Annex 1 | 5.17 | [10 empty] | 0
Schedule 18: Annex 1 | 5.18 | [10 empty] | 0
Schedule 18: Annex 1 | 5.19 | [10 empty] | 0
Schedule 18: Annex 1 | 5.2 | [10 empty] | 0
Schedule 18: Annex 1 | 5.21 | [10 empty] | 0
Schedule 18: Annex 1 | 5.22 | [10 empty] | 0
Schedule 18: Annex 1 | 5.23 | [10 empty] | 0
Schedule 18: Annex 1 | 5.24 | [10 empty] | 0
Schedule 18: Annex 1 | 5.25 | [10 empty] | 0
Schedule 18: Annex 1 | 5.26 | [10 empty] | 0
Schedule 18: Annex 1 | 5.27 | [10 empty] | 0
Schedule 18: Annex 1 | 5.28 | [10 empty] | 0
Schedule 18: Annex 1 | 5.29 | [10 empty] | 0
Schedule 18: Annex 1 | 5.3 | [10 empty] | 0
Schedule 18: Annex 1 | 5.31 | [10 empty] | 0
Schedule 18: Annex 1 | 5.32 | [10 empty] | 0
Schedule 18: Annex 1 | 5.33 | [10 empty] | 0
Schedule 18: Annex 1 | 5.34 | [10 empty] | 0
Schedule 18: Annex 1 | 5.35 | [10 empty] | 0
Schedule 18: Annex 1 | 5.36 | [10 empty] | 0
Schedule 18: Annex 1 | 5.37 | [10 empty] | 0
Schedule 18: Annex 1 | 5.38 | [10 empty] | 0
Schedule 18: Annex 1 | 5.39 | [10 empty] | 0
Schedule 18: Annex 1 | 5.4 | [10 empty] | 0
Schedule 18: Annex 1 | 5.41 | [10 empty] | 0
Schedule 18: Annex 1 | 5.42 | [10 empty] | 0
Schedule 18: Annex 1 | 6 | [10 empty] | 0
Schedule 18: Annex 1 | 6.1 | [10 empty] | 0
Schedule 18: Annex 1 | 6.2 | [10 empty] | 0
Schedule 18: Annex 1 | 6.3 | [10 empty] | 0
Schedule 18: Annex 1 | 6.4 | [10 empty] | 0
Schedule 18: Annex 1 | 6.5 | [10 empty] | 0
Schedule 18: Annex 1 | 6.6 | [10 empty] | 0
Schedule 18: Annex 1 | 6.7 | [10 empty] | 0
Schedule 18: Annex 1 | 6.8 | [10 empty] | 0
Schedule 18: Annex 1 | 6.9 | [10 empty] | 0
Schedule 18: Annex 1 | 6.1 | [10 empty] | 0
Schedule 18: Annex 1 | 6.11 | [10 empty] | 0
Schedule 18: Annex 1 | 6.12 | [10 empty] | 0
Schedule 18: Annex 1 | 6.13 | [10 empty] | 0
Schedule 18: Annex 1 | 6.14 | [10 empty] | 0
Schedule 18: Annex 1 | 6.15 | [10 empty] | 0
Schedule 18: Annex 1 | 6.16 | [10 empty] | 0
Schedule 18: Annex 1 | 6.17 | [10 empty] | 0
Schedule 18: Annex 1 | 6.18 | [10 empty] | 0
Schedule 18: Annex 1 | 6.19 | [10 empty] | 0
Schedule 18: Annex 1 | 6.2 | [10 empty] | 0
Schedule 18: Annex 1 | 6.21 | [10 empty] | 0
Schedule 18: Annex 1 | 6.22 | [10 empty] | 0
Schedule 18: Annex 1 | 6.23 | [10 empty] | 0
Schedule 18: Annex 1 | 6.24 | [10 empty] | 0
Schedule 18: Annex 1 | 6.25 | [10 empty] | 0
Schedule 18: Annex 1 | 6.26 | [10 empty] | 0
Schedule 18: Annex 1 | 6.27 | [10 empty] | 0
Schedule 18: Annex 1 | 6.28 | [10 empty] | 0
Schedule 18: Annex 1 | 6.29 | [10 empty] | 0
Schedule 18: Annex 1 | 6.3 | [10 empty] | 0
Schedule 18: Annex 1 | 6.31 | [10 empty] | 0
Schedule 18: Annex 1 | 6.32 | [10 empty] | 0
Schedule 18: Annex 1 | 6.33 | [10 empty] | 0
Schedule 18: Annex 1 | 6.34 | [10 empty] | 0
Schedule 18: Annex 1 | 7 | [10 empty] | 0
Schedule 18: Annex 1 | 7.1 | [10 empty] | 0
Schedule 18: Annex 1 | 7.2 | [10 empty] | 0
Schedule 18: Annex 1 | 7.3 | [10 empty] | 0
Schedule 18: Annex 1 | 7.4 | [10 empty] | 0
Schedule 18: Annex 1 | 7.5 | [10 empty] | 0
Schedule 18: Annex 1 | 8 | [10 empty] | 0
Schedule 18: Annex 1 | 8.1 | [10 empty] | 0
Schedule 18: Annex 1 | 8.2 | [10 empty] | 0
Schedule 18: Annex 1 | 8.3 | [10 empty] | 0
Schedule 18: Annex 1 | 8.4 | [10 empty] | 0
Schedule 18: Annex 1 | 8.5 | [10 empty] | 0
Schedule 18: Annex 1 | 8.6 | [10 empty] | 0
Schedule 18: Annex 1 | 8.7 | [10 empty] | 0
Schedule 18: Annex 1 | 8.8 | [10 empty] | 0
Schedule 18: Annex 1 | 8.9 | [10 empty] | 0
Schedule 18: Annex 1 | 8.1 | [10 empty] | 0
Schedule 18: Annex 1 | 8.11 | [10 empty] | 0
Schedule 18: Annex 1 | 8.12 | [10 empty] | 0
Schedule 18: Annex 1 | 8.13 | [10 empty] | 0
Schedule 18: Annex 1 | 8.14 | [10 empty] | 0
Schedule 18: Annex 1 | 8.15 | [10 empty] | 0
Schedule 18: Annex 1 | 8.16 | [10 empty] | 0
Schedule 18: Annex 1 | 8.17 | [10 empty] | 0
Schedule 18: Annex 1 | 8.18 | [10 empty] | 0
Schedule 18: Annex 1 | 8.19 | [10 empty] | 0
Schedule 18: Annex 1 | 8.2 | [10 empty] | 0
Schedule 18: Annex 1 | 8.21 | [10 empty] | 0
Schedule 18: Annex 1 | Attachment 1 | [10 empty] | 0
Schedule 18: Annex 1 | Attachment 2 | [10 empty] | 0
Schedule 18: Annex 1 | Attachment 3 | [10 empty] | 0
Schedule 18: Annex 2 | Annex 2 | [10 empty] | 0
0
Schedule 20 | Introduction |  |  | YES | [7 empty] | 1
Schedule 20 | 1.1 |  |  | YES | [7 empty] | 1
Schedule 20 | 2.1 |  |  | YES | [7 empty] | 1
Schedule 20 | 3.1 |  |  | YES | [7 empty] | 1
Schedule 20 | 3.2 |  |  | YES | [7 empty] | 1
0
Schedule 29 | Introduction | [10 empty] | 0
Schedule 29 | 1 | [10 empty] | 0
Schedule 29 | 1A | [10 empty] | 0
Schedule 29 | 2 | [10 empty] | 0
Schedule 29 | 3 | [10 empty] | 0
Schedule 29 | 4 | [10 empty] | 0
Schedule 29 | 5 | [10 empty] | 0
Schedule 29 | 6 | [10 empty] | 0
Schedule 29 | 7 | [10 empty] | 0
Schedule 29 | 8 | [10 empty] | 0
Schedule 29 | 9 | [10 empty] | 0
Schedule 29 | 10 | [10 empty] | 0
Schedule 29 | 11 | [10 empty] | 0
Schedule 29 | 11A | [10 empty] | 0
Schedule 29 | 12 | [10 empty] | 0
Schedule 29 | 13 | [10 empty] | 0
Schedule 29 | 14 | [10 empty] | 0
Schedule 29 | 15 | [10 empty] | 0
Schedule 29 | 16 | [10 empty] | 0
Schedule 29 | 17 | [10 empty] | 0
Schedule 29 | 18 | [10 empty] | 0
Schedule 29 | 19 | [10 empty] | 0
Schedule 29 | 20 | [10 empty] | 0
Schedule 29 | 21 | [10 empty] | 0
Schedule 29 | 22 | [10 empty] | 0
Schedule 29 | 23 | [10 empty] | 0
Schedule 29 | 24 | [10 empty] | 0
Schedule 29 | 25 | [10 empty] | 0
Schedule 29 | 26 | [10 empty] | 0
Schedule 29 | 27 | [10 empty] | 0
Schedule 29 | 28 | [10 empty] | 0
Schedule 29 | 29 | [10 empty] | 0
Schedule 29 | 30 | [10 empty] | 0
Schedule 29 | 31 | [10 empty] | 0
Schedule 29 | 32 | [10 empty] | 0
Schedule 29 | 33 | [10 empty] | 0
Schedule 29 | 34 | [10 empty] | 0
Schedule 29 | 35 | [10 empty] | 0
Schedule 29 | 36 | [10 empty] | 0
Schedule 29 | 37 | [10 empty] | 0
Schedule 29 | 38 | [10 empty] | 0
Schedule 29 | 39 | [10 empty] | 0
Schedule 29 | 40 | [10 empty] | 0
Schedule 29 | 41 | [10 empty] | 0
Schedule 29 | 42 | [10 empty] | 0
Schedule 29 | 43 | [10 empty] | 0
Schedule 29 | 44 | [10 empty] | 0
Schedule 29 | 45 | [10 empty] | 0
Schedule 29 | 46 | [10 empty] | 0
Schedule 29 | 46A | [10 empty] | 0
Schedule 29 | 47 | [10 empty] | 0
0
Schedule 32 | 1 | [10 empty] | 0
Schedule 32 | 1.1 | [10 empty] | 0
Schedule 32 | 1.2 | [10 empty] | 0
Schedule 32 | 1.2A | [10 empty] | 0
Schedule 32 | 1.3 | [10 empty] | 0
Schedule 32 | 1.4 | [10 empty] | 0
Schedule 32 | 1.5 | [10 empty] | 0
Schedule 32 | 1.6 | [10 empty] | 0
Schedule 32 | 1.7 | [10 empty] | 0
Schedule 32 | 1.8 |  |  |  |  | YES | [5 empty] | 1
Schedule 32 | 1.9 | [10 empty] | 0
Schedule 32 | 1.10 |  |  |  |  | YES | [5 empty] | 1
Schedule 32 | 2 | [10 empty] | 0
Schedule 32 | 2.1 | [10 empty] | 0
Schedule 32 | 2.2 | [10 empty] | 0
Schedule 32 | 2.3 | [10 empty] | 0
Schedule 32 | 2.4 | [10 empty] | 0
Schedule 32 | 2.5 | [10 empty] | 0
Schedule 32 | 3 | [10 empty] | 0
Schedule 32 | 3.1 |  |  |  |  | YES | [5 empty] | 1
Schedule 32 | 3.2 | [10 empty] | 0
Schedule 32 | 3.3 | [10 empty] | 0
Schedule 32 | 3.4 | [10 empty] | 0
Schedule 32 | 3.5 | [10 empty] | 0
Schedule 32 | 3.6 | [10 empty] | 0
Schedule 32 | 4 | [10 empty] | 0
Schedule 32 | 4.1 |  |  |  |  | YES | [5 empty] | 1
Schedule 32 | 4.2 |  |  |  |  | YES | [5 empty] | 1
Schedule 32 | 4.2A |  |  |  |  | YES | [5 empty] | 1
Schedule 32 | 4.3 | [10 empty] | 0
Schedule 32 | 4.4 | [10 empty] | 0
Schedule 32 | 4.5 |  |  |  |  | YES | [5 empty] | 1
Schedule 32 | 4.6 | [10 empty] | 0
Schedule 32 | 5 | [10 empty] | 0
Schedule 32 | 5.1 | [10 empty] | 0
Schedule 32 | 5.2 | [10 empty] | 0
Schedule 32 | 5.3 | [10 empty] | 0
Schedule 32 | 5A. |  |  |  |  | YES | [5 empty] | 1
Schedule 32 | 5A.1 | [10 empty] | 0
Schedule 32 | 5A.1A | [10 empty] | 0
Schedule 32 | 5A.2 | [10 empty] | 0
Schedule 32 | 6 | [10 empty] | 0
Schedule 32 | 6.1 | [5 empty] | YES |  |  |  |  | 1
Schedule 32 | 6.2 | [5 empty] | YES |  |  |  |  | 1
Schedule 32 | 6.3 |  |  |  |  | YES | [5 empty] | 1
Schedule 32 | 6.4 | [7 empty] | YES |  |  | 1
Schedule 32 | 6.4A | [10 empty] | 0
Schedule 32 | 6.5 |  |  |  |  | YES | [5 empty] | 1
Schedule 32 | 6.6 | [10 empty] | 0
Schedule 32 | 6.7 | [10 empty] | 0
Schedule 32 | 6.8 | [10 empty] | 0
Schedule 32 | 6.9 | [10 empty] | 0
Schedule 32 | 6.10 | [10 empty] | 0
Schedule 32 | 6.11 | [7 empty] | YES |  |  | 1
Schedule 32 | 6.12 | [10 empty] | 0
Schedule 32 | 7 | [10 empty] | 0
Schedule 32 | 7.1 | [10 empty] | 0
Schedule 32 | 7.2 | [10 empty] | 0
Schedule 32 | 7.3 | [10 empty] | 0
Schedule 32 | 7.4 | [10 empty] | 0
Schedule 32 | 7.5 | [10 empty] | 0
Schedule 32 | 7.6 | [10 empty] | 0
Schedule 32 | 7.7 | [10 empty] | 0
Schedule 32 | 7.8 | [10 empty] | 0
Schedule 32 | 7.9 | [10 empty] | 0
Schedule 32 | 7.1 | [10 empty] | 0
Schedule 32 | 7.11 | [10 empty] | 0
Schedule 32 | 7.12 | [10 empty] | 0
Schedule 32 | 7.13 | [10 empty] | 0
Schedule 32 | 7.14 | [10 empty] | 0
Schedule 32 | 7.15 | [10 empty] | 0
Schedule 32 | 7.16 | [10 empty] | 0
Schedule 32 | 7.17 | [7 empty] | YES |  |  | 1
Schedule 32 | 8 | [10 empty] | 0
Schedule 32 | 8.1 | [10 empty] | 0
Schedule 32 | 8.2 | [10 empty] | 0
Schedule 32 | Definitions |  |  |  |  | YES | YES |  |  |  |  | 2
Charging Methodology CPs Legal Text Overlap Tracker