## CPs
| CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Current Status | Status Changed in the last month | Date Issued to Ofgem | Original Expected Decision Date | Latest Expected Decision Date
STATUS - INITIAL ASSESSMENT
N/A
STATUS - DEFINITION
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | The intent of this modification is to define “Mixed Demand” Sites and apply a proportionate Residual charge where a Site meets the mixed demand definition. | General | 1 | John Lawton / Andy Green | Andrew Malley | 14/04/2021 | 17 | Yes - See comments in status column | TBC | The Working Group met on 02 October to review the need for a BSC change. It was agreed that a BSC change was required and that DCP 388 couldn’t be progressed until the BSC modification had been defined so DCP 388 has been paused until the Proposer raises the required BSC modification.
DCP 419 | Pre-Notifications of Planned Supply De-Energisations | This change seeks to ensure that all DCUSA Parties, that de-energise metering equipment as part of any planned work, provide the Distributor with advance notification of the supply interruption. | General | 1 | Alysson Pena / Richard Colwill | TBC | 2023-03-06 | 15 | No | Next scheduled release following approval | This CP is on hold. | #REF!
DCP 420 | Provide targeted relief from residual charges for electric vehicle charging sites | The intent of this Change Proposal is to provide targeted relief from residual charges to publicly accessible electric vehicle (“EV”) charging sites. This may be a temporary fix to be put in place until the charging stations included are commercially viable. | General | 1 | Craig Booth / Richard Colwill | Thomas Holderness | 2023-03-29 | 18 | Yes - See comments in status column | TBC | The DCUSA Secretariat is currently completing the impact assessment and will share the findings with the working group shortly. | #REF!
DCP 423 | LDNO Discounts for negative scaling | The purpose of this change proposal is to set a floor on the LDNO discount applied to negative tariff components, after scaling, for demand tariffs. The intent of this change proposal is to seek to remedy what the proposer believes is an unintended outcome of the implementation of Ofgem’s Targeted Charging Review where LDNO tariffs can be higher than the equivalent all-the-way tariff i.e. the LDNO margin is negative for that component. | CDCM | 1 | Melissa Kendal / Andy Green | TBC | 2023-05-09 | 7 | No | 2026-04-01 | The proposer has advised that they intend to withdraw this CP formally so we await that formal withdrawal notice. | #REF!
DCP 424 | Use of System charging for complex sites | This change proposal enables the correct DUoS to be paid by meters that are class F or G within a Class 5 or Class 6 Complex Site as described in BSC Modification P441 (where netting of Import and Export takes place for BSC Settlement purposes) in a practical manner. Under p441 where generation and demand are netted before settlement, the gross values must be added to the D0036 or D0275 to ensure the correct DUoS is charged. However, for class F and G the MPAN counts are included on the D0030 data flows but the volumes are zero. In order for the volumes to be correctly charged DUoS it is proposed that these volumes are included in the D0036 or D0275 using a pseudo MPAN for the gross value. | CDCM | 1 | Andy Green / Craig Booth | TBC | 2023-10-05 | 8 | Yes - See comments in status column | Aligned to BSC Mod P441 Implementation Date | A consultation has been issued with a deadline of responses set at 14 November 2025.
DCP 442 | Aligning enduring flexible connections | The intent of this Change Proposal is to align (and clarify) the two approaches that currently may result in a flexible connection being provided on an enduring basis. A flexible connection on an enduring basis is an arrangement that allows a Customer’s import/export of electricity via a connection to be restricted by a DNO/IDNO Party in perpetuity. This CP proposes that such a connection shall be a Flexible Connection rather than a Curtailable Connection. | General | 1 | Melissa Kendall / Craig Booth | TBC | 2024-07-01 | 7 | Yes - See comments in status column | 2026-04-01 | The next Working Group is currently TBC - due to the Proposer's availability. Once the next meeting has been scheduled, the aim is to finalise the draft Consultation ready to issue to wider industry. | DEFINITION
DCP 443 | Excess Capacity | The purpose of this Change Proposal is to drive the correct customer behaviour regarding exceeding capacity. | CDCM / EDCM | 1 | Melissa Kendal / Andy Green | TBC | 2024-09-07 | 16 | No | 2026-01-04 | The Working Group have agreed to issue a second consultation on this change and are reviewing/considering the consultation document.
DCP 452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | The intent of this Change Proposal is to correct an oversight in DCUSA which results in customers connecting directly to Grid Supply Point incorrectly facing a locational FCP charge relating to assets downstream of their connection. | EDCM | 1 | George Kestner / Dylan Townsend | Thomas Holderness | 2025-02-28 | 5 | No | 2027-04-01 | DCP 452 Working Group Meeting 09 was held on 28 August 2025, where the Working Group were provided with an update on progress of modelling and completion of Impact Assessment by DNOs, conducted a review of updated EDCM models and documentation, conducted a review of consultation document and draft legal text. It is hoped that a consultation will be issued within a week or two. | DEFINITION
DCP 454 | Provide enduring targeted relief from residual charges for electric vehicle charging sites | The intent of this CP is to provide enduring targeted relief from residual charges to publicly accessible electric vehicle (“EV”) charging sites. | CDCM | 1 | Craig Booth / Richard Colwill | Thomas Holderness | 2025-05-06 | 1 | Yes - See comments in status column | 2028-04-01 | The DCUSA Secretariat is currently completing the impact assessment and will share the findings with the working group shortly. | DEFINITION
DCP 458 | Amend DCP 414 process | To apply a default capacity of 71kVA following the 12 months non-applicability of capacity charging arising from DCP 414. | CDCM | 2 | Craig Booth / Andy Green | N/A | 17/07/2025 | 2 | No | 27/10/2025 | It is expected that the change report will be issued to the panel for review shortly. This will be provided ex-committee as this was raised as an urgent change. | DEFINITION
DCP 459 | DNO invoices to Embedded DNO | The intent of the Change Proposal is to require separate invoice backing data to be provided by DNO Parties when issuing invoices to EDNOs. | General | 2 | Hannah Proffitt / Andy Green | N/A | 2025-08-01 | 1 | No | 2026-02-26 | The DCP 459 consultation is currently ongoing, responses are due by 21 November 2025. |  | CONSULTATION
DCP 461 | Reducing the Impact of Transmission Distribution Charges | This Change Proposal seeks to address a growing set of structural, economic, and policy misalignments that are actively hindering the UK’s energy transition. | CCCM | 1 | Melissa Kendall / Craig Booth | N/A | 2025-08-13 | 7 | No | TBC | The DCP 461 consultation has been issued with a deadline for responses set at 28 November 2025. |  | CONSULTATION
DCP 463 | Charging non-consuming De-energised CT-Metered sites | This Change Proposal seeks to charge DUoS fixed and capacity charges to non-consuming CT-metered de-energised sites. | CCCM | 1 | Hannah Proffitt / Andy Green | N/A | 2025-09-05 | 1 | No | 2027-04-01 | The DCP 463 consultation is currently ongoing, responses are due by 28 November 2025. |  | CONSULTATION
DCP 464 | IDNO Connection Applications: Treatment of Existing Assets | The intent of this Change Proposal is to clarify and align the DNO approach to the charging methodology applied to network asset(s) for IDNO applications when the IDNO is the sole user of specific network asset(s). | General | 1 | Melissa Kendall / Craig Booth | N/A | 2025-09-08 | 2 | No | 2026-04-01 | The Working Group discussed the solutions on offer and have agreed to meet again on 25 November 2025 to work on the consultation. |  | DEFINITION
DCP 465 | NFD Generator and Battery Capacity Charges | The CDCM differs from the EDCM in that it does not treat generation sites differently to demand sites when determining the Capacity charge. This change proposal is to align The Differential In Generator and Battery Capacity charges between the two methodologies and therefore reduce the capacity charges for CDCM Generators and Batteries. | CDCM | 1 | Melissa Kendal / TBC | TBC | 2025-10-15 | 0 | No | 2028-04-01 | The panel are currently waiting for Ofgem approval for this Change Proposal due to the potential interaction with their DUoS SCR. |  | DEFINITION
STATUS - CHANGE REPORT
N/A | N/A | [7 empty] | No
STATUS - VOTING
N/A | N/A | [7 empty] | No
STATUS - AWAITING AUTHORITY CONSENT
DCP 412 | Allocation of banding for TCR Charges for ‘Peaky’ Final Demand Customers | The intent of this CP is to consider the residual charge for ‘peaky’ customers, removing the disproportionate impact of allocating residual charges on the basis of the Agreed Supply Capacity. | CDCM / EDCM | 1 | Craig Booth / Richard Colwill | Andrew Malley | 2022-10-11 | 39 | No | 10 Working Days following Authority Decision | The Working Group have finalised the change report and legal text and this is being tabled at the February Panel. DCP 412 was approved by the Panel during their meeting in February and subsequently issued to Parties for voting on 20 February 2025, with a deadline of 13 March 2025. A Change Declaration was issued to both Parties and Ofgem on 19 March 2025. | AWAITING AUTHORITY CONSENT |  | 2025-03-19 | TBC
DCP 446 | Emergency Disconnections | To enable distributors to charge customers covered by section 2 of the National Terms of Connection for emergency disconnections that have been caused by their act or omission. | General | 1 | Hannah Proffitt / Craig Booth | N/A | 2024-11-07 | 3 | No | Next scheduled release following approval | The Working Group has reviewed the legal text and change report both of which were subsequently submitted to the Panel in March, for their agreement for it to be progressed to the voting phase. The Change Report was approved at the March Panel and subsequently issued to Parties for voting. A Change Declaration was issued to both Parties and Ofgem on 17 April 2025. | AWAITING AUTHORITY CONSENT |  | 2025-04-17 | TBC
DCP 439 | Backdating Tariff Changes | This change proposal seeks to add a sensible backstop to backdating. | CDCM | 1 | Hannah Proffitt / Andy Green | James Harvey | 2024-03-14 | 9 | No | 2026-04-01 | The Change Report is due to be presented to the Panel at the July meeting. If approved it will be issued for voting on 17 July with a deadline of 08 August. | #REF! |  | 2025-08-12 | TBC
STATUS - AWAITING IMPLEMENTATION
2026-02-26
DCP 455 | Align RAV price-inflation with that used in ED2 | ED2 PCFM uses a combination of RPI and CPIH to uplift from 2020/21 to outturn prices. This change seeks to align the prescribed calculation of RAV in Schedule 1, to retain consistency of credit cover calculation with ED2 PCFM. | General | 2 | Hannah Proffitt / Richard Colwill | N/A | 2025-05-22 | 0 | No | 2025-12-01 | DCP 455 will be implemented on 26/02/2026 - this follows on from the Party voting, the outcome for which was a decision that the change be made. |  | AWAITING IMPLEMENTATION
2027-04-01
DCP 440 | Consuming “de-energised” sites | To ensure all consuming “de-energised” sites are charged DUoS. | CDCM | 1 | Hannah Proffitt / Andy Green | Shaun McRaith | 2024-03-14 | 10 | No | 2027-04-01 | On 29 August 2025, Ofgem issued their decision to approve DCP 456. DCP 440 will be implemented on 01/04/2027.
DCP 450 | Managing the effects of surplus residual charge in the CDCM | To determine the appropriate arrangements for managing the effects of large residual values in the CDCM. | CDCM | 1 | Hannah Proffitt / Craig Booth | James Harvey | 2025-02-10 | 3 | No | 2027-04-01 | On 20 October 2025, Ofgem published their decision to accept DCP 450. The Change is now awaiting implementation. DCP 450 will be implemented on 01/04/2027. |  | AWAITING IMPLEMENTATION
STATUS - SENT BACK
N/A | N/A | [7 empty] | No
STATUS - IMPLEMENTED
DCP 460 | Updating Incorrect Company Names Referenced throughout the DCUSA | The intent of this CP is to ensure that any references to the company names of specific Parties within the DCUSA are correct and to explore the possibility of future proofing these against any future changes. | Standard | 2 | Dylan Townsend | N/A | 2025-08-12 | 9 | No | 2025-11-06 | DCP 460 was presented to the DCUSA Panel for their initial assessment during their meeting on 20 August 2025. The DCUSA Panel agreed that it could be progressed directly to the Change Report phase, with the caveat that should it be determined to require input from Parties post legal review, then the Panel may re-direct the Change Proposal to be assessed by a Working Group. |  | IMPLEMENTED
DCP 457 | Housekeeping Items | To fix housekeeping items 124, 125, 126, 128, 129, 130, 131. | Standard | 2 | Dylan Townsend | N/A | 2024-03-14 | 9 | No | 2025-11-06 | DCP 457 was presented to the DCUSA Panel for their initial assessment during their meeting on 17 July 2024. The DCUSA Panel agreed that DCP 457 be progressed directly to the Change Report phase. The Change Report was presented to the Panel at the Auigust meeting, where the Panel approved for it to be issued for voting on 20 August. |  | IMPLEMENTED
DCP 325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20. | The intent of this Change Proposal is to combine, review and if appropriate, amend the requirements of Section 35A, Section 35B, Schedule 15 and Schedule 20 to improve transparency and efficiency in the data published by DNOs | General | 2 | Richard Colwill / Melissa Kendal | N/A | 2018-07-11 | 19 | No | 2025-11-06 | Legal text finalised and the Change Report has been agreed. The modelling was approved by the DCUSA panel on 09 June 2025 and issued to CEPA/TNEI on the same day. |  | IMPLEMENTED
DCP 462 | Impact of MHHS on certain DCUSA owned flows | The intent of the Change Proposal is to facilitate change to DCUSA owned Market Messages and to make updates to specific Market Messages, which have Scenario Variants that are solely owned by DCUSA, to align the requirements for MHHS, including any appropriate additional Scenario Variants that might need to be added for newly created for MHHS entities. | General | 1 | Dylan Townsend | N/A | 2025-09-12 | N/A | No | 2025-10-22 | The Panel approved for the Change Report for DCP 462 to be issued to Parties for voting on 18 September 2025 for a period of 5 Working Days. On 25 September 2025, the Party votes were counted and then a Change Declaration issued. The outcome of the Party vote was that Parties had voted to accept the proposed variation as well as the proposed implementation date. The change was subsequently issued to Ofgem for final decision. Ofgem's decision to approve DCP 462 was provided on 07 October 2025 |  | IMPLEMENTED
STATUS - REJECTED
DCP 437 | To Shorten the DUoS Pricing Notice Periods | This change proposal aims to shorten the DUoS Pricing Notice Periods so there is longer period between the publication of the PCFM where OFGEM have the option to make changes to our allowed revenue at short notice and the setting of the prices | CDCM | 1 | Hannah Proffitt / Richard Colwill | James Harvey | 45335 | 7 | No | 1 Working Day following approval | The Change Declaration for DCP 437 was issued to Ofgem on 16 June 2025. On 10 October 2025 the Authority issued their decision letter, which set out their decision to reject DCP 437. | SENT BACK | REJECTED
STATUS - WITHDRAWN
N/A
Change Register - November 2025

## Status Changes
[14 empty] | AWAITING IMPLEMENTATION | 0
[14 empty] | IMPLEMENTED | 0
[14 empty] | REJECTED | 0
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status | Status Changed in the last month | DEFINITION | 4
DCP 459 | DNO invoices to Embedded DNO | The intent of the Change Proposal is to require separate invoice backing data to be provided by DNO Parties when issuing invoices to EDNOs. | General | 2 | Hannah Proffitt / Andy Green | N/A | 2025-08-01 | 1 | No | 46079 | The DCP 459 consultation is currently ongoing, responses are due by 21 November 2025. | 0 | CONSULTATION
DCP 461 | Reducing the Impact of Transmission Distribution Charges | This Change Proposal seeks to address a growing set of structural, economic, and policy misalignments that are actively hindering the UK’s energy transition. | CCCM | 1 | Melissa Kendall / Craig Booth | N/A | 2025-08-13 | 7 | No | TBC | The DCP 461 consultation has been issued with a deadline for responses set at 28 November 2025. | 0 | CONSULTATION
DCP 463 | Charging non-consuming De-energised CT-Metered sites | This Change Proposal seeks to charge DUoS fixed and capacity charges to non-consuming CT-metered de-energised sites. | CCCM | 1 | Hannah Proffitt / Andy Green | N/A | 2025-09-05 | 1 | No | 2027-04-01 | The DCP 463 consultation is currently ongoing, responses are due by 28 November 2025. | 0 | CONSULTATION
DCP 464 | IDNO Connection Applications: Treatment of Existing Assets | The intent of this Change Proposal is to clarify and align the DNO approach to the charging methodology applied to network asset(s) for IDNO applications when the IDNO is the sole user of specific network asset(s). | General | 1 | Melissa Kendall / Craig Booth | N/A | 2025-09-08 | 2 | No | 46113 | The Working Group discussed the solutions on offer and have agreed to meet again on 25 November 2025 to work on the consultation. | 0 | DEFINITION
DCP 465 | NFD Generator and Battery Capacity Charges | The CDCM differs from the EDCM in that it does not treat generation sites differently to demand sites when determining the Capacity charge. This change proposal is to align The Differential In Generator and Battery Capacity charges between the two methodologies and therefore reduce the capacity charges for CDCM Generators and Batteries. | CDCM | 1 | Melissa Kendal / TBC | TBC | 2025-10-15 | 0 | No | 2028-04-01 | The panel are currently waiting for Ofgem approval for this Change Proposal due to the potential interaction with their DUoS SCR. | 0 | DEFINITION
DCP 455 | Align RAV price-inflation with that used in ED2 | ED2 PCFM uses a combination of RPI and CPIH to uplift from 2020/21 to outturn prices. This change seeks to align the prescribed calculation of RAV in Schedule 1, to retain consistency of credit cover calculation with ED2 PCFM. | General | 2 | Hannah Proffitt / Richard Colwill | N/A | 2025-05-22 | 0 | No | 45992 | DCP 455 will be implemented on 26/02/2026 - this follows on from the Party voting, the outcome for which was a decision that the change be made. | 0 | AWAITING IMPLEMENTATION
DCP 450 | Managing the effects of surplus residual charge in the CDCM | To determine the appropriate arrangements for managing the effects of large residual values in the CDCM. | CDCM | 1 | Hannah Proffitt / Craig Booth | James Harvey | 2025-02-10 | 3 | No | 46478 | On 20 October 2025, Ofgem published their decision to accept DCP 450. The Change is now awaiting implementation. DCP 450 will be implemented on 01/04/2027. | 0 | AWAITING IMPLEMENTATION
DCP 460 | Updating Incorrect Company Names Referenced throughout the DCUSA | The intent of this CP is to ensure that any references to the company names of specific Parties within the DCUSA are correct and to explore the possibility of future proofing these against any future changes. | Standard | 2 | Dylan Townsend | N/A | 2025-08-12 | 9 | No | 45967 | DCP 460 was presented to the DCUSA Panel for their initial assessment during their meeting on 20 August 2025. The DCUSA Panel agreed that it could be progressed directly to the Change Report phase, with the caveat that should it be determined to require input from Parties post legal review, then the Panel may re-direct the Change Proposal to be assessed by a Working Group. | 0 | IMPLEMENTED
DCP 457 | Housekeeping Items | To fix housekeeping items 124, 125, 126, 128, 129, 130, 131. | Standard | 2 | Dylan Townsend | N/A | 2024-03-14 | 9 | No | 45967 | DCP 457 was presented to the DCUSA Panel for their initial assessment during their meeting on 17 July 2024. The DCUSA Panel agreed that DCP 457 be progressed directly to the Change Report phase. The Change Report was presented to the Panel at the Auigust meeting, where the Panel approved for it to be issued for voting on 20 August. | 0 | IMPLEMENTED
DCP 325 | Reviewing the requirements of Sections 35A, 35B, Schedule 15 and Schedule 20. | The intent of this Change Proposal is to combine, review and if appropriate, amend the requirements of Section 35A, Section 35B, Schedule 15 and Schedule 20 to improve transparency and efficiency in the data published by DNOs | General | 2 | Richard Colwill / Melissa Kendal | N/A | 2018-07-11 | 19 | No | 45967 | Legal text finalised and the Change Report has been agreed. The modelling was approved by the DCUSA panel on 09 June 2025 and issued to CEPA/TNEI on the same day. | 0 | IMPLEMENTED
DCP 462 | Impact of MHHS on certain DCUSA owned flows | The intent of the Change Proposal is to facilitate change to DCUSA owned Market Messages and to make updates to specific Market Messages, which have Scenario Variants that are solely owned by DCUSA, to align the requirements for MHHS, including any appropriate additional Scenario Variants that might need to be added for newly created for MHHS entities. | General | 1 | Dylan Townsend | N/A | 2025-09-12 | N/A | No | 45952 | The Panel approved for the Change Report for DCP 462 to be issued to Parties for voting on 18 September 2025 for a period of 5 Working Days. On 25 September 2025, the Party votes were counted and then a Change Declaration issued. The outcome of the Party vote was that Parties had voted to accept the proposed variation as well as the proposed implementation date. The change was subsequently issued to Ofgem for final decision. Ofgem's decision to approve DCP 462 was provided on 07 October 2025 | 0 | IMPLEMENTED
DCP 437 | To Shorten the DUoS Pricing Notice Periods | This change proposal aims to shorten the DUoS Pricing Notice Periods so there is longer period between the publication of the PCFM where OFGEM have the option to make changes to our allowed revenue at short notice and the setting of the prices | CDCM | 1 | Hannah Proffitt / Richard Colwill | James Harvey | 2024-02-13 | 7 | No | 1 Working Day following approval | The Change Declaration for DCP 437 was issued to Ofgem on 16 June 2025. On 10 October 2025 the Authority issued their decision letter, which set out their decision to reject DCP 437. | SENT BACK | REJECTED
Status Change - November 2025

## Timetables
DCP | Title | Part 1/ Part 2 Matter | Timetable Change | Nov | Dec | Jan | Feb
464 | IDNO Connection Applications: Treatment of Existing Assets | Part 1 | N | CON | DEF | CR
463 | Charging non-consuming De-energised CT-Metered sites | Part 1 | N | CON | DEF | DEF | CR
461 | Reducing the Impact of Transmission Distribution Charges | Part 1 | N | CON | DEF | DEF | CR
459 | DNO invoices to Embedded DNO | Part 1 | N | DEF | CR
458 | Amend DCP 414 process | Part 2 | N | CR
454 | Provide enduring targeted relief from residual charges for electric vehicle charging sites | Part 1 | N | DEF | CON | DEF | CR
452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | Part 1 | N | DEF | CR
443 | Excess Capacity | Part 1 | N | CR
Timetable Change |  |  |  | DEF | CON | DEF | CR
442 | Aligning enduring flexible connections | Part 1 | N | O/H
424 | Use of System charging for complex sites | Part 1 | N | O/H
423 | LDNO Discounts for negative scaling | Part 1 | N | O/H
420 | Include Car Charging Stations In The Definition For Non Final Demand | Part 1 | N | DEF | CON | DEF | CR
419 | Pre-notification of Planned Supply De-energisations | Part 1 | N | On hold
388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | Part 1 | N | O/H
| DEFINITION | DEF
| RFI | RFI
| CONSULTATION | CON/ CON 2
| CHANGE REPORT | CR
| ON HOLD | O/H

## Legal Text Overlap Tracker
YES
|  | DCP 424 | DCP 423 | DCP 388 | DCP 412 | DCP 420 | DCP 439 | DCP 440 | DCP 450 | DCP 443 | DCP 458 | DCP 463 | DCP 452
|  | 2026-12-31 | 2026-04-01 | 2027-01-18 | TBC | 2026-11-01 | 2026-04-01 | 2027-04-01 | 2027-04-01 | 2026-04-01 | 2025-11-28 | 2027-04-01 | 2028-04-01 |  | NOTES TO ASSIST
Schedules | Paragraph Number | Consultation | Definition | On Hold | Awaiting Consent | Definition | Awaiting Consent | Awaiting Implementation | Awaiting Implementation | Definition | Definition | Definition | Definition | Number of CPs Impacting Paragraph
Schedule 15 | - | [12 empty] | 0
0
Schedule 16 | Introduction | [12 empty] | 0
Schedule 16 | 1 | [12 empty] | 0
Schedule 16 | 2 | [12 empty] | 0
Schedule 16 | 3 | [12 empty] | 0
Schedule 16 | 4 | [12 empty] | 0
Schedule 16 | 5 | [12 empty] | 0
Schedule 16 | 6 | [12 empty] | 0
Schedule 16 | 7 | [12 empty] | 0
Schedule 16 | 7A | [12 empty] | 0
Schedule 16 | 8 | [12 empty] | 0
Schedule 16 | 9 | [12 empty] | 0
Schedule 16 | 10 | [12 empty] | 0
Schedule 16 | 10A | [12 empty] | 0
Schedule 16 | 11 | [12 empty] | 0
Schedule 16 | 12 | [12 empty] | 0
Schedule 16 | 13 | [12 empty] | 0
Schedule 16 | 14 | [12 empty] | 0
Schedule 16 | 15 | [12 empty] | 0
Schedule 16 | 16 | [12 empty] | 0
Schedule 16 | 17 | [12 empty] | 0
Schedule 16 | 18 | [12 empty] | 0
Schedule 16 | 19 | [12 empty] | 0
Schedule 16 | 20 | [12 empty] | 0
Schedule 16 | 21 | [12 empty] | 0
Schedule 16 | 22 | [12 empty] | 0
Schedule 16 | 23 | [12 empty] | 0
Schedule 16 | 24 | [12 empty] | 0
Schedule 16 | 25 | [12 empty] | 0
Schedule 16 | 26 | [12 empty] | 0
Schedule 16 | 27 | [12 empty] | 0
Schedule 16 | 28 | [12 empty] | 0
Schedule 16 | 29 | [12 empty] | 0
Schedule 16 | 30 | [12 empty] | 0
Schedule 16 | 31 | [12 empty] | 0
Schedule 16 | 32 | [12 empty] | 0
Schedule 16 | 33 | [12 empty] | 0
Schedule 16 | 34 | [12 empty] | 0
Schedule 16 | 35 | [12 empty] | 0
Schedule 16 | 36 | [12 empty] | 0
Schedule 16 | 37 | [12 empty] | 0
Schedule 16 | 38 | [12 empty] | 0
Schedule 16 | 39 | [12 empty] | 0
Schedule 16 | 40 | [12 empty] | 0
Schedule 16 | 41 | [12 empty] | 0
Schedule 16 | 41A | [12 empty] | 0
Schedule 16 | 41B | [12 empty] | 0
Schedule 16 | 42 | [12 empty] | 0
Schedule 16 | 42A | [12 empty] | 0
Schedule 16 | 43 | [12 empty] | 0
Schedule 16 | 44 | [12 empty] | 0
Schedule 16 | 45 | [12 empty] | 0
Schedule 16 | 46 | [12 empty] | 0
Schedule 16 | 47 | [12 empty] | 0
Schedule 16 | 48 | [12 empty] | 0
Schedule 16 | 49 | [12 empty] | 0
Schedule 16 | 50 | [12 empty] | 0
Schedule 16 | 51 | [12 empty] | 0
Schedule 16 | 52 | [12 empty] | 0
Schedule 16 | 52A | [12 empty] | 0
Schedule 16 | 53 | [12 empty] | 0
Schedule 16 | 54 | [12 empty] | 0
Schedule 16 | 55 | [12 empty] | 0
Schedule 16 | 56 | [12 empty] | 0
Schedule 16 | 57 | [12 empty] | 0
Schedule 16 | 58 | [12 empty] | 0
Schedule 16 | 59 | [12 empty] | 0
Schedule 16 | 60 | [12 empty] | 0
Schedule 16 | 61 | [12 empty] | 0
Schedule 16 | 62 | [12 empty] | 0
Schedule 16 | 63 | [12 empty] | 0
Schedule 16 | 64 | [12 empty] | 0
Schedule 16 | 65 | [12 empty] | 0
Schedule 16 | 66 | [12 empty] | 0
Schedule 16 | 67 | [12 empty] | 0
Schedule 16 | 68 | [12 empty] | 0
Schedule 16 | 69 | [12 empty] | 0
Schedule 16 | 70 | [12 empty] | 0
Schedule 16 | 71 | [12 empty] | 0
Schedule 16 | 72 | [12 empty] | 0
Schedule 16 | 72A | [12 empty] | 0
Schedule 16 | 73 | [12 empty] | 0
Schedule 16 | 74 | [12 empty] | 0
Schedule 16 | 75 | [12 empty] | 0
Schedule 16 | 76 | [12 empty] | 0
Schedule 16 | 77 | [12 empty] | 0
Schedule 16 | 78 | [12 empty] | 0
Schedule 16 | 79 | [12 empty] | 0
Schedule 16 | 80 | [12 empty] | 0
Schedule 16 | 81 | [12 empty] | 0
Schedule 16 | 82 | [12 empty] | 0
Schedule 16 | 83 | [12 empty] | 0
Schedule 16 | 84 | [12 empty] | 0
Schedule 16 | 85 | [12 empty] | 0
Schedule 16 | 86 | [12 empty] | 0
Schedule 16 | 87 | [12 empty] | 0
Schedule 16 | 88 | [12 empty] | 0
Schedule 16 | 89 | [12 empty] | 0
Schedule 16 | 90 | [12 empty] | 0
Schedule 16 | 91 | [12 empty] | 0
Schedule 16 | 92 | [12 empty] | 0
Schedule 16 | 92A | [12 empty] | 0
Schedule 16 | 92B | [12 empty] | 0
Schedule 16 | 92C | [12 empty] | 0
Schedule 16 | 93 | [12 empty] | 0
Schedule 16 | 94 | [12 empty] | 0
Schedule 16 | 94A | [12 empty] | 0
Schedule 16 | 94B | [7 empty] | YES |  |  |  |  | 1
Schedule 16 | 95 | [12 empty] | 0
Schedule 16 | 96 | [12 empty] | 0
Schedule 16 | 97 | [12 empty] | 0
Schedule 16 | 98 |  | YES | [10 empty] | 1
Schedule 16 | 99 | [12 empty] | 0
Schedule 16 | 100 | [12 empty] | 0
Schedule 16 | 101 | [12 empty] | 0
Schedule 16 | 102 | [12 empty] | 0
Schedule 16 | 102A | [12 empty] | 0
Schedule 16 | 102B | [12 empty] | 0
Schedule 16 | 103 | [12 empty] | 0
Schedule 16 | 104 | [12 empty] | 0
Schedule 16 | 105 | [12 empty] | 0
Schedule 16 | 106 | [12 empty] | 0
Schedule 16 | 107 | [12 empty] | 0
Schedule 16 | 108 | [12 empty] | 0
Schedule 16 | 108A | [12 empty] | 0
Schedule 16 | 109 | [12 empty] | 0
Schedule 16 | 110 | [12 empty] | 0
Schedule 16 | 111 | [12 empty] | 0
Schedule 16 | 112 | [12 empty] | 0
Schedule 16 | 112A | [12 empty] | 0
Schedule 16 | 113 | [12 empty] | 0
Schedule 16 | 113A | [12 empty] | 0
Schedule 16 | 113B | [12 empty] | 0
Schedule 16 | 113C | [12 empty] | 0
Schedule 16 | 113D | [12 empty] | 0
Schedule 16 | 113E | [12 empty] | 0
Schedule 16 | 114 | [12 empty] | 0
Schedule 16 | 115 | [12 empty] | 0
Schedule 16 | 116 | [12 empty] | 0
Schedule 16 | 117 | [12 empty] | 0
Schedule 16 | 118 | [12 empty] | 0
Schedule 16 | 119 | [12 empty] | 0
Schedule 16 | 120 | [12 empty] | 0
Schedule 16 | 121 | [12 empty] | 0
Schedule 16 | 122 | [12 empty] | 0
Schedule 16 | 123 | [12 empty] | 0
Schedule 16 | 124 | [12 empty] | 0
Schedule 16 | 125 | [12 empty] | 0
Schedule 16 | 126 | [12 empty] | 0
Schedule 16 | 127 | [12 empty] | 0
Schedule 16 | 127A | [12 empty] | 0
Schedule 16 | 128 | YES | [11 empty] | 1
Schedule 16 | 129 | [12 empty] | 0
Schedule 16 | 130 | [12 empty] | 0
Schedule 16 | 131 | [12 empty] | 0
Schedule 16 | 132 | [12 empty] | 0
Schedule 16 | 132A | [12 empty] | 0
Schedule 16 | 132B | [12 empty] | 0
Schedule 16 | 132C | [12 empty] | 0
Schedule 16 | 132D | [12 empty] | 0
Schedule 16 | 133 | [12 empty] | 0
Schedule 16 | 134 | [12 empty] | 0
Schedule 16 | 135 | [12 empty] | 0
Schedule 16 | 135A | [12 empty] | 0 | MHHS CP seeks to remove the last column containing applicable Measurement Class
Schedule 16 | 135B | [12 empty] | 0
Schedule 16 | 136 | [12 empty] | 0
Schedule 16 | 137 | [12 empty] | 0
Schedule 16 | 138 | [12 empty] | 0
Schedule 16 | 139 | [6 empty] | YES |  |  |  | YES |  | 2
Schedule 16 | 140 | [6 empty] | YES |  |  |  | YES |  | 2
Schedule 16 | 140A | [12 empty] | 0
Schedule 16 | 140B | [12 empty] | 0
Schedule 16 | 140C | [12 empty] | 0
Schedule 16 | 140D | [12 empty] | 0
Schedule 16 | 140E | [12 empty] | 0
Schedule 16 | 141 | [12 empty] | 0
Schedule 16 | 142 | [12 empty] | 0
Schedule 16 | 143 | [12 empty] | 0
Schedule 16 | 144 | [12 empty] | 0
Schedule 16 | 145 | [12 empty] | 0
Schedule 16 | 146 | [12 empty] | 0
Schedule 16 | 147 | [12 empty] | 0
Schedule 16 | 148 | [12 empty] | 0
Schedule 16 | 149 | [12 empty] | 0
Schedule 16 | 150 | [12 empty] | 0
Schedule 16 | 151 | [12 empty] | 0
Schedule 16 | 152 | [12 empty] | 0
Schedule 16 | 153 | [8 empty] | YES |  |  |  | 1
Schedule 16 | 154 | [12 empty] | 0
Schedule 16 | 155 | [12 empty] | 0
Schedule 16 | 156 | [12 empty] | 0
Schedule 16 | 157 | [12 empty] | 0
Schedule 16 | 158 | [12 empty] | 0
Schedule 16 | 159 | [12 empty] | 0
Schedule 16 | 160 | [12 empty] | 0
Schedule 16 | 161 | [12 empty] | 0
Schedule 16 | 162 | [12 empty] | 0
Schedule 16 | 163 | [12 empty] | 0
Schedule 16 | 164 | [12 empty] | 0
Schedule 16 | 165 | [12 empty] | 0
Schedule 16 | 166 | [12 empty] | 0
Schedule 16 | 167 | [12 empty] | 0
Schedule 16 | 168 | [12 empty] | 0
Schedule 16 | 169 | [12 empty] | 0
Schedule 16 | 170 | [12 empty] | 0
Schedule 16 | 171 | [12 empty] | 0
Schedule 16 | 172 | [12 empty] | 0
Schedule 16 | 173 | [12 empty] | 0
Schedule 16 | 173A | [5 empty] | YES | [6 empty] | 1 | DCP 439 Introduces new Paragraph 173A
Schedule 16 | 174 | [12 empty] | 0
Schedule 16 | 175 | [12 empty] | 0
Schedule 16 | 176 | [12 empty] | 0
Schedule 16 | 177 | [12 empty] | 0
Schedule 16 | 178 | [12 empty] | 0
Schedule 16 | 179 | [12 empty] | 0
Schedule 16 | 180 | [12 empty] | 0
Schedule 16 | 181 | [9 empty] | YES |  |  | 1
Schedule 16 | 182 | [9 empty] | YES |  |  | 1
Schedule 16 | 183 | [12 empty] | 0
Schedule 16 | 184 | [12 empty] | 0
Schedule 16 | Glossary | [12 empty] | 0
0
Schedule 17 | Introduction | [12 empty] | 0
Schedule 17 | 1 | [12 empty] | 0
Schedule 17 | 1.1 | [12 empty] | 0
Schedule 17 | 1.2 | [12 empty] | 0
Schedule 17 | 1.3 | [12 empty] | 0 | Model reference number and date
Schedule 17 | 1.3A | [12 empty] | 0
Schedule 17 | 1.4 | [12 empty] | 0
Schedule 17 | 1.5 | [12 empty] | 0
Schedule 17 | 1.6 | [12 empty] | 0
Schedule 17 | 1.7 | [12 empty] | 0
Schedule 17 | 1.8 | [12 empty] | 0
Schedule 17 | 1.9 | [12 empty] | 0
Schedule 17 | 2 | [12 empty] | 0
Schedule 17 | 2.1 | [12 empty] | 0
Schedule 17 | 2.2 | [12 empty] | 0
Schedule 17 | 2.3 | [12 empty] | 0
Schedule 17 | 2.4 | [12 empty] | 0
Schedule 17 | 2.5 | [12 empty] | 0
Schedule 17 | 2.6 | [12 empty] | 0
Schedule 17 | 2.7 | [11 empty] | YES | 0
Schedule 17 | 2.8 | [12 empty] | 0
Schedule 17 | 2.9 | [12 empty] | 0
Schedule 17 | 2.1 | [12 empty] | 0
Schedule 17 | 2.11 | [12 empty] | 0
Schedule 17 | 2.12 | [12 empty] | 0
Schedule 17 | 2.13 | [12 empty] | 0
Schedule 17 | 2.14 | [12 empty] | 0
Schedule 17 | 2.15 | [12 empty] | 0
Schedule 17 | 2.16 | [12 empty] | 0
Schedule 17 | 2.17 | [12 empty] | 0
Schedule 17 | 2.18 | [12 empty] | 0
Schedule 17 | 2.19 | [12 empty] | 0
Schedule 17 | 3 | [12 empty] | 0
Schedule 17 | 3.1 | [12 empty] | 0
Schedule 17 | 3.2 | [12 empty] | 0
Schedule 17 | 3.3 | [12 empty] | 0
Schedule 17 | 3.4 | [12 empty] | 0
Schedule 17 | 3.5 | [12 empty] | 0
Schedule 17 | 3.6 | [12 empty] | 0
Schedule 17 | 3.7 | [12 empty] | 0
Schedule 17 | 4 | [12 empty] | 0
Schedule 17 | 4.1 | [12 empty] | 0
Schedule 17 | 5 | [12 empty] | 0
Schedule 17 | 5.1 | [12 empty] | 0
Schedule 17 | 6 | [12 empty] | 0
Schedule 17 | 6.1 | [12 empty] | 0
Schedule 17 | 6.2 | [11 empty] | YES | 0
Schedule 17 | 6.3 | [11 empty] | YES | 0
Schedule 17 | 7 | [12 empty] | 0
Schedule 17 | 7.1 | [12 empty] | 0
Schedule 17 | 8 | [12 empty] | 0
Schedule 17 | 8.1 | [12 empty] | 0
Schedule 17 | 8.2 | [12 empty] | 0
Schedule 17 | 8.3 | [12 empty] | 0
Schedule 17 | 8.4 | [12 empty] | 0
Schedule 17 | 9 | [12 empty] | 0
Schedule 17 | 9.1 | [12 empty] | 0
Schedule 17 | 9.2 | [12 empty] | 0
Schedule 17 | 9.3 | [12 empty] | 0
Schedule 17 | 10 | [12 empty] | 0
Schedule 17 | 10.1 | [12 empty] | 0
Schedule 17 | 10.2 | [12 empty] | 0
Schedule 17 | 10.3 | [12 empty] | 0
Schedule 17 | 10.4 | [12 empty] | 0
Schedule 17 | 11 | [12 empty] | 0
Schedule 17 | 11.1 | [12 empty] | 0
Schedule 17 | 12 | [12 empty] | 0
Schedule 17 | 12.1 | [12 empty] | 0
Schedule 17 | 12.2 | [12 empty] | 0
Schedule 17 | 12.3 | [12 empty] | 0
Schedule 17 | 13 | [12 empty] | 0
Schedule 17 | 13.1 | [12 empty] | 0
Schedule 17 | 13.2 | [12 empty] | 0
Schedule 17 | 13.3 | [12 empty] | 0
Schedule 17 | 13.4 | [12 empty] | 0
Schedule 17 | 14 | [12 empty] | 0
Schedule 17 | 14.1 | [12 empty] | 0
Schedule 17 | 14.2 | [12 empty] | 0
Schedule 17 | 14.3 | [12 empty] | 0
Schedule 17 | 14.4 | [12 empty] | 0
Schedule 17 | 14.5 | [12 empty] | 0
Schedule 17 | 15 | [12 empty] | 0
Schedule 17 | 15.1 | [12 empty] | 0
Schedule 17 | 15.2 | [12 empty] | 0
Schedule 17 | 15.3 | [12 empty] | 0
Schedule 17 | 15.4 | [12 empty] | 0
Schedule 17 | 15.5 | [12 empty] | 0
Schedule 17 | 15.6 | [12 empty] | 0
Schedule 17 | 15.7 | [12 empty] | 0
Schedule 17 | 15.8 | [12 empty] | 0
Schedule 17 | 15.9 | [12 empty] | 0
Schedule 17 | 15.1 | [12 empty] | 0
Schedule 17 | 15.11 | [12 empty] | 0
Schedule 17 | 15.12 | [12 empty] | 0
Schedule 17 | 15.15 | [12 empty] | 0
Schedule 17 | 16 | [12 empty] | 0
Schedule 17 | 16.1 | [12 empty] | 0
Schedule 17 | 16.2 | [12 empty] | 0
Schedule 17 | 16.3 | [12 empty] | 0
Schedule 17 | 16.4 | [12 empty] | 0
Schedule 17 | 16.5 | [12 empty] | 0
Schedule 17 | 16.6 | [12 empty] | 0
Schedule 17 | 16.7 | [12 empty] | 0
Schedule 17 | 16.8 | [12 empty] | 0
Schedule 17 | 16.9 | [12 empty] | 0
Schedule 17 | 16.1 | [12 empty] | 0
Schedule 17 | 17 | [12 empty] | 0
Schedule 17 | 17.1 | [12 empty] | 0
Schedule 17 | 17.2 | [12 empty] | 0
Schedule 17 | 17.3 | [12 empty] | 0
Schedule 17 | 18 | [12 empty] | 0
Schedule 17 | 18.1 | [12 empty] | 0
Schedule 17 | 18.2 | [12 empty] | 0
Schedule 17 | 18.3 | [12 empty] | 0
Schedule 17 | 18.4 | [12 empty] | 0
Schedule 17 | 18.5 | [12 empty] | 0
Schedule 17 | 18.6 | [12 empty] | 0
Schedule 17 | 18.7 | [12 empty] | 0
Schedule 17 | 18.8 | [12 empty] | 0
Schedule 17 | 18.9 | [12 empty] | 0
Schedule 17 | 18.1 | [12 empty] | 0
Schedule 17 | 18.11 | [12 empty] | 0
Schedule 17 | 18.12 | [12 empty] | 0
Schedule 17 | 18.13 | [12 empty] | 0
Schedule 17 | 18.14 | [12 empty] | 0
Schedule 17 | 18.15 | [12 empty] | 0
Schedule 17 | 18.16 | [12 empty] | 0
Schedule 17 | 18.17 | [12 empty] | 0
Schedule 17 | 18.18 | [12 empty] | 0
Schedule 17 | 18.19 | [12 empty] | 0
Schedule 17 | 18.2 | [12 empty] | 0
Schedule 17 | 18.21 | [12 empty] | 0
Schedule 17 | 19 | [12 empty] | 0
Schedule 17 | 19.1 | [12 empty] | 0
Schedule 17 | 19.2 | [12 empty] | 0
Schedule 17 | 19.3 | [12 empty] | 0
Schedule 17 | 19.4 | [12 empty] | 0
Schedule 17 | 19.5 | [12 empty] | 0
Schedule 17 | 19.6 | [12 empty] | 0
Schedule 17 | 19.7 | [12 empty] | 0
Schedule 17 | 19.8 | [12 empty] | 0
Schedule 17 | 19.9 | [12 empty] | 0
Schedule 17 | 19.1 | [12 empty] | 0
Schedule 17 | 19.11 | [12 empty] | 0
Schedule 17 | 20 | [12 empty] | 0
Schedule 17 | 20.1 | [12 empty] | 0
Schedule 17 | 20.2 | [12 empty] | 0
Schedule 17 | 20.3 | [12 empty] | 0
Schedule 17 | 20.4 | [12 empty] | 0
Schedule 17 | 20.5 | [12 empty] | 0
Schedule 17 | 20.6 | [8 empty] | YES |  |  |  | 1
Schedule 17 | 20.7 | [8 empty] | YES |  |  |  | 1
Schedule 17 | 20.8 | [12 empty] | 0
Schedule 17 | 20.9 | [8 empty] | YES |  |  |  | 1
Schedule 17 | 21 | [12 empty] | 0
Schedule 17 | 21.1 | [12 empty] | 0
Schedule 17 | 21.2 | [12 empty] | 0
Schedule 17 | 22 | [12 empty] | 0
Schedule 17 | 22.1 | [12 empty] | 0
Schedule 17 | 22.2 | [12 empty] | 0
Schedule 17 | 22.3 | [12 empty] | 0
Schedule 17 | 22.4 | [12 empty] | 0
Schedule 17 | 23 | [12 empty] | 0
Schedule 17 | 23.1 | [12 empty] | 0
Schedule 17 | 23.2 | [12 empty] | 0
Schedule 17 | 23.3 | [12 empty] | 0
Schedule 17 | 23.4 | [12 empty] | 0
Schedule 17 | 23.5 | [12 empty] | 0
Schedule 17 | 24 | [12 empty] | 0
Schedule 17 | 24.1 | [12 empty] | 0
Schedule 17 | 24.2 | [12 empty] | 0
Schedule 17 | 24.3 | [12 empty] | 0
Schedule 17 | 24.4 | [12 empty] | 0
Schedule 17 | 24.5 | [12 empty] | 0
Schedule 17 | 24.6 | [12 empty] | 0
Schedule 17 | 24.7 | [12 empty] | 0
Schedule 17 | 24.8 | [12 empty] | 0
Schedule 17 | 24.9 | [12 empty] | 0
Schedule 17 | 25 | [12 empty] | 0
Schedule 17 | 25.1 | [12 empty] | 0
Schedule 17 | 25.2 | [12 empty] | 0
Schedule 17 | 25.3 | [12 empty] | 0
Schedule 17 | 25.4 | [12 empty] | 0
Schedule 17 | 25.5 | [12 empty] | 0
Schedule 17 | 25.6 | [12 empty] | 0
Schedule 17 | 25.7 | [12 empty] | 0
Schedule 17 | 25.8 | [12 empty] | 0
Schedule 17 | 25.9 | [12 empty] | 0
Schedule 17 | 25.1 | [12 empty] | 0
Schedule 17 | 25.11 | [12 empty] | 0
Schedule 17 | 25.12 | [12 empty] | 0
Schedule 17 | 25.13 | [12 empty] | 0
Schedule 17 | 25.14 | [12 empty] | 0
Schedule 17 | 25.15 | [12 empty] | 0
Schedule 17 | 25.16 | [12 empty] | 0
Schedule 17 | 25.17 | [12 empty] | 0
Schedule 17 | 25.18 | [12 empty] | 0
Schedule 17 | 25.19 | [12 empty] | 0
Schedule 17 | 26 | [12 empty] | 0
Schedule 17 | 26.1 | [12 empty] | 0
Schedule 17 | 26.2 | [12 empty] | 0
Schedule 17 | 26.3 | [12 empty] | 0
Schedule 17 | 26.4 | [12 empty] | 0
Schedule 17 | 26.5 | [12 empty] | 0
Schedule 17 | 26.6 | [12 empty] | 0
Schedule 17 | 26.7 | [12 empty] | 0
Schedule 17 | 26.8 | [12 empty] | 0
Schedule 17 | 26.9 | [12 empty] | 0
Schedule 17 | 26.1 | [12 empty] | 0
Schedule 17 | 26.11 | [12 empty] | 0
Schedule 17 | 27 | [12 empty] | 0
Schedule 17 | 27.1 | [12 empty] | 0
Schedule 17 | 27.2 | [12 empty] | 0
Schedule 17 | 27.3 | [12 empty] | 0
Schedule 17 | 27.4 | [12 empty] | 0
Schedule 17 | 28 | [12 empty] | 0
Schedule 17 | 28.1 | [12 empty] | 0
Schedule 17 | 28.2 | [12 empty] | 0
Schedule 17 | 29 | [12 empty] | 0
Schedule 17 | 29.1 | [12 empty] | 0
Schedule 17 | 29.2 | [12 empty] | 0
Schedule 17 | 29.3 | [12 empty] | 0
Schedule 17 | 29.4 | [12 empty] | 0
Schedule 17 | 30 | [12 empty] | 0
Schedule 17 | 30.1 | [12 empty] | 0
Schedule 17 | 30.2 | [12 empty] | 0
Schedule 17 | 30.3 | [12 empty] | 0
Schedule 17 | 30.4 | [12 empty] | 0
Schedule 17 | 30.5 | [12 empty] | 0
Schedule 17 | 30.6 | [12 empty] | 0
Schedule 17 | 30.7 | [12 empty] | 0
Schedule 17 | 30.8 | [12 empty] | 0
Schedule 17 | 30.9 | [12 empty] | 0
Schedule 17 | 30.1 | [12 empty] | 0
Schedule 17 | 30.11 | [12 empty] | 0
Schedule 17 | 31 | [5 empty] | YES | [6 empty] | 1 | DCP 439 Introduces new Paragraph 31
Schedule 17 | 31.1 | [5 empty] | YES | [6 empty] | 1 | DCP 439 Introduces new Paragraph 31.1
Schedule 17: Annex 1 | 1 | [12 empty] | 0
Schedule 17: Annex 1 | 2 | [12 empty] | 0
Schedule 17: Annex 1 | 2.1 | [12 empty] | 0
Schedule 17: Annex 1 | 2.2 | [12 empty] | 0
Schedule 17: Annex 1 | 2.3 | [12 empty] | 0
Schedule 17: Annex 1 | 2.4 | [12 empty] | 0
Schedule 17: Annex 1 | 2.5 | [12 empty] | 0
Schedule 17: Annex 1 | 3 | [12 empty] | 0
Schedule 17: Annex 1 | Definitions | [12 empty] | 0
Schedule 17: Annex 1 | 4 | [12 empty] | 0
Schedule 17: Annex 1 | 4.1 | [12 empty] | 0
Schedule 17: Annex 1 | 4.2 | [12 empty] | 0
Schedule 17: Annex 1 | 4.3 | [12 empty] | 0
Schedule 17: Annex 1 | 4.4 | [12 empty] | 0
Schedule 17: Annex 1 | 4.5 | [12 empty] | 0
Schedule 17: Annex 1 | 4.6 | [12 empty] | 0
Schedule 17: Annex 1 | 4.7 | [12 empty] | 0
Schedule 17: Annex 1 | 4.8 | [12 empty] | 0
Schedule 17: Annex 1 | 4.9 | [12 empty] | 0
Schedule 17: Annex 1 | 4.1 | [12 empty] | 0
Schedule 17: Annex 1 | 5 | [12 empty] | 0
Schedule 17: Annex 1 | 5.1 | [12 empty] | 0
Schedule 17: Annex 1 | 5.2 | [12 empty] | 0
Schedule 17: Annex 1 | 5.3 | [12 empty] | 0
Schedule 17: Annex 1 | 5.4 | [12 empty] | 0
Schedule 17: Annex 1 | 5.5 | [12 empty] | 0
Schedule 17: Annex 1 | 5.6 | [12 empty] | 0
Schedule 17: Annex 1 | 5.7 | [12 empty] | 0
Schedule 17: Annex 1 | 5.8 | [12 empty] | 0
Schedule 17: Annex 1 | 5.9 | [12 empty] | 0
Schedule 17: Annex 1 | 5.1 | [12 empty] | 0
Schedule 17: Annex 1 | 5.11 | [12 empty] | 0
Schedule 17: Annex 1 | 5.12 | [12 empty] | 0
Schedule 17: Annex 1 | 5.13 | [12 empty] | 0
Schedule 17: Annex 1 | 5.14 | [12 empty] | 0
Schedule 17: Annex 1 | 5.15 | [12 empty] | 0
Schedule 17: Annex 1 | 5.16 | [12 empty] | 0
Schedule 17: Annex 1 | 5.17 | [12 empty] | 0
Schedule 17: Annex 1 | 5.18 | [12 empty] | 0
Schedule 17: Annex 1 | 5.19 | [12 empty] | 0
Schedule 17: Annex 1 | 5.2 | [12 empty] | 0
Schedule 17: Annex 1 | 5.21 | [12 empty] | 0
Schedule 17: Annex 1 | 5.22 | [12 empty] | 0
Schedule 17: Annex 1 | 5.23 | [12 empty] | 0
Schedule 17: Annex 1 | 5.24 | [12 empty] | 0
Schedule 17: Annex 1 | 5.25 | [12 empty] | 0
Schedule 17: Annex 1 | 5.26 | [12 empty] | 0
Schedule 17: Annex 1 | 5.27 | [12 empty] | 0
Schedule 17: Annex 1 | 5.28 | [12 empty] | 0
Schedule 17: Annex 1 | 5.29 | [12 empty] | 0
Schedule 17: Annex 1 | 5.3 | [12 empty] | 0
Schedule 17: Annex 1 | 5.31 | [12 empty] | 0
Schedule 17: Annex 1 | 5.32 | [12 empty] | 0
Schedule 17: Annex 1 | 5.33 | [12 empty] | 0
Schedule 17: Annex 1 | 5.34 | [12 empty] | 0
Schedule 17: Annex 1 | 5.35 | [12 empty] | 0
Schedule 17: Annex 1 | 5.36 | [12 empty] | 0
Schedule 17: Annex 1 | 5.37 | [12 empty] | 0
Schedule 17: Annex 1 | 5.38 | [12 empty] | 0
Schedule 17: Annex 1 | 5.39 | [12 empty] | 0
Schedule 17: Annex 1 | 5.4 | [12 empty] | 0
Schedule 17: Annex 1 | 5.41 | [12 empty] | 0
Schedule 17: Annex 1 | 5.42 | [12 empty] | 0
Schedule 17: Annex 1 | 5.43 | [12 empty] | 0
Schedule 17: Annex 1 | 5.44 | [12 empty] | 0
Schedule 17: Annex 1 | 5.45 | [12 empty] | 0
Schedule 17: Annex 1 | 6 | [12 empty] | 0
Schedule 17: Annex 1 | 6.1 | [12 empty] | 0
Schedule 17: Annex 1 | 6.2 | [12 empty] | 0
Schedule 17: Annex 1 | 6.3 | [11 empty] | YES | 0
Schedule 17: Annex 1 | 6.4 | [12 empty] | 0
Schedule 17: Annex 1 | 6.5 | [12 empty] | 0
Schedule 17: Annex 1 | 6.6 | [12 empty] | 0
Schedule 17: Annex 1 | 6.7 | [12 empty] | 0
Schedule 17: Annex 1 | 6.8 | [12 empty] | 0
Schedule 17: Annex 1 | 7 | [12 empty] | 0
Schedule 17: Annex 1 | 7.1 | [12 empty] | 0
Schedule 17: Annex 1 | 7.2 | [12 empty] | 0
Schedule 17: Annex 1 | 7.3 | [12 empty] | 0
Schedule 17: Annex 1 | 7.4 | [12 empty] | 0
Schedule 17: Annex 1 | 7.5 | [12 empty] | 0
Schedule 17: Annex 1 | 7.6 | [12 empty] | 0
Schedule 17: Annex 1 | 7.7 | [12 empty] | 0
Schedule 17: Annex 1 | 7.8 | [12 empty] | 0
Schedule 17: Annex 1 | 8 | [12 empty] | 0
Schedule 17: Annex 1 | 8.1 | [12 empty] | 0
Schedule 17: Annex 1 | 8.2 | [12 empty] | 0
Schedule 17: Annex 1 | 8.3 | [12 empty] | 0
Schedule 17: Annex 1 | 8.4 | [12 empty] | 0
Schedule 17: Annex 1 | 9 | [12 empty] | 0
Schedule 17: Annex 1 | 9.1 | [12 empty] | 0
Schedule 17: Annex 1 | 9.2 | [12 empty] | 0
Schedule 17: Annex 1 | 9.3 | [12 empty] | 0
Schedule 17: Annex 1 | 9.4 | [12 empty] | 0
Schedule 17: Annex 1 | 9.5 | [12 empty] | 0
Schedule 17: Annex 1 | 9.6 | [12 empty] | 0
Schedule 17: Annex 1 | 9.7 | [12 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [12 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [12 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [12 empty] | 0
Schedule 17: Annex 1 | Attachment 3 | [12 empty] | 0
Schedule 17: Annex 2 | Annex 2 | [12 empty] | 0
0
Schedule 18 | Introduction | [12 empty] | 0
Schedule 18 | 1 | [12 empty] | 0
Schedule 18 | 1.1 | [12 empty] | 0
Schedule 18 | 1.2 | [12 empty] | 0
Schedule 18 | 1.3 | [12 empty] | 0 | Model reference number and date
Schedule 18 | 1.3A | [12 empty] | 0
Schedule 18 | 1.4 | [12 empty] | 0
Schedule 18 | 1.5 | [12 empty] | 0
Schedule 18 | 1.6 | [12 empty] | 0
Schedule 18 | 1.7 | [12 empty] | 0
Schedule 18 | 1.8 | [12 empty] | 0
Schedule 18 | 1.9 | [12 empty] | 0
Schedule 18 | 2 | [12 empty] | 0
Schedule 18 | 2.1 | [12 empty] | 0
Schedule 18 | 2.2 | [12 empty] | 0
Schedule 18 | 2.3 | [12 empty] | 0
Schedule 18 | 2.4 | [12 empty] | 0
Schedule 18 | 2.5 | [12 empty] | 0
Schedule 18 | 2.6 | [12 empty] | 0
Schedule 18 | 2.7 | [12 empty] | 0
Schedule 18 | 2.8 | [12 empty] | 0
Schedule 18 | 2.9 | [12 empty] | 0
Schedule 18 | 2.1 | [12 empty] | 0
Schedule 18 | 2.11 | [12 empty] | 0
Schedule 18 | 2.12 | [12 empty] | 0
Schedule 18 | 2.13 | [12 empty] | 0
Schedule 18 | 2.14 | [12 empty] | 0
Schedule 18 | 2.15 | [12 empty] | 0
Schedule 18 | 2.16 | [12 empty] | 0
Schedule 18 | 2.17 | [12 empty] | 0
Schedule 18 | 2.18 | [12 empty] | 0
Schedule 18 | 2.19 | [12 empty] | 0
Schedule 18 | 2.2 | [12 empty] | 0
Schedule 18 | 2.21 | [12 empty] | 0
Schedule 18 | 2.22 | [12 empty] | 0
Schedule 18 | 2.23 | [12 empty] | 0
Schedule 18 | 2.24 | [12 empty] | 0
Schedule 18 | 2.25 | [12 empty] | 0
Schedule 18 | 2.26 | [12 empty] | 0
Schedule 18 | 2.27 | [12 empty] | 0
Schedule 18 | 2.28 | [12 empty] | 0
Schedule 18 | 2.29 | [12 empty] | 0
Schedule 18 | 2.3 | [12 empty] | 0
Schedule 18 | 3 | [12 empty] | 0
Schedule 18 | 3.1 | [12 empty] | 0
Schedule 18 | 3.2 | [12 empty] | 0
Schedule 18 | 3.3 | [12 empty] | 0
Schedule 18 | 3.4 | [12 empty] | 0
Schedule 18 | 3.5 | [12 empty] | 0
Schedule 18 | 3.6 | [12 empty] | 0
Schedule 18 | 3.7 | [12 empty] | 0
Schedule 18 | 4 | [12 empty] | 0
Schedule 18 | 4.1 | [12 empty] | 0
Schedule 18 | 5 | [12 empty] | 0
Schedule 18 | 5.1 | [12 empty] | 0
Schedule 18 | 6 | [12 empty] | 0
Schedule 18 | 6.1 | [12 empty] | 0
Schedule 18 | 6.2 | [12 empty] | 0
Schedule 18 | 6.3 | [12 empty] | 0
Schedule 18 | 6.4 | [12 empty] | 0
Schedule 18 | 6.5 | [12 empty] | 0
Schedule 18 | 7 | [12 empty] | 0
Schedule 18 | 7.1 | [12 empty] | 0
Schedule 18 | 8 | [12 empty] | 0
Schedule 18 | 8.1 | [12 empty] | 0
Schedule 18 | 8.2 | [12 empty] | 0
Schedule 18 | 8.3 | [12 empty] | 0
Schedule 18 | 8.4 | [12 empty] | 0
Schedule 18 | 9 | [12 empty] | 0
Schedule 18 | 9.1 | [12 empty] | 0
Schedule 18 | 9.2 | [12 empty] | 0
Schedule 18 | 10 | [12 empty] | 0
Schedule 18 | 10.1 | [12 empty] | 0
Schedule 18 | 10.2 | [12 empty] | 0
Schedule 18 | 10.3 | [12 empty] | 0
Schedule 18 | 10.4 | [12 empty] | 0
Schedule 18 | 10.5 | [12 empty] | 0
Schedule 18 | 11 | [12 empty] | 0
Schedule 18 | 11.1 | [12 empty] | 0
Schedule 18 | 12 | [12 empty] | 0
Schedule 18 | 12.1 | [12 empty] | 0
Schedule 18 | 12.2 | [12 empty] | 0
Schedule 18 | 12.3 | [12 empty] | 0
Schedule 18 | 12.4 | [12 empty] | 0
Schedule 18 | 12.5 | [12 empty] | 0
Schedule 18 | 12.6 | [12 empty] | 0
Schedule 18 | 13 | [12 empty] | 0
Schedule 18 | 13.1 | [12 empty] | 0
Schedule 18 | 13.2 | [12 empty] | 0
Schedule 18 | 13.3 | [12 empty] | 0
Schedule 18 | 13.4 | [12 empty] | 0
Schedule 18 | 14 | [12 empty] | 0
Schedule 18 | 14.1 | [12 empty] | 0
Schedule 18 | 14.2 | [12 empty] | 0
Schedule 18 | 14.3 | [12 empty] | 0
Schedule 18 | 14.4 | [12 empty] | 0
Schedule 18 | 14.5 | [12 empty] | 0
Schedule 18 | 15 | [12 empty] | 0
Schedule 18 | 15.1 | [12 empty] | 0
Schedule 18 | 15.2 | [12 empty] | 0
Schedule 18 | 15.3 | [12 empty] | 0
Schedule 18 | 15.4 | [12 empty] | 0
Schedule 18 | 15.5 | [12 empty] | 0
Schedule 18 | 15.6 | [12 empty] | 0
Schedule 18 | 15.7 | [12 empty] | 0
Schedule 18 | 15.8 | [12 empty] | 0
Schedule 18 | 15.9 | [12 empty] | 0
Schedule 18 | 15.1 | [12 empty] | 0
Schedule 18 | 15.11 | [12 empty] | 0
Schedule 18 | 15.12 | [12 empty] | 0
Schedule 18 | 15.15 | [12 empty] | 0
Schedule 18 | 16 | [12 empty] | 0
Schedule 18 | 16.1 | [12 empty] | 0
Schedule 18 | 16.2 | [12 empty] | 0
Schedule 18 | 16.3 | [12 empty] | 0
Schedule 18 | 16.4 | [12 empty] | 0
Schedule 18 | 16.5 | [12 empty] | 0
Schedule 18 | 16.6 | [12 empty] | 0
Schedule 18 | 16.7 | [12 empty] | 0
Schedule 18 | 16.8 | [12 empty] | 0
Schedule 18 | 16.9 | [12 empty] | 0
Schedule 18 | 16.1 | [12 empty] | 0
Schedule 18 | 17 | [12 empty] | 0
Schedule 18 | 17.1 | [12 empty] | 0
Schedule 18 | 17.2 | [12 empty] | 0
Schedule 18 | 17.3 | [12 empty] | 0
Schedule 18 | 18 | [12 empty] | 0
Schedule 18 | 18.1 | [12 empty] | 0
Schedule 18 | 18.2 | [12 empty] | 0
Schedule 18 | 18.3 | [12 empty] | 0
Schedule 18 | 18.4 | [12 empty] | 0
Schedule 18 | 18.5 | [12 empty] | 0
Schedule 18 | 18.6 | [12 empty] | 0
Schedule 18 | 18.7 | [12 empty] | 0
Schedule 18 | 18.8 | [12 empty] | 0
Schedule 18 | 18.9 | [12 empty] | 0
Schedule 18 | 18.1 | [12 empty] | 0
Schedule 18 | 18.11 | [12 empty] | 0
Schedule 18 | 18.12 | [12 empty] | 0
Schedule 18 | 18.13 | [12 empty] | 0
Schedule 18 | 18.14 | [12 empty] | 0
Schedule 18 | 18.15 | [12 empty] | 0
Schedule 18 | 18.16 | [12 empty] | 0
Schedule 18 | 18.17 | [12 empty] | 0
Schedule 18 | 18.18 | [12 empty] | 0
Schedule 18 | 18.19 | [12 empty] | 0
Schedule 18 | 18.2 | [12 empty] | 0
Schedule 18 | 18.21 | [12 empty] | 0
Schedule 18 | 19 | [12 empty] | 0
Schedule 18 | 19.1 | [12 empty] | 0
Schedule 18 | 19.2 | [12 empty] | 0
Schedule 18 | 19.3 | [12 empty] | 0
Schedule 18 | 19.4 | [12 empty] | 0
Schedule 18 | 19.5 | [12 empty] | 0
Schedule 18 | 19.6 | [12 empty] | 0
Schedule 18 | 19.7 | [12 empty] | 0
Schedule 18 | 19.8 | [12 empty] | 0
Schedule 18 | 19.9 | [12 empty] | 0
Schedule 18 | 19.1 | [12 empty] | 0
Schedule 18 | 19.11 | [12 empty] | 0
Schedule 18 | 20 | [12 empty] | 0
Schedule 18 | 20.1 | [12 empty] | 0
Schedule 18 | 20.2 | [12 empty] | 0
Schedule 18 | 20.3 | [12 empty] | 0
Schedule 18 | 20.4 | [12 empty] | 0
Schedule 18 | 20.5 | [12 empty] | 0
Schedule 18 | 20.6 | [8 empty] | YES |  |  |  | 1
Schedule 18 | 20.7 | [8 empty] | YES |  |  |  | 1
Schedule 18 | 20.8 | [12 empty] | 0
Schedule 18 | 20.9 | [8 empty] | YES |  |  |  | 1
Schedule 18 | 21 | [12 empty] | 0
Schedule 18 | 21.1 | [12 empty] | 0
Schedule 18 | 21.2 | [12 empty] | 0
Schedule 18 | 22 | [12 empty] | 0
Schedule 18 | 22.1 | [12 empty] | 0
Schedule 18 | 22.2 | [12 empty] | 0
Schedule 18 | 22.3 | [12 empty] | 0
Schedule 18 | 22.4 | [12 empty] | 0
Schedule 18 | 23 | [12 empty] | 0
Schedule 18 | 23.1 | [12 empty] | 0
Schedule 18 | 23.2 | [12 empty] | 0
Schedule 18 | 23.3 | [12 empty] | 0
Schedule 18 | 23.4 | [12 empty] | 0
Schedule 18 | 23.5 | [12 empty] | 0
Schedule 18 | 24 | [12 empty] | 0
Schedule 18 | 24.1 | [12 empty] | 0
Schedule 18 | 24.2 | [12 empty] | 0
Schedule 18 | 24.3 | [12 empty] | 0
Schedule 18 | 24.4 | [12 empty] | 0
Schedule 18 | 24.5 | [12 empty] | 0
Schedule 18 | 24.6 | [12 empty] | 0
Schedule 18 | 24.7 | [12 empty] | 0
Schedule 18 | 24.8 | [12 empty] | 0
Schedule 18 | 24.9 | [12 empty] | 0
Schedule 18 | 25 | [12 empty] | 0
Schedule 18 | 25.1 | [12 empty] | 0
Schedule 18 | 25.2 | [12 empty] | 0
Schedule 18 | 25.3 | [12 empty] | 0
Schedule 18 | 25.4 | [12 empty] | 0
Schedule 18 | 25.5 | [12 empty] | 0
Schedule 18 | 25.6 | [12 empty] | 0
Schedule 18 | 25.7 | [12 empty] | 0
Schedule 18 | 25.8 | [12 empty] | 0
Schedule 18 | 25.9 | [12 empty] | 0
Schedule 18 | 25.1 | [12 empty] | 0
Schedule 18 | 25.11 | [12 empty] | 0
Schedule 18 | 25.12 | [12 empty] | 0
Schedule 18 | 25.13 | [12 empty] | 0
Schedule 18 | 25.14 | [12 empty] | 0
Schedule 18 | 25.15 | [12 empty] | 0
Schedule 18 | 25.16 | [12 empty] | 0
Schedule 18 | 25.17 | [12 empty] | 0
Schedule 18 | 25.18 | [12 empty] | 0
Schedule 18 | 25.19 | [12 empty] | 0
Schedule 18 | 26 | [12 empty] | 0
Schedule 18 | 26.1 | [12 empty] | 0
Schedule 18 | 26.2 | [12 empty] | 0
Schedule 18 | 26.3 | [12 empty] | 0
Schedule 18 | 26.4 | [12 empty] | 0
Schedule 18 | 26.5 | [12 empty] | 0
Schedule 18 | 26.6 | [12 empty] | 0
Schedule 18 | 26.7 | [12 empty] | 0
Schedule 18 | 26.8 | [12 empty] | 0
Schedule 18 | 26.9 | [12 empty] | 0
Schedule 18 | 26.1 | [12 empty] | 0
Schedule 18 | 26.11 | [12 empty] | 0
Schedule 18 | 27 | [12 empty] | 0
Schedule 18 | 27.1 | [12 empty] | 0
Schedule 18 | 27.2 | [12 empty] | 0
Schedule 18 | 27.3 | [12 empty] | 0
Schedule 18 | 27.4 | [12 empty] | 0
Schedule 18 | 28 | [12 empty] | 0
Schedule 18 | 28.1 | [12 empty] | 0
Schedule 18 | 28.2 | [12 empty] | 0
Schedule 18 | 29 | [12 empty] | 0
Schedule 18 | 29.1 | [12 empty] | 0
Schedule 18 | 29.2 | [12 empty] | 0
Schedule 18 | 29.3 | [12 empty] | 0
Schedule 18 | 29.4 | [12 empty] | 0
Schedule 18 | 30 | [12 empty] | 0
Schedule 18 | 30.1 | [12 empty] | 0
Schedule 18 | 30.2 | [12 empty] | 0
Schedule 18 | 30.3 | [12 empty] | 0
Schedule 18 | 30.4 | [12 empty] | 0
Schedule 18 | 30.5 | [12 empty] | 0
Schedule 18 | 30.6 | [12 empty] | 0
Schedule 18 | 30.7 | [12 empty] | 0
Schedule 18 | 30.8 | [12 empty] | 0
Schedule 18 | 30.9 | [12 empty] | 0
Schedule 18 | 30.1 | [12 empty] | 0
Schedule 18 | 30.11 | [12 empty] | 0
Schedule 18 | 31 | [12 empty] | 0 | DCP 439 Introduces new Paragraph 31
Schedule 18 | 31.1 | [12 empty] | 0 | DCP 439 Introduces new Paragraph 31.1
Schedule 18: Annex 1 | 1 | [12 empty] | 0
Schedule 18: Annex 1 | 1.1 | [12 empty] | 0
Schedule 18: Annex 1 | 2 | [12 empty] | 0
Schedule 18: Annex 1 | 2.1 | [12 empty] | 0
Schedule 18: Annex 1 | 2.2 | [12 empty] | 0
Schedule 18: Annex 1 | 2.3 | [12 empty] | 0
Schedule 18: Annex 1 | 2.4 | [12 empty] | 0
Schedule 18: Annex 1 | 2.5 | [12 empty] | 0
Schedule 18: Annex 1 | 3 | [12 empty] | 0
Schedule 18: Annex 1 | Definitions | [12 empty] | 0
Schedule 18: Annex 1 | 4 | [12 empty] | 0
Schedule 18: Annex 1 | 4.1 | [12 empty] | 0
Schedule 18: Annex 1 | 4.2 | [12 empty] | 0
Schedule 18: Annex 1 | 4.3 | [12 empty] | 0
Schedule 18: Annex 1 | 4.4 | [12 empty] | 0
Schedule 18: Annex 1 | 4.5 | [12 empty] | 0
Schedule 18: Annex 1 | 4.6 | [12 empty] | 0
Schedule 18: Annex 1 | 4.7 | [12 empty] | 0
Schedule 18: Annex 1 | 4.8 | [12 empty] | 0
Schedule 18: Annex 1 | 4.9 | [12 empty] | 0
Schedule 18: Annex 1 | 5 | [12 empty] | 0
Schedule 18: Annex 1 | 5.1 | [12 empty] | 0
Schedule 18: Annex 1 | 5.2 | [12 empty] | 0
Schedule 18: Annex 1 | 5.3 | [12 empty] | 0
Schedule 18: Annex 1 | 5.4 | [12 empty] | 0
Schedule 18: Annex 1 | 5.5 | [12 empty] | 0
Schedule 18: Annex 1 | 5.6 | [12 empty] | 0
Schedule 18: Annex 1 | 5.7 | [12 empty] | 0
Schedule 18: Annex 1 | 5.8 | [12 empty] | 0
Schedule 18: Annex 1 | 5.9 | [12 empty] | 0
Schedule 18: Annex 1 | 5.1 | [12 empty] | 0
Schedule 18: Annex 1 | 5.11 | [12 empty] | 0
Schedule 18: Annex 1 | 5.12 | [12 empty] | 0
Schedule 18: Annex 1 | 5.13 | [12 empty] | 0
Schedule 18: Annex 1 | 5.14 | [12 empty] | 0
Schedule 18: Annex 1 | 5.15 | [12 empty] | 0
Schedule 18: Annex 1 | 5.16 | [12 empty] | 0
Schedule 18: Annex 1 | 5.17 | [12 empty] | 0
Schedule 18: Annex 1 | 5.18 | [12 empty] | 0
Schedule 18: Annex 1 | 5.19 | [12 empty] | 0
Schedule 18: Annex 1 | 5.2 | [12 empty] | 0
Schedule 18: Annex 1 | 5.21 | [12 empty] | 0
Schedule 18: Annex 1 | 5.22 | [12 empty] | 0
Schedule 18: Annex 1 | 5.23 | [12 empty] | 0
Schedule 18: Annex 1 | 5.24 | [12 empty] | 0
Schedule 18: Annex 1 | 5.25 | [12 empty] | 0
Schedule 18: Annex 1 | 5.26 | [12 empty] | 0
Schedule 18: Annex 1 | 5.27 | [12 empty] | 0
Schedule 18: Annex 1 | 5.28 | [12 empty] | 0
Schedule 18: Annex 1 | 5.29 | [12 empty] | 0
Schedule 18: Annex 1 | 5.3 | [12 empty] | 0
Schedule 18: Annex 1 | 5.31 | [12 empty] | 0
Schedule 18: Annex 1 | 5.32 | [12 empty] | 0
Schedule 18: Annex 1 | 5.33 | [12 empty] | 0
Schedule 18: Annex 1 | 5.34 | [12 empty] | 0
Schedule 18: Annex 1 | 5.35 | [12 empty] | 0
Schedule 18: Annex 1 | 5.36 | [12 empty] | 0
Schedule 18: Annex 1 | 5.37 | [12 empty] | 0
Schedule 18: Annex 1 | 5.38 | [12 empty] | 0
Schedule 18: Annex 1 | 5.39 | [12 empty] | 0
Schedule 18: Annex 1 | 5.4 | [12 empty] | 0
Schedule 18: Annex 1 | 5.41 | [12 empty] | 0
Schedule 18: Annex 1 | 5.42 | [12 empty] | 0
Schedule 18: Annex 1 | 6 | [12 empty] | 0
Schedule 18: Annex 1 | 6.1 | [12 empty] | 0
Schedule 18: Annex 1 | 6.2 | [12 empty] | 0
Schedule 18: Annex 1 | 6.3 | [12 empty] | 0
Schedule 18: Annex 1 | 6.4 | [12 empty] | 0
Schedule 18: Annex 1 | 6.5 | [12 empty] | 0
Schedule 18: Annex 1 | 6.6 | [12 empty] | 0
Schedule 18: Annex 1 | 6.7 | [12 empty] | 0
Schedule 18: Annex 1 | 6.8 | [12 empty] | 0
Schedule 18: Annex 1 | 6.9 | [12 empty] | 0
Schedule 18: Annex 1 | 6.1 | [12 empty] | 0
Schedule 18: Annex 1 | 6.11 | [12 empty] | 0
Schedule 18: Annex 1 | 6.12 | [12 empty] | 0
Schedule 18: Annex 1 | 6.13 | [12 empty] | 0
Schedule 18: Annex 1 | 6.14 | [12 empty] | 0
Schedule 18: Annex 1 | 6.15 | [12 empty] | 0
Schedule 18: Annex 1 | 6.16 | [12 empty] | 0
Schedule 18: Annex 1 | 6.17 | [12 empty] | 0
Schedule 18: Annex 1 | 6.18 | [12 empty] | 0
Schedule 18: Annex 1 | 6.19 | [12 empty] | 0
Schedule 18: Annex 1 | 6.2 | [12 empty] | 0
Schedule 18: Annex 1 | 6.21 | [12 empty] | 0
Schedule 18: Annex 1 | 6.22 | [12 empty] | 0
Schedule 18: Annex 1 | 6.23 | [12 empty] | 0
Schedule 18: Annex 1 | 6.24 | [12 empty] | 0
Schedule 18: Annex 1 | 6.25 | [12 empty] | 0
Schedule 18: Annex 1 | 6.26 | [12 empty] | 0
Schedule 18: Annex 1 | 6.27 | [12 empty] | 0
Schedule 18: Annex 1 | 6.28 | [12 empty] | 0
Schedule 18: Annex 1 | 6.29 | [12 empty] | 0
Schedule 18: Annex 1 | 6.3 | [12 empty] | 0
Schedule 18: Annex 1 | 6.31 | [12 empty] | 0
Schedule 18: Annex 1 | 6.32 | [12 empty] | 0
Schedule 18: Annex 1 | 6.33 | [12 empty] | 0
Schedule 18: Annex 1 | 6.34 | [12 empty] | 0
Schedule 18: Annex 1 | 7 | [12 empty] | 0
Schedule 18: Annex 1 | 7.1 | [12 empty] | 0
Schedule 18: Annex 1 | 7.2 | [12 empty] | 0
Schedule 18: Annex 1 | 7.3 | [12 empty] | 0
Schedule 18: Annex 1 | 7.4 | [12 empty] | 0
Schedule 18: Annex 1 | 7.5 | [12 empty] | 0
Schedule 18: Annex 1 | 8 | [12 empty] | 0
Schedule 18: Annex 1 | 8.1 | [12 empty] | 0
Schedule 18: Annex 1 | 8.2 | [12 empty] | 0
Schedule 18: Annex 1 | 8.3 | [12 empty] | 0
Schedule 18: Annex 1 | 8.4 | [12 empty] | 0
Schedule 18: Annex 1 | 8.5 | [12 empty] | 0
Schedule 18: Annex 1 | 8.6 | [12 empty] | 0
Schedule 18: Annex 1 | 8.7 | [12 empty] | 0
Schedule 18: Annex 1 | 8.8 | [12 empty] | 0
Schedule 18: Annex 1 | 8.9 | [12 empty] | 0
Schedule 18: Annex 1 | 8.1 | [12 empty] | 0
Schedule 18: Annex 1 | 8.11 | [12 empty] | 0
Schedule 18: Annex 1 | 8.12 | [12 empty] | 0
Schedule 18: Annex 1 | 8.13 | [12 empty] | 0
Schedule 18: Annex 1 | 8.14 | [12 empty] | 0
Schedule 18: Annex 1 | 8.15 | [12 empty] | 0
Schedule 18: Annex 1 | 8.16 | [12 empty] | 0
Schedule 18: Annex 1 | 8.17 | [12 empty] | 0
Schedule 18: Annex 1 | 8.18 | [12 empty] | 0
Schedule 18: Annex 1 | 8.19 | [12 empty] | 0
Schedule 18: Annex 1 | 8.2 | [12 empty] | 0
Schedule 18: Annex 1 | 8.21 | [12 empty] | 0
Schedule 18: Annex 1 | Attachment 1 | [12 empty] | 0
Schedule 18: Annex 1 | Attachment 2 | [12 empty] | 0
Schedule 18: Annex 1 | Attachment 3 | [12 empty] | 0
Schedule 18: Annex 2 | Annex 2 | [12 empty] | 0
0
Schedule 20 | Introduction | [12 empty] | 0
Schedule 20 | 1.1 | [12 empty] | 0
Schedule 20 | 2.1 | [12 empty] | 0
Schedule 20 | 3.1 | [12 empty] | 0
Schedule 20 | 3.2 | [12 empty] | 0
0
Schedule 29 | Introduction | [12 empty] | 0
Schedule 29 | 1 | [12 empty] | 0
Schedule 29 | 1A | [12 empty] | 0
Schedule 29 | 2 | [12 empty] | 0
Schedule 29 | 3 | [12 empty] | 0
Schedule 29 | 4 | [12 empty] | 0
Schedule 29 | 5 | [12 empty] | 0
Schedule 29 | 6 | [12 empty] | 0
Schedule 29 | 7 | [12 empty] | 0
Schedule 29 | 8 | [12 empty] | 0
Schedule 29 | 9 | [12 empty] | 0
Schedule 29 | 10 | [12 empty] | 0
Schedule 29 | 11 | [12 empty] | 0
Schedule 29 | 11A | [12 empty] | 0
Schedule 29 | 12 | [12 empty] | 0
Schedule 29 | 13 | [12 empty] | 0
Schedule 29 | 14 | [12 empty] | 0
Schedule 29 | 15 | [12 empty] | 0
Schedule 29 | 16 | [12 empty] | 0
Schedule 29 | 17 | [12 empty] | 0
Schedule 29 | 18 | [12 empty] | 0
Schedule 29 | 19 | [12 empty] | 0
Schedule 29 | 20 | [12 empty] | 0
Schedule 29 | 21 | [12 empty] | 0
Schedule 29 | 22 | [12 empty] | 0
Schedule 29 | 23 | [12 empty] | 0
Schedule 29 | 24 | [12 empty] | 0
Schedule 29 | 25 | [12 empty] | 0
Schedule 29 | 26 | [12 empty] | 0
Schedule 29 | 27 | [12 empty] | 0
Schedule 29 | 28 | [12 empty] | 0
Schedule 29 | 29 | [12 empty] | 0
Schedule 29 | 30 | [12 empty] | 0
Schedule 29 | 31 | [12 empty] | 0
Schedule 29 | 32 | [12 empty] | 0
Schedule 29 | 33 | [12 empty] | 0
Schedule 29 | 34 | [12 empty] | 0
Schedule 29 | 35 | [12 empty] | 0
Schedule 29 | 36 | [12 empty] | 0
Schedule 29 | 37 | [12 empty] | 0
Schedule 29 | 38 | [12 empty] | 0
Schedule 29 | 39 | [12 empty] | 0
Schedule 29 | 40 | [12 empty] | 0
Schedule 29 | 41 | [12 empty] | 0
Schedule 29 | 42 | [12 empty] | 0
Schedule 29 | 43 | [12 empty] | 0
Schedule 29 | 44 | [12 empty] | 0
Schedule 29 | 45 | [12 empty] | 0
Schedule 29 | 46 | [12 empty] | 0
Schedule 29 | 46A | [12 empty] | 0
Schedule 29 | 47 | [12 empty] | 0
0
Schedule 32 | 1 | [12 empty] | 0
Schedule 32 | 1.1 | [12 empty] | 0
Schedule 32 | 1.2 | [12 empty] | 0
Schedule 32 | 1.2A | [12 empty] | 0
Schedule 32 | 1.3 | [12 empty] | 0
Schedule 32 | 1.4 | [12 empty] | 0
Schedule 32 | 1.5 | [12 empty] | 0
Schedule 32 | 1.6 | [12 empty] | 0
Schedule 32 | 1.7 | [12 empty] | 0
Schedule 32 | 1.8 |  |  | YES | [9 empty] | 1
Schedule 32 | 1.9 | [12 empty] | 0
Schedule 32 | 1.10 |  |  | YES | [9 empty] | 1
Schedule 32 | 2 | [12 empty] | 0
Schedule 32 | 2.1 | [12 empty] | 0
Schedule 32 | 2.2 | [12 empty] | 0
Schedule 32 | 2.3 | [12 empty] | 0
Schedule 32 | 2.4 | [12 empty] | 0
Schedule 32 | 2.5 | [12 empty] | 0
Schedule 32 | 3 | [12 empty] | 0
Schedule 32 | 3.1 |  |  | YES | [9 empty] | 1
Schedule 32 | 3.2 | [12 empty] | 0
Schedule 32 | 3.3 | [12 empty] | 0
Schedule 32 | 3.4 | [12 empty] | 0
Schedule 32 | 3.5 | [12 empty] | 0
Schedule 32 | 3.6 | [12 empty] | 0
Schedule 32 | 4 | [12 empty] | 0
Schedule 32 | 4.1 |  |  | YES | [9 empty] | 1
Schedule 32 | 4.2 |  |  | YES | [9 empty] | 1
Schedule 32 | 4.2A |  |  | YES | [9 empty] | 1
Schedule 32 | 4.3 | [12 empty] | 0
Schedule 32 | 4.4 | [12 empty] | 0
Schedule 32 | 4.5 |  |  | YES | [9 empty] | 1
Schedule 32 | 4.6 | [12 empty] | 0
Schedule 32 | 5 | [12 empty] | 0
Schedule 32 | 5.1 | [12 empty] | 0
Schedule 32 | 5.2 | [12 empty] | 0
Schedule 32 | 5.3 | [12 empty] | 0
Schedule 32 | 5A. |  |  | YES | [9 empty] | 1
Schedule 32 | 5A.1 | [12 empty] | 0
Schedule 32 | 5A.1A | [12 empty] | 0
Schedule 32 | 5A.2 | [12 empty] | 0
Schedule 32 | 6 | [12 empty] | 0
Schedule 32 | 6.1 |  |  |  | YES | [8 empty] | 1
Schedule 32 | 6.2 |  |  |  | YES | [8 empty] | 1
Schedule 32 | 6.3 |  |  | YES | [9 empty] | 1
Schedule 32 | 6.4 | [5 empty] | YES | [6 empty] | 1
Schedule 32 | 6.4A | [12 empty] | 0
Schedule 32 | 6.5 |  |  | YES | [9 empty] | 1
Schedule 32 | 6.6 | [12 empty] | 0
Schedule 32 | 6.7 | [12 empty] | 0
Schedule 32 | 6.8 | [12 empty] | 0
Schedule 32 | 6.9 | [12 empty] | 0
Schedule 32 | 6.10 | [12 empty] | 0
Schedule 32 | 6.11 | [5 empty] | YES | [6 empty] | 1
Schedule 32 | 6.12 | [12 empty] | 0
Schedule 32 | 7 | [12 empty] | 0
Schedule 32 | 7.1 | [12 empty] | 0
Schedule 32 | 7.2 | [12 empty] | 0
Schedule 32 | 7.3 | [12 empty] | 0
Schedule 32 | 7.4 | [12 empty] | 0
Schedule 32 | 7.5 | [12 empty] | 0
Schedule 32 | 7.6 | [12 empty] | 0
Schedule 32 | 7.7 | [12 empty] | 0
Schedule 32 | 7.8 | [12 empty] | 0
Schedule 32 | 7.9 | [12 empty] | 0
Schedule 32 | 7.1 | [12 empty] | 0
Schedule 32 | 7.11 | [12 empty] | 0
Schedule 32 | 7.12 | [12 empty] | 0
Schedule 32 | 7.13 | [12 empty] | 0
Schedule 32 | 7.14 | [12 empty] | 0
Schedule 32 | 7.15 | [12 empty] | 0
Schedule 32 | 7.16 | [12 empty] | 0
Schedule 32 | 7.17 | [5 empty] | YES | [6 empty] | 1
Schedule 32 | 8 | [12 empty] | 0
Schedule 32 | 8.1 | [12 empty] | 0
Schedule 32 | 8.2 | [12 empty] | 0
Schedule 32 | Definitions |  |  | YES | YES | [8 empty] | 2
Charging Methodology CPs Legal Text Overlap Tracker

## Website (hidden)
Change Proposal Number | Change Proposal Name | Column1 | Status of the Change | Status Effective Date | Status Expected End Date | Expected Implementation Date | Proposer Party | Date Proposal Raised | Reasons for Change | Matter (Part 1 or 2) | Urgency Status | Impacted Parties | Next Event | Last Updated
DCP 442 | Aligning enduring flexible connections |  | On Hold | 05/03/2025 | - | 2026-02-26 | NORTHERN POWERGRID (NORTHEAST) PLC | 2024-07-01 |  | Part 1 Matter | Standard | DNO, IDNO |  | 12/08/2025
DCP 423 | LDNO Discounts for Negative Scaling | CDCM | On Hold | - | - | 2026-04-01 | THE ELECTRICITY NETWORK COMPANY LIMITED | 2023-05-09 | It is recognised that there are other elements of the tariffs where the LDNO tariff is lower than the all the-way equivalent and the LDNO will earn a margin in these areas reflective of the discount calculated in Schedule 29. However, the current application of the pass through and scaling creates a situation where this margin is altered without economic justification. Although it requires a specific set of circumstances for this situation to arise (for there to be sufficient negative scaling for the fixed charge to become floored at zero, and also for there to be bad debt or SoLR costs recovered in that year), it has been observed in the 2023-24 tariffs for UKPN’s London region. The scale of the issue is not necessarily limited as the size of the negative margin on the fixed charge component is dependent on the size of the pass through and the potential size of the negative scaling factor. | Part 1 Matter | Standard | DNO, IDNO |  | 1 day ago
DCP 419 | Pre-Notifications of Planned Supply De-Energisations |  | On Hold | - | - | 2026-02-26 | SCOTTISH HYDRO ELECTRIC POWER DISTRIBUTION PLC | 2023-03-06 | Within Ofgem’s ‘Regulatory Instructions and Guidance (RIG): Annex F – Interruptions’ document, there is an obligation on Distributors as below: Section 2.11 Single premises power outage alerts originating from a smart meter are not reasonably expected to indicate no supply. Where an outage alert is received, the DNO should contact the customer as soon as reasonably practicable thereafter to check whether the customer is without power, but only between 8am and 9pm. However, this should not restrict the DNO from contacting a customer outside of those hours if the DNO considers it in the customer’s interest to do so. The single premises power outage alert originating from a smart meter will be deemed to have been received at the earliest of either 8am or when there is contact with the customer. In order to meet their regulatory requirements and to maintain a positive customer experience Distributors will need to receive prior notification of any planned supply de-energisations which are being undertaken by DCUSA Parties in the course of their normal works. This proposal seeks to make the necessary changes to DCUSA legal text that satisfies this requirement. Having prior notification of planned supply interruptions will enable Distributors identify the POAs that should be ignored and help to avoid contacting the customer unnecessarily while maintaining a positive experience for the customer when dealing with DCUSA Parties. | Part 1 Matter | Standard | CRMC, DNO, IDNO, SIP, ES |  | 17 hours ago
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | RESIDUAL | On Hold | 01/11/2023 | 16/12/2026 | 2027-01-18 | E.ON ENERGY SOLUTIONS LIMITED | 2021-04-14 | This CP has been raised to enable DNOs to satisfy specific requirements set out in the TCR Direction. The DCUSA and the CUSC are increasingly likely to become inconsistent regarding the treatment of the residual charge over transmission and distribution, leading to inappropriate charging arrangements in terms of how the residual charge calculation is set out for mixed use sites over both transmission & distribution connections and to ensure that the network companies are fully compliant with Ofgem’s TCR direction and SCR principles. | Part 1 Matter | Standard | CVA, DNO, IDNO, ES |  | 16/07/2025
DCP 465 | NFD Generator and Battery Capacity Charges | CDCM | Initial Assessment | 15/10/2025 | 29/10/2025 | 2028-04-01 | NATIONAL GRID ELECTRICITY DISTRIBUTION (EAST MIDLANDS) PLC | 2025-10-15 | Following the access SCR and zeroing of the customer contributions the Capacity charge in the CDCM has increased to a level that sites with a high import capacity, such as Batteries, may find difficult for commercial operation. The CDCM differs from the EDCM in that it does not treat generation sites differently to demand sites when determining the Capacity charge. This creates a disparity between the two different methodologies creating boundaries and cliff edges and pricing differentials depending on the level of connection. This may lead to non-optimal behaviour. | Part 1 Matter | Standard | CVA, DNO, IDNO, ES |  | 22/10/2025
DCP 464 | IDNO Connection Applications: Treatment of Existing Assets |  | Definition | 18/09/2025 | 10/11/2025 | 2026-04-01 | SOUTHERN ELECTRIC POWER DISTRIBUTION PLC | 2025-09-08 |  | Part 1 Matter | Standard | DNO, IDNO |  | 16 hours ago
DCP 454 | Provide enduring targeted relief from residual charges for electric vehicle charging sites | CDCM | Definition | 22/05/2025 | 15/12/2025 | 2028-04-01 |  | 2025-05-06 |  | Part 1 Matter | Standard | DNO, IDNO, ES |  | 05/06/2025
DCP 452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | EDCM | Definition | 20/03/2025 | 31/10/2025 | 2028-04-01 | FIELD GAIA LTD | 2025-03-05 |  | Part 1 Matter | Standard | CVA, DNO, ES |  | 07/10/2025
DCP 463 | Charging non-consuming De-energised CT-Metered sites | CDCM | Consultation 1 | 10/11/2025 | 01/12/2025 | 2027-04-01 | EASTERN POWER NETWORKS PLC | 2025-09-05 |  | Part 1 Matter | Standard | CVA, DNO, IDNO, ES | DCP 463 Working Group Meeting 02 - 01/12/2025 at 13:00 | 4 days ago
DCP 461 | Reducing the Impact of Transmission Distribution Charges |  | Consultation 1 | 06/11/2025 | 01/12/2025 |  | NATIONAL GRID ELECTRICITY DISTRIBUTION (EAST MIDLANDS) PLC | 2025-08-13 |  | Part 1 Matter | Standard | DNO, IDNO | DCP 461 Working Group Meeting 08 - 09/12/2025 at 13:00 | 5 days ago
DCP 459 | DNO invoices to Embedded DNO |  | Consultation 1 | 31/10/2025 | 17/12/2025 | 2026-02-26 | UK POWER DISTRIBUTION LIMITED | 2025-08-01 | The current Distribution Use of System (DUoS) invoicing process for non-aggregated Meter Point Administration Numbers (MPANs) from Distribution Network Operators (DNOs) to Embedded Distribution Network Operators (EDNOs) is fit for purpose but inefficient. It requires manual work which wastes time, and introduces the risk of error. The problem comes from the fact that the invoices are sent as a PDF document, which the EDNO need to then enter in their accounting system. Ideally, the invoices would be supported with a xls document that the EDNO can easily and "load" into their accounting system. Clauses 43.6.2 and Schedule 19 describe how the charging and in part invoicing needs to be done, but are not specific on the format of the invoices. We suggest amending Schedule 19 to add a requirement to accompany the PDF format of an invoice for non-aggregated MPANs, with an excel spreadsheet that contains minimum fields to support the automatic "load". We note that some DNOs may already be providing an equivalent to some EDNOs, in which case this change proposal intends to bring every party to the same playing field in an open manner, and bring the expected positive impacts to all | Part 2 Matter | Standard | DNO, IDNO |  | 31/10/2025
DCP 424 | Use of System charging for Complex Sites | CDCM | Consultation 1 | 17/07/2024 | 16/07/2025 | 2026-12-31 | GREEN ENERGY (UK) LIMITED | 2023-05-10 | For certain types of Complex Site, Half Hourly Data Collectors (HHDCs) may (for BSC Settlement purposes) net off Import and Export values, provided that they represent exempt supply by a generator to a customer within a local area. For these types of Complex Site, the half hourly metered data submitted to BSC Settlement is netted, and therefore not appropriate for calculation of DUoS charges. This creates an issue for MPANs in Measurement Classes F and G, as the CDCM currently requires billing for such MPANs to be based on BSC Settlement data received on the D0030 data flow. The required change to the CDCM is therefore to allow charges for Measurement Class F and G customers within such Complex Sites to be calculated using gross metered data provided by the HHDC, rather than net Settlement data on the D0030 data flow. | Part 1 Matter | Standard | DNO, IDNO, ES |  | 1 day ago
DCP 458 | Amend DCP 414 process | CDCM | Post-Consultation 1 Refinement | 01/09/2025 | 17/09/2025 | 2025-11-28 | EASTERN POWER NETWORKS PLC | 2025-07-17 | The Proposer believes that the DCP414 process is unwieldy and unworkable and that a simpler solution is required. This proposal does not restrict the customers ability to contact the Distributor to agree a capacity. | Part 2 Matter | Urgent | DNO, IDNO, ES |  | 25/07/2025
DCP 443 | Excess Capacity | CDCM | Post-Consultation 1 Refinement | 01/01/2025 | 20/08/2025 | 2026-04-01 | EASTERN POWER NETWORKS PLC | 2024-07-09 |  | Part 1 Matter | Standard | CVA, DNO, IDNO, ES |  | 09/09/2025
DCP 420 | Provide targeted relief from residual charges for electric vehicle charging sites | RESIDUAL | Post-Consultation 1 Refinement | 29/10/2024 | 15/12/2025 | 2026-11-01 | NATIONAL GRID ELECTRICITY DISTRIBUTION (EAST MIDLANDS) PLC | 2023-03-29 | NGED has received an example of a council who is continuing with their roll out of EV charging stations to meet Welsh and UK Government aims to decarbonise the transport system. However a number of their charging stations have attracted standing charges rates that are so high that the EV charging stations are unsustainable. It is a consequence of the Targeted Charging Review (TCR) that decarbonisation initiatives such as the provision of EV Charging points have such high standing charges that the charging points are either unviable or too expensive for users to access (as they will need to pass costs on the end user – the EV car driver). The chargers are used infrequently at present and the revenue from the charge posts will not cover the standing charge costs for the provision of the incoming electrical supply and metering. | Part 1 Matter | Standard | DNO, IDNO, ES |  | 01/07/2025
DCP 446 | Emergency Disconnections |  | Awaiting Authority Decision | 16/04/2025 | 30/06/2025 | 2025-11-06 | EASTERN POWER NETWORKS PLC | 2024-11-07 | In order to support network cost allocation more appropriately, provision for emergency disconnection charging should be broadened to act across all strands of the national terms of connection rather than being limited to larger connections only, as described in sections 3 and 4 of the National Terms of Connection (Schedule 2B). There is inconsistency between sections 3 and 4 and section 2 of the NTC. Sections 3 (Clause 6.3) and 4 (Clause 6.3) allow the costs of emergency disconnections to be recovered but section 2 does not. In order to avoid socialisation of emergency disconnection costs to all users, wording should be introduced into section 2 which supports DNOs, where appropriate, to recharge reasonable costs to users, or their agents, who drive the need for emergency disconnections. | Part 1 Matter | Standard | DNO, IDNO |  | 11/10/2025
DCP 439 | Backdating Tariff Changes |  | Awaiting Authority Decision | 12/08/2025 | - | 2026-04-01 | EASTERN POWER NETWORKS PLC | 2024-03-14 | Currently where an MPAN is identified as having an incorrect LLFC due to the Distributor’s oversight, the charging statements say it must be corrected up to six years back. This proposal seeks to change that to a more sensible time period. | Part 1 Matter | Standard | CVA, DNO, IDNO, ES |  | 11/10/2025
DCP 412 | Allocation of banding for TCR Charges for ‘Peaky’ Final Demand Customers | RESIDUAL | Awaiting Authority Decision | 19/03/2025 | - |  | E.ON UK PLC | 2022-10-11 | The recent reform of residual charges through the Targeted Charging Review (TCR) and subsequent DCUSA Change Proposals (such as DCP360) has led to an unintended consequence whereby customers with low annual consumption, but with high-capacity requirement needs are seeing bills that are overly excessive on the basis that such customers residual costs are allocated based on the Agreed Supply Capacity (ASC) over both Distribution & Transmission Use of System charging. For such customers the new fixed residual charge is based on connection agreements which in most cases the ASC reflects as a regular anticipated peak capacity. However for others, this peak capacity is very infrequently used and most of their demand is at significantly far lower levels of maximum capacity requirements. | Part 1 Matter | Urgent | DNO, IDNO, ES |  | 12/10/2025
DCP 455 | Align RAV price-inflation with that used in ED2 |  | Approved: Awaiting Implementation | 06/11/2025 | 26/02/2026 | 2026-02-26 | ELECTRICITY NORTH WEST LIMITED | 2025-05-22 |  | Part 2 Matter | Standard | DNO, IDNO, ES |  | 5 days ago
DCP 450 | Managing the effects of surplus residual charge in the CDCM | CDCM | Approved: Awaiting Implementation | 20/10/2025 | - | 2027-04-01 | EASTERN POWER NETWORKS PLC | 2025-02-10 | At the time of setting charges for 2025/26 in December 2023, some DNOs were only aware late in the process that when following the charging methodology, it was not possible to create a full set of charges without errors due to the size of the residual. This required last minute discussions with Ofgem, as well as for some, derogations being granted in order to be able to calculate charges. Following this, early in 2024, discussions took place with Ofgem over a number of months to understand if the same problems were expected to be seen with the calculation of 2026/27 charges. This resulted in some guidance notes being issued by Ofgem for the calculation of the 2026/27 charges. The guidance can be accessed using the link in paragraph 1.3. Although the guidance document relates to both Common Distribution Charging Methodology (CDCM) and Extra-High Voltage Distribution Charging Methodology (EDCM), this change solely relates to the CDCM. A separate change will be brought forward for the EDCMs. | Part 1 Matter | Standard | CVA, DNO, IDNO, ES |  | 15/09/2025
DCP 440 | Consuming “de-energised” sites | CDCM | Approved: Awaiting Implementation | 26/08/2025 | - | 2027-04-01 | EASTERN POWER NETWORKS PLC | 2024-04-15 | Where an MPAN is marked as “de-energised” in the registration system but there are actual meter readings, it is clear that the MPAN is not actually de-energised. For NHH/Supercustomer/Aggregated DUoS charges, settlements includes actual consumption recorded against de-energised MPANs and counts the MPAN. However, the incorrect flagging of an MPAN means that site-specific charges are avoided, under the CDCM, unless the supplier corrects the status. | Part 1 Matter | Standard | CVA, DNO, IDNO, ES |  | 17/06/2025