## CPs
| CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Current Status | Status Changed in the last month | Date Issued to Ofgem | Original Expected Decision Date | Latest Expected Decision Date
STATUS - INITIAL ASSESSMENT
N/A
STATUS - DEFINITION
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | The intent of this modification is to define “Mixed Demand” Sites and apply a proportionate Residual charge where a Site meets the mixed demand definition. | General | 1 | John Lawton / Andy Green | Andrew Malley | 14/04/2021 | 17 | Yes - See comments in status column | TBC | The Working Group met on 02 October to review the need for a BSC change. It was agreed that a BSC change was required and that DCP 388 couldn’t be progressed until the BSC modification had been defined so DCP 388 has been paused until the Proposer raises the required BSC modification.
DCP 419 | Pre-Notifications of Planned Supply De-Energisations | This change seeks to ensure that all DCUSA Parties, that de-energise metering equipment as part of any planned work, provide the Distributor with advance notification of the supply interruption. | General | 1 | Melissa Kendal / Richard Colwill | TBC | 2023-03-06 | 15 | No | Next scheduled release following approval | This CP is on hold pending the outcome of a REC change. | #REF!
DCP 420 | Provide targeted relief from residual charges for electric vehicle charging sites | The intent of this Change Proposal is to provide targeted relief from residual charges to publicly accessible electric vehicle (“EV”) charging sites. This may be a temporary fix to be put in place until the charging stations included are commercially viable. | General | 1 | Craig Booth / Richard Colwill | Thomas Holderness | 2023-03-29 | 19 | Yes - See comments in status column | TBC | The DCUSA Secretariat completed an initial draft of an impact assessment and presented this to the Working Group. The Working Group identified a number of actions required to make the analysis robust and fit for purpose. These actions are being progressed offline and the next meeting will be arrange via a poll. A NESO representative has offered to provide help in understanding the TNUoS impacts of this CP, however it has been challenging to identify a convenient time to meet to complete the work. This is being progress as a matter of priority. | #REF!
DCP 423 | LDNO Discounts for negative scaling | The purpose of this change proposal is to set a floor on the LDNO discount applied to negative tariff components, after scaling, for demand tariffs. The intent of this change proposal is to seek to remedy what the proposer believes is an unintended outcome of the implementation of Ofgem’s Targeted Charging Review where LDNO tariffs can be higher than the equivalent all-the-way tariff i.e. the LDNO margin is negative for that component. | CDCM | 1 | Melissa Kendal / Andy Green | TBC | 2023-05-09 | 7 | No | 2026-04-01 | The proposer has advised that they intend to withdraw this CP formally so we await that formal withdrawal notice. | #REF!
DCP 424 | Use of System charging for complex sites | This change proposal enables the correct DUoS to be paid by meters that are class F or G within a Class 5 or Class 6 Complex Site as described in BSC Modification P441 (where netting of Import and Export takes place for BSC Settlement purposes) in a practical manner. Under p441 where generation and demand are netted before settlement, the gross values must be added to the D0036 or D0275 to ensure the correct DUoS is charged. However, for class F and G the MPAN counts are included on the D0030 data flows but the volumes are zero. In order for the volumes to be correctly charged DUoS it is proposed that these volumes are included in the D0036 or D0275 using a pseudo MPAN for the gross value. | CDCM | 1 | Andy Green / Craig Booth | TBC | 2023-10-05 | 8 | No | Aligned to BSC Mod P441 Implementation Date | Bi lateral calls with REC, BSC and suppliers have taken place since the meeting on 11 December. Legal text is being updated and will be reviewed at the next Working Group in early Febuary.
DCP 442 | Aligning enduring flexible connections | The intent of this Change Proposal is to align (and clarify) the two approaches that currently may result in a flexible connection being provided on an enduring basis. A flexible connection on an enduring basis is an arrangement that allows a Customer’s import/export of electricity via a connection to be restricted by a DNO/IDNO Party in perpetuity. This CP proposes that such a connection shall be a Flexible Connection rather than a Curtailable Connection. | General | 1 | Melissa Kendal / Craig Booth | TBC | 2024-07-01 | 7 | Yes - See comments in status column | 2026-04-01 | The next Working Group is currently TBC - due to the Proposer's availability. Once the next meeting has been scheduled, the aim is to finalise the draft Consultation ready to issue to wider industry. | DEFINITION
DCP 443 | Excess Capacity | The purpose of this Change Proposal is to drive the correct customer behaviour regarding exceeding capacity. | CDCM / EDCM | 1 | Melissa Kendal / Andy Green | TBC | 2024-09-07 | 16 | No | 2026-01-04 | The Working Group have agreed to issue a second consultation on this change and are reviewing/considering the consultation document.
DCP 452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | The intent of this Change Proposal is to correct an oversight in DCUSA which results in customers connecting directly to Grid Supply Point incorrectly facing a locational FCP charge relating to assets downstream of their connection. | EDCM | 1 | George Kestner / Dylan Townsend | Thomas Holderness | 2025-02-28 | 5 | No | 2027-04-01 | The Working Group issued a consultation on 16 December. The next Working Group meeting is due to be held in the week commencing 19 January 2026 where the group will review the consultation responses. | DEFINITION | POST CONSULTATION REFINEMENT
DCP 454 | Provide enduring targeted relief from residual charges for electric vehicle charging sites | The intent of this CP is to provide enduring targeted relief from residual charges to publicly accessible electric vehicle (“EV”) charging sites. | CDCM | 1 | Craig Booth / Richard Colwill | Thomas Holderness | 2025-05-06 | 1 | Yes - See comments in status column | 2028-04-01 | The DCUSA Secretariat completed an initial draft of an impact assessment and presented this to the DCP 420 Working Group. The same impact assessment will form the basis of the impact assessment for DCP 454, but will be amended. The DCP 420 update is therefore relevant to this. | DEFINITION
DCP 459 | DNO invoices to Embedded DNO | The intent of the Change Proposal is to require separate invoice backing data to be provided by DNO Parties when issuing invoices to EDNOs. | General | 2 | Hannah Proffitt / Andy Green | N/A | 2025-08-01 | 2 | No | 2026-02-26 | An RFI was issued on 06 February, with responses due by 27 February. A poll is ongoing to establish a date for the next meeting. |  | RFI
DCP 461 | Reducing the Impact of Transmission Distribution Charges | This Change Proposal seeks to address a growing set of structural, economic, and policy misalignments that are actively hindering the UK’s energy transition. | CCCM | 1 | Melissa Kendal / Craig Booth | N/A | 2025-08-13 | 12 | No | TBC | The DCP 461 consultation responses have been reviewed by the Working Group. The Working Group intends to raise additional CPs to cover the various defects and options identified. A paper was presented at the January Panel for this, with three new CPs intended to be raised ex-committee. However, there has been a delay in one of the CPs being raised by the Proposer. We are continuing to chase this. The next meeting is scheduled for 19 February to finalse the Consultation 2 document and legal text options. |  | POST CONSULTATION REFINEMENT
DCP 463 | Charging non-consuming De-energised CT-Metered sites | This Change Proposal seeks to charge DUoS fixed and capacity charges to non-consuming CT-metered de-energised sites. | CCCM | 1 | Hannah Proffitt / Andy Green | N/A | 2025-09-05 | 4 | No | 2027-04-01 | A consultation was issued on 04 February, with responses due by 25 February. A poll is ongoing to establish a date for the next meeting. |  | CONSULTATION
DCP 464 | IDNO Connection Applications: Treatment of Existing Assets | The intent of this Change Proposal is to clarify and align the DNO approach to the charging methodology applied to network asset(s) for IDNO applications when the IDNO is the sole user of specific network asset(s). | General | 1 | Melissa Kendal / Andy Green | N/A | 2025-09-08 | 4 | No | 2026-04-01 | The Working Group met on 04 February 2026 to review the collated Consultation responses. The next Working Group meeting is scheduled for 17 February 2026 to continue reviewing the collated Consultation responses and develop the solution. |  | CONSULTATION
DCP 465 | NFD Generator and Battery Capacity Charges | The CDCM differs from the EDCM in that it does not treat generation sites differently to demand sites when determining the Capacity charge. This change proposal is to align The Differential In Generator and Battery Capacity charges between the two methodologies and therefore reduce the capacity charges for CDCM Generators and Batteries. | CDCM | 1 | Melissa Kendal / Craig Booth | TBC | 2025-10-15 | 0 | No | 2028-04-01 | The first meeting took place and a number of actions identified in order to produce the consultation, including the need for an RFI to be issued to DNOs so that an imapct assessment can be produced. The RFI has concluded with one response having not been received, so this is being chased. The next meeting is being arranged via poll.
DCP 466 | Tariff Band to Follow Capacity | To ensure tariff bands for HH settled sites are aligned to a customer’s capacity at all times (e.g. tariff bands are assessed/changed whenever a capacity change is agreed.) | General | 1 | Melissa Kendal / Richard Colwill | TBC | 23/10.2025 | 3 | No | TBC | The first meeting was held on 11 December 2025, the second meeting was subsequently held on 07/01/2026 and the third on 12/01/2026 where the group discussed a draft consultation and legal text amendments. The fourth Working Group meeting is scheduled for 11/02/2026 where it is expected that the group will review consultation responses.
DCP 467 | Online reporting tools for Category A and B defects | To mandate that relevant DCUSA Parties utilise online reporting tools where DNOs have made them available for the purpose of reporting Category A and B situations. | General | 2 | Hannah Proffitt / Richard Colwill | TBC | 2025-12-10 | 1 | No | TBC | The first Working Group meeting was held on 12 January 2026. Members discussed the proposal and agreed to issue an RFI to seek further information from parties. This is being drafted offline.
DCP 468 | Remove Redundant DataFlow from DTC/EMDS | D0164 / MM00069 might be a redundant relic from 1998. The Proposer can find no current obligation, nor any right, under DCUSA which would either be discharged or exercised (respectively) by its use. If no longer required, any such redundant data flows should be removed from DTC/EMDS. | General | 2 | Melissa Kendal / Craig Booth | N/A |  | 0 | No | 2026-11-05 | DCP 468 Working Group - Meeting 01 - 26/02/2026 at 13:00 |  | DEFINITION
DCP 469 | Cross Code Standardisation of Charging Arrangement Notice Periods | Cross Code standardisation of Charging Arrangement Notice Periods. | General | 1 | Melissa Kendal / Richard Colwill |  |  | 0 | No | 2026-09-30 | DCP 469 Working Group - Meeting 01 - 11/02/2026 at 10:00 |  | DEFINITION
DCP 470 | Independent Credit Assessments | The purpose of this Change Proposal is to allow the Company to apply an independent credit assessment where a User has not requested it. | General | 2 | Melissa Kendal / Andy Green |  |  | 0 | No | 2026-06-25 | DCP 470 Working Group Meeting 01 - 12/02/2026 at 13:00 |  | DEFINITION
STATUS - CHANGE REPORT
N/A | N/A | [7 empty] | No
STATUS - VOTING
N/A | N/A | [7 empty] | No
STATUS - AWAITING AUTHORITY CONSENT
DCP 412 | Allocation of banding for TCR Charges for ‘Peaky’ Final Demand Customers | The intent of this CP is to consider the residual charge for ‘peaky’ customers, removing the disproportionate impact of allocating residual charges on the basis of the Agreed Supply Capacity. | CDCM / EDCM | 1 | Craig Booth / Richard Colwill | Andrew Malley | 2022-10-11 | 39 | No | 10 Working Days following Authority Decision | The Working Group have finalised the change report and legal text and this is being tabled at the February Panel. DCP 412 was approved by the Panel during their meeting in February and subsequently issued to Parties for voting on 20 February 2025, with a deadline of 13 March 2025. A Change Declaration was issued to both Parties and Ofgem on 19 March 2025. The Authority has seen been in touch to request the Secretariat conducts additional work on the impact assessment (this is not a send back). | AWAITING AUTHORITY CONSENT |  | 2025-03-19 | TBC
DCP 446 | Emergency Disconnections | To enable distributors to charge customers covered by section 2 of the National Terms of Connection for emergency disconnections that have been caused by their act or omission. | General | 1 | Hannah Proffitt / Craig Booth | N/A | 2024-11-07 | 3 | No | Next scheduled release following approval | The Working Group has reviewed the legal text and change report both of which were subsequently submitted to the Panel in March, for their agreement for it to be progressed to the voting phase. The Change Report was approved at the March Panel and subsequently issued to Parties for voting. A Change Declaration was issued to both Parties and Ofgem on 17 April 2025. | AWAITING AUTHORITY CONSENT |  | 2025-04-17 | TBC
STATUS - AWAITING IMPLEMENTATION
2026-02-26
DCP 455 | Align RAV price-inflation with that used in ED2 | ED2 PCFM uses a combination of RPI and CPIH to uplift from 2020/21 to outturn prices. This change seeks to align the prescribed calculation of RAV in Schedule 1, to retain consistency of credit cover calculation with ED2 PCFM. | General | 2 | Hannah Proffitt / Richard Colwill | N/A | 2025-05-22 | 0 | No | 2026-02-26 | DCP 455 will be implemented on 26/02/2026 - this follows on from the Party voting, the outcome for which was a decision that the change be made.
2027-04-01
DCP 440 | Consuming “de-energised” sites | To ensure all consuming “de-energised” sites are charged DUoS. | CDCM | 1 | Hannah Proffitt / Andy Green | Shaun McRaith | 2024-03-14 | 10 | No | 2027-04-01 | On 29 August 2025, Ofgem issued their decision to approve DCP 456. DCP 440 will be implemented on 01/04/2027.
DCP 450 | Managing the effects of surplus residual charge in the CDCM | To determine the appropriate arrangements for managing the effects of large residual values in the CDCM. | CDCM | 1 | Hannah Proffitt / Craig Booth | James Harvey | 2025-02-10 | 3 | No | 2027-04-01 | On 20 October 2025, Ofgem published their decision to accept DCP 450. The Change is now awaiting implementation. DCP 450 will be implemented on 01/04/2027.
STATUS - SENT BACK
N/A | N/A | [7 empty] | No
STATUS - IMPLEMENTED
DCP 458 | Amend DCP 414 process | To apply a default capacity of 71kVA following the 12 months non-applicability of capacity charging arising from DCP 414. | CDCM | 2 | Craig Booth / Andy Green | N/A | 17/07/2025 | 2 | No | 2026-01-22 | The Change Report was issued to Panel ex-committee for decision to progress to voting stage on 10 December. The outcome of the vote was that Parties have accepted Solution B and so that solution will be implemented on 22 January 2026. |  | IMPLEMENTED
STATUS - REJECTED
N/A
STATUS - WITHDRAWN
N/A
Change Register - February 2026

## Status Changes
[14 empty] | AWAITING IMPLEMENTATION | 0
[14 empty] | IMPLEMENTED | 0
[14 empty] | REJECTED | 0
DCP No | CP Title | CP Intent | CP Type | Part 1 / 2 Matter | Lead Analyst / WG Chair | Ofgem Representative | Proposal Date | WG meetings held to date | Is there anything delaying the progression of this CP? | Implementation Date | Status | Status | Status Changed in the last month | DEFINITION | 3
DCP 452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | The intent of this Change Proposal is to correct an oversight in DCUSA which results in customers connecting directly to Grid Supply Point incorrectly facing a locational FCP charge relating to assets downstream of their connection. | EDCM | 1 | George Kestner / Dylan Townsend | Thomas Holderness | 2025-02-28 | 5 | No | 46478 | The Working Group issued a consultation on 16 December. The next Working Group meeting is due to be held in the week commencing 19 January 2026 where the group will review the consultation responses. | DEFINITION | POST CONSULTATION REFINEMENT
DCP 459 | DNO invoices to Embedded DNO | The intent of the Change Proposal is to require separate invoice backing data to be provided by DNO Parties when issuing invoices to EDNOs. | General | 2 | Hannah Proffitt / Andy Green | N/A | 2025-08-01 | 2 | No | 46079 | An RFI was issued on 06 February, with responses due by 27 February. A poll is ongoing to establish a date for the next meeting. | 0 | RFI
DCP 461 | Reducing the Impact of Transmission Distribution Charges | This Change Proposal seeks to address a growing set of structural, economic, and policy misalignments that are actively hindering the UK’s energy transition. | CCCM | 1 | Melissa Kendal / Craig Booth | N/A | 2025-08-13 | 12 | No | TBC | The DCP 461 consultation responses have been reviewed by the Working Group. The Working Group intends to raise additional CPs to cover the various defects and options identified. A paper was presented at the January Panel for this, with three new CPs intended to be raised ex-committee. However, there has been a delay in one of the CPs being raised by the Proposer. We are continuing to chase this. The next meeting is scheduled for 19 February to finalse the Consultation 2 document and legal text options. | 0 | POST CONSULTATION REFINEMENT
DCP 463 | Charging non-consuming De-energised CT-Metered sites | This Change Proposal seeks to charge DUoS fixed and capacity charges to non-consuming CT-metered de-energised sites. | CCCM | 1 | Hannah Proffitt / Andy Green | N/A | 2025-09-05 | 4 | No | 46478 | A consultation was issued on 04 February, with responses due by 25 February. A poll is ongoing to establish a date for the next meeting. | 0 | CONSULTATION
DCP 464 | IDNO Connection Applications: Treatment of Existing Assets | The intent of this Change Proposal is to clarify and align the DNO approach to the charging methodology applied to network asset(s) for IDNO applications when the IDNO is the sole user of specific network asset(s). | General | 1 | Melissa Kendal / Andy Green | N/A | 2025-09-08 | 4 | No | 2026-04-01 | The Working Group met on 04 February 2026 to review the collated Consultation responses. The next Working Group meeting is scheduled for 17 February 2026 to continue reviewing the collated Consultation responses and develop the solution. | 0 | CONSULTATION
DCP 468 | Remove Redundant DataFlow from DTC/EMDS | D0164 / MM00069 might be a redundant relic from 1998. The Proposer can find no current obligation, nor any right, under DCUSA which would either be discharged or exercised (respectively) by its use. If no longer required, any such redundant data flows should be removed from DTC/EMDS. | General | 2 | Melissa Kendal / Craig Booth | N/A | 0 | 0 | No | 46331 | DCP 468 Working Group - Meeting 01 - 26/02/2026 at 13:00 | 0 | DEFINITION
DCP 469 | Cross Code Standardisation of Charging Arrangement Notice Periods | Cross Code standardisation of Charging Arrangement Notice Periods. | General | 1 | Melissa Kendal / Richard Colwill | 0 | 0 | 0 | No | 46295 | DCP 469 Working Group - Meeting 01 - 11/02/2026 at 10:00 | 0 | DEFINITION
DCP 470 | Independent Credit Assessments | The purpose of this Change Proposal is to allow the Company to apply an independent credit assessment where a User has not requested it. | General | 2 | Melissa Kendal / Andy Green | 0 | 0 | 0 | No | 46198 | DCP 470 Working Group Meeting 01 - 12/02/2026 at 13:00 | 0 | DEFINITION
DCP 458 | Amend DCP 414 process | To apply a default capacity of 71kVA following the 12 months non-applicability of capacity charging arising from DCP 414. | CDCM | 2 | Craig Booth / Andy Green | N/A | 17/07/2025 | 2 | No | 46044 | The Change Report was issued to Panel ex-committee for decision to progress to voting stage on 10 December. The outcome of the vote was that Parties have accepted Solution B and so that solution will be implemented on 22 January 2026. | 0 | IMPLEMENTED
Status Change - February 2026

## Timetables
DCP | Title | Part 1/ Part 2 Matter | Timetable Change | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
470 | Independent Credit Assessments | Part 2 | N | DEF | CON | DEF | DEF | CR
469 | Cross Code Standardisation of Charging Arrangement Notice Periods | Part 1 | N | DEF | CON | DEF | DEF | CR
468 | Remove Redundant DataFlow from DTC/EMDS | Part 2 | N | DEF | CON | DEF | DEF | CR
467 | Online reporting tools for Category A and B defects | Part 1 | N | Feb: CON; Mar: DEF; Apr: CR
466 | To ensure tariff bands for HH settled sites are aligned to a customer’s capacity at all times (e.g. tariff bands are assessed/changed whenever a capacity change is agreed.) | Part 1 | N | Feb: CON; Mar: DEF; Apr: CR
465 | NFD Generator and Battery Capacity Charges | Part 1 | N | DEF | CON | DEF | DEF | DEF | DEF | DEF | CR
464 | IDNO Connection Applications: Treatment of Existing Assets | Part 1 | N: N; DEF: DEF; CON: CR
463 | Charging non-consuming De-energised CT-Metered sites | Part 1 | N: N; DEF: DEF; CON: CR
461 | Reducing the Impact of Transmission Distribution Charges | Part 1 | N: N; DEF: CON; CON: DEF; DEF: CR
459 | DNO invoices to Embedded DNO | Part 1 | bar: N to DEF
Timetable Change |  |  | DEF: CON; CON: DEF; DEF: CR
454 | Provide enduring targeted relief from residual charges for electric vehicle charging sites | Part 1 | N | DEF | DEF | CON | DEF | DEF | CR
452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | Part 1 | N: N; DEF: DEF; CON: CR
443 | Excess Capacity | Part 1 | N: N; DEF: DEF; CON: CR
442 | Aligning enduring flexible connections | Part 1 | N: N; DEF: O/H
424 | Use of System charging for complex sites | Part 1 | N | CON | DEF | DEF | DEF | CR
423 | LDNO Discounts for negative scaling | Part 1 | N: N; DEF: O/H
420 | Include Car Charging Stations In The Definition For Non Final Demand | Part 1 | N: N; DEF: DEF; CON: DEF; DEF: CON; DEF: CR
419 | Pre-notification of Planned Supply De-energisations | Part 1 | N: N; DEF: O/H
388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | Part 1 | N: N; DEF: O/H
| DEFINITION | DEF
| RFI | RFI
| CONSULTATION | CON/ CON 2
| CHANGE REPORT | CR
| ON HOLD | O/H

## Legal Text Overlap Tracker
YES
|  | DCP 424 | DCP 423 | DCP 388 | DCP 412 | DCP 420 | DCP 439 | DCP 440 | DCP 450 | DCP 443 | DCP 458 | DCP 463 | DCP 452
|  | 2026-12-31 | 2026-04-01 | 2027-01-18 | TBC | 2026-11-01 | 2026-04-01 | 2027-04-01 | 2027-04-01 | 2026-04-01 | 2025-11-28 | 2027-04-01 | 2028-04-01 |  | NOTES TO ASSIST
Schedules | Paragraph Number | Consultation | Definition | On Hold | Awaiting Consent | Definition | Awaiting Consent | Awaiting Implementation | Awaiting Implementation | Definition | Definition | Definition | Definition | Number of CPs Impacting Paragraph
Schedule 15 | - | [12 empty] | 0
0
Schedule 16 | Introduction | [12 empty] | 0
Schedule 16 | 1 | [12 empty] | 0
Schedule 16 | 2 | [12 empty] | 0
Schedule 16 | 3 | [12 empty] | 0
Schedule 16 | 4 | [12 empty] | 0
Schedule 16 | 5 | [12 empty] | 0
Schedule 16 | 6 | [12 empty] | 0
Schedule 16 | 7 | [12 empty] | 0
Schedule 16 | 7A | [12 empty] | 0
Schedule 16 | 8 | [12 empty] | 0
Schedule 16 | 9 | [12 empty] | 0
Schedule 16 | 10 | [12 empty] | 0
Schedule 16 | 10A | [12 empty] | 0
Schedule 16 | 11 | [12 empty] | 0
Schedule 16 | 12 | [12 empty] | 0
Schedule 16 | 13 | [12 empty] | 0
Schedule 16 | 14 | [12 empty] | 0
Schedule 16 | 15 | [12 empty] | 0
Schedule 16 | 16 | [12 empty] | 0
Schedule 16 | 17 | [12 empty] | 0
Schedule 16 | 18 | [12 empty] | 0
Schedule 16 | 19 | [12 empty] | 0
Schedule 16 | 20 | [12 empty] | 0
Schedule 16 | 21 | [12 empty] | 0
Schedule 16 | 22 | [12 empty] | 0
Schedule 16 | 23 | [12 empty] | 0
Schedule 16 | 24 | [12 empty] | 0
Schedule 16 | 25 | [12 empty] | 0
Schedule 16 | 26 | [12 empty] | 0
Schedule 16 | 27 | [12 empty] | 0
Schedule 16 | 28 | [12 empty] | 0
Schedule 16 | 29 | [12 empty] | 0
Schedule 16 | 30 | [12 empty] | 0
Schedule 16 | 31 | [12 empty] | 0
Schedule 16 | 32 | [12 empty] | 0
Schedule 16 | 33 | [12 empty] | 0
Schedule 16 | 34 | [12 empty] | 0
Schedule 16 | 35 | [12 empty] | 0
Schedule 16 | 36 | [12 empty] | 0
Schedule 16 | 37 | [12 empty] | 0
Schedule 16 | 38 | [12 empty] | 0
Schedule 16 | 39 | [12 empty] | 0
Schedule 16 | 40 | [12 empty] | 0
Schedule 16 | 41 | [12 empty] | 0
Schedule 16 | 41A | [12 empty] | 0
Schedule 16 | 41B | [12 empty] | 0
Schedule 16 | 42 | [12 empty] | 0
Schedule 16 | 42A | [12 empty] | 0
Schedule 16 | 43 | [12 empty] | 0
Schedule 16 | 44 | [12 empty] | 0
Schedule 16 | 45 | [12 empty] | 0
Schedule 16 | 46 | [12 empty] | 0
Schedule 16 | 47 | [12 empty] | 0
Schedule 16 | 48 | [12 empty] | 0
Schedule 16 | 49 | [12 empty] | 0
Schedule 16 | 50 | [12 empty] | 0
Schedule 16 | 51 | [12 empty] | 0
Schedule 16 | 52 | [12 empty] | 0
Schedule 16 | 52A | [12 empty] | 0
Schedule 16 | 53 | [12 empty] | 0
Schedule 16 | 54 | [12 empty] | 0
Schedule 16 | 55 | [12 empty] | 0
Schedule 16 | 56 | [12 empty] | 0
Schedule 16 | 57 | [12 empty] | 0
Schedule 16 | 58 | [12 empty] | 0
Schedule 16 | 59 | [12 empty] | 0
Schedule 16 | 60 | [12 empty] | 0
Schedule 16 | 61 | [12 empty] | 0
Schedule 16 | 62 | [12 empty] | 0
Schedule 16 | 63 | [12 empty] | 0
Schedule 16 | 64 | [12 empty] | 0
Schedule 16 | 65 | [12 empty] | 0
Schedule 16 | 66 | [12 empty] | 0
Schedule 16 | 67 | [12 empty] | 0
Schedule 16 | 68 | [12 empty] | 0
Schedule 16 | 69 | [12 empty] | 0
Schedule 16 | 70 | [12 empty] | 0
Schedule 16 | 71 | [12 empty] | 0
Schedule 16 | 72 | [12 empty] | 0
Schedule 16 | 72A | [12 empty] | 0
Schedule 16 | 73 | [12 empty] | 0
Schedule 16 | 74 | [12 empty] | 0
Schedule 16 | 75 | [12 empty] | 0
Schedule 16 | 76 | [12 empty] | 0
Schedule 16 | 77 | [12 empty] | 0
Schedule 16 | 78 | [12 empty] | 0
Schedule 16 | 79 | [12 empty] | 0
Schedule 16 | 80 | [12 empty] | 0
Schedule 16 | 81 | [12 empty] | 0
Schedule 16 | 82 | [12 empty] | 0
Schedule 16 | 83 | [12 empty] | 0
Schedule 16 | 84 | [12 empty] | 0
Schedule 16 | 85 | [12 empty] | 0
Schedule 16 | 86 | [12 empty] | 0
Schedule 16 | 87 | [12 empty] | 0
Schedule 16 | 88 | [12 empty] | 0
Schedule 16 | 89 | [12 empty] | 0
Schedule 16 | 90 | [12 empty] | 0
Schedule 16 | 91 | [12 empty] | 0
Schedule 16 | 92 | [12 empty] | 0
Schedule 16 | 92A | [12 empty] | 0
Schedule 16 | 92B | [12 empty] | 0
Schedule 16 | 92C | [12 empty] | 0
Schedule 16 | 93 | [12 empty] | 0
Schedule 16 | 94 | [12 empty] | 0
Schedule 16 | 94A | [12 empty] | 0
Schedule 16 | 94B | [7 empty] | YES |  |  |  |  | 1
Schedule 16 | 95 | [12 empty] | 0
Schedule 16 | 96 | [12 empty] | 0
Schedule 16 | 97 | [12 empty] | 0
Schedule 16 | 98 |  | YES | [10 empty] | 1
Schedule 16 | 99 | [12 empty] | 0
Schedule 16 | 100 | [12 empty] | 0
Schedule 16 | 101 | [12 empty] | 0
Schedule 16 | 102 | [12 empty] | 0
Schedule 16 | 102A | [12 empty] | 0
Schedule 16 | 102B | [12 empty] | 0
Schedule 16 | 103 | [12 empty] | 0
Schedule 16 | 104 | [12 empty] | 0
Schedule 16 | 105 | [12 empty] | 0
Schedule 16 | 106 | [12 empty] | 0
Schedule 16 | 107 | [12 empty] | 0
Schedule 16 | 108 | [12 empty] | 0
Schedule 16 | 108A | [12 empty] | 0
Schedule 16 | 109 | [12 empty] | 0
Schedule 16 | 110 | [12 empty] | 0
Schedule 16 | 111 | [12 empty] | 0
Schedule 16 | 112 | [12 empty] | 0
Schedule 16 | 112A | [12 empty] | 0
Schedule 16 | 113 | [12 empty] | 0
Schedule 16 | 113A | [12 empty] | 0
Schedule 16 | 113B | [12 empty] | 0
Schedule 16 | 113C | [12 empty] | 0
Schedule 16 | 113D | [12 empty] | 0
Schedule 16 | 113E | [12 empty] | 0
Schedule 16 | 114 | [12 empty] | 0
Schedule 16 | 115 | [12 empty] | 0
Schedule 16 | 116 | [12 empty] | 0
Schedule 16 | 117 | [12 empty] | 0
Schedule 16 | 118 | [12 empty] | 0
Schedule 16 | 119 | [12 empty] | 0
Schedule 16 | 120 | [12 empty] | 0
Schedule 16 | 121 | [12 empty] | 0
Schedule 16 | 122 | [12 empty] | 0
Schedule 16 | 123 | [12 empty] | 0
Schedule 16 | 124 | [12 empty] | 0
Schedule 16 | 125 | [12 empty] | 0
Schedule 16 | 126 | [12 empty] | 0
Schedule 16 | 127 | [12 empty] | 0
Schedule 16 | 127A | [12 empty] | 0
Schedule 16 | 128 | YES | [11 empty] | 1
Schedule 16 | 129 | [12 empty] | 0
Schedule 16 | 130 | [12 empty] | 0
Schedule 16 | 131 | [12 empty] | 0
Schedule 16 | 132 | [12 empty] | 0
Schedule 16 | 132A | [12 empty] | 0
Schedule 16 | 132B | [12 empty] | 0
Schedule 16 | 132C | [12 empty] | 0
Schedule 16 | 132D | [12 empty] | 0
Schedule 16 | 133 | [12 empty] | 0
Schedule 16 | 134 | [12 empty] | 0
Schedule 16 | 135 | [12 empty] | 0
Schedule 16 | 135A | [12 empty] | 0 | MHHS CP seeks to remove the last column containing applicable Measurement Class
Schedule 16 | 135B | [12 empty] | 0
Schedule 16 | 136 | [12 empty] | 0
Schedule 16 | 137 | [12 empty] | 0
Schedule 16 | 138 | [12 empty] | 0
Schedule 16 | 139 | [6 empty] | YES |  |  |  | YES |  | 2
Schedule 16 | 140 | [6 empty] | YES |  |  |  | YES |  | 2
Schedule 16 | 140A | [12 empty] | 0
Schedule 16 | 140B | [12 empty] | 0
Schedule 16 | 140C | [12 empty] | 0
Schedule 16 | 140D | [12 empty] | 0
Schedule 16 | 140E | [12 empty] | 0
Schedule 16 | 141 | [12 empty] | 0
Schedule 16 | 142 | [12 empty] | 0
Schedule 16 | 143 | [12 empty] | 0
Schedule 16 | 144 | [12 empty] | 0
Schedule 16 | 145 | [12 empty] | 0
Schedule 16 | 146 | [12 empty] | 0
Schedule 16 | 147 | [12 empty] | 0
Schedule 16 | 148 | [12 empty] | 0
Schedule 16 | 149 | [12 empty] | 0
Schedule 16 | 150 | [12 empty] | 0
Schedule 16 | 151 | [12 empty] | 0
Schedule 16 | 152 | [12 empty] | 0
Schedule 16 | 153 | [8 empty] | YES |  |  |  | 1
Schedule 16 | 154 | [12 empty] | 0
Schedule 16 | 155 | [12 empty] | 0
Schedule 16 | 156 | [12 empty] | 0
Schedule 16 | 157 | [12 empty] | 0
Schedule 16 | 158 | [12 empty] | 0
Schedule 16 | 159 | [12 empty] | 0
Schedule 16 | 160 | [12 empty] | 0
Schedule 16 | 161 | [12 empty] | 0
Schedule 16 | 162 | [12 empty] | 0
Schedule 16 | 163 | [12 empty] | 0
Schedule 16 | 164 | [12 empty] | 0
Schedule 16 | 165 | [12 empty] | 0
Schedule 16 | 166 | [12 empty] | 0
Schedule 16 | 167 | [12 empty] | 0
Schedule 16 | 168 | [12 empty] | 0
Schedule 16 | 169 | [12 empty] | 0
Schedule 16 | 170 | [12 empty] | 0
Schedule 16 | 171 | [12 empty] | 0
Schedule 16 | 172 | [12 empty] | 0
Schedule 16 | 173 | [12 empty] | 0
Schedule 16 | 173A | [5 empty] | YES | [6 empty] | 1 | DCP 439 Introduces new Paragraph 173A
Schedule 16 | 174 | [12 empty] | 0
Schedule 16 | 175 | [12 empty] | 0
Schedule 16 | 176 | [12 empty] | 0
Schedule 16 | 177 | [12 empty] | 0
Schedule 16 | 178 | [12 empty] | 0
Schedule 16 | 179 | [12 empty] | 0
Schedule 16 | 180 | [12 empty] | 0
Schedule 16 | 181 | [9 empty] | YES |  |  | 1
Schedule 16 | 182 | [9 empty] | YES |  |  | 1
Schedule 16 | 183 | [12 empty] | 0
Schedule 16 | 184 | [12 empty] | 0
Schedule 16 | Glossary | [12 empty] | 0
0
Schedule 17 | Introduction | [12 empty] | 0
Schedule 17 | 1 | [12 empty] | 0
Schedule 17 | 1.1 | [12 empty] | 0
Schedule 17 | 1.2 | [12 empty] | 0
Schedule 17 | 1.3 | [12 empty] | 0 | Model reference number and date
Schedule 17 | 1.3A | [12 empty] | 0
Schedule 17 | 1.4 | [12 empty] | 0
Schedule 17 | 1.5 | [12 empty] | 0
Schedule 17 | 1.6 | [12 empty] | 0
Schedule 17 | 1.7 | [12 empty] | 0
Schedule 17 | 1.8 | [12 empty] | 0
Schedule 17 | 1.9 | [12 empty] | 0
Schedule 17 | 2 | [12 empty] | 0
Schedule 17 | 2.1 | [12 empty] | 0
Schedule 17 | 2.2 | [12 empty] | 0
Schedule 17 | 2.3 | [12 empty] | 0
Schedule 17 | 2.4 | [12 empty] | 0
Schedule 17 | 2.5 | [12 empty] | 0
Schedule 17 | 2.6 | [12 empty] | 0
Schedule 17 | 2.7 | [11 empty] | YES | 0
Schedule 17 | 2.8 | [12 empty] | 0
Schedule 17 | 2.9 | [12 empty] | 0
Schedule 17 | 2.1 | [12 empty] | 0
Schedule 17 | 2.11 | [12 empty] | 0
Schedule 17 | 2.12 | [12 empty] | 0
Schedule 17 | 2.13 | [12 empty] | 0
Schedule 17 | 2.14 | [12 empty] | 0
Schedule 17 | 2.15 | [12 empty] | 0
Schedule 17 | 2.16 | [12 empty] | 0
Schedule 17 | 2.17 | [12 empty] | 0
Schedule 17 | 2.18 | [12 empty] | 0
Schedule 17 | 2.19 | [12 empty] | 0
Schedule 17 | 3 | [12 empty] | 0
Schedule 17 | 3.1 | [12 empty] | 0
Schedule 17 | 3.2 | [12 empty] | 0
Schedule 17 | 3.3 | [12 empty] | 0
Schedule 17 | 3.4 | [12 empty] | 0
Schedule 17 | 3.5 | [12 empty] | 0
Schedule 17 | 3.6 | [12 empty] | 0
Schedule 17 | 3.7 | [12 empty] | 0
Schedule 17 | 4 | [12 empty] | 0
Schedule 17 | 4.1 | [12 empty] | 0
Schedule 17 | 5 | [12 empty] | 0
Schedule 17 | 5.1 | [12 empty] | 0
Schedule 17 | 6 | [12 empty] | 0
Schedule 17 | 6.1 | [12 empty] | 0
Schedule 17 | 6.2 | [11 empty] | YES | 0
Schedule 17 | 6.3 | [11 empty] | YES | 0
Schedule 17 | 7 | [12 empty] | 0
Schedule 17 | 7.1 | [12 empty] | 0
Schedule 17 | 8 | [12 empty] | 0
Schedule 17 | 8.1 | [12 empty] | 0
Schedule 17 | 8.2 | [12 empty] | 0
Schedule 17 | 8.3 | [12 empty] | 0
Schedule 17 | 8.4 | [12 empty] | 0
Schedule 17 | 9 | [12 empty] | 0
Schedule 17 | 9.1 | [12 empty] | 0
Schedule 17 | 9.2 | [12 empty] | 0
Schedule 17 | 9.3 | [12 empty] | 0
Schedule 17 | 10 | [12 empty] | 0
Schedule 17 | 10.1 | [12 empty] | 0
Schedule 17 | 10.2 | [12 empty] | 0
Schedule 17 | 10.3 | [12 empty] | 0
Schedule 17 | 10.4 | [12 empty] | 0
Schedule 17 | 11 | [12 empty] | 0
Schedule 17 | 11.1 | [12 empty] | 0
Schedule 17 | 12 | [12 empty] | 0
Schedule 17 | 12.1 | [12 empty] | 0
Schedule 17 | 12.2 | [12 empty] | 0
Schedule 17 | 12.3 | [12 empty] | 0
Schedule 17 | 13 | [12 empty] | 0
Schedule 17 | 13.1 | [12 empty] | 0
Schedule 17 | 13.2 | [12 empty] | 0
Schedule 17 | 13.3 | [12 empty] | 0
Schedule 17 | 13.4 | [12 empty] | 0
Schedule 17 | 14 | [12 empty] | 0
Schedule 17 | 14.1 | [12 empty] | 0
Schedule 17 | 14.2 | [12 empty] | 0
Schedule 17 | 14.3 | [12 empty] | 0
Schedule 17 | 14.4 | [12 empty] | 0
Schedule 17 | 14.5 | [12 empty] | 0
Schedule 17 | 15 | [12 empty] | 0
Schedule 17 | 15.1 | [12 empty] | 0
Schedule 17 | 15.2 | [12 empty] | 0
Schedule 17 | 15.3 | [12 empty] | 0
Schedule 17 | 15.4 | [12 empty] | 0
Schedule 17 | 15.5 | [12 empty] | 0
Schedule 17 | 15.6 | [12 empty] | 0
Schedule 17 | 15.7 | [12 empty] | 0
Schedule 17 | 15.8 | [12 empty] | 0
Schedule 17 | 15.9 | [12 empty] | 0
Schedule 17 | 15.1 | [12 empty] | 0
Schedule 17 | 15.11 | [12 empty] | 0
Schedule 17 | 15.12 | [12 empty] | 0
Schedule 17 | 15.15 | [12 empty] | 0
Schedule 17 | 16 | [12 empty] | 0
Schedule 17 | 16.1 | [12 empty] | 0
Schedule 17 | 16.2 | [12 empty] | 0
Schedule 17 | 16.3 | [12 empty] | 0
Schedule 17 | 16.4 | [12 empty] | 0
Schedule 17 | 16.5 | [12 empty] | 0
Schedule 17 | 16.6 | [12 empty] | 0
Schedule 17 | 16.7 | [12 empty] | 0
Schedule 17 | 16.8 | [12 empty] | 0
Schedule 17 | 16.9 | [12 empty] | 0
Schedule 17 | 16.1 | [12 empty] | 0
Schedule 17 | 17 | [12 empty] | 0
Schedule 17 | 17.1 | [12 empty] | 0
Schedule 17 | 17.2 | [12 empty] | 0
Schedule 17 | 17.3 | [12 empty] | 0
Schedule 17 | 18 | [12 empty] | 0
Schedule 17 | 18.1 | [12 empty] | 0
Schedule 17 | 18.2 | [12 empty] | 0
Schedule 17 | 18.3 | [12 empty] | 0
Schedule 17 | 18.4 | [12 empty] | 0
Schedule 17 | 18.5 | [12 empty] | 0
Schedule 17 | 18.6 | [12 empty] | 0
Schedule 17 | 18.7 | [12 empty] | 0
Schedule 17 | 18.8 | [12 empty] | 0
Schedule 17 | 18.9 | [12 empty] | 0
Schedule 17 | 18.1 | [12 empty] | 0
Schedule 17 | 18.11 | [12 empty] | 0
Schedule 17 | 18.12 | [12 empty] | 0
Schedule 17 | 18.13 | [12 empty] | 0
Schedule 17 | 18.14 | [12 empty] | 0
Schedule 17 | 18.15 | [12 empty] | 0
Schedule 17 | 18.16 | [12 empty] | 0
Schedule 17 | 18.17 | [12 empty] | 0
Schedule 17 | 18.18 | [12 empty] | 0
Schedule 17 | 18.19 | [12 empty] | 0
Schedule 17 | 18.2 | [12 empty] | 0
Schedule 17 | 18.21 | [12 empty] | 0
Schedule 17 | 19 | [12 empty] | 0
Schedule 17 | 19.1 | [12 empty] | 0
Schedule 17 | 19.2 | [12 empty] | 0
Schedule 17 | 19.3 | [12 empty] | 0
Schedule 17 | 19.4 | [12 empty] | 0
Schedule 17 | 19.5 | [12 empty] | 0
Schedule 17 | 19.6 | [12 empty] | 0
Schedule 17 | 19.7 | [12 empty] | 0
Schedule 17 | 19.8 | [12 empty] | 0
Schedule 17 | 19.9 | [12 empty] | 0
Schedule 17 | 19.1 | [12 empty] | 0
Schedule 17 | 19.11 | [12 empty] | 0
Schedule 17 | 20 | [12 empty] | 0
Schedule 17 | 20.1 | [12 empty] | 0
Schedule 17 | 20.2 | [12 empty] | 0
Schedule 17 | 20.3 | [12 empty] | 0
Schedule 17 | 20.4 | [12 empty] | 0
Schedule 17 | 20.5 | [12 empty] | 0
Schedule 17 | 20.6 | [8 empty] | YES |  |  |  | 1
Schedule 17 | 20.7 | [8 empty] | YES |  |  |  | 1
Schedule 17 | 20.8 | [12 empty] | 0
Schedule 17 | 20.9 | [8 empty] | YES |  |  |  | 1
Schedule 17 | 21 | [12 empty] | 0
Schedule 17 | 21.1 | [12 empty] | 0
Schedule 17 | 21.2 | [12 empty] | 0
Schedule 17 | 22 | [12 empty] | 0
Schedule 17 | 22.1 | [12 empty] | 0
Schedule 17 | 22.2 | [12 empty] | 0
Schedule 17 | 22.3 | [12 empty] | 0
Schedule 17 | 22.4 | [12 empty] | 0
Schedule 17 | 23 | [12 empty] | 0
Schedule 17 | 23.1 | [12 empty] | 0
Schedule 17 | 23.2 | [12 empty] | 0
Schedule 17 | 23.3 | [12 empty] | 0
Schedule 17 | 23.4 | [12 empty] | 0
Schedule 17 | 23.5 | [12 empty] | 0
Schedule 17 | 24 | [12 empty] | 0
Schedule 17 | 24.1 | [12 empty] | 0
Schedule 17 | 24.2 | [12 empty] | 0
Schedule 17 | 24.3 | [12 empty] | 0
Schedule 17 | 24.4 | [12 empty] | 0
Schedule 17 | 24.5 | [12 empty] | 0
Schedule 17 | 24.6 | [12 empty] | 0
Schedule 17 | 24.7 | [12 empty] | 0
Schedule 17 | 24.8 | [12 empty] | 0
Schedule 17 | 24.9 | [12 empty] | 0
Schedule 17 | 25 | [12 empty] | 0
Schedule 17 | 25.1 | [12 empty] | 0
Schedule 17 | 25.2 | [12 empty] | 0
Schedule 17 | 25.3 | [12 empty] | 0
Schedule 17 | 25.4 | [12 empty] | 0
Schedule 17 | 25.5 | [12 empty] | 0
Schedule 17 | 25.6 | [12 empty] | 0
Schedule 17 | 25.7 | [12 empty] | 0
Schedule 17 | 25.8 | [12 empty] | 0
Schedule 17 | 25.9 | [12 empty] | 0
Schedule 17 | 25.1 | [12 empty] | 0
Schedule 17 | 25.11 | [12 empty] | 0
Schedule 17 | 25.12 | [12 empty] | 0
Schedule 17 | 25.13 | [12 empty] | 0
Schedule 17 | 25.14 | [12 empty] | 0
Schedule 17 | 25.15 | [12 empty] | 0
Schedule 17 | 25.16 | [12 empty] | 0
Schedule 17 | 25.17 | [12 empty] | 0
Schedule 17 | 25.18 | [12 empty] | 0
Schedule 17 | 25.19 | [12 empty] | 0
Schedule 17 | 26 | [12 empty] | 0
Schedule 17 | 26.1 | [12 empty] | 0
Schedule 17 | 26.2 | [12 empty] | 0
Schedule 17 | 26.3 | [12 empty] | 0
Schedule 17 | 26.4 | [12 empty] | 0
Schedule 17 | 26.5 | [12 empty] | 0
Schedule 17 | 26.6 | [12 empty] | 0
Schedule 17 | 26.7 | [12 empty] | 0
Schedule 17 | 26.8 | [12 empty] | 0
Schedule 17 | 26.9 | [12 empty] | 0
Schedule 17 | 26.1 | [12 empty] | 0
Schedule 17 | 26.11 | [12 empty] | 0
Schedule 17 | 27 | [12 empty] | 0
Schedule 17 | 27.1 | [12 empty] | 0
Schedule 17 | 27.2 | [12 empty] | 0
Schedule 17 | 27.3 | [12 empty] | 0
Schedule 17 | 27.4 | [12 empty] | 0
Schedule 17 | 28 | [12 empty] | 0
Schedule 17 | 28.1 | [12 empty] | 0
Schedule 17 | 28.2 | [12 empty] | 0
Schedule 17 | 29 | [12 empty] | 0
Schedule 17 | 29.1 | [12 empty] | 0
Schedule 17 | 29.2 | [12 empty] | 0
Schedule 17 | 29.3 | [12 empty] | 0
Schedule 17 | 29.4 | [12 empty] | 0
Schedule 17 | 30 | [12 empty] | 0
Schedule 17 | 30.1 | [12 empty] | 0
Schedule 17 | 30.2 | [12 empty] | 0
Schedule 17 | 30.3 | [12 empty] | 0
Schedule 17 | 30.4 | [12 empty] | 0
Schedule 17 | 30.5 | [12 empty] | 0
Schedule 17 | 30.6 | [12 empty] | 0
Schedule 17 | 30.7 | [12 empty] | 0
Schedule 17 | 30.8 | [12 empty] | 0
Schedule 17 | 30.9 | [12 empty] | 0
Schedule 17 | 30.1 | [12 empty] | 0
Schedule 17 | 30.11 | [12 empty] | 0
Schedule 17 | 31 | [5 empty] | YES | [6 empty] | 1 | DCP 439 Introduces new Paragraph 31
Schedule 17 | 31.1 | [5 empty] | YES | [6 empty] | 1 | DCP 439 Introduces new Paragraph 31.1
Schedule 17: Annex 1 | 1 | [12 empty] | 0
Schedule 17: Annex 1 | 2 | [12 empty] | 0
Schedule 17: Annex 1 | 2.1 | [12 empty] | 0
Schedule 17: Annex 1 | 2.2 | [12 empty] | 0
Schedule 17: Annex 1 | 2.3 | [12 empty] | 0
Schedule 17: Annex 1 | 2.4 | [12 empty] | 0
Schedule 17: Annex 1 | 2.5 | [12 empty] | 0
Schedule 17: Annex 1 | 3 | [12 empty] | 0
Schedule 17: Annex 1 | Definitions | [12 empty] | 0
Schedule 17: Annex 1 | 4 | [12 empty] | 0
Schedule 17: Annex 1 | 4.1 | [12 empty] | 0
Schedule 17: Annex 1 | 4.2 | [12 empty] | 0
Schedule 17: Annex 1 | 4.3 | [12 empty] | 0
Schedule 17: Annex 1 | 4.4 | [12 empty] | 0
Schedule 17: Annex 1 | 4.5 | [12 empty] | 0
Schedule 17: Annex 1 | 4.6 | [12 empty] | 0
Schedule 17: Annex 1 | 4.7 | [12 empty] | 0
Schedule 17: Annex 1 | 4.8 | [12 empty] | 0
Schedule 17: Annex 1 | 4.9 | [12 empty] | 0
Schedule 17: Annex 1 | 4.1 | [12 empty] | 0
Schedule 17: Annex 1 | 5 | [12 empty] | 0
Schedule 17: Annex 1 | 5.1 | [12 empty] | 0
Schedule 17: Annex 1 | 5.2 | [12 empty] | 0
Schedule 17: Annex 1 | 5.3 | [12 empty] | 0
Schedule 17: Annex 1 | 5.4 | [12 empty] | 0
Schedule 17: Annex 1 | 5.5 | [12 empty] | 0
Schedule 17: Annex 1 | 5.6 | [12 empty] | 0
Schedule 17: Annex 1 | 5.7 | [12 empty] | 0
Schedule 17: Annex 1 | 5.8 | [12 empty] | 0
Schedule 17: Annex 1 | 5.9 | [12 empty] | 0
Schedule 17: Annex 1 | 5.1 | [12 empty] | 0
Schedule 17: Annex 1 | 5.11 | [12 empty] | 0
Schedule 17: Annex 1 | 5.12 | [12 empty] | 0
Schedule 17: Annex 1 | 5.13 | [12 empty] | 0
Schedule 17: Annex 1 | 5.14 | [12 empty] | 0
Schedule 17: Annex 1 | 5.15 | [12 empty] | 0
Schedule 17: Annex 1 | 5.16 | [12 empty] | 0
Schedule 17: Annex 1 | 5.17 | [12 empty] | 0
Schedule 17: Annex 1 | 5.18 | [12 empty] | 0
Schedule 17: Annex 1 | 5.19 | [12 empty] | 0
Schedule 17: Annex 1 | 5.2 | [12 empty] | 0
Schedule 17: Annex 1 | 5.21 | [12 empty] | 0
Schedule 17: Annex 1 | 5.22 | [12 empty] | 0
Schedule 17: Annex 1 | 5.23 | [12 empty] | 0
Schedule 17: Annex 1 | 5.24 | [12 empty] | 0
Schedule 17: Annex 1 | 5.25 | [12 empty] | 0
Schedule 17: Annex 1 | 5.26 | [12 empty] | 0
Schedule 17: Annex 1 | 5.27 | [12 empty] | 0
Schedule 17: Annex 1 | 5.28 | [12 empty] | 0
Schedule 17: Annex 1 | 5.29 | [12 empty] | 0
Schedule 17: Annex 1 | 5.3 | [12 empty] | 0
Schedule 17: Annex 1 | 5.31 | [12 empty] | 0
Schedule 17: Annex 1 | 5.32 | [12 empty] | 0
Schedule 17: Annex 1 | 5.33 | [12 empty] | 0
Schedule 17: Annex 1 | 5.34 | [12 empty] | 0
Schedule 17: Annex 1 | 5.35 | [12 empty] | 0
Schedule 17: Annex 1 | 5.36 | [12 empty] | 0
Schedule 17: Annex 1 | 5.37 | [12 empty] | 0
Schedule 17: Annex 1 | 5.38 | [12 empty] | 0
Schedule 17: Annex 1 | 5.39 | [12 empty] | 0
Schedule 17: Annex 1 | 5.4 | [12 empty] | 0
Schedule 17: Annex 1 | 5.41 | [12 empty] | 0
Schedule 17: Annex 1 | 5.42 | [12 empty] | 0
Schedule 17: Annex 1 | 5.43 | [12 empty] | 0
Schedule 17: Annex 1 | 5.44 | [12 empty] | 0
Schedule 17: Annex 1 | 5.45 | [12 empty] | 0
Schedule 17: Annex 1 | 6 | [12 empty] | 0
Schedule 17: Annex 1 | 6.1 | [12 empty] | 0
Schedule 17: Annex 1 | 6.2 | [12 empty] | 0
Schedule 17: Annex 1 | 6.3 | [11 empty] | YES | 0
Schedule 17: Annex 1 | 6.4 | [12 empty] | 0
Schedule 17: Annex 1 | 6.5 | [12 empty] | 0
Schedule 17: Annex 1 | 6.6 | [12 empty] | 0
Schedule 17: Annex 1 | 6.7 | [12 empty] | 0
Schedule 17: Annex 1 | 6.8 | [12 empty] | 0
Schedule 17: Annex 1 | 7 | [12 empty] | 0
Schedule 17: Annex 1 | 7.1 | [12 empty] | 0
Schedule 17: Annex 1 | 7.2 | [12 empty] | 0
Schedule 17: Annex 1 | 7.3 | [12 empty] | 0
Schedule 17: Annex 1 | 7.4 | [12 empty] | 0
Schedule 17: Annex 1 | 7.5 | [12 empty] | 0
Schedule 17: Annex 1 | 7.6 | [12 empty] | 0
Schedule 17: Annex 1 | 7.7 | [12 empty] | 0
Schedule 17: Annex 1 | 7.8 | [12 empty] | 0
Schedule 17: Annex 1 | 8 | [12 empty] | 0
Schedule 17: Annex 1 | 8.1 | [12 empty] | 0
Schedule 17: Annex 1 | 8.2 | [12 empty] | 0
Schedule 17: Annex 1 | 8.3 | [12 empty] | 0
Schedule 17: Annex 1 | 8.4 | [12 empty] | 0
Schedule 17: Annex 1 | 9 | [12 empty] | 0
Schedule 17: Annex 1 | 9.1 | [12 empty] | 0
Schedule 17: Annex 1 | 9.2 | [12 empty] | 0
Schedule 17: Annex 1 | 9.3 | [12 empty] | 0
Schedule 17: Annex 1 | 9.4 | [12 empty] | 0
Schedule 17: Annex 1 | 9.5 | [12 empty] | 0
Schedule 17: Annex 1 | 9.6 | [12 empty] | 0
Schedule 17: Annex 1 | 9.7 | [12 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [12 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [12 empty] | 0
Schedule 17: Annex 1 | Attachment 1 | [12 empty] | 0
Schedule 17: Annex 1 | Attachment 3 | [12 empty] | 0
Schedule 17: Annex 2 | Annex 2 | [12 empty] | 0
0
Schedule 18 | Introduction | [12 empty] | 0
Schedule 18 | 1 | [12 empty] | 0
Schedule 18 | 1.1 | [12 empty] | 0
Schedule 18 | 1.2 | [12 empty] | 0
Schedule 18 | 1.3 | [12 empty] | 0 | Model reference number and date
Schedule 18 | 1.3A | [12 empty] | 0
Schedule 18 | 1.4 | [12 empty] | 0
Schedule 18 | 1.5 | [12 empty] | 0
Schedule 18 | 1.6 | [12 empty] | 0
Schedule 18 | 1.7 | [12 empty] | 0
Schedule 18 | 1.8 | [12 empty] | 0
Schedule 18 | 1.9 | [12 empty] | 0
Schedule 18 | 2 | [12 empty] | 0
Schedule 18 | 2.1 | [12 empty] | 0
Schedule 18 | 2.2 | [12 empty] | 0
Schedule 18 | 2.3 | [12 empty] | 0
Schedule 18 | 2.4 | [12 empty] | 0
Schedule 18 | 2.5 | [12 empty] | 0
Schedule 18 | 2.6 | [12 empty] | 0
Schedule 18 | 2.7 | [12 empty] | 0
Schedule 18 | 2.8 | [12 empty] | 0
Schedule 18 | 2.9 | [12 empty] | 0
Schedule 18 | 2.1 | [12 empty] | 0
Schedule 18 | 2.11 | [12 empty] | 0
Schedule 18 | 2.12 | [12 empty] | 0
Schedule 18 | 2.13 | [12 empty] | 0
Schedule 18 | 2.14 | [12 empty] | 0
Schedule 18 | 2.15 | [12 empty] | 0
Schedule 18 | 2.16 | [12 empty] | 0
Schedule 18 | 2.17 | [12 empty] | 0
Schedule 18 | 2.18 | [12 empty] | 0
Schedule 18 | 2.19 | [12 empty] | 0
Schedule 18 | 2.2 | [12 empty] | 0
Schedule 18 | 2.21 | [12 empty] | 0
Schedule 18 | 2.22 | [12 empty] | 0
Schedule 18 | 2.23 | [12 empty] | 0
Schedule 18 | 2.24 | [12 empty] | 0
Schedule 18 | 2.25 | [12 empty] | 0
Schedule 18 | 2.26 | [12 empty] | 0
Schedule 18 | 2.27 | [12 empty] | 0
Schedule 18 | 2.28 | [12 empty] | 0
Schedule 18 | 2.29 | [12 empty] | 0
Schedule 18 | 2.3 | [12 empty] | 0
Schedule 18 | 3 | [12 empty] | 0
Schedule 18 | 3.1 | [12 empty] | 0
Schedule 18 | 3.2 | [12 empty] | 0
Schedule 18 | 3.3 | [12 empty] | 0
Schedule 18 | 3.4 | [12 empty] | 0
Schedule 18 | 3.5 | [12 empty] | 0
Schedule 18 | 3.6 | [12 empty] | 0
Schedule 18 | 3.7 | [12 empty] | 0
Schedule 18 | 4 | [12 empty] | 0
Schedule 18 | 4.1 | [12 empty] | 0
Schedule 18 | 5 | [12 empty] | 0
Schedule 18 | 5.1 | [12 empty] | 0
Schedule 18 | 6 | [12 empty] | 0
Schedule 18 | 6.1 | [12 empty] | 0
Schedule 18 | 6.2 | [12 empty] | 0
Schedule 18 | 6.3 | [12 empty] | 0
Schedule 18 | 6.4 | [12 empty] | 0
Schedule 18 | 6.5 | [12 empty] | 0
Schedule 18 | 7 | [12 empty] | 0
Schedule 18 | 7.1 | [12 empty] | 0
Schedule 18 | 8 | [12 empty] | 0
Schedule 18 | 8.1 | [12 empty] | 0
Schedule 18 | 8.2 | [12 empty] | 0
Schedule 18 | 8.3 | [12 empty] | 0
Schedule 18 | 8.4 | [12 empty] | 0
Schedule 18 | 9 | [12 empty] | 0
Schedule 18 | 9.1 | [12 empty] | 0
Schedule 18 | 9.2 | [12 empty] | 0
Schedule 18 | 10 | [12 empty] | 0
Schedule 18 | 10.1 | [12 empty] | 0
Schedule 18 | 10.2 | [12 empty] | 0
Schedule 18 | 10.3 | [12 empty] | 0
Schedule 18 | 10.4 | [12 empty] | 0
Schedule 18 | 10.5 | [12 empty] | 0
Schedule 18 | 11 | [12 empty] | 0
Schedule 18 | 11.1 | [12 empty] | 0
Schedule 18 | 12 | [12 empty] | 0
Schedule 18 | 12.1 | [12 empty] | 0
Schedule 18 | 12.2 | [12 empty] | 0
Schedule 18 | 12.3 | [12 empty] | 0
Schedule 18 | 12.4 | [12 empty] | 0
Schedule 18 | 12.5 | [12 empty] | 0
Schedule 18 | 12.6 | [12 empty] | 0
Schedule 18 | 13 | [12 empty] | 0
Schedule 18 | 13.1 | [12 empty] | 0
Schedule 18 | 13.2 | [12 empty] | 0
Schedule 18 | 13.3 | [12 empty] | 0
Schedule 18 | 13.4 | [12 empty] | 0
Schedule 18 | 14 | [12 empty] | 0
Schedule 18 | 14.1 | [12 empty] | 0
Schedule 18 | 14.2 | [12 empty] | 0
Schedule 18 | 14.3 | [12 empty] | 0
Schedule 18 | 14.4 | [12 empty] | 0
Schedule 18 | 14.5 | [12 empty] | 0
Schedule 18 | 15 | [12 empty] | 0
Schedule 18 | 15.1 | [12 empty] | 0
Schedule 18 | 15.2 | [12 empty] | 0
Schedule 18 | 15.3 | [12 empty] | 0
Schedule 18 | 15.4 | [12 empty] | 0
Schedule 18 | 15.5 | [12 empty] | 0
Schedule 18 | 15.6 | [12 empty] | 0
Schedule 18 | 15.7 | [12 empty] | 0
Schedule 18 | 15.8 | [12 empty] | 0
Schedule 18 | 15.9 | [12 empty] | 0
Schedule 18 | 15.1 | [12 empty] | 0
Schedule 18 | 15.11 | [12 empty] | 0
Schedule 18 | 15.12 | [12 empty] | 0
Schedule 18 | 15.15 | [12 empty] | 0
Schedule 18 | 16 | [12 empty] | 0
Schedule 18 | 16.1 | [12 empty] | 0
Schedule 18 | 16.2 | [12 empty] | 0
Schedule 18 | 16.3 | [12 empty] | 0
Schedule 18 | 16.4 | [12 empty] | 0
Schedule 18 | 16.5 | [12 empty] | 0
Schedule 18 | 16.6 | [12 empty] | 0
Schedule 18 | 16.7 | [12 empty] | 0
Schedule 18 | 16.8 | [12 empty] | 0
Schedule 18 | 16.9 | [12 empty] | 0
Schedule 18 | 16.1 | [12 empty] | 0
Schedule 18 | 17 | [12 empty] | 0
Schedule 18 | 17.1 | [12 empty] | 0
Schedule 18 | 17.2 | [12 empty] | 0
Schedule 18 | 17.3 | [12 empty] | 0
Schedule 18 | 18 | [12 empty] | 0
Schedule 18 | 18.1 | [12 empty] | 0
Schedule 18 | 18.2 | [12 empty] | 0
Schedule 18 | 18.3 | [12 empty] | 0
Schedule 18 | 18.4 | [12 empty] | 0
Schedule 18 | 18.5 | [12 empty] | 0
Schedule 18 | 18.6 | [12 empty] | 0
Schedule 18 | 18.7 | [12 empty] | 0
Schedule 18 | 18.8 | [12 empty] | 0
Schedule 18 | 18.9 | [12 empty] | 0
Schedule 18 | 18.1 | [12 empty] | 0
Schedule 18 | 18.11 | [12 empty] | 0
Schedule 18 | 18.12 | [12 empty] | 0
Schedule 18 | 18.13 | [12 empty] | 0
Schedule 18 | 18.14 | [12 empty] | 0
Schedule 18 | 18.15 | [12 empty] | 0
Schedule 18 | 18.16 | [12 empty] | 0
Schedule 18 | 18.17 | [12 empty] | 0
Schedule 18 | 18.18 | [12 empty] | 0
Schedule 18 | 18.19 | [12 empty] | 0
Schedule 18 | 18.2 | [12 empty] | 0
Schedule 18 | 18.21 | [12 empty] | 0
Schedule 18 | 19 | [12 empty] | 0
Schedule 18 | 19.1 | [12 empty] | 0
Schedule 18 | 19.2 | [12 empty] | 0
Schedule 18 | 19.3 | [12 empty] | 0
Schedule 18 | 19.4 | [12 empty] | 0
Schedule 18 | 19.5 | [12 empty] | 0
Schedule 18 | 19.6 | [12 empty] | 0
Schedule 18 | 19.7 | [12 empty] | 0
Schedule 18 | 19.8 | [12 empty] | 0
Schedule 18 | 19.9 | [12 empty] | 0
Schedule 18 | 19.1 | [12 empty] | 0
Schedule 18 | 19.11 | [12 empty] | 0
Schedule 18 | 20 | [12 empty] | 0
Schedule 18 | 20.1 | [12 empty] | 0
Schedule 18 | 20.2 | [12 empty] | 0
Schedule 18 | 20.3 | [12 empty] | 0
Schedule 18 | 20.4 | [12 empty] | 0
Schedule 18 | 20.5 | [12 empty] | 0
Schedule 18 | 20.6 | [8 empty] | YES |  |  |  | 1
Schedule 18 | 20.7 | [8 empty] | YES |  |  |  | 1
Schedule 18 | 20.8 | [12 empty] | 0
Schedule 18 | 20.9 | [8 empty] | YES |  |  |  | 1
Schedule 18 | 21 | [12 empty] | 0
Schedule 18 | 21.1 | [12 empty] | 0
Schedule 18 | 21.2 | [12 empty] | 0
Schedule 18 | 22 | [12 empty] | 0
Schedule 18 | 22.1 | [12 empty] | 0
Schedule 18 | 22.2 | [12 empty] | 0
Schedule 18 | 22.3 | [12 empty] | 0
Schedule 18 | 22.4 | [12 empty] | 0
Schedule 18 | 23 | [12 empty] | 0
Schedule 18 | 23.1 | [12 empty] | 0
Schedule 18 | 23.2 | [12 empty] | 0
Schedule 18 | 23.3 | [12 empty] | 0
Schedule 18 | 23.4 | [12 empty] | 0
Schedule 18 | 23.5 | [12 empty] | 0
Schedule 18 | 24 | [12 empty] | 0
Schedule 18 | 24.1 | [12 empty] | 0
Schedule 18 | 24.2 | [12 empty] | 0
Schedule 18 | 24.3 | [12 empty] | 0
Schedule 18 | 24.4 | [12 empty] | 0
Schedule 18 | 24.5 | [12 empty] | 0
Schedule 18 | 24.6 | [12 empty] | 0
Schedule 18 | 24.7 | [12 empty] | 0
Schedule 18 | 24.8 | [12 empty] | 0
Schedule 18 | 24.9 | [12 empty] | 0
Schedule 18 | 25 | [12 empty] | 0
Schedule 18 | 25.1 | [12 empty] | 0
Schedule 18 | 25.2 | [12 empty] | 0
Schedule 18 | 25.3 | [12 empty] | 0
Schedule 18 | 25.4 | [12 empty] | 0
Schedule 18 | 25.5 | [12 empty] | 0
Schedule 18 | 25.6 | [12 empty] | 0
Schedule 18 | 25.7 | [12 empty] | 0
Schedule 18 | 25.8 | [12 empty] | 0
Schedule 18 | 25.9 | [12 empty] | 0
Schedule 18 | 25.1 | [12 empty] | 0
Schedule 18 | 25.11 | [12 empty] | 0
Schedule 18 | 25.12 | [12 empty] | 0
Schedule 18 | 25.13 | [12 empty] | 0
Schedule 18 | 25.14 | [12 empty] | 0
Schedule 18 | 25.15 | [12 empty] | 0
Schedule 18 | 25.16 | [12 empty] | 0
Schedule 18 | 25.17 | [12 empty] | 0
Schedule 18 | 25.18 | [12 empty] | 0
Schedule 18 | 25.19 | [12 empty] | 0
Schedule 18 | 26 | [12 empty] | 0
Schedule 18 | 26.1 | [12 empty] | 0
Schedule 18 | 26.2 | [12 empty] | 0
Schedule 18 | 26.3 | [12 empty] | 0
Schedule 18 | 26.4 | [12 empty] | 0
Schedule 18 | 26.5 | [12 empty] | 0
Schedule 18 | 26.6 | [12 empty] | 0
Schedule 18 | 26.7 | [12 empty] | 0
Schedule 18 | 26.8 | [12 empty] | 0
Schedule 18 | 26.9 | [12 empty] | 0
Schedule 18 | 26.1 | [12 empty] | 0
Schedule 18 | 26.11 | [12 empty] | 0
Schedule 18 | 27 | [12 empty] | 0
Schedule 18 | 27.1 | [12 empty] | 0
Schedule 18 | 27.2 | [12 empty] | 0
Schedule 18 | 27.3 | [12 empty] | 0
Schedule 18 | 27.4 | [12 empty] | 0
Schedule 18 | 28 | [12 empty] | 0
Schedule 18 | 28.1 | [12 empty] | 0
Schedule 18 | 28.2 | [12 empty] | 0
Schedule 18 | 29 | [12 empty] | 0
Schedule 18 | 29.1 | [12 empty] | 0
Schedule 18 | 29.2 | [12 empty] | 0
Schedule 18 | 29.3 | [12 empty] | 0
Schedule 18 | 29.4 | [12 empty] | 0
Schedule 18 | 30 | [12 empty] | 0
Schedule 18 | 30.1 | [12 empty] | 0
Schedule 18 | 30.2 | [12 empty] | 0
Schedule 18 | 30.3 | [12 empty] | 0
Schedule 18 | 30.4 | [12 empty] | 0
Schedule 18 | 30.5 | [12 empty] | 0
Schedule 18 | 30.6 | [12 empty] | 0
Schedule 18 | 30.7 | [12 empty] | 0
Schedule 18 | 30.8 | [12 empty] | 0
Schedule 18 | 30.9 | [12 empty] | 0
Schedule 18 | 30.1 | [12 empty] | 0
Schedule 18 | 30.11 | [12 empty] | 0
Schedule 18 | 31 | [12 empty] | 0 | DCP 439 Introduces new Paragraph 31
Schedule 18 | 31.1 | [12 empty] | 0 | DCP 439 Introduces new Paragraph 31.1
Schedule 18: Annex 1 | 1 | [12 empty] | 0
Schedule 18: Annex 1 | 1.1 | [12 empty] | 0
Schedule 18: Annex 1 | 2 | [12 empty] | 0
Schedule 18: Annex 1 | 2.1 | [12 empty] | 0
Schedule 18: Annex 1 | 2.2 | [12 empty] | 0
Schedule 18: Annex 1 | 2.3 | [12 empty] | 0
Schedule 18: Annex 1 | 2.4 | [12 empty] | 0
Schedule 18: Annex 1 | 2.5 | [12 empty] | 0
Schedule 18: Annex 1 | 3 | [12 empty] | 0
Schedule 18: Annex 1 | Definitions | [12 empty] | 0
Schedule 18: Annex 1 | 4 | [12 empty] | 0
Schedule 18: Annex 1 | 4.1 | [12 empty] | 0
Schedule 18: Annex 1 | 4.2 | [12 empty] | 0
Schedule 18: Annex 1 | 4.3 | [12 empty] | 0
Schedule 18: Annex 1 | 4.4 | [12 empty] | 0
Schedule 18: Annex 1 | 4.5 | [12 empty] | 0
Schedule 18: Annex 1 | 4.6 | [12 empty] | 0
Schedule 18: Annex 1 | 4.7 | [12 empty] | 0
Schedule 18: Annex 1 | 4.8 | [12 empty] | 0
Schedule 18: Annex 1 | 4.9 | [12 empty] | 0
Schedule 18: Annex 1 | 5 | [12 empty] | 0
Schedule 18: Annex 1 | 5.1 | [12 empty] | 0
Schedule 18: Annex 1 | 5.2 | [12 empty] | 0
Schedule 18: Annex 1 | 5.3 | [12 empty] | 0
Schedule 18: Annex 1 | 5.4 | [12 empty] | 0
Schedule 18: Annex 1 | 5.5 | [12 empty] | 0
Schedule 18: Annex 1 | 5.6 | [12 empty] | 0
Schedule 18: Annex 1 | 5.7 | [12 empty] | 0
Schedule 18: Annex 1 | 5.8 | [12 empty] | 0
Schedule 18: Annex 1 | 5.9 | [12 empty] | 0
Schedule 18: Annex 1 | 5.1 | [12 empty] | 0
Schedule 18: Annex 1 | 5.11 | [12 empty] | 0
Schedule 18: Annex 1 | 5.12 | [12 empty] | 0
Schedule 18: Annex 1 | 5.13 | [12 empty] | 0
Schedule 18: Annex 1 | 5.14 | [12 empty] | 0
Schedule 18: Annex 1 | 5.15 | [12 empty] | 0
Schedule 18: Annex 1 | 5.16 | [12 empty] | 0
Schedule 18: Annex 1 | 5.17 | [12 empty] | 0
Schedule 18: Annex 1 | 5.18 | [12 empty] | 0
Schedule 18: Annex 1 | 5.19 | [12 empty] | 0
Schedule 18: Annex 1 | 5.2 | [12 empty] | 0
Schedule 18: Annex 1 | 5.21 | [12 empty] | 0
Schedule 18: Annex 1 | 5.22 | [12 empty] | 0
Schedule 18: Annex 1 | 5.23 | [12 empty] | 0
Schedule 18: Annex 1 | 5.24 | [12 empty] | 0
Schedule 18: Annex 1 | 5.25 | [12 empty] | 0
Schedule 18: Annex 1 | 5.26 | [12 empty] | 0
Schedule 18: Annex 1 | 5.27 | [12 empty] | 0
Schedule 18: Annex 1 | 5.28 | [12 empty] | 0
Schedule 18: Annex 1 | 5.29 | [12 empty] | 0
Schedule 18: Annex 1 | 5.3 | [12 empty] | 0
Schedule 18: Annex 1 | 5.31 | [12 empty] | 0
Schedule 18: Annex 1 | 5.32 | [12 empty] | 0
Schedule 18: Annex 1 | 5.33 | [12 empty] | 0
Schedule 18: Annex 1 | 5.34 | [12 empty] | 0
Schedule 18: Annex 1 | 5.35 | [12 empty] | 0
Schedule 18: Annex 1 | 5.36 | [12 empty] | 0
Schedule 18: Annex 1 | 5.37 | [12 empty] | 0
Schedule 18: Annex 1 | 5.38 | [12 empty] | 0
Schedule 18: Annex 1 | 5.39 | [12 empty] | 0
Schedule 18: Annex 1 | 5.4 | [12 empty] | 0
Schedule 18: Annex 1 | 5.41 | [12 empty] | 0
Schedule 18: Annex 1 | 5.42 | [12 empty] | 0
Schedule 18: Annex 1 | 6 | [12 empty] | 0
Schedule 18: Annex 1 | 6.1 | [12 empty] | 0
Schedule 18: Annex 1 | 6.2 | [12 empty] | 0
Schedule 18: Annex 1 | 6.3 | [12 empty] | 0
Schedule 18: Annex 1 | 6.4 | [12 empty] | 0
Schedule 18: Annex 1 | 6.5 | [12 empty] | 0
Schedule 18: Annex 1 | 6.6 | [12 empty] | 0
Schedule 18: Annex 1 | 6.7 | [12 empty] | 0
Schedule 18: Annex 1 | 6.8 | [12 empty] | 0
Schedule 18: Annex 1 | 6.9 | [12 empty] | 0
Schedule 18: Annex 1 | 6.1 | [12 empty] | 0
Schedule 18: Annex 1 | 6.11 | [12 empty] | 0
Schedule 18: Annex 1 | 6.12 | [12 empty] | 0
Schedule 18: Annex 1 | 6.13 | [12 empty] | 0
Schedule 18: Annex 1 | 6.14 | [12 empty] | 0
Schedule 18: Annex 1 | 6.15 | [12 empty] | 0
Schedule 18: Annex 1 | 6.16 | [12 empty] | 0
Schedule 18: Annex 1 | 6.17 | [12 empty] | 0
Schedule 18: Annex 1 | 6.18 | [12 empty] | 0
Schedule 18: Annex 1 | 6.19 | [12 empty] | 0
Schedule 18: Annex 1 | 6.2 | [12 empty] | 0
Schedule 18: Annex 1 | 6.21 | [12 empty] | 0
Schedule 18: Annex 1 | 6.22 | [12 empty] | 0
Schedule 18: Annex 1 | 6.23 | [12 empty] | 0
Schedule 18: Annex 1 | 6.24 | [12 empty] | 0
Schedule 18: Annex 1 | 6.25 | [12 empty] | 0
Schedule 18: Annex 1 | 6.26 | [12 empty] | 0
Schedule 18: Annex 1 | 6.27 | [12 empty] | 0
Schedule 18: Annex 1 | 6.28 | [12 empty] | 0
Schedule 18: Annex 1 | 6.29 | [12 empty] | 0
Schedule 18: Annex 1 | 6.3 | [12 empty] | 0
Schedule 18: Annex 1 | 6.31 | [12 empty] | 0
Schedule 18: Annex 1 | 6.32 | [12 empty] | 0
Schedule 18: Annex 1 | 6.33 | [12 empty] | 0
Schedule 18: Annex 1 | 6.34 | [12 empty] | 0
Schedule 18: Annex 1 | 7 | [12 empty] | 0
Schedule 18: Annex 1 | 7.1 | [12 empty] | 0
Schedule 18: Annex 1 | 7.2 | [12 empty] | 0
Schedule 18: Annex 1 | 7.3 | [12 empty] | 0
Schedule 18: Annex 1 | 7.4 | [12 empty] | 0
Schedule 18: Annex 1 | 7.5 | [12 empty] | 0
Schedule 18: Annex 1 | 8 | [12 empty] | 0
Schedule 18: Annex 1 | 8.1 | [12 empty] | 0
Schedule 18: Annex 1 | 8.2 | [12 empty] | 0
Schedule 18: Annex 1 | 8.3 | [12 empty] | 0
Schedule 18: Annex 1 | 8.4 | [12 empty] | 0
Schedule 18: Annex 1 | 8.5 | [12 empty] | 0
Schedule 18: Annex 1 | 8.6 | [12 empty] | 0
Schedule 18: Annex 1 | 8.7 | [12 empty] | 0
Schedule 18: Annex 1 | 8.8 | [12 empty] | 0
Schedule 18: Annex 1 | 8.9 | [12 empty] | 0
Schedule 18: Annex 1 | 8.1 | [12 empty] | 0
Schedule 18: Annex 1 | 8.11 | [12 empty] | 0
Schedule 18: Annex 1 | 8.12 | [12 empty] | 0
Schedule 18: Annex 1 | 8.13 | [12 empty] | 0
Schedule 18: Annex 1 | 8.14 | [12 empty] | 0
Schedule 18: Annex 1 | 8.15 | [12 empty] | 0
Schedule 18: Annex 1 | 8.16 | [12 empty] | 0
Schedule 18: Annex 1 | 8.17 | [12 empty] | 0
Schedule 18: Annex 1 | 8.18 | [12 empty] | 0
Schedule 18: Annex 1 | 8.19 | [12 empty] | 0
Schedule 18: Annex 1 | 8.2 | [12 empty] | 0
Schedule 18: Annex 1 | 8.21 | [12 empty] | 0
Schedule 18: Annex 1 | Attachment 1 | [12 empty] | 0
Schedule 18: Annex 1 | Attachment 2 | [12 empty] | 0
Schedule 18: Annex 1 | Attachment 3 | [12 empty] | 0
Schedule 18: Annex 2 | Annex 2 | [12 empty] | 0
0
Schedule 20 | Introduction | [12 empty] | 0
Schedule 20 | 1.1 | [12 empty] | 0
Schedule 20 | 2.1 | [12 empty] | 0
Schedule 20 | 3.1 | [12 empty] | 0
Schedule 20 | 3.2 | [12 empty] | 0
0
Schedule 29 | Introduction | [12 empty] | 0
Schedule 29 | 1 | [12 empty] | 0
Schedule 29 | 1A | [12 empty] | 0
Schedule 29 | 2 | [12 empty] | 0
Schedule 29 | 3 | [12 empty] | 0
Schedule 29 | 4 | [12 empty] | 0
Schedule 29 | 5 | [12 empty] | 0
Schedule 29 | 6 | [12 empty] | 0
Schedule 29 | 7 | [12 empty] | 0
Schedule 29 | 8 | [12 empty] | 0
Schedule 29 | 9 | [12 empty] | 0
Schedule 29 | 10 | [12 empty] | 0
Schedule 29 | 11 | [12 empty] | 0
Schedule 29 | 11A | [12 empty] | 0
Schedule 29 | 12 | [12 empty] | 0
Schedule 29 | 13 | [12 empty] | 0
Schedule 29 | 14 | [12 empty] | 0
Schedule 29 | 15 | [12 empty] | 0
Schedule 29 | 16 | [12 empty] | 0
Schedule 29 | 17 | [12 empty] | 0
Schedule 29 | 18 | [12 empty] | 0
Schedule 29 | 19 | [12 empty] | 0
Schedule 29 | 20 | [12 empty] | 0
Schedule 29 | 21 | [12 empty] | 0
Schedule 29 | 22 | [12 empty] | 0
Schedule 29 | 23 | [12 empty] | 0
Schedule 29 | 24 | [12 empty] | 0
Schedule 29 | 25 | [12 empty] | 0
Schedule 29 | 26 | [12 empty] | 0
Schedule 29 | 27 | [12 empty] | 0
Schedule 29 | 28 | [12 empty] | 0
Schedule 29 | 29 | [12 empty] | 0
Schedule 29 | 30 | [12 empty] | 0
Schedule 29 | 31 | [12 empty] | 0
Schedule 29 | 32 | [12 empty] | 0
Schedule 29 | 33 | [12 empty] | 0
Schedule 29 | 34 | [12 empty] | 0
Schedule 29 | 35 | [12 empty] | 0
Schedule 29 | 36 | [12 empty] | 0
Schedule 29 | 37 | [12 empty] | 0
Schedule 29 | 38 | [12 empty] | 0
Schedule 29 | 39 | [12 empty] | 0
Schedule 29 | 40 | [12 empty] | 0
Schedule 29 | 41 | [12 empty] | 0
Schedule 29 | 42 | [12 empty] | 0
Schedule 29 | 43 | [12 empty] | 0
Schedule 29 | 44 | [12 empty] | 0
Schedule 29 | 45 | [12 empty] | 0
Schedule 29 | 46 | [12 empty] | 0
Schedule 29 | 46A | [12 empty] | 0
Schedule 29 | 47 | [12 empty] | 0
0
Schedule 32 | 1 | [12 empty] | 0
Schedule 32 | 1.1 | [12 empty] | 0
Schedule 32 | 1.2 | [12 empty] | 0
Schedule 32 | 1.2A | [12 empty] | 0
Schedule 32 | 1.3 | [12 empty] | 0
Schedule 32 | 1.4 | [12 empty] | 0
Schedule 32 | 1.5 | [12 empty] | 0
Schedule 32 | 1.6 | [12 empty] | 0
Schedule 32 | 1.7 | [12 empty] | 0
Schedule 32 | 1.8 |  |  | YES | [9 empty] | 1
Schedule 32 | 1.9 | [12 empty] | 0
Schedule 32 | 1.10 |  |  | YES | [9 empty] | 1
Schedule 32 | 2 | [12 empty] | 0
Schedule 32 | 2.1 | [12 empty] | 0
Schedule 32 | 2.2 | [12 empty] | 0
Schedule 32 | 2.3 | [12 empty] | 0
Schedule 32 | 2.4 | [12 empty] | 0
Schedule 32 | 2.5 | [12 empty] | 0
Schedule 32 | 3 | [12 empty] | 0
Schedule 32 | 3.1 |  |  | YES | [9 empty] | 1
Schedule 32 | 3.2 | [12 empty] | 0
Schedule 32 | 3.3 | [12 empty] | 0
Schedule 32 | 3.4 | [12 empty] | 0
Schedule 32 | 3.5 | [12 empty] | 0
Schedule 32 | 3.6 | [12 empty] | 0
Schedule 32 | 4 | [12 empty] | 0
Schedule 32 | 4.1 |  |  | YES | [9 empty] | 1
Schedule 32 | 4.2 |  |  | YES | [9 empty] | 1
Schedule 32 | 4.2A |  |  | YES | [9 empty] | 1
Schedule 32 | 4.3 | [12 empty] | 0
Schedule 32 | 4.4 | [12 empty] | 0
Schedule 32 | 4.5 |  |  | YES | [9 empty] | 1
Schedule 32 | 4.6 | [12 empty] | 0
Schedule 32 | 5 | [12 empty] | 0
Schedule 32 | 5.1 | [12 empty] | 0
Schedule 32 | 5.2 | [12 empty] | 0
Schedule 32 | 5.3 | [12 empty] | 0
Schedule 32 | 5A. |  |  | YES | [9 empty] | 1
Schedule 32 | 5A.1 | [12 empty] | 0
Schedule 32 | 5A.1A | [12 empty] | 0
Schedule 32 | 5A.2 | [12 empty] | 0
Schedule 32 | 6 | [12 empty] | 0
Schedule 32 | 6.1 |  |  |  | YES | [8 empty] | 1
Schedule 32 | 6.2 |  |  |  | YES | [8 empty] | 1
Schedule 32 | 6.3 |  |  | YES | [9 empty] | 1
Schedule 32 | 6.4 | [5 empty] | YES | [6 empty] | 1
Schedule 32 | 6.4A | [12 empty] | 0
Schedule 32 | 6.5 |  |  | YES | [9 empty] | 1
Schedule 32 | 6.6 | [12 empty] | 0
Schedule 32 | 6.7 | [12 empty] | 0
Schedule 32 | 6.8 | [12 empty] | 0
Schedule 32 | 6.9 | [12 empty] | 0
Schedule 32 | 6.10 | [12 empty] | 0
Schedule 32 | 6.11 | [5 empty] | YES | [6 empty] | 1
Schedule 32 | 6.12 | [12 empty] | 0
Schedule 32 | 7 | [12 empty] | 0
Schedule 32 | 7.1 | [12 empty] | 0
Schedule 32 | 7.2 | [12 empty] | 0
Schedule 32 | 7.3 | [12 empty] | 0
Schedule 32 | 7.4 | [12 empty] | 0
Schedule 32 | 7.5 | [12 empty] | 0
Schedule 32 | 7.6 | [12 empty] | 0
Schedule 32 | 7.7 | [12 empty] | 0
Schedule 32 | 7.8 | [12 empty] | 0
Schedule 32 | 7.9 | [12 empty] | 0
Schedule 32 | 7.1 | [12 empty] | 0
Schedule 32 | 7.11 | [12 empty] | 0
Schedule 32 | 7.12 | [12 empty] | 0
Schedule 32 | 7.13 | [12 empty] | 0
Schedule 32 | 7.14 | [12 empty] | 0
Schedule 32 | 7.15 | [12 empty] | 0
Schedule 32 | 7.16 | [12 empty] | 0
Schedule 32 | 7.17 | [5 empty] | YES | [6 empty] | 1
Schedule 32 | 8 | [12 empty] | 0
Schedule 32 | 8.1 | [12 empty] | 0
Schedule 32 | 8.2 | [12 empty] | 0
Schedule 32 | Definitions |  |  | YES | YES | [8 empty] | 2
Charging Methodology CPs Legal Text Overlap Tracker

## Website
Change Proposal Number | Change Proposal Name | Status of the Change | Status Effective Date | Status Expected End Date | Expected Implementation Date | Proposer Party | Date Proposal Raised | Reasons for Change | Matter (Part 1 or 2) | Urgency Status | Impacted Parties | Next Event | Last Updated
DCP 388 | Amendments to Facilitate Appropriate Residual Charging for Sites with a Mix of Final and Non-Final Demand | On Hold | 01/11/2023 | 16/12/2026 | 2027-01-18 | E.ON ENERGY SOLUTIONS LIMITED | 2021-04-14 | This CP has been raised to enable DNOs to satisfy specific requirements set out in the TCR Direction. The DCUSA and the CUSC are increasingly likely to become inconsistent regarding the treatment of the residual charge over transmission and distribution, leading to inappropriate charging arrangements in terms of how the residual charge calculation is set out for mixed use sites over both transmission & distribution connections and to ensure that the network companies are fully compliant with Ofgem’s TCR direction and SCR principles. | Part 1 Matter | Standard | CVA, DNO, IDNO, ES |  | 16/07/2025
DCP 412 | Allocation of banding for TCR Charges for ‘Peaky’ Final Demand Customers | Awaiting Authority Decision | 19/03/2025 | - |  | E.ON UK PLC | 2022-10-11 | The recent reform of residual charges through the Targeted Charging Review (TCR) and subsequent DCUSA Change Proposals (such as DCP360) has led to an unintended consequence whereby customers with low annual consumption, but with high-capacity requirement needs are seeing bills that are overly excessive on the basis that such customers residual costs are allocated based on the Agreed Supply Capacity (ASC) over both Distribution & Transmission Use of System charging. For such customers the new fixed residual charge is based on connection agreements which in most cases the ASC reflects as a regular anticipated peak capacity. However for others, this peak capacity is very infrequently used and most of their demand is at significantly far lower levels of maximum capacity requirements. | Part 1 Matter | Urgent | DNO, IDNO, ES |  | 12/10/2025
DCP 419 | Pre-Notifications of Planned Supply De-Energisations | On Hold | - | - | 2026-02-26 | SCOTTISH HYDRO ELECTRIC POWER DISTRIBUTION PLC | 2023-03-06 | Within Ofgem’s ‘Regulatory Instructions and Guidance (RIG): Annex F – Interruptions’ document, there is an obligation on Distributors as below: Section 2.11 Single premises power outage alerts originating from a smart meter are not reasonably expected to indicate no supply. Where an outage alert is received, the DNO should contact the customer as soon as reasonably practicable thereafter to check whether the customer is without power, but only between 8am and 9pm. However, this should not restrict the DNO from contacting a customer outside of those hours if the DNO considers it in the customer’s interest to do so. The single premises power outage alert originating from a smart meter will be deemed to have been received at the earliest of either 8am or when there is contact with the customer. In order to meet their regulatory requirements and to maintain a positive customer experience Distributors will need to receive prior notification of any planned supply de-energisations which are being undertaken by DCUSA Parties in the course of their normal works. This proposal seeks to make the necessary changes to DCUSA legal text that satisfies this requirement. Having prior notification of planned supply interruptions will enable Distributors identify the POAs that should be ignored and help to avoid contacting the customer unnecessarily while maintaining a positive experience for the customer when dealing with DCUSA Parties. | Part 1 Matter | Standard | CRMC, DNO, IDNO, SIP, ES |  | 10/11/2025
DCP 420 | Provide targeted relief from residual charges for electric vehicle charging sites | Post-Consultation 1 Refinement | 29/10/2024 | 15/12/2025 | 2026-11-01 | NATIONAL GRID ELECTRICITY DISTRIBUTION (EAST MIDLANDS) PLC | 2023-03-29 | NGED has received an example of a council who is continuing with their roll out of EV charging stations to meet Welsh and UK Government aims to decarbonise the transport system. However a number of their charging stations have attracted standing charges rates that are so high that the EV charging stations are unsustainable. It is a consequence of the Targeted Charging Review (TCR) that decarbonisation initiatives such as the provision of EV Charging points have such high standing charges that the charging points are either unviable or too expensive for users to access (as they will need to pass costs on the end user – the EV car driver). The chargers are used infrequently at present and the revenue from the charge posts will not cover the standing charge costs for the provision of the incoming electrical supply and metering. | Part 1 Matter | Standard | DNO, IDNO, ES |  | 01/07/2025
DCP 423 | LDNO Discounts for Negative Scaling | On Hold | - | - | 2026-04-01 | THE ELECTRICITY NETWORK COMPANY LIMITED | 2023-05-09 | It is recognised that there are other elements of the tariffs where the LDNO tariff is lower than the all the-way equivalent and the LDNO will earn a margin in these areas reflective of the discount calculated in Schedule 29. However, the current application of the pass through and scaling creates a situation where this margin is altered without economic justification. Although it requires a specific set of circumstances for this situation to arise (for there to be sufficient negative scaling for the fixed charge to become floored at zero, and also for there to be bad debt or SoLR costs recovered in that year), it has been observed in the 2023-24 tariffs for UKPN’s London region. The scale of the issue is not necessarily limited as the size of the negative margin on the fixed charge component is dependent on the size of the pass through and the potential size of the negative scaling factor. | Part 1 Matter | Standard | DNO, IDNO |  | 10/11/2025
DCP 424 | Use of System charging for Complex Sites | Post-Consultation 1 Refinement | - | - | 2026-12-31 | GREEN ENERGY (UK) LIMITED | 2023-05-10 | For certain types of Complex Site, Half Hourly Data Collectors (HHDCs) may (for BSC Settlement purposes) net off Import and Export values, provided that they represent exempt supply by a generator to a customer within a local area. For these types of Complex Site, the half hourly metered data submitted to BSC Settlement is netted, and therefore not appropriate for calculation of DUoS charges. This creates an issue for MPANs in Measurement Classes F and G, as the CDCM currently requires billing for such MPANs to be based on BSC Settlement data received on the D0030 data flow. The required change to the CDCM is therefore to allow charges for Measurement Class F and G customers within such Complex Sites to be calculated using gross metered data provided by the HHDC, rather than net Settlement data on the D0030 data flow. | Part 1 Matter | Standard | DNO, IDNO, ES |  | 02/02/2026
DCP 440 | Consuming “de-energised” sites | Approved: Awaiting Implementation | 26/08/2025 | - | 2027-04-01 | EASTERN POWER NETWORKS PLC | 2024-04-15 | Where an MPAN is marked as “de-energised” in the registration system but there are actual meter readings, it is clear that the MPAN is not actually de-energised. For NHH/Supercustomer/Aggregated DUoS charges, settlements includes actual consumption recorded against de-energised MPANs and counts the MPAN. However, the incorrect flagging of an MPAN means that site-specific charges are avoided, under the CDCM, unless the supplier corrects the status. | Part 1 Matter | Standard | CVA, DNO, IDNO, ES |  | 17/06/2025
DCP 442 | Aligning enduring flexible connections | On Hold | 05/03/2025 | - |  | NORTHERN POWERGRID (NORTHEAST) PLC | 2024-07-01 |  | Part 1 Matter | Standard | DNO, IDNO |  | 20/01/2026
DCP 443 | Excess Capacity | Post-Consultation 1 Refinement | 01/01/2025 | 20/08/2025 | 2026-04-01 | EASTERN POWER NETWORKS PLC | 2024-07-09 |  | Part 1 Matter | Standard | CVA, DNO, IDNO, ES |  | 09/09/2025
DCP 446 | Emergency Disconnections | Awaiting Authority Decision | 16/04/2025 | 30/06/2025 | 2026-04-01 | EASTERN POWER NETWORKS PLC | 2024-11-07 | In order to support network cost allocation more appropriately, provision for emergency disconnection charging should be broadened to act across all strands of the national terms of connection rather than being limited to larger connections only, as described in sections 3 and 4 of the National Terms of Connection (Schedule 2B). There is inconsistency between sections 3 and 4 and section 2 of the NTC. Sections 3 (Clause 6.3) and 4 (Clause 6.3) allow the costs of emergency disconnections to be recovered but section 2 does not. In order to avoid socialisation of emergency disconnection costs to all users, wording should be introduced into section 2 which supports DNOs, where appropriate, to recharge reasonable costs to users, or their agents, who drive the need for emergency disconnections. | Part 1 Matter | Standard | DNO, IDNO |  | 20/01/2026
DCP 450 | Managing the effects of surplus residual charge in the CDCM | Approved: Awaiting Implementation | 20/10/2025 | - | 2027-04-01 | EASTERN POWER NETWORKS PLC | 2025-02-10 | At the time of setting charges for 2025/26 in December 2023, some DNOs were only aware late in the process that when following the charging methodology, it was not possible to create a full set of charges without errors due to the size of the residual. This required last minute discussions with Ofgem, as well as for some, derogations being granted in order to be able to calculate charges. Following this, early in 2024, discussions took place with Ofgem over a number of months to understand if the same problems were expected to be seen with the calculation of 2026/27 charges. This resulted in some guidance notes being issued by Ofgem for the calculation of the 2026/27 charges. The guidance can be accessed using the link in paragraph 1.3. Although the guidance document relates to both Common Distribution Charging Methodology (CDCM) and Extra-High Voltage Distribution Charging Methodology (EDCM), this change solely relates to the CDCM. A separate change will be brought forward for the EDCMs. | Part 1 Matter | Standard | CVA, DNO, IDNO, ES |  | 15/09/2025
DCP 452 | Correct application of Forward Cost Pricing EDCM charges to users connected directly to a Grid Supply Point | Post-Consultation 1 Refinement | 13/01/2026 | 11/03/2026 | 2028-04-01 | FIELD GAIA LTD | 2025-03-05 | Under the Forward Cost Pricing (FCP) variant of the Extra High Voltage (EHV) Distribution Charging Methodology (EDCM), all Connectees which connect direct to a Grid Supply Point (GSP) are exposed to forward looking charges/credits in respect of future thermal reinforcement on the downstream FCP Network Group in that location. This Change Proposal seeks to remove the non-cost-reflective application of FCP charges/credits to GSP-connected customers at non-interconnected GSPs. There is no equivalent issue under the Long Run Incremental Cost (LRIC) variant of the EDCM. The LRIC approach derives a zero charge for all Connectees which are connected direct to a GSP. Connectees at all voltages in the EDCM and CDCM should face forward looking charges/credits in respect of assets on which they are deemed to drive costs. For CDCM Connectees, this is applied by charging customers only for voltages upstream of their connection point, up to the GSP. Connectees directly connecting to a non-interconnected GSP under the FCP variant of the EDCM are exposed to charges/credits in respect of a downstream voltage on which they will never be deemed to drive cost in the power flow model underpinning the EDCM (which only considers thermal reinforcement). As a result, the inclusion of such customers in the power flow modelling introduces a cross-subsidy from GSP-connected customers to other customers downstream who do drive the need for thermal reinforcement. | Part 1 Matter | Standard | CVA, DNO, ES | DCP 452 Working Group - Meeting 11 - 12/02/2026 at 10:00 | 02/02/2026
DCP 454 | Provide enduring targeted relief from residual charges for electric vehicle charging sites | Definition | 22/05/2025 | 15/12/2025 | 2028-04-01 |  | 2025-05-06 |  | Part 1 Matter | Standard | DNO, IDNO, ES |  | 05/06/2025
DCP 455 | Align RAV price-inflation with that used in ED2 | Approved: Awaiting Implementation | 06/11/2025 | 26/02/2026 | 2026-02-26 | ELECTRICITY NORTH WEST LIMITED | 2025-05-22 |  | Part 2 Matter | Standard | DNO, IDNO, ES |  | 06/11/2025
DCP 459 | DNO invoices to Embedded DNO | Post-Consultation 1 Refinement | 21/11/2025 | 15/04/2026 | 2026-06-15 | UK POWER DISTRIBUTION LIMITED | 2025-08-01 | The current Distribution Use of System (DUoS) invoicing process for non-aggregated Meter Point Administration Numbers (MPANs) from Distribution Network Operators (DNOs) to Embedded Distribution Network Operators (EDNOs) is fit for purpose but inefficient. It requires manual work which wastes time, and introduces the risk of error. The problem comes from the fact that the invoices are sent as a PDF document, which the EDNO need to then enter in their accounting system. Ideally, the invoices would be supported with a xls document that the EDNO can easily and "load" into their accounting system. Clauses 43.6.2 and Schedule 19 describe how the charging and in part invoicing needs to be done, but are not specific on the format of the invoices. We suggest amending Schedule 19 to add a requirement to accompany the PDF format of an invoice for non-aggregated MPANs, with an excel spreadsheet that contains minimum fields to support the automatic "load". We note that some DNOs may already be providing an equivalent to some EDNOs, in which case this change proposal intends to bring every party to the same playing field in an open manner, and bring the expected positive impacts to all | Part 2 Matter | Standard | DNO, IDNO |  | 4 days ago
DCP 461 | Reducing the Impact of Transmission Distribution Charges | Post-Consultation 1 Refinement | 01/12/2025 | 16/02/2026 |  | NATIONAL GRID ELECTRICITY DISTRIBUTION (EAST MIDLANDS) PLC | 2025-08-13 |  | Part 1 Matter | Standard | DNO, IDNO | DCP 461 Working Group Meeting 14 - 19/02/2026 at 13:00 | 02/02/2026
DCP 463 | Charging non-consuming De-energised CT-Metered sites | Consultation 2 | 04/02/2026 | 18/03/2026 | 2027-04-01 | EASTERN POWER NETWORKS PLC | 2025-09-05 |  | Part 1 Matter | Standard | CVA, DNO, IDNO, ES |  | 6 days ago
DCP 464 | IDNO Connection Applications: Treatment of Existing Assets | Post-Consultation 1 Refinement | 01/12/2025 | 18/03/2026 | 2026-04-01 | SOUTHERN ELECTRIC POWER DISTRIBUTION PLC | 2025-09-08 |  | Part 1 Matter | Standard | DNO, IDNO | DCP 464 Working Group - Meeting 06 - 17/02/2026 at 13:00 | 02/02/2026
DCP 465 | NFD Generator and Battery Capacity Charges | Definition | 29/10/2025 | 03/03/2026 | 2028-04-01 | NATIONAL GRID ELECTRICITY DISTRIBUTION (EAST MIDLANDS) PLC | 2025-10-15 | Following the access SCR and zeroing of the customer contributions the Capacity charge in the CDCM has increased to a level that sites with a high import capacity, such as Batteries, may find difficult for commercial operation. The CDCM differs from the EDCM in that it does not treat generation sites differently to demand sites when determining the Capacity charge. This creates a disparity between the two different methodologies creating boundaries and cliff edges and pricing differentials depending on the level of connection. This may lead to non-optimal behaviour. | Part 1 Matter | Standard | CVA, DNO, IDNO, ES |  | 13/01/2026
DCP 466 | Tariff Band to Follow Capacity | Consultation 1 | 20/01/2026 | 15/04/2026 |  | EASTERN POWER NETWORKS PLC | 2025-10-23 | Change the rules such that, for those customers whose tariff band is based on their capacity, the band is aligned to their capacity at all times. When a change of capacity is agreed between the distributor and the customer, the tariff band is amended as required as per the published capacity bands. The arbitrary greater than 50% change threshold and the need for a customer application results in discriminatory application of the tariff bands. We have had many conversations with customers who are not happy with the way the re-banding currently works. | Part 1 Matter | Standard | CVA, DNO, IDNO, ES | DCP 466 Working Group Meeting 04 - 20/02/2026 at 10:00 | 22/01/2026
DCP 467 | Online reporting tools for Category A and B defects | Definition | 19/11/2025 | 26/01/2026 |  | LONDON POWER NETWORKS PLC | 2025-10-21 | Where smart enhanced reporting facilities are provided to report Category A and B defect reports to DNO’s, these shall be fully adopted by the relevant DCUSA Parties (Suppliers and their appointed agents, SIPs). Where DNOs have created an online reporting mechanism to report defects, there is enhanced function and features such as it is delivered to the DNO immediately as opposed to one working day and it allows for additional information to be sent such as photos. Where photos are provided it allows for the DNO to make a better assessment as to what is required to resolve the issue and has proven to reduce occasions od double visit to sites. By mandating the use of such systems if made available, may encourage other DNOs to invest and subsequently see the benefits of the enhanced features. | Part 1 Matter | Standard | DNO, IDNO, SIP, ES |  | 13/01/2026
DCP 468 | Remove Redundant DataFlow from DTC/EMDS | Definition | 21/01/2026 | 16/03/2026 | 2026-11-05 | ELECTRICITY NORTH WEST LIMITED | 2025-11-14 | It is evident that existing market participants and code bodies have routinely produced D0164s during testing which are of no value, consuming resources unnecessarily. Secretariat has confirmed from sources within Electralink that: Only 674 instances of D0164 have been sent since April 2012 These were sent from MPIDs of 12 IDNOs, 2 DNOs and 3 REC/MRA Of which 565 were from REC/MRA and 32 from IDNOs, all tagged as ‘test’ flows. Of the remaining 77 instances, 76 were sent in 4 batches on two dates in 2013 (totalling 25) from 1 DNO, and on two dates in 2023 (totalling 51) from 1 IDNO. Although none of these batches were tagged as ‘test’, given their ‘one-off batch’ nature, it seems likely they were test, or at least unlikely that they related to actual supply interruptions. That leaves 1, sent by a second DNO which was not tagged as ‘test’ flow. The Proposer considers that it might be worthwhile for Secretariat to ask the two DNOs and the one IDNO to confirm that these 77 flows were indeed not ‘live operational’ dataflows. Retaining redundant flows in EMDS runs the risk that they are sent/received erroneously to market participants. This could result in non-value time and effort to assess what it is to be used for. It is also conceivable that market participants, particularly those new to the industry, could be misled into believing it has a role, worst case developing processes or systems to use it only to find it is of no practical value It is a simple principle of efficiency that unnecessary processes should be eliminated. The retention of redundant data flows is a credibility risk for industry, particularly at a time of criticism about complexity in the industry. | Part 2 Matter | Standard | CVA, DNO, GS, IDNO, OTSO, ES |  | 6 days ago
DCP 469 | Cross Code Standardisation of Charging Arrangement Notice Periods | Definition | 21/01/2026 | 23/03/2026 | 2026-09-30 | EASTERN POWER NETWORKS PLC | 2026-01-13 | Currently notice periods across Electricity and Gas differ considerably, with the most extreme being two months for TNUoS and fifteen months for DUoS. Setting charges so far in advance can and does require the charges to be set based on a number of assumptions which creates significant volatility year on year. We have reviewed the send back letter and decision on DCP437 ‘To shorten the DUoS Pricing Notice Periods’ and note the concerns raised by Suppliers to the risk premium which would be required if the notice period was to be shortened. We believe that by currently having several very different notice periods across different codes cannot provide suitable assurances to Suppliers, especially where the arrangements for Distribution and Transmission of Electricity currently differ by over a full year, this would make it surely impossible to set any charges or forecasts with any known certainty. As a result we believe that by aligning all notice periods (as detailed in clause 1.11 of this change proposal) would ensure that all Suppliers have access to an indicative and final view on charges at the same time, and when final charges are published they would include the latest available information rather than a number of assumptions which is currently the case. This would significantly reduce the amount of volatility seen between charging years, which has been considerable over the ED2 period. We believe that by reducing the volatility this comfortably outweighs the impact on risk premium which Suppliers would otherwise need to consider, especially when only one element of the ‘networks’ charge is known so far in advance. | Part 1 Matter | Urgent | CVA, DNO, IDNO, ES | DCP 469 Working Group - Meeting 01 - 11/02/2026 at 10:00 | 26/01/2026
DCP 470 | Independent Credit Assessments | Definition | 21/01/2026 | 16/03/2026 | 2026-06-25 | EASTERN POWER NETWORKS PLC |  | We review the credit cover position of Users frequently. We write to Users who are in “Cover Default” under the credit cover arrangements. Some Users do not respond. However, we can see from credit assessment companies that those Users are not of concern. Similarly, the values may be immaterial. These Users are technically in cover Default and we could suspend registrations. This seems a harsh sanction for immaterial values where we can see from independent assessments that the User is financially viable. Currently we can’t use this information unless the User requests us to do so. This results in us continuing to write to them and whilst they keep not responding | Part 2 Matter | Standard | CVA, DNO, IDNO, ES | DCP 470 Working Group Meeting 01 - 12/02/2026 at 13:00 | 6 days ago